- Worksheet for Rulemaking Schedule

- Rule Title:  CWSRF-Stimulus Permanent Rulemaking

- Project lead/phone:   		Date prepared:

| Develop Rulemaking | Option 1 | Option 2 | Option 3 |
| --- | --- | --- | --- |
| Start Rulemaking Proposal | Initial |  |  |
| Route Start Rulemaking Proposal to Section Mgr |  |  |  |
| Route Start Rulemaking Proposal to Division Rules Coordinator (DRC) |  |  |  |
| Route Start Rulemaking Proposal to lead Administrator |  |  |  |
| Submit Start Rulemaking Proposal to OD (9:00 a.m.) |  |  |  |
| Dry Run Start Rulemaking Proposal w/lead Administrator & others |  |  |  |
| Start Rulemaking Proposal meeting – EMT | 4/14 |  |  |
| Fee Approval |  |  |  |
| *Request DAS to approve new & increased fees (at least 30 days prior to filing notice w/SOS or date rule is effective) | NA |  |  |
| *Obtain DAS approval or denial of fees (goal = within 30 days of submittal) |  |  |  |
| Draft Notice of Proposed Rulemaking Package |  |  |  |
| Route draft Notice of Proposed Rulemaking package to Section Mgr | 6/16 |  |  |
| Route draft Notice of Proposed Rulemaking package to DRC | NA, will be included 6/19 |  |  |
| Route draft Notice of Proposed Rulemaking package to lead Administrator | tentatively 6/17 |  |  |
| Submit draft Notice of Proposed Rulemaking package to reviewers (author) | 6/19 |  |  |
| Reviewer comments to author | 6/25 |  |  |
| Final Notice of Proposed Rulemaking Package |  |  |  |
| Route final Notice of Proposed Rulemaking package to Section Mgr | 7/1 |  |  |
| Route final Notice of Proposed Rulemaking package to DRC | NA, will be included 7/6 |  |  |
| Route final Notice of Proposed Rulemaking package to lead Administrator | See 7/13 |  |  |
| Submit final Notice of Proposed Rulemaking package for concurrence review | 7/6 |  |  |
| Concurrence reviews due to author | 7/10 |  |  |
| Submit final Notice of Proposed Rulemaking package for lead Administrator for approval | 7/13 |  |  |
| Lead Administrator authorizes publication of Notice | 7/13 |  |  |
| Public Notice, Hearing & Comment |  |  |  |
| Send Notice to Secretary of State for Bulletin (by 15th;earlier if weekend/holiday) | 7/15 |  |  |
| Mail Notice to mailing & e-mail lists (at least 28 days prior to hearing, excluding mailing date) | 7/17 |  |  |
| Notice published in Bulletin (1st of Month; 21 days before effective date) | 8/1 |  |  |
| Public Hearing(s) (At least 14 days after notice in Bulletin, excluding pub date) | 8/17 -19 |  |  |
| Public Comment deadline (usually 3 to 7 days after hearing) | 8/24 |  |  |

Worksheet for Rulemaking Schedule

- Rule Title:

- Project lead/phone:   		Date prepared:

| Adopt Rule - EQC | Option 1 | Option 2 | Option 3 |
| --- | --- | --- | --- |
| Draft Final Rulemaking Package |  |  |  |
| Brief Director with lead Administrator before preparing Final Rulemaking package | NA |  |  |
| Route draft Final Rulemaking package to Section Mgr | 8/26 |  |  |
| Route draft Final Rulemaking package to DRC | NA, will be included 8/28 |  |  |
| Route draft Final Rulemaking package to lead Administrator | NA, see 9/8 |  |  |
| Distribute draft Final Rulemaking package to reviewers (author) | 8/28 |  |  |
| Reviewer comments due to author | NA, see 9/8 |  |  |
| # Final Rulemaking Package | NA |  |  |
| Route Final Rulemaking package to Section Mgr | NA |  |  |
| Route Final Rulemaking package to DRC | NA |  |  |
| Route Final Rulemaking package to lead Administrator | NA |  |  |
| Route Final Rulemaking package for concurrence review | NA |  |  |
| Concurrence reviews due to author | 9/8 |  |  |
| Route Final Rulemaking package to lead Administrator for approval for submittal to OD | 9/9 |  |  |
| Submit Final Rulemaking package to OD for signature and distribution (5:00 p.m.) (e-mail and 1 hard copy w/signed staff report) | 9/11 |  |  |
| OD mails EQC Staff Report w/attachments to EQC |  |  |  |
| EQC Meeting |  |  |  |
| Dry run EQC Presentation w/ lead Administrator & others |  |  |  |
| EQC meeting date | 10/22 |  |  |