## updated 5-19-09
|  | 2008 |  |  | 2009 | [11 empty] | 2010
|  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
Active Rules (Start Rulemaking approved by management)
WQ - 2009 Permit Fee Increase (Chris Clipper) | 2008-10-12 | 2009 Feb: SOS; 2009 Apr: on hold
WQ - Standards - Turbidity (Deb S.) |  | 2009 Mar: on hold; 2010 Mar: SOS; 2010 Nov: Fall 2010
WQ - Standards/Revisions Human Health Criteria (fish consumption basis) (Deb S.) | 2008-10-12 | 2010 Feb: SOS; 2010 Jun: Early Summer 2010
WQ - Streamlining WQ Gen. Permit Adoption (Beth Moore) |  | 2008 Nov: 2008-12-01; 2009 Aug: SOS; 2010 Jan: 2009-12-10
WQ - State Revolving Fund Stimulus Perm. Rule (Larry McAllister) self -managing |  | 2009 Mar: 2009-04-06; 2009 July: SOS; 2009 Nov: 2009-10-22
Inactive Rules (awaiting management approval to start rulemaking)
WQ - Restore On-site Septic System Program (Mike Kucinski) |  | 2009 July: 2009-08-10; 2010 Nov: not provided
WQ - Gray Water Systems (Judy Johndohl) |  | 2009 Sept: 2009-10-05 |  | 2011-10-01
WQ - Identification of Pollutants Requiring Reduction Programs (Cheryl Grabham) |  | 2009 Sept: 2009-10-05; 2010 Feb: SOS; 2010 Nov: 2010-10-01
WQ - Underground Injection Control (UIC) Program (Barbara Priest) |  | 2010 Jul: 2010-08-02
WQ - State Revolving Fund Longterm (Larry McAllister) self -managing |  | 2009 Sept: 2009-10-05; 2010 Jun: SOS | 2010-12-01
indicates new rule since EQC last reviewed Rulemaking Agenda in Dec, 2007
First Date = ODAM SRP Meeting (even months only)
Second Date = Publication of notice in SOS Bulletin (monthly, first day of the month)
Third Date = EQC Meeting (even months only)
Updated: 5/19/09