## Database Format
Rule | Task # | Date
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 1 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 2 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 3 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 4 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 5 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 6 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 7 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 8 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 9 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 10 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 11 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 12 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 13 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 14 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 15 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 16 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 17 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 18 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 19 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 20 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 21 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 22 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 23 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 24 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 25 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 26 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 27 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 28 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 29 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 30 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 31 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 32 | 0
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 33 | 2008-08-29
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 34 | 2008-09-08
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 35 | 2008-09-29
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 36 | 2008-10-16
RAI-727 Amend LRAPA, Title 47, Open Burning Rules | 37 | 2008-10-23

## AQ Rulemaking Schedule
Air Quality Worksheet for Rulemaking Schedule
Rule Title: RAI-727 Amend LRAPA, Title 47, Open Burning Rules |  |  |  |  | Clear All Blackouts
Project Lead & Phone: Hough, Merlyn 541.736.1056 x216 |  |  |  |  | Date | [5 empty] | Day of Week |  |  | Days since previous act
DA | # Days | DB | Develop Rulemaking | N/A | Option 1 | Calc 1 | Option 2 | Calc 2 | Option 3 | Calc 3 | Option 1 | Option 2 | Option 3 | Option 1 | Option 2 | Option 3
Current Option in Use >
|  |  | Start Rulemaking Proposal | [13 empty] | 1 | Sunday
| 0 |  | Route Start Rulemaking Proposal to Section Mgr (at least 5 days prior to DA due date) | [13 empty] | 2 | Monday
IN | 0 |  | Route Start Rulemaking Proposal to Division Administrator (at least 1 week prior to OD due date) | [13 empty] | 3 | Tuesday
OUT |  | 1 | Submit Start Rulemaking Proposal to OD (9:00 a.m.) | [13 empty] | 4 | Wednesday
APT |  |  | Dry Run Start Rulemaking Proposal w/DA & others (Thurs., 1-2 wks. prior to ODAM Mtg. - contact DRC to schedule.) | [13 empty] | 5 | Thursday
MTG |  | 2 | Start Rulemaking Proposal meeting – ODAM | [13 empty] | 6 | Friday
|  |  | Fee Approval | [13 empty] | 7 | Saturday
| 0 |  | *Request DAS to approve new & increased fees (at least 30 days prior to filing notice w/SOS or date rule is effective)
|  |  | *Obtain DAS approval or denial of fees (goal = within 30 days of submittal) If DAS Approval is Not Required, DAS must still be notified of Fee Changes. DAS enters all agency fees into a database. | [14 empty] | 1
Draft Notice of Proposed Rulemaking Package
| 0 |  | Route draft Notice of Proposed Rulemaking package to Section Mgr (at least 5 days prior to DA due date) | [13 empty] | Project Lead & Phone:
IN | 0 |  | Route draft Notice of Proposed Rulemaking package to Division Administrator (at least 1 week prior to submitting to reviewers) | [13 empty] | Andrea Curtis 503.229.6866 | Project Lead & Phone: Andrea Curtis 503.229.6866
OUT |  | 3 | Submit draft Notice of Proposed Rulemaking package to reviewers (author) | [13 empty] | Brandy Albertson 503.229.6459 | Project Lead & Phone: Brandy Albertson 503.229.6459
|  |  | Reviewer comments to author | [13 empty] | Brian Finneran 503.229.6278 | Project Lead & Phone: Brian Finneran 503.229.6278
|  |  | Final Notice of Proposed Rulemaking Package | [13 empty] | Dave Nordberg 503.229.5519 | Project Lead & Phone: Dave Nordberg 503.229.5519
| 0 |  | Route final Notice of Proposed Rulemaking package to Section Mgr (at least 5 days prior to DA due date) | [13 empty] | David Collier 503.229.5177 | Project Lead & Phone: David Collier 503.229.5177
IN | 0 |  | Route final Notice of Proposed Rulemaking package to Division Administrator (at least 1 week prior to submitting to reviewers) | [13 empty] | Ed Druback 503.667.8414 x55014 | Project Lead & Phone: Ed Druback 503.667.8414 x55014
OUT |  | 4 | Submit final Notice of Proposed Rulemaking package for concurrence review | [13 empty] | Gregg Dahmen 503.229.5108 | Project Lead & Phone: Gregg Dahmen 503.229.5108
|  |  | Concurrence reviews due to author | [13 empty] | Jerry Coffer 503.731.3050 x229 | Project Lead & Phone: Jerry Coffer 503.731.3050 x229
IN |  |  | Submit final Notice of Proposed Rulemaking package to Division Administrator for approval | [13 empty] | Jerry Ebersole 503.229.6974 | Project Lead & Phone: Jerry Ebersole 503.229.6974
AUTH |  |  | Division Administrator authorizes publication of Notice | [13 empty] | Karen White-Fallon 503.378.5315 | Project Lead & Phone: Karen White-Fallon 503.378.5315
|  |  | Public Notice, Hearing & Comment | [13 empty] | Kevin Downing 503.229.6549 | Project Lead & Phone: Kevin Downing 503.229.6549
OUT |  | 5 | Send Notice to Secretary of State for Bulletin (by 15th;earlier if weekend/holiday) | [13 empty] | Larry Calkins 541.567.8297 x25 | Project Lead & Phone: Larry Calkins 541.567.8297 x25
| 0 |  | Send Notice to EPA (at least 45 days prior to hearing) Only applies to SIP rules – make sure the AG’s office has reviewed the rule prior to submitting it to EPA | [13 empty] | Larry McAllister 503.229.6412 | Project Lead & Phone: Larry McAllister 503.229.6412
| 0 |  | Mail Notice to mailing & e-mail lists (at least 28 days prior to hearing, excluding mailing date, if a SIP rule, must be mailed 30 days prior to hearing) | [13 empty] | Marianne Fitzgerald 503.229.5946 | Project Lead & Phone: Marianne Fitzgerald 503.229.5946
| 0 |  | Publish legal ad in local newspapers (at least 30 days prior to hearing, excluding publication and hearing date) Applies whenever hearings held. | [13 empty] | Melinda Mahoney 503.731.3050 x | Project Lead & Phone: Melinda Mahoney 503.731.3050 x
| 0 | 6 | Notice published in Bulletin (1st of Month; 21 days before effective date) | [13 empty] | Hough, Merlyn 541.736.1056 x216 | Project Lead & Phone: Hough, Merlyn 541.736.1056 x216
| 0 | 7 | Public Hearing(s) (At least 15 days after notice in Bulletin, excluding pub date) (An evening time slot will allow the working public a greater opportunity to attend. This is STRONGLY advised!) | [13 empty] | Phil Allen 503.229.6904 | Project Lead & Phone: Phil Allen 503.229.6904
| 0 | 8 | Public Comment deadline (usually 3 to 7 days after hearing) | [13 empty] | Rachel Sakata 503.229.5659 | Project Lead & Phone: Rachel Sakata 503.229.5659
|  |  | Adopt Rule - EQC | [13 empty] | Sarah Armitage 503.229.5186 | Project Lead & Phone: Sarah Armitage 503.229.5186
|  |  | Draft Final Rulemaking Package | [13 empty] | Shari Jay 503.731.3050 x | Project Lead & Phone: Shari Jay 503.731.3050 x
| 0 |  | Route draft Final Rulemaking package to Section Mgr (at least 5 days prior to DA due date) | [13 empty] | UNKNOWN AT THIS TIME | Project Lead & Phone: UNKNOWN AT THIS TIME
IN | 0 |  | Route draft Final Rulemaking package to Division Administrator (at least 1 week prior to submitting to reviewers)
OUT |  | 9 | Distribute draft Final Rulemaking package to reviewers (author)
|  | 10 | Reviewer comments due to author
Final Rulemaking Package
| 0 |  | Route Final Rulemaking package to Section Mgr (at least 5 days prior to DA due date)
IN | 0 |  | Route Final Rulemaking package to Division Administrator (at least 1 week prior to submitting to reviewers)
OUT |  | 11 | Route Final Rulemaking package for concurrence review
|  | 12 | Concurrence reviews due to author
IN |  | 13 | Route Final Rulemaking package to Division Administrator for approval for submittal to OD |  | 2008-08-29 | 2008-08-29 |  |  |  |  | Friday
OUT | 21 |  | Submit Final Rulemaking package to OD for signature and distribution (5:00 p.m.) (e-mail and 1 hard copy w/signed staff report) (At least 21 days before mailing to EQC). |  | 2008-09-08 | 2008-09-08 |  |  |  |  | Monday |  |  | 10
| 24 | 14 | OD mails EQC Staff Report w/attachments to EQC (At least 24 days before EQC meeting date). |  | 2008-09-29 | 2008-09-29 |  |  |  |  | Monday |  |  | 21
EQC Meeting
APT |  |  | Dry run EQC Presentation w/ DA & others at HAMM Mtg. (Thurs., 1-2 wks. prior to EQC Mtg., usually 1/2 hr. - contact DRC to schedule.) |  | 2008-10-16 | 2008-10-16 |  |  |  |  | Thursday |  |  | 17
MTG |  | 15 | EQC meeting date |  | 2008-10-23 | 2008-10-23 |  |  |  |  | Thursday |  |  | 7
|  | Key: | Column 'DA' are dates rulemaking involves the DA. Some are by appointment.
|  |  | Column '#' Days is the calculation of days for the row requirement. Red is bad! | Days
|  |  | Column 'DB' indicates the 15 dates needed for the DEQ Rulemaking Database. Bolded dates in 12 pt. font (#2, 6 & 15) are the minimum dates required for the database. | Mths
Formulas:
Calc 1 = IF([N/A]="",IF([Date]<>"",[Date],""),[Calc 1, row above])
Calc 1 = IF([N/A]="",IF([Date]<>"",[Date],""),G48)
Note on A3: Select Cell; Use dropdown menu to select rule writer.
Note on B30: Gary Beyer: This calculated number of days must be: If SIP related; at least 30. If NOT SIP related; at least 28.
Note on B31: Gary Beyer: This calculated number of days must be at least 30. Only applies to SIP rules!
Note on D29: Gary Beyer: See # Days column (B) for calculated number of days. If the number is RED it does not meet the SIP requirement. Option 1, 2, or 3 (above) must be selected for this calculation to occur.
Note on D30: Gary Beyer: See # Days column (B) for calculated number of days. If the number is RED it does not meet the SIP requirement. Option 1, 2, or 3 (above) must be selected for this calculation to occur.
Note on D31: Gary Beyer: See # Days column (B) for calculated number of days. If the number is RED it does not meet the SIP requirement. Option 1, 2, or 3 (above) must be selected for this calculation to occur.
Note on D32: Gary Beyer: See # Days column (B) for calculated number of days. If the number is RED it does not meet the SIP requirement. Option 1, 2, or 3 (above) must be selected for this calculation to occur.
Note on D33: Gary Beyer: See # Days column (B) for calculated number of days. If the number is RED it does not meet the SIP requirement. Option 1, 2, or 3 (above) must be selected for this calculation to occur.