Draft Rulemaking Timeline

Human Health Toxics Criteria and Implementation Rulemaking

| Milestone | Deliverables | Completion Date |
| --- | --- | --- |
| Develop draft proposed rule package | Draft proposed rules Issue papers implementation plan statement of need and fiscal impact | Oct 27, 2010 |
| Draft rule package for review: IRT, PMT, budget, communications, rule coordinators, EPA, and AG review (cc to EMT as a heads up) | Draft rule package for Secretary of State (SOS) Meeting w/ IRT | Nov 3 - Nov 17, 2010 Nov 10, 2010 |
| Final rule package for EMT review | Final rule package for SOS Concurrence forms Neil signature | Dec 1 - Dec 8, 2010 Dec 13, 2010 Dec 14, 2010 |
| Prepare for public comment | Rulemaking documents sent to SOS Notice published in SOS bulletin | Dec 15, 2010 Jan 3, 2011 |
| Public comment and hearings | Public comment period (est.) Public hearings (est.) | Jan 3 - Feb 18, 2011 Feb 1 - Feb 11, 2011 |
| Response to public comment and final proposed rules | Response to public comment final proposed rules supporting documents implementation plan | April 29, 2011 |
| EQC informational presentation | staff report and presentation EQC Meeting | March 22, 2011 April 29 – 30, 2011 |
| EQC action item | Staff report and presentation EQC meeting and rule adoption | May 10, 2011 June 16 -17, 2011 |
| Submit revised standards to EPA for approval | AG certification of rule adoption rules filed with SOS submittal package to EPA | July 22, 2011 |
| EPA action item | CWA requires EPA action within 90 days of submission (est.) | Oct 20, 2011 |