****

**Draft Rulemaking Timeline**

**Human Health Toxics Criteria and Implementation Rulemaking**

|  |  |  |
| --- | --- | --- |
| **Milestone** | **Deliverables** | **Completion Date** |
| Develop draft proposed rule package | Draft proposed rulesIssue papersimplementation planstatement of need and fiscal impact | Oct 27, 2010 |
| Draft rule package for review: IRT, PMT, budget, communications, rule coordinators, EPA, and AG review (cc to EMT as a heads up) | Draft rule package for Secretary of State (SOS)Meeting w/ IRT | Nov 3 - Nov 17, 2010Nov 10, 2010 |
| Final rule package for EMT review | Final rule package for SOSConcurrence formsNeil signature | Dec 1 - Dec 8, 2010Dec 13, 2010Dec 14, 2010 |
| Prepare for public comment | Rulemaking documents sent to SOSNotice published in SOS bulletin | **Dec 15, 2010**Jan 3, 2011 |
| Public comment and hearings | Public comment period (est.)Public hearings (est.) | Jan 3 - Feb 18, 2011Feb 1 - Feb 11, 2011 |
| Response to public comment and final proposed rules | Response to public commentfinal proposed rulessupporting documentsimplementation plan | April 29, 2011 |
| EQC informational presentation |  staff report and presentation EQC Meeting | March 22, 2011April 29 – 30, 2011 |
| EQC action item | Staff report and presentation EQC meeting and rule adoption | May 10, 2011**June 16 -17, 2011** |
| Submit revised standards to EPA for approval | AG certification of rule adoptionrules filed with SOSsubmittal package to EPA | July 22, 2011 |
| EPA action item | CWA requires EPA action within 90 days of submission (est.) | Oct 20, 2011 |