| Action Items for Rulemaking | Deliverables | Due Date |
| --- | --- | --- |
| NPDES PACKAGE |  |  |
| NPDES Issue Paper | Final Issue Paper | Dec. 14 |
| (Andrea) | Internal Review (IRT/PMT/AG/EPA) | Nov 17 |
| [Intake Credit Rule, Human Health Compliance Sched., Variances, MDV, Background Pollutant Allowance, General Permit, Restoration Standards, Delayed Implementation] | Revisions for manager approval | Nov. 24 |
|  | EMT Review | Dec. 1 - 8 |
|  | Neil Concurrence | Dec. 14 |
|  | Response to public comments | April 29, 2011 |
|  | Final for June EQC Action | XXXX |
| Intake Credit Rule | Final rule language | Dec. 14 |
| (Spencer) | Final Issue Paper | Dec. 14 |
|  | Develop ICR piece in RPA IMD | Aug. 2011 |
| Human Health Compliance Schedule (Jane) | Final Issue Paper | Dec. 14 |
| Variance Provision | Final rule language | Dec. 14 |
| (Andrea) | Final Issue Paper | Dec. 14 |
| (Jane) | Variance Workshop w/ EPA | Dec. 6-7 |
|  | Variance Symposium w/ stakeholders | Week of Jan 24? |
|  | IMD outline for internal Review/EPA Share | XXXX |
|  | Draft final IMD outline | Dec. 29 |
|  | Draft IMD narrative | March 2011 |
|  | Draft Final IMD narrative | May 2011 |
|  | Final IMD narrative | August 2011 |
| Multiple Discharger Variance (Andrea) | Final Issue Paper | Dec. 14 |
| Background Pollutant Allowance | Final rule language | Dec. 14 |
| (Deb) | Final Issue Paper | Dec. 14 |
| (?) | IMD outline for internal Review/EPA Share | XXXX |
|  | Draft final IMD outline | Dec. 29 |
|  | Draft IMD narrative | March 2011 |
|  | Draft Final IMD narrative | May 2011 |
|  | Final IMD narrative/Update RPA IMD | August 2011 |
| General Permit (Spencer) | Final Issue Paper | Dec. 14 |
| Restoration Standards (Andrea) | Final Issue Paper | Dec. 14 |
| Delayed Implementation (Andrea) | Final Issue Paper | Dec. 14 |
| Human Health Criteria Table | Final rule language/criteria | Dec. 14 |
| (Andrea) | Final Issue Paper | Dec. 14 |
|  | Internal Review (IRT/PMT/AG/EPA) | Nov 17 |
|  | Revisions for manager approval | Nov. 24 |
|  | EMT Review | Dec. 1 - 8 |
|  | Neil Concurrence | Dec. 14 |
|  | Response to public comments | April 29, 2011 |
|  | Final for June EQC Action | XXXX |
| NON-NPDES PACKAGE |  |  |
| Div. 41 and 42 Revisions | Final rule language | Dec. 14 |
| (Koto and Gene) | Final Issue Paper | Dec. 14 |
|  | Internal Review of IP (IRT/PMT/AG/EPA) | Nov. 17 |
|  | Revisions for manager approval | Nov. 24 |
|  | EMT Review | Dec. 1 - 8 |
|  | Neil Concurrence | Dec. 14 |
|  | Response to public comments | April 29, 2011 |
|  | Final for June EQC Action | XXXX |
| Implementation-Ready TMDLs | Final Issue Paper | Dec. 14 |
| (Koto and Gene) | Internal Review of IP (IRT/PMT/AG/EPA) | Nov. 17 |
|  | IMD outline for internal Review/EPA Share | XXXX |
|  | Draft final IMD outline | Dec. 29 |
|  | Draft IMD narrative | March 2011 |
|  | Draft Final IMD narrative | May 2011 |
|  | Final IMD narrative | August 2011 |
| Source Control (Tiffany) | Final Issue Paper | Dec. 14 |
| Antidegradation | Final Issue Paper | Dec. 14 |
| (Deb) | Draft Update Antideg IMD NPS Chapter | June 2011 |
|  | Internal Review/ EPA Share IMD | XXXX |
|  | Final IMD | Dec. 2011 |
| Sediment and Toxics (Josh) | Final Issue Paper | Dec. 14 |
| RULEMAKING PACKAGE |  |  |
| Proposed Rulemaking Package (Andrea + input from other rule writers) | Fiscal and Economic Impact Land Use Evaluation Statement Relationship to Federal Requirements Rule Implementation Plan Checklist and Implementation Plan Strikeout Rule Revisions Other Supporting Documents (Issue Papers, etc.) | Oct. 27, 2010 |
| Proposed Rulemaking Package for IRT, PMT, budget, OCO, rule coordinators, AG, and EPA Review (Andrea + input from other rule writers) | -Proposed Rulemaking package for SOS review (see above) -IRT Meeting -Revised rule language/issue papers for manager’s review before going to EMT | Nov. 3 - 17, 2010 Nov. 10 Nov. 24 |
| Schedule Hearings and Public Comment (Andrea, Stephanie, Martha) | -Portland, Eugene, Medford, Coos Bay, Pendleton, Bend, and Ontario | Nov. 26 |
| Stakeholder Meeting | Present rulemaking package | Dec. 2 |
| Proposed Rulemaking Package for EMT opt in review + Maggie V., Joannie, and Jim Roys (Andrea + input from other rule writers) | -Final rule package for SOS + Proposed Rulemaking Announcement and Notice of Proposed Rulemaking Hearing -Meeting with Neil -EMT concurrence forms due -Neil signature | Dec. 1 - 8, 2010 Dec. 10 or 13 Dec. 13 Dec. 14 |
| Prepare for Public Comment (Andrea and Stephanie) | -Rulemaking documents sent to SOS -Post rulemaking materials + supporting docs to website -Notice published in SOS bulletin and gov delivery -Public comment period -Public Hearings | Dec. 15, 2010 Dec. 29, 2010 Jan. 3, 2011 Jan. 3 – Feb. 18 Feb. 1 – Feb. 11 |
| Response to Public Comment and Final Proposed Rules (Andrea + input from other rule writers) | Response to public comment Final proposed rules Supporting documents Implementation Plan | April 29, 2011 |
| Submit Revised Standards to EPA for Approval (Andrea) | AG certification of rule adoption Rules filed with SOS Submittal package to EPA EPA action item | July 22, 2011 Oct. 20, 2011 |
| EQC MEETINGS |  |  |
| EQC Information Presentation (Koto and others) | Staff Reports and PPTs | Nov. 12, 2010 (sent out Nov. 22) |
|  | Director’s Dialogue | Nov. 22, 2010 |
|  | Meeting (Portland) | Dec. 9 – 10, 2010 |
| EQC Information Presentation | Staff Reports and PPTs | Jan. 13, 2011 (?) |
| (Deb and others) | Director’s Dialogue | Feb. 3, 2011 (?) |
|  | Meeting (?) | Feb. 17 – 18, 2011 |
| EQC Information Presentation | Staff Reports and PPTs | March 24, 2011? |
| (Deb and others) | Director’s Dialogue | April 7, 2011? |
|  | Meeting (?) | April 21 – 22, 2011? |
| EQC Action Item | Staff Reports and PPTs | May 10, 2011(?) |
| (Deb and others) | Director’s Dialogue | May 23, 2011(?) |
|  | Meeting (?) | June 16 – 17, 2011 (?) (plan for 1 full day) |