| Action Items for Rulemaking | Deliverables | Due Date |
| --- | --- | --- |
| NPDES PACKAGE | | |
| NPDES Issue Paper | Final Issue Paper | Dec. 14 |
| *(Andrea)* | Internal Review (IRT/PMT/AG/EPA) | Nov 17 |
| [Intake Credit Rule, Human Health Compliance Sched., Variances, MDV, Background Pollutant Allowance, General Permit, Restoration Standards, Delayed Implementation] | Revisions for manager approval | Nov. 24 |
|  | EMT Review | Dec. 1 - 8 |
|  | Neil Concurrence | Dec. 14 |
|  | Response to public comments | April 29, 2011 |
|  | Final for June EQC Action | XXXX |
|  |  |  |
| Intake Credit Rule | Final rule language | Dec. 14 |
| *(Spencer)* | Final Issue Paper | Dec. 14 |
|  | Develop ICR piece in RPA IMD | Aug. 2011 |
|  |  |  |
| Human Health Compliance Schedule  *(Jane)* | Final Issue Paper | Dec. 14 |
|  |  |  |
| Variance Provision | Final rule language | Dec. 14 |
| *(Andrea)* | Final Issue Paper | Dec. 14 |
| *(Jane)* | Variance Workshop w/ EPA | Dec. 6-7 |
|  | Variance Symposium w/ stakeholders | Week of Jan 24? |
|  | IMD outline for internal Review/EPA Share | XXXX |
|  | Draft final IMD outline | Dec. 29 |
|  | Draft IMD narrative | March 2011 |
|  | Draft Final IMD narrative | May 2011 |
|  | Final IMD narrative | August 2011 |
|  |  |  |
| Multiple Discharger Variance  *(Andrea)* | Final Issue Paper | Dec. 14 |
|  |  |  |
| Background Pollutant Allowance | Final rule language | Dec. 14 |
| *(Deb)* | Final Issue Paper | Dec. 14 |
| *(?)* | IMD outline for internal Review/EPA Share | XXXX |
|  | Draft final IMD outline | Dec. 29 |
|  | Draft IMD narrative | March 2011 |
|  | Draft Final IMD narrative | May 2011 |
|  | Final IMD narrative/Update RPA IMD | August 2011 |
|  |  |  |
| General Permit  *(Spencer)* | Final Issue Paper | Dec. 14 |
|  |  |  |
| Restoration Standards  *(Andrea)* | Final Issue Paper | Dec. 14 |
|  |  |  |
| Delayed Implementation  *(Andrea)* | Final Issue Paper | Dec. 14 |
|  |  |  |
| Human Health Criteria Table | Final rule language/criteria | Dec. 14 |
| *(Andrea)* | Final Issue Paper | Dec. 14 |
|  | Internal Review (IRT/PMT/AG/EPA) | Nov 17 |
|  | Revisions for manager approval | Nov. 24 |
|  | EMT Review | Dec. 1 - 8 |
|  | Neil Concurrence | Dec. 14 |
|  | Response to public comments | April 29, 2011 |
|  | Final for June EQC Action | XXXX |
|  |  |  |
| NON-NPDES PACKAGE | | |
| Div. 41 and 42 Revisions | Final rule language | Dec. 14 |
| *(Koto and Gene)* | Final Issue Paper | Dec. 14 |
|  | Internal Review of IP (IRT/PMT/AG/EPA) | Nov. 17 |
|  | Revisions for manager approval | Nov. 24 |
|  | EMT Review | Dec. 1 - 8 |
|  | Neil Concurrence | Dec. 14 |
|  | Response to public comments | April 29, 2011 |
|  | Final for June EQC Action | XXXX |
|  |  |  |
| Implementation-Ready TMDLs | Final Issue Paper | Dec. 14 |
| *(Koto and Gene)* | Internal Review of IP (IRT/PMT/AG/EPA) | Nov. 17 |
|  | IMD outline for internal Review/EPA Share | XXXX |
|  | Draft final IMD outline | Dec. 29 |
|  | Draft IMD narrative | March 2011 |
|  | Draft Final IMD narrative | May 2011 |
|  | Final IMD narrative | August 2011 |
|  |  |  |
| Source Control  *(Tiffany)* | Final Issue Paper | Dec. 14 |
|  |  |  |
| Antidegradation | Final Issue Paper | Dec. 14 |
| *(Deb)* | Draft Update Antideg IMD NPS Chapter | June 2011 |
|  | Internal Review/ EPA Share IMD | XXXX |
|  | Final IMD | Dec. 2011 |
|  |  |  |
| Sediment and Toxics  *(Josh)* | Final Issue Paper | Dec. 14 |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
| RULEMAKING PACKAGE | | |
| Proposed Rulemaking Package  *(Andrea + input from other rule writers)* | Fiscal and Economic Impact  Land Use Evaluation Statement  Relationship to Federal Requirements  Rule Implementation Plan Checklist and Implementation Plan  Strikeout Rule Revisions  Other Supporting Documents (Issue Papers, etc.) | Oct. 27, 2010 |
|  |  |  |
| Proposed Rulemaking Package for IRT, PMT, budget, OCO, rule coordinators, AG, and EPA Review  *(Andrea + input from other rule writers)* | -Proposed Rulemaking package for SOS review (see above)  -IRT Meeting  -Revised rule language/issue papers for manager’s review before going to EMT | Nov. 3 - 17, 2010  Nov. 10  Nov. 24 |
|  |  |  |
| Schedule Hearings and Public Comment  *(Andrea, Stephanie, Martha)* | -Portland, Eugene, Medford, Coos Bay,  Pendleton, Bend, and Ontario | Nov. 26 |
|  |  |  |
| Stakeholder Meeting | Present rulemaking package | Dec. 2 |
|  |  |  |
| Proposed Rulemaking Package for EMT opt in review + Maggie V., Joannie, and Jim Roys  *(Andrea + input from other rule writers)* | -Final rule package for SOS  + Proposed Rulemaking Announcement and Notice of Proposed Rulemaking Hearing  -Meeting with Neil  -EMT concurrence forms due  -Neil signature | Dec. 1 - 8, 2010  Dec. 10 or 13  Dec. 13  Dec. 14 |
|  |  |  |
| Prepare for Public Comment  *(Andrea and Stephanie)* | -Rulemaking documents sent to SOS  -Post rulemaking materials + supporting docs to website  -Notice published in SOS bulletin and gov delivery  -Public comment period  -Public Hearings | **Dec. 15, 2010**  Dec. 29, 2010  Jan. 3, 2011  Jan. 3 – Feb. 18  Feb. 1 – Feb. 11 |
|  |  |  |
| Response to Public Comment and Final Proposed Rules  *(Andrea + input from other rule writers)* | Response to public comment  Final proposed rules  Supporting documents  Implementation Plan | April 29, 2011 |
|  |  |  |
| Submit Revised Standards to EPA for Approval  *(Andrea)* | AG certification of rule adoption  Rules filed with SOS  Submittal package to EPA  EPA action item | July 22, 2011  Oct. 20, 2011 |
| EQC MEETINGS | | |
| EQC Information Presentation  *(Koto and others)* | Staff Reports and PPTs | Nov. 12, 2010  *(sent out Nov. 22)* |
|  | Director’s Dialogue | Nov. 22, 2010 |
|  | Meeting (Portland) | **Dec. 9 – 10, 2010** |
|  |  |  |
| EQC Information Presentation | Staff Reports and PPTs | Jan. 13, 2011 (?) |
| *(Deb and others)* | Director’s Dialogue | Feb. 3, 2011 (?) |
|  | Meeting (?) | **Feb. 17 – 18, 2011** |
|  |  |  |
| EQC Information Presentation | Staff Reports and PPTs | March 24, 2011? |
| *(Deb and others)* | Director’s Dialogue | April 7, 2011? |
|  | Meeting (?) | **April 21 – 22, 2011?** |
|  |  |  |
| EQC Action Item | Staff Reports and PPTs | May 10, 2011(?) |
| *(Deb and others)* | Director’s Dialogue | May 23, 2011(?) |
|  | Meeting (?) | **June 16 – 17, 2011** (?)  *(plan for 1 full day)* |