# WQS HH Toxics Rule:  Rulemaking Package Status

November 5, 2010 DRAFT

| Product | Who | Status/Target Date | Notes/Issues to be Resolved |
| --- | --- | --- | --- |
| Issue Papers |  |  |  |
| Criteria Issue Paper | Andrea | IRT Draft Complete EMT Draft 12/1/2010 |  |
| NPDES Issue Paper Intake Credits Variances Background Pollutant Allowance Other options considered | Andrea /Deb/Annette? | IRT Draft Complete EMT Draft 12/1/2010 | - Respond to rulemaking workgroup comments/letters in EMT Draft |
| Implementation-Ready TMDL issue paper | Koto | IRT Draft Complete EMT Draft 12/1/2010 | - Respond to rulemaking workgroup comments/letters in EMT Draft |
| Div. 41&42 Issue Paper | Koto | IRT Draft Complete EMT Draft 12/1/2010 | - Respond to rulemaking workgroup comments/letters in EMT Draft |
| Sediment | Josh | IRT Draft Complete |  |
| Source Control | Tiffany/Karen | IRT Draft Complete EMT Draft 12/1/2010 | - Respond to rulemaking workgroup comments/letters in EMT Draft |
| Antidegradation | Deb | IRT Draft Complete EMT Draft 12/1/2010 | - Identify timeframe for IMD development - Respond to rulemaking workgroup comments/letters in EMT Draft |
| Rulemaking Package (Document containing reg language only) | Andrea | IRT Draft Complete EMT Draft 12/1/2010 |  |
| Rulemaking Docs |  |  |  |
| Fiscal and economic form | Andrea | IRT Draft Complete EMT Draft 12/1/2010 |  |
| Land Use Evaluation | Andrea | IRT Draft Complete EMT Draft 12/1/2010 |  |
| Implementation Plan | Andrea | IRT Draft Complete EMT Draft 12/1/2010 |  |
| Relationship to federal requirements | Andrea | IRT Draft Complete EMT Draft 12/1/2010 |  |
| Internal Management Directives |  |  |  |
| Variances and Pollutant Reduction Plans Symposium (EPA/DEQ) Detailed Outline Symposium (EPA/DEQ/Stakeholders) Draft Final Draft | Jane/Andrea | Dec 6-7, 2010 Dec 31, 2010 Jan? 2011 March 2011 May 2011 | Symposium with stakeholders to be scheduled—need to fit in amongst public hearing dates |
| Background Pollutant Allowance (part of RPA IMD?) If separate Detailed Outline Draft Final Draft |  | Dec 31, 2010 March 2011 May 2011 |  |
| Implementation-Ready TMDLs Detailed Outline Draft Final Draft | Koto | Dec 31, 2010 March 2011 May 2011 |  |
| Intake Credit Updates to RPA IMD | Spencer |  |  |
| Antidegradation Implementation for NPS—add chapter to existing IMD | S&A Section/WM Section | Draft June 2011 Final 6 months after EQC adoption of rule | Add chapter to existing IMD describing how DEQ would implement the antideg policy for NPS. Dates for draft and final IMDs are from the recommendation contained in the latest (5/2010) antideg issue paper |
| Public Hearings (1/18/2011-2/7/2011) Candidate Locations: Portland Pendleton Medford Coos Bay Bend Eugene Astoria? Ontario/Burns? | Andrea/Stephanie B | Scheduled by 12/10 | Given both point source and nonpoint source concerns, and interest among people concerned with fish consumption, the locations noted are being considered |