WQS HH Toxics Rule: Rulemaking Package Status

November 5, 2010 DRAFT

| **Product** | **Who** | **Status/Target Date** | **Notes/Issues to be Resolved** |
| --- | --- | --- | --- |
| **Issue Papers** |
| Criteria Issue Paper | Andrea | IRT Draft CompleteEMT Draft 12/1/2010 |  |
| NPDES Issue PaperIntake CreditsVariancesBackground Pollutant AllowanceOther options considered | Andrea /Deb/Annette? | IRT Draft CompleteEMT Draft 12/1/2010 | * Respond to rulemaking workgroup comments/letters in EMT Draft
 |
| Implementation-Ready TMDL issue paper | Koto  | IRT Draft CompleteEMT Draft 12/1/2010 | * Respond to rulemaking workgroup comments/letters in EMT Draft
 |
| Div. 41&42 Issue Paper | Koto  | IRT Draft CompleteEMT Draft 12/1/2010 | * Respond to rulemaking workgroup comments/letters in EMT Draft
 |
| Sediment | Josh  | IRT Draft Complete |  |
| Source Control | Tiffany/Karen | IRT Draft CompleteEMT Draft 12/1/2010 | * Respond to rulemaking workgroup comments/letters in EMT Draft
 |
| Antidegradation | Deb  | IRT Draft CompleteEMT Draft 12/1/2010 | * Identify timeframe for IMD development
* Respond to rulemaking workgroup comments/letters in EMT Draft
 |
| **Rulemaking Package** (Document containing reg language only) | Andrea  | IRT Draft CompleteEMT Draft 12/1/2010 |  |
|  |  |  |  |
| **Rulemaking Docs** |
| Fiscal and economic form | Andrea | IRT Draft CompleteEMT Draft 12/1/2010 |  |
| Land Use Evaluation | Andrea | IRT Draft CompleteEMT Draft 12/1/2010 |  |
| Implementation Plan | Andrea | IRT Draft CompleteEMT Draft 12/1/2010 |  |
| Relationship to federal requirements | Andrea | IRT Draft CompleteEMT Draft 12/1/2010 |  |
|  |  |  |  |
| **Internal Management Directives** |
| Variances and Pollutant Reduction PlansSymposium (EPA/DEQ)Detailed OutlineSymposium (EPA/DEQ/Stakeholders)DraftFinal Draft | Jane/Andrea | Dec 6-7, 2010Dec 31, 2010Jan? 2011March 2011May 2011 | Symposium with stakeholders to be scheduled—need to fit in amongst public hearing dates |
| Background Pollutant Allowance (part of RPA IMD?)*If separate*Detailed OutlineDraftFinal Draft |  | Dec 31, 2010March 2011May 2011 |  |
| Implementation-Ready TMDLs Detailed OutlineDraftFinal Draft | Koto | Dec 31, 2010March 2011May 2011 |  |
| Intake Credit Updates to RPA IMD | Spencer |  |  |
| Antidegradation Implementation for NPS—add chapter to existing IMD | S&A Section/WM Section | Draft June 2011 Final 6 months after EQC adoption of rule | Add chapter to existing IMD describing how DEQ would implement the antideg policy for NPS.Dates for draft and final IMDs are from the recommendation contained in the latest (5/2010) antideg issue paper  |
|  |  |  |  |
| **Public Hearings (1/18/2011-2/7/2011)**Candidate Locations:PortlandPendletonMedfordCoos BayBendEugeneAstoria?Ontario/Burns? | Andrea/Stephanie B | Scheduled by 12/10 | Given both point source and nonpoint source concerns, and interest among people concerned with fish consumption, the locations noted are being considered |