# Rule Implementation Plan Checklist

EMT 5/01

Date	Date

Planned		Completed	N.A.

| 1. | Nov 2010 | _________ _____ | Develop rule and implementation plan. Include forms and templates. |
| --- | --- | --- | --- |
|  |  |  | Staff assigned: __Debra Sturdevant and Spencer Bohaboy_______ |
| 2. | _________ | _________ _X__ | Develop new enforcement guidance. |
|  |  |  | Staff assigned: ___NA_________________ |
| 3. | _________ | _________ _X__ | Division 12 rules changes. |
|  |  |  | Staff assigned: ____NA________________ |
| 4. | Aug. 30, 10 | _________ _____ | An FTE analysis must be completed in conjunction with: |
|  |  |  | Date: Date: Date: PMT __July 27__ Lab August 30 IT ___NA___ MSD __NA_______ Enf __NA_______ |
|  |  |  | Staff assigned: _Raeann Haynes___________________ |
| 5. | _________ | _________ _X_ | Additional staff will be hired for assigned work. |
|  |  |  | How many? ____________________ |
| 6. | _________ | _________ _X__ | Additional support staff hired for assigned work. |
|  |  |  | How many? ____________________ |
| 7. | _________ | _________ _X__ | If work going to existing staff, date staff workload adjusted to accommodate new work. |
| 8. | July 28, 10 | July 27, 10 _____ | Date PMT agreed this work can be undertaken without additional resources. |
| 9. | _________ | Oct, 2008_ _____ | Discussions with EMT during topic review. |
| 10. | _________ | _________ _X__ | Develop tracking tools or modify existing database to account for this work. Staff assigned: ____________________ Who will be responsible for ongoing work? |
|  |  |  | Staff assigned: ____________________ |
| 11. | March, 2011 | _________ _____ | Training plan and schedule developed. Training will be conducted for staff and managers by same team that wrote rule and implementation plan. This plan should be detailed enough to show why we are doing this new rule/policy; What steps staff need to go through to implement this new activity (e.g., in conjunction with an existing inspection, a separate inspection is needed, etc.); copies of any templates/forms/enforcement guidance; and, a schedule for providing the training to staff. |
| 12. | Sept, 2011 | _________ _____ | Date this training packet was placed on the intranet so staff can refer to it as needed. |
|  |  |  | Staff assigned: Annette Liebe |
| 13. | Dec, 2010 | _________ _____ | Communication strategy developed. Staff assigned: _Debra Sturdevant___________ Who to call if questions: _Debra Sturdevant______________ |