| Action Items for Rulemaking | Deliverables | Send Out | Due Date |
| --- | --- | --- | --- |
| Assumptions: -Stephanie B. can spend a significant amount of time on organizing comments -Deb and Spencer can spend time responding to comments -Jane with permit writers on workgroup can complete variance IMD -Koto has time to work on TMDL IMD -Does not include time spent on responding to Congressional inquiries, etc. on the rule -Assumes the FCR is not revised |  |  |  |
| RULEMAKING PACKAGE |  |  |  |
| Hearings (Andrea, Stephanie) | Transcriptions (9) (Stephanie/Contractor) Officer Reports (9) (Andrea) To Do: Medford and Portland | Done | May 12 |
| Draft IMDs (Jane, Koto, other permit writers) | Variances—Jane working with others TMDLs—sent out to regional staff for input -Spencer to incorporate BPA and Intake Credits into “Phase II” of the RPA IMD—i.e. after June |  | For June EQC |
| Process Comments (Stephanie) | -Log in each commenter on master spreadsheet -Electronic and 5 hard copy files of all comments received | Ongoing | April 22, 2011 |
| Sort Comments and Assign Responders (Cheryl) | -Review logged in comments and copy/paste comments into relevant sections of the Response to Comments document -Re-organize/Lump as necessary -Strategize on how to organize and respond to form letters | Ongoing | April 22--substantive comments *May 5--rest of minor/form letter comments * To meet this deadline, RTC document might not reflect every single comment |
| Draft Response to Comments and Proposed Rules (Andrea, Koto, Spencer, Deb) | -Address additional comments per Cheryl’s additions -Simultaneously elevate issues as needed for Neil discussion -Simultaneously revise and finalize rules if necessary (e.g. BPA) |  | *May 3, 2011 *Assumes Spencer can finish drafting the BPA AND review and respond to permitting comments the week of April 25 |
| Draft Staff Report (review by Wigal, Foster, Liebe, Clipper, Mullane, IRT) | -Review Response to Comment, Revised Rules, Staff Report -Staff work on updating issue papers during this manager review time -Schedule a meeting w/ IRT members around May 5 -get RTC to Michele for formatting for EMT review (probably don’t need) | May 4, 2011 May 6, but probably later | May 9, 2011 |
| Draft Staff Report (review by EMT opt-ins, Larry K., Maggie V., Stephanie Clark for Dick, Joanie, etc. ) | - EQC Staff Report – with the following attachments: Proposed rule revisions (strikeout/underline; Summary of Public Comments and Agency Responses; Presiding Officer’s Report; Statement of Need and Fiscal and Economic Impact (from notice package); Land Use Evaluation Statement (from notice package); Relationship to Federal Requirements Questions (from notice package); Advisory Committee Membership and Report; issue papers - Rule Implementation Plan Checklist and Plan - Facilitator’s Report (Donna Silverberg) May 18 due *Staff report and other rulemaking docs mostly complete *Stephanie C. will get docs into EQC format | May 13, 2011 | May 19, 2011 |
| Final Staff Report (for Dick’s sig) | See above Everything final | May 24, 2011 | May 26, 2011 |
| Final Staff Report (to EQC) | See above, plus Accompanying Materials: -Memo describing MOU with ODF and MOA with ODA -Variance and TMDL IMDs -Facilitator’s Report - Issue Papers |  | May 26, 2011 (Stephanie C. needs to send Report to EQC by May 27) |
| Submit Revised Standards to EPA for Approval (Andrea) | AG certification of rule adoption Rules filed with SOS Submittal package to EPA EPA action item |  | July 21, 2011 Oct. 20, 2011 |
| Final IMDs (Jane, Koto, Deb, Andrea, Spencer, other permit writers??) | Variances TMDLs Antidegradation |  | See Timeline for Follow Up Action Items Doc |
| EQC MEETINGS |  |  |  |
| EQC Information Presentation | Staff Reports and PPTs |  | March 17, 2011 |
| (Deb and others) | Director’s Dialogue |  | April 7, 2011 |
|  | Meeting |  | April 21 – 22, 2011 |
| EQC Action Item | Staff Reports and PPTs |  | May 12, 2011 |
| (Deb and others) | Director’s Dialogue |  | June 2, 2011 |
|  | Meeting |  | June 16, 2011 |