Milestones and Estimated Timeline:

Human Health Criteria and Permitting Tools Rulemaking

| Milestone | Deliverable | Estimated Completion Date |
| --- | --- | --- |
| Start Rulemaking Proposal | Briefing at ODAM meeting | October 2008 |
| Convene and work with stakeholder rulemaking group | Draft proposed rules | December 2008-November 2009 |
| EQC Director’s Dialogue | Briefing w Dick, memo | October 2009 |
| Obtain input on proposed rules from Rulemaking Workgroup & Toxics Stakeholder Group | Draft proposed rules Supporting documents | November 2009 |
| Develop draft proposed rules and supporting documents | Draft proposed rules Supporting documents | December 2009 |
| Develop Draft Implementation Plan | Draft implementation plan | January 2010 |
| Informational presentation to EQC | EQC staff report and presentation on draft proposed rules & implementation plan | February 2010 |
| Prepare for public comment | Rulemaking documents Notice published in SOS bulletin | March 15, 2010 April 1, 2010 |
| Public comment and hearings | Public hearings Hearing Officer reports Response to comments | April 2010 May 2010 June 2010 |
| Finalize proposed rules, support documents and implementation plan | Final proposed rules Supporting documents | July 2010 |
| EQC Info Item EQC Action Item | EQC staff report, presentation EQC staff report, rule adoption | August 2010 October 2010 |
| Submit revised standards to EPA for approval | AG certification of rule adoption Rules filed w SOS Letter of submittal, rules as filed and supporting documents Letter of receipt from EPA | December 2010 |

Rules included in this review:  1) water quality toxics criteria for human health to protect the consumption of fish and water based on a new fish consumption rate of 175 grams per day, and 2) provisions related to the implementation of the new criteria in CWA regulatory programs, particularly NPDES permits.

The completion dates above were estimated assuming that from July, 2009 forward there will be 2 standards staff and part time assistance from a permit staff person working on this project.