# Rule Implementation Plan Checklist

EMT 5/01

Date	Date

Planned		Completed	N.A.

| 1. | 10/27/10_ | 11/03/10_ ____ | Develop rule and implementation plan. Include forms and templates. |
| --- | --- | --- | --- |
|  |  |  | Staff assigned: _Andrea Matzke___________________ |
| 2. | _________ | _________ _X__ | Develop new enforcement guidance. |
|  |  |  | Staff assigned: ___NA_________________ |
| 3. | _________ | _________ _X__ | Division 12 rules changes. |
|  |  |  | Staff assigned: ____NA________________ |
| 4. | 10/04/10__ | _________ _____ | An FTE analysis must be completed in conjunction with: |
|  |  |  | Date: Date: Date: PMT __09/20/10__ Lab 09/20/10 IT ___NA___ MSD __NA_______ Enf __NA_______ |
|  |  |  | Staff assigned: _Andrea Matzke and Koto Kishida___________________ |
| 5. | _________ | _________ _X_ | Additional staff will be hired for assigned work. |
|  |  |  | How many? ____________________ |
| 6. | _________ | _________ _X__ | Additional support staff hired for assigned work. |
|  |  |  | How many? ____________________ |
| 7. | _TBD____ | _________ ____ | If work going to existing staff, date staff workload adjusted to accommodate new work. |
| 8. | _10/04/10__ | 11/17/10__ __ | Date PMT agreed this work can be undertaken without additional resources. |
| 9. | _________ | 11/02/10 (ongoing)__ | Discussions with EMT during topic review. |
| 10. | _________ | _________ X___ | Develop tracking tools or modify existing database to account for this work. Staff assigned: ____________________ Who will be responsible for ongoing work? |
|  |  |  | Staff assigned: ____________________ |
| 11. | 08/11____ | _________ _____ | Training plan and schedule developed. Training will be conducted for staff and managers by same team that wrote rule and implementation plan. This plan should be detailed enough to show why we are doing this new rule/policy; What steps staff need to go through to implement this new activity (e.g., in conjunction with an existing inspection, a separate inspection is needed, etc.); copies of any templates/forms/enforcement guidance; and, a schedule for providing the training to staff. |
| 12. | _10/11___ | _________ _____ | Date this training packet was placed on the intranet so staff can refer to it as needed. |
|  |  |  | Staff assigned: ____________________ |
| 13. | _________ | _02/25/11___ ____ | Communication strategy developed. Staff assigned: Andrea Matzke___ Who to call if questions: ____________________ |