**Draft**

**Milestones and Estimated Timeline:**

**Human Health Criteria and Permitting Tools Rulemaking**

|  |  |  |
| --- | --- | --- |
| **Milestone** | **Deliverable** | **Estimated Completion Date** |
| Start Rulemaking Proposal | Briefing at ODAM meeting | October 2008  |
| Convene and work with stakeholder rulemaking group | Draft proposed rules | December 2008-February 2010 |
| EQC Director’s Dialogue | Briefing w Dick, memo | October 2009 |
| Obtain input on proposed rules from Rulemaking Workgroup & Toxics Stakeholder Group | Draft proposed rules Supporting documents | February 2010 |
| Informational presentation to EQC | EQC staff report and presentation  on status of proposed rules &  implementation plan | February 18, 2010 |
| Develop draft proposed rules and supporting documents | Draft proposed rules Supporting documents | March 2010 |
| Develop Draft Implementation Plan | Draft implementation plan | March 2010 |
| Prepare for public comment | Rulemaking documents for SOSNotice published in SOS bulletin | **April 15, 2010**May 1, 2010 |
| Public comment and hearings | Public comment period (est.)Public hearings (est.)Response to comments | May 3-June 18, 2010May 18-June 11 2010July 2010 |
| Finalize proposed rules, support documents and implementation plan | Final proposed rulesSupporting documents | August 2010 |
| EQC Action Item | Staff reportEQC rule adoption | Sept. 13, 2010**October 21, 2010** |
| Submit revised standards to EPA for approval | AG certification of rule adoptionRules filed with SOSLetter of submittal, rules as filed and supporting documentsLetter of receipt from EPA | **Nov./Dec. 2010** |