Draft

Milestones and Estimated Timeline:

Human Health Criteria and Permitting Tools Rulemaking

| Milestone | Deliverable | Estimated Completion Date |
| --- | --- | --- |
| Start Rulemaking Proposal | Briefing at ODAM meeting | October 2008 |
| Convene and work with stakeholder rulemaking group | Draft proposed rules | December 2008-February 2010 |
| EQC Director’s Dialogue | Briefing w Dick, memo | October 2009 |
| Obtain input on proposed rules from Rulemaking Workgroup & Toxics Stakeholder Group | Draft proposed rules Supporting documents | February 2010 |
| Informational presentation to EQC | EQC staff report and presentation on status of proposed rules & implementation plan | February 18, 2010 |
| Develop draft proposed rules and supporting documents | Draft proposed rules Supporting documents | March 2010 |
| Develop Draft Implementation Plan | Draft implementation plan | March 2010 |
| Prepare for public comment | Rulemaking documents for SOS Notice published in SOS bulletin | April 15, 2010 May 1, 2010 |
| Public comment and hearings | Public comment period (est.) Public hearings (est.) Response to comments | May 3-June 18, 2010 May 18-June 11 2010 July 2010 |
| Finalize proposed rules, support documents and implementation plan | Final proposed rules Supporting documents | August 2010 |
| EQC Action Item | Staff report EQC rule adoption | Sept. 13, 2010 October 21, 2010 |
| Submit revised standards to EPA for approval | AG certification of rule adoption Rules filed with SOS Letter of submittal, rules as filed and supporting documents Letter of receipt from EPA | Nov./Dec. 2010 |