| Action Items to Prepare for February RWG Meeting |  |  |  |  |
| --- | --- | --- | --- | --- |
| WHAT | ADDITIONAL RWG DISCUSSION | RESOLUTION | NEXT STEPS | COMMUNICATION |
| Intake Credit Rule | No | -DEQ going forward w/ existing rule language -resolve/justify legal issue: Why doesn’t EPA consider the ICR as a standards provision? EPA: Not a standards provision as long as the WQS is met at the end of pipe or MZ if not WQL. DEQ: need to revise the boilerplate language in the permit to allow intake credits in meeting QBELs. | Call Michael—Deb--DONE E-mail RWG—Melinda/Jannine provide response? Wrap up remaining revisions--Spencer | e-mail RWG w/ final language in a separate e-mail (along w/ other final products) indicating no other action needed--Andrea Work w/ Larry/Jane on permit language--Spencer |
| HHC Schedule | No | -Proceed with Option #3 (separate HHC sched. Language) -Check existing reg lang for consistency -Check gaps for implementation for pre-TMDL timeframe and pre WQS effectiveness | - Confirm Neil wants to proceed w/ this option—Spencer/DONE -Call Michael—Deb -call Nina—Neil/DONE -call Deb Smith (CA) for input on what they’ve been doing—Deb/Jennifer-DONE -revise language to reflect current reg. language, but only refer to HHC -- Spencer | e-mail to RWG w/ final language in a separate e-mail (along w/ other final products) indicating no other action needed--Andrea Find out if Jane needs to review our rule language before going to Larry at DOJ—what’s her role? Andrea/Spencer |
| Variance White Paper and Reg. Language | Yes | -How much detail do we want in the regulation, IMD, and white paper? -Does DEQ want to pursue a MDV? -specific issues and questions that still need resolution | -Meet w/ Nina to get her opinion and discuss her concerns ASAP—Andrea - DONE -Receive RWG comments by 12/18 and incorporate if applicable—Andrea -Incorporate comments, as needed, from IRT meeting on Jan 6 —Andrea -incorporate revisions as needed in the regulation and white paper -Schedule 3 govt meeting for 1/8—Andrea DONE -Issues to bring forward to EPA HQ? IN PROGRESS—waiting to hear on NPS and existing use questions -Develop an options paper for a RWG variance conference call and provide opportunity for comments | -e-mail straw poll: send reg language ASAP to RWG and ask for support (1 – 5). If 4 or 5, explain hesitation/concerns—Andrea-- DONE -Enables DEQ to understand major issues and evaluates ability to address them. -send conference call e-mail to RWG for Jan. 13 or 15—Andrea-DONE |
| Background Concentration Allowance | Yes | -implementation plan for DEQ and EPA approval -what does 5 yr review mean?—Melinda & Jannine (MI MDV—EPA needs to do a review every 5 yrs.) | -ID likely pollutant categories (303d list?)—Deb -develop 1 pg. paper describing process 12/31—Andrea/Melinda-- DONE/IN PROGRESS -EPA to explore justification based on HH use—Melinda DONE/IN PROGRESS -develop multiple pass cooling alternatives 1 pg. paper 12/31—Spencer -determine approximate number of multiple pass cooling systems in OR 12/18—Spencer (sent out e-mail request 12/11) DONE | -call Michael to help w/ ID of pollutants—Deb |