Oregon Water Quality Standards: Non-Point Source Issues

Timeline  updated 11/17

| Phase I: Information & Grounding November 2009 (11/18) | Phase II: Processing January 2010 Date: TBD | Phase III: Producing February 2010 Date: TBD |
| --- | --- | --- |
| Phase I Purpose: Acquaint with People & Tasks and Establish Frame Work for Discussions November 18 – Grounding meeting - Get group grounded in WQS work to date - Clarify purpose and scope - Clarify NPS issues for discussion - Authority - Actions - Determine information needed to accomplish goals - Develop questions to be answered - Set schedule | Phase II Purpose: Review & Discuss Information Relevant to Answer DEQ Questions January – Processing Meeting - Clarify gaps - Suggest ideas for addressing the gaps - Agree on short list of changes for rule - Begin to develop possible strategies | Phase III Purpose: Produce Rule Recommendations to meet EQC Directive February – Final Meeting - Review draft rule language - What are the recommended actions? - What rule changes are needed to support these actions? Mid-February -- Recommendations presented to EQC |

DS Consulting 11-9-09 draft

Additional upcoming stakeholder meetings related to the water quality standards rulemaking:

Date			Group				Topics

December 3, 2009	Toxics Stakeholder Group	Toxics reduction strategy, SB 737 process, Standards implementation

December 9, 2009	Rulemaking Workgroup		Implementation provisions for permitted point sources

January TBD, 2010	Rulemaking Workgroup		Draft proposed criteria table, implementation provisions and nonpoint sources issues