## Database Format
Rule | Task # | Date
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 1 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 2 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 3 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 4 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 5 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 6 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 7 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 8 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 9 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 10 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 11 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 12 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 13 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 14 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 15 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 16 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 17 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 18 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 19 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 20 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 21 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 22 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 23 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 24 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 25 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 26 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 27 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 28 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 29 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 30 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 31 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 32 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 33 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 34 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 35 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 36 | FALSE
AQ-13: NSPS/NESHAP Adoption by Reference for 2012 | 37 | FALSE

## AQ Rulemaking Schedule
Air Quality Worksheet for Rulemaking Schedule
Rule Title: AQ-13: NSPS/NESHAP Adoption by Reference for 2012 |  |  |  |  | Clear All Blackouts
Project Lead & Phone: Jerry Ebersole 503.229.6974 |  |  |  |  | Date | [5 empty] | Day of Week |  |  | Days since previous act
DA | # | DB | Develop Rulemaking | N/A | Option 1 | Calc 1 | Option 2 | Calc 2 | Option 3 | Calc 3 | Option 1 | Option 2 | Option 3 | Option 1 | Option 2 | Option 3
Current Option in Use >
|  |  | Start Rulemaking Proposal | [13 empty] | 1 | Sunday
| NA |  | Route Start Rulemaking Proposal to Section Mgr (at least 5 days prior to DA due date) |  | 2012-01-26 | 2012-01-26 | 2012-03-08 | 2012-03-08 |  |  | Thursday | Thursday |  |  |  |  | 2 | Monday
IN | NA |  | Route Start Rulemaking Proposal to Division Administrator (at least 1 week prior to OD due date) |  | 2012-02-02 | 2012-02-02 | 2012-03-15 | 2012-03-15 |  |  | Thursday | Thursday |  | 7 | 7 |  | 3 | Tuesday
OUT |  | 1 | Submit Start Rulemaking Proposal to OD (9:00 a.m.) |  | 2012-02-09 | 2012-02-09 | 2012-03-29 | 2012-03-29 |  |  | Thursday | Thursday |  | 7 | 14 |  | 4 | Wednesday
APT |  |  | Dry Run Start Rulemaking Proposal w/Division Administrator & others (the Thursday before the EMT meeting) |  | 2012-02-16 | 2012-02-16 | 2012-03-28 | 2012-03-28 |  |  | Thursday | Wednesday |  | 7 | -1 |  | 5 | Thursday
|  | 2 | Start Rulemaking Proposal meeting – EMT |  | 2012-02-23 | 2012-02-23 | 2012-04-05 | 2012-04-05 |  |  | Thursday | Thursday |  | 7 | 8 |  | 6 | Friday
|  |  | Fee Approval | [13 empty] | 7 | Saturday
| NA |  | *Request DAS to approve new & increased fees (at least 30 days prior to filing notice w/SOS or date rule is effective)
|  |  | *Obtain DAS approval or denial of fees (goal = within 30 days of submittal) If DAS Approval is Not Required, DAS must still be notified of Fee Changes. DAS enters all agency fees into a database. | [13 empty] | 1
Draft Notice of Proposed Rulemaking Package
| NA |  | Route draft Notice of Proposed Rulemaking package to Section Mgr (at least 5 days prior to DA due date) |  | 2012-03-07 | 2012-03-07 | 2012-05-07 | 2012-05-07 |  |  | Wednesday | Monday |  |  |  |  | Project Lead & Phone:
IN | NA |  | Route draft Notice of Proposed Rulemaking package to Division Administrator (at least 1 week prior to submitting to reviewers) |  | 2012-03-14 | 2012-03-14 | 2012-05-14 | 2012-05-14 |  |  | Wednesday | Monday |  | 7 | 7 |  | Andrea Curtis 503.229.6866 | Project Lead & Phone: Andrea Curtis 503.229.6866
OUT |  | 3 | Submit draft Notice of Proposed Rulemaking package to reviewers (author) |  | 2012-03-21 | 2012-03-21 | 2012-05-21 | 2012-05-21 |  |  | Wednesday | Monday |  | 7 | 7 |  | Brandy Albertson 503.229.6459 | Project Lead & Phone: Brandy Albertson 503.229.6459
|  |  | Reviewer comments to author |  | 2012-03-28 | 2012-03-28 | 2012-05-30 | 2012-05-30 |  |  | Wednesday | Wednesday |  | 7 | 9 |  | Brian Finneran 503.229.6278 | Project Lead & Phone: Brian Finneran 503.229.6278
|  |  | Final Notice of Proposed Rulemaking Package | [13 empty] | Dave Nordberg 503.229.5519 | Project Lead & Phone: Dave Nordberg 503.229.5519
| NA |  | Route final Notice of Proposed Rulemaking package to Section Mgr (at least 5 days prior to DA due date) |  | 2012-04-06 | 2012-04-06 | 2012-06-06 | 2012-06-06 |  |  | Friday | Wednesday |  | 9 | 7 |  | David Collier 503.229.5177 | Project Lead & Phone: David Collier 503.229.5177
IN | NA |  | Route final Notice of Proposed Rulemaking package to Division Administrator (at least 1 week prior to submitting to reviewers) |  | 2012-04-11 | 2012-04-11 | 2012-06-12 | 2012-06-12 |  |  | Wednesday | Tuesday |  | 5 | 6 |  | Ed Druback 503.667.8414 x55014 | Project Lead & Phone: Ed Druback 503.667.8414 x55014
OUT |  | 4 | Submit final Notice of Proposed Rulemaking package for concurrence review |  | 2012-04-18 | 2012-04-18 | 2012-06-20 | 2012-06-20 |  |  | Wednesday | Wednesday |  | 7 | 8 |  | Gregg Dahmen 503.229.5108 | Project Lead & Phone: Gregg Dahmen 503.229.5108
|  |  | Concurrence reviews due to author |  | 2012-04-25 | 2012-04-25 | 2012-06-26 | 2012-06-26 |  |  | Wednesday | Tuesday |  | 7 | 6 |  | Jerry Coffer 503.731.3050 x229 | Project Lead & Phone: Jerry Coffer 503.731.3050 x229
|  |  | Submit final Notice of Proposed Rulemaking package for Division Administrator for approval |  | 2012-05-04 | 2012-05-04 | 2012-07-02 | 2012-07-02 |  |  | Friday | Monday |  | 9 | 6 |  | Jerry Ebersole 503.229.6974 | Project Lead & Phone: Jerry Ebersole 503.229.6974
IN |  |  | Division Administrator authorizes publication of Notice |  | 2012-05-11 | 2012-05-11 | 2012-07-09 | 2012-07-09 |  |  | Friday | Monday |  | 7 | 7 |  | Karen White-Fallon 503.378.5315 | Project Lead & Phone: Karen White-Fallon 503.378.5315
|  |  | Public Notice, Hearing & Comment | [13 empty] | Kevin Downing 503.229.6549 | Project Lead & Phone: Kevin Downing 503.229.6549
OUT |  | 5 | Send Notice to Secretary of State for Bulletin (by 15th;earlier if weekend/holiday) |  | 2012-05-15 | 2012-05-15 | 2012-08-15 | 2012-08-15 |  |  | Tuesday | Wednesday |  | 4 | 37 |  | Larry Calkins 541.567.8297 x25 | Project Lead & Phone: Larry Calkins 541.567.8297 x25
| NA |  | Send Notice to EPA (at least 45 days prior to hearing) Only applies to SIP rules – make sure the AG’s office has reviewed the rule prior to submitting it to EPA |  | 2012-05-09 | 2012-05-09 | 2012-08-03 | 2012-08-03 |  |  | Wednesday | Friday |  | -6 | -12 |  | Marianne Fitzgerald 503.229.5946 | Project Lead & Phone: Marianne Fitzgerald 503.229.5946
| NA |  | Mail Notice to mailing & e-mail lists (at least 28 days prior to hearing, excluding mailing date, if a SIP rule, must be mailed 30 days prior to hearing) |  | 2012-05-22 | 2012-05-22 | 2012-08-15 | 2012-08-15 |  |  | Tuesday | Wednesday |  | 13 | 12 |  | Melinda Mahoney 503.731.3050 x | Project Lead & Phone: Melinda Mahoney 503.731.3050 x
| NA |  | Publish legal ad in local newspapers (at least 30 days prior to hearing, excluding publication and hearing date) Applies whenever hearings held. |  | 2012-05-22 | 2012-05-22 | 2012-08-23 | 2012-08-23 |  |  | Tuesday | Thursday |  | 0 | 8 |  | Phil Allen 503.229.6904 | Project Lead & Phone: Phil Allen 503.229.6904
| NA | 6 | Notice published in Bulletin (1st of Month; 21 days before effective date) |  | 2012-06-01 | 2012-06-01 | 2012-09-01 | 2012-09-01 |  |  | Friday | Saturday |  | 10 | 9 |  | Rachel Sakata 503.229.5659 | Project Lead & Phone: Rachel Sakata 503.229.5659
| NA | 7 | Public Hearing(s) (At least 15 days after notice in Bulletin, excluding pub date) (An evening time slot will allow the working public a greater opportunity to attend. This is STRONGLY advised!) |  | 2012-06-25 | 2012-06-25 | 2012-09-24 | 2012-09-24 |  |  | Monday | Monday |  | 24 | 23 |  | Sarah Armitage 503.229.5186 | Project Lead & Phone: Sarah Armitage 503.229.5186
| NA | 8 | Public Comment deadline (usually 3 to 7 days after hearing) |  | 2012-07-02 | 2012-07-02 | 2012-09-28 | 2012-09-28 |  |  | Monday | Friday |  | 7 | 4 |  | Shari Jay 503.731.3050 x | Project Lead & Phone: Shari Jay 503.731.3050 x
|  |  | Adopt Rule - EQC | [13 empty] | UNKNOWN AT THIS TIME | Project Lead & Phone: UNKNOWN AT THIS TIME
Draft Final Rulemaking Package
| NA |  | Route draft Final Rulemaking package to Section Mgr (at least 5 days prior to DA due date) |  | 2012-07-13 | 2012-07-13 | 2012-09-11 | 2012-09-11 |  |  | Friday | Tuesday |  | 11 | -17
IN | NA |  | Route draft Final Rulemaking package to Division Administrator (at least 1 week prior to submitting to reviewers) |  | 2012-07-20 | 2012-07-20 | 2012-09-18 | 2012-09-18 |  |  | Friday | Tuesday |  | 7 | 7
OUT |  | 9 | Distribute draft Final Rulemaking package to reviewers (author) |  | 2012-07-30 | 2012-07-30 | 2012-09-25 | 2012-09-25 |  |  | Monday | Tuesday |  | 10 | 7
|  | 10 | Reviewer comments due to author |  | 2012-08-06 | 2012-08-06 | 2012-10-02 | 2012-10-02 |  |  | Monday | Tuesday |  | 7 | 7
Final Rulemaking Package
| NA |  | Route Final Rulemaking package to Section Mgr (at least 5 days prior to DA due date) |  | 2012-08-08 | 2012-08-08 | 2012-10-08 | 2012-10-08 |  |  | Wednesday | Monday |  | 2 | 6
IN | NA |  | Route Final Rulemaking package to Division Administrator (at least 1 week prior to submitting to reviewers) |  | 2012-08-15 | 2012-08-15 | 2012-10-15 | 2012-10-15 |  |  | Wednesday | Monday |  | 7 | 7
OUT |  | 11 | Route Final Rulemaking package for concurrence review |  | 2012-08-24 | 2012-08-24 | 2012-10-22 | 2012-10-22 |  |  | Friday | Monday |  | 9 | 7
|  | 12 | Concurrence reviews due to author |  | 2012-08-31 | 2012-08-31 | 2012-10-26 | 2012-10-26 |  |  | Friday | Friday |  | 7 | 4
IN |  | 13 | Route Final Rulemaking package to Division Administrator for approval for submittal to OD |  | 2012-09-05 | 2012-09-05 | 2012-10-26 | 2012-10-26 |  |  | Wednesday | Friday |  | 5 | 0
OUT | NA |  | Submit Final Rulemaking package to OD for signature and distribution (5:00 p.m.) (e-mail and 1 hard copy w/signed staff report) (At least 21 days before mailing to EQC. |  | 2012-09-12 | 2012-09-12 | 2012-11-02 | 2012-11-02 |  |  | Wednesday | Friday |  | 7 | 7
| NA | 14 | OD mails EQC Staff Report w/attachments to EQC (At least 24 days before EQC meeting date. |  | 2012-10-01 | 2012-10-01 | 2012-11-19 | 2012-11-19 |  |  | Monday | Monday |  | 19 | 17
EQC Meeting
APT |  |  | Dry run EQC Presentation w/ Division Administrator & others |  | 2012-10-11 | 2012-10-11 | 2012-11-29 | 2012-11-29 |  |  | Thursday | Thursday |  | 10 | 10
|  | 15 | EQC meeting date |  | 2012-10-18 | 2012-10-18 | 2012-12-13 | 2012-12-13 |  |  | Thursday | Thursday |  | 7 | 14
|  | Key: | Column 'DA' are dates rulemaking involves the DA. Some are by appointment.
|  |  | Column '#' is the calculation of days for the row requirement. Red is bad! | Days | 266 |  | 280
|  |  | Column 'DB' is for the rule coordinator. | Mths | 8.7452 |  | 9.2055
Formulas:
Calc 1 = IF([Date]<>"",[Date],"")
Calc 1 = IF([N/A]="",IF([Date]<>"",[Date],""),[Calc 1, row above])
Calc 2 = IF([Option 2]<>"",[Option 2],"")
Calc 2 = IF([N/A]="",IF([Option 2]<>"",[Option 2],""),[Calc 2, row above])
Note on D29: Gary Beyer: See LA column (A) for calculated number of days. If the number is RED it does not meet the SIP requirement. Option 1, 2, or 3 (above) must be selected for this calculation to occur.
Note on B30: Gary Beyer: This calculated number of days must be: If SIP related; at least 30. If NOT SIP related; at least 28.
Note on D30: Gary Beyer: See LA column (A) for calculated number of days. If the number is RED it does not meet the SIP requirement. Option 1, 2, or 3 (above) must be selected for this calculation to occur.
Note on B31: Gary Beyer: This calculated number of days must be at least 30. Only applies to SIP rules!
Note on D31: Gary Beyer: See LA column (A) for calculated number of days. If the number is RED it does not meet the SIP requirement. Option 1, 2, or 3 (above) must be selected for this calculation to occur.
Note on D32: Gary Beyer: See LA column (A) for calculated number of days. If the number is RED it does not meet the SIP requirement. Option 1, 2, or 3 (above) must be selected for this calculation to occur.
Note on D33: Gary Beyer: See LA column (A) for calculated number of days. If the number is RED it does not meet the SIP requirement. Option 1, 2, or 3 (above) must be selected for this calculation to occur.