## Orientation (hidden)
This Excel workbook is part of the blueprint for your rulemaking
It helps manage the new rulemaking process
| z | Tailor rulemaking tasks to risks and complexity
| z | Reduce the number of edits
| z | Eliminate disconnected instructions and guidance
| z | Eliminate duplication and multiple forms
| z | Help capture the actual cost of rulemaking
Helps create the work product
| z | Fee approval
| z | Notice
| z | EQC
| z | Supporting materials
|  | O | Letters
|  | O | Forms
|  | O | Certificates
Stimulates early and ongoing thinking about:
| z | Risks to the success of the rulemaking and implementation
| z | Rulemaking scope and issues
| z | Stakeholder involvement
| z | Resources needed for rulemaking and implementation
Provides help and opportunity for input
| z | Process improvement
| z | Movable messages
| z | In cell prompts
| z | Guidance
The GO-TO place to review:
| z | Schedule
| z | The work product
Records management
| z | Archiving copies of the blueprint at decision points
| z | Documents have retention schedule and name
| z | Hardcopy cover sheets
What is the blueprint?

## WorkFlow (hidden)
DEQ Rulemaking | [10 empty] | Under construction
| Concept | [9 empty] | Start rulemaking |  | Advisory Committee |  | SIP | Fee Approval | [10 empty] | Notice | [7 empty] | Public comment and response | [6 empty] | EQC | [6 empty] | Post EQC
|  |  | Identify |  | Develop |  |  | Review |  | Decide | [7 empty] | Identify |  |  | Develop |  |  | Review |  | Decide |  | Identify | Develop |  | Review |  | Decide |  |  | Identify | Develop |  | Review | Decide |  |  | Identify | Develop |  | Review | Decide |  |  | Identify | Develop |  | Review | Decide
|  | LDA and Core Rule Design Team |  | Draft rulemaking concept |  |  | Concept signoff |  | Prepare draft concept for EMT | [7 empty] | Requirement for DAS fee approval |  |  | Fee approval documents |  |  | Fee submittal signoff |  | Prepare draft concept for EMT | [6 empty] | Prepare draft concept for EMT
Click on:
o to go to Overview |  |  | Lead division administrator |  | Considerations worksheet | t |  | RDT-LM keeps LDA informed about concept |  | LDA approves concept |  | o |  | o |  |  |  | Determine DAS fee approval requirement |  |  | Considerations worksheet - fee section | o |  | RDT-LM keeps LDA informed about fees |  | Deputy director emails submittal to DAS
t to go to Table of Content | [5 empty] | o | [5 empty] | t |  | t |  |  |  |  | Y |  |  | t
s to go to Schedule | [5 empty] | s | [5 empty] | s |  | s | [7 empty] | s
w to go to Worksheet | [5 empty] | w | [5 empty] | w |  | w | [7 empty] | w
| Deliverables | [9 empty] | Deliverables |  | Deliverables |  | Deliverables | Deliverables |  | N | [8 empty] | Deliverables | [7 empty] | Deliverables | [6 empty] | Deliverables | [6 empty] | Deliverables
| 2012 plan | [9 empty] | Contact list |  | Contact list |  | EPA letter | DAS emails | [10 empty] | ALL notice documents | [7 empty] | List of respondents | [6 empty] | Staff report | [6 empty] | Notice of filing
| EQC Involvement |  | RDT: program manager |  | Resources | t |  | RDT completes draft concept |  | Rules group consolidates agency concepts | Charter |  | Charter |  | EPA SIP Insert | DAS submittal |  | Email DAS when submitting Notice to SOS |  |  | Proposal worksheet - fee section | o |  | RDT completes fee approval |  | Follow up with DAS | SOS submittal | [7 empty] | Comment/response worksheet | [13 empty] | DAS fee notification
[6 empty] | o |  |  |  |  | Website template |  | Website template | [8 empty] | t |  |  |  |  | Announcement
[6 empty] | s |  |  |  |  | Agenda template |  | Agenda template | [8 empty] | s
[6 empty] | w |  |  |  |  | Minutes template |  | Minutes template | [8 empty] | w | [7 empty] | w |  |  |  | w |  |  |  | w |  |  | w |  |  |  | w |  |  | w |  |  |  | w |  |  | w
| Kaizen principals | [9 empty] | Kaizen principals |  | Kaizen principals |  | Kaizen principals | Kaizen principals | [10 empty] | Kaizen principals | [7 empty] | Kaizen principals | [6 empty] | Kaizen principals | [6 empty] | Kaizen principals
| Though developing the annual plan was out of scope, the following principal are incorporated. |  | RDT: process expert |  | Proposal in Plan view | t |  | RDT-LM approves concept release to LDA |  | LDA, LM review/approve consolidated draft annual plan | [7 empty] | Email DAS when filing with SOS |  |  | Supporting documents | o |  | RDT-LM approves release to DAS |  | If DAS approves file Fee Approval form for post-EQC activities | Eliminate duplication
[6 empty] | o | [15 empty] | t |  |  |  |  | Reduce review cycles
[6 empty] | s | [15 empty] | s |  |  |  |  | Provide uniformity
[6 empty] | w | [15 empty] | w |  |  |  |  | Streamline information capture |  |  | w |  |  |  | w |  |  |  | w |  |  | w |  |  |  | w |  |  | w |  |  |  | w |  |  | w
| o Eliminate SRP, incorporate factors into annual planning | [19 empty] | Get input from advisors: fiscal, budget, accounting, BSD | o
|  |  | RDT: subject expert |  | Key dates |  |  | RDT presents draft concept to LDA |  | All LDA, LM, ARC present draft plan to EMT | [11 empty] | t |  |  |  | If DAS denies, RDT decides how to respond
s
| o Early EMT decision whether to expend resources |  |  |  |  | s | [15 empty] | w
w
o Creates comprehensive rule design team
[8 empty] | LDA reviews concept |  | IF EMT approves - continue rulemaking
o Establishes agency rules group
– Process experts (3)
– Process assistant (1)
– Agency rules coordinator (1)
Note on X10: Go to table of contents.
Note on X11: Go to schedule.
Note on X12: Go to worksheet.
Note on AL9: Go to overview.
Note on AL10: Go to table of contents.
Note on AL11: Go to schedule.
Note on AL12: Go to worksheet.
Add concept to annual rulemaking plan
Does the proposal nvolve the State Implementation Plan
Does the team plan to convene an advisory committee
Does the rule proposal include fees
Will there be a notice of proposed rulemaking
Did DEQ receive public comment
Is it time to prepare for the EQC
Is it time for Post EQC activities
Does the team plan to convene an advisory committee

## Considerations
Considerations Formulas
DEQ Rulemaking | [7 empty] | 2026-08-04 | [12 empty] | Protect Orange columns | [7 empty] | Days added to schedule
Considerations | [20 empty] | Calculations are in pale yellow on the same row where use.
| Update Oregon rules to address federal air quality regulations | [19 empty] | Y | [7 empty] | #NAME?
Table of Content |  | Overview
Executive summary
This is an overview of the Considerations section of this planning document as of the date on the header to this section. This is a PERMANENT rule proposal that involves land use rules and DEQ's State Implementation Plan. | [20 empty] | This is an overview of the Considerations section of this planning document as of the date on the header to this section. This is a PERMANENT rule proposal that involves land use rules and DEQ's State Implementation Plan.
The proposed rules would adopt new and amended federal air quality regulations and related permit rules. This includes adopting new national standards for sources such as gold mine ore processing and production, boilers, and solid waste incinerators, as well as changes to the federal gasoline dispensing facility rules. The rulemaking proposal would also clarify when and if ACDP permits are required for sources subject to NSPS and NESHAP.
Schedule |  | The rule design team plans to START RULEMAKING in the first quarter of 2012. The planned EQC ACTION DATE is in the fourth quarter of 2012 and the estimated EFFECTIVE date is the first quarter of 2013. | [18 empty] | The rule design team plans to START RULEMAKING in the first quarter of 2012. The planned EQC ACTION DATE is in the fourth quarter of 2012 and the estimated EFFECTIVE date is the first quarter of 2013.
Compliance |  | The proposed rules do not involve include new, expanded or reduced compliance requirements. See section 8 below. | [18 empty] | The proposed rules do not involve include new, expanded or reduced compliance requirements. See section 8 below.
Penalties |  | The proposed rules do not involve penalties. See section 8 below. | [18 empty] | The proposed rules do not involve penalties. See section 8 below.
Requirements |  | The proposed rules include a new, expanded or reduced regulatory program. See section 8 below. | [18 empty] | The proposed rules include a new, expanded or reduced regulatory program. See section 8 below.
Permits, Certifications |  | The proposed rules INCLUDE new or expanded 'Air quality' permit, licence, certification or registration requirements. See section 9 below. | [18 empty] | The proposed rules INCLUDE new or expanded 'Air quality' permit, licence, certification or registration requirements. See section 9 below.
Fees |  | The proposed rules do not affect fees. See section 10 below. | [18 empty] | The proposed rules do not affect fees. See section 10 below.
Regulated party |  | The proposed rules do not involve previously unregulated parties. See section 11. | [18 empty] | The proposed rules do not involve previously unregulated parties. See section 11.
Rule support |  | Risks associated with support for the proposed rules is medium within DEQ, medium for the private stakeholders and medium for public stakeholders. See section 12 below. | [7 empty] | Risk rating low → high
[10 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3 | Risks associated with support for the proposed rules is medium within DEQ, medium for the private stakeholders and medium for public stakeholders. See section 12 below.
Considerations |  | The team has and will continue to identify issues that relate to the rule proposal in the following areas: | [7 empty] | Risk rating low → high 1: Risk rating low → high
1. Program | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3
2. Technology | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3
3. Timing | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 6
4. Policy | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0
5. Environmental | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 5
6. Fiscal | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0
7. Legal | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 6
8. Political | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 6
9. Implementation | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0
Brainstorming
Complete the idea that this rule proposal would…
| Action |  | Object | [5 empty] | Driver
| align |  | existing regulatory program | [5 empty] | federal regulations
| carry out |  | a commitment in PPA | [5 empty] | EPA direction
| improve |  | existing regulatory program | [5 empty] | program business decision
| expand |  | existing regulatory program | [5 empty] | federal regulations
| implement |  | existing regulatory program | [5 empty] | federal regulations
Topic discussion
This rulemaking will address several objectives as listed above.
Scope | [27 empty] | 60 | 59
1. Proposed rules basics
[28 empty] | 5 | 4
The proposed rules would adopt new and amended federal air quality regulations and related permit rules. This includes adopting new national standards for sources such as gold mine ore processing and production, boilers, and solid waste incinerators, as well as changes to the federal gasoline dispensing facility rules. The rulemaking proposal would also clarify when and if ACDP permits are required for sources subject to NSPS and NESHAP.
Rulemaking type |  | PERMANENT |  |  |  |  | Program |  | Air Quality Program Operations Section
Media |  | air
[5 empty] | Chapter 340 divisions involved |  |  |  | 200,216, 230,232,238,244
Schedule |  | Milestone |  | Year | Quarter | [20 empty] | ExSum
|  | Start |  | 2012 | Q1 |  |  |  | Y | Risk rating low → high 2 2 2 2 2 2 2 2 2: Land use rules |  | The rule design team plans to START RULEMAKING in the first quarter of 2012. The planned EQC ACTION DATE is in the fourth quarter of 2012 and the estimated EFFECTIVE date is the first quarter of 2013. | 1 | that involves land use rules and DEQ's State Implementation Plan. |  |  | This is a PERMANENT rule proposal that involves land use rules and DEQ's State Implementation Plan.
|  | EQC Action |  | 2012 | Q4 | [15 empty] | The rule design team plans to START RULEMAKING in the first quarter of 2012.
|  | Effective |  | 2013 | Q1 |  |  |  | Y | Risk rating low → high 2 2 2 2 2 2 2 2 2: State Implementation Plan |  | The planned EQC ACTION DATE is in the fourth quarter of 2012 | 1
and the estimated EFFECTIVE date is the first quarter of 2013.
The proposed rule
[5 empty] | Risk option |  |  |  |  | Risk rating low → high 1 1 1 1 1 1 1 1 1: Riskometer
| ...had prior public input |  |  |  | somewhat true |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3
| ...is backed by science |  |  |  | somewhat true |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3
| ...is backed by data |  |  |  | somewhat true |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3
| ...will make DEQ's work easier |  |  |  | somewhat true |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3
| ...would minimize DEQ costs |  |  |  | somewhat true |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3
| ...furthers DEQ priorities |  |  |  | somewhat true |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3 | [6 empty] | Days added to schedule
| ...supports strategic directions |  |  |  | somewhat true |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3
| ...supports sustainability |  |  |  | somewhat true |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3 | [6 empty] | 0 | 0
[5 empty] | Risk average |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3
Topic discussion
December 2012 is the target date, but there is no set deadline for this rulemaking.
2. What problem is DEQ trying to solve?
3. How would the proposed rule solve the problem?
4. How will DEQ know the problem has been solved?
5. What alternatives did DEQ consider?
Topic discussion
No additional discussion
6. Out of the scope of this rulemaking.
Topic | [6 empty] | Reasoning
None
Include description in: |  |  |  | Committee charter |  |  | Message Map |  |  | 1: Proposal |  | 0 | FALSE |  |  | 0
7. If the EQC does not amend, adopt or repeal the proposed rules, DEQ risks: | [20 empty] | Column1 | Column2
| Loss of delegation |  |  |  | Y |  | Delay in public health protection | [13 empty] | 1899-12-31 | 1899-12-31 | bar: 1 to 10
| Failure to comply with CWA | [5 empty] | Rules does not align with law | [13 empty] | 0 | 1899-12-31 | bar: 1 to 10
| Failure to comply with CAA |  |  |  | Y |  | Increased difficulty doing business | [13 empty] | 1899-12-31 | 0
| Failure to keep commitment |  |  |  | Y |  | Loss of program funding | [13 empty] | 1899-12-31 | 0
| Failure to respond to legislature | [5 empty] | Noncompliance | [13 empty] | 0 | 1899-12-31 | bar: 1 to 10
| Science does not apply to Oregon | [5 empty] | Unclear rules | [13 empty] | 0 | 1899-12-31 | bar: 1 to 10
| Loss of federal funding | [5 empty] | Failure to address cost | [13 empty] | 0 | 0
| Loss of reputation |  |  |  |  | Imposes undue administrative burden | [14 empty] | 0 | 1899-12-31 | bar: 1 to 10
Topic discussion | [27 empty] | #REF! | #REF!
No additional discussion
8. Compliance, regulatory programs and penalties
The proposed rules:
o | Include new, expanded or reduced compliance requirements.
o | Do not involve penalties.
o | Include a new, expanded or reduced regulatory program.
[10 empty] | 1: New; 5: Expanded; 10: Reduced | [5 empty] | score |  |  | Days Added
| The proposed rules involve… | [6 empty] | Involved |  | 1: Requirements
| Compliance | [6 empty] | Y | [12 empty] | 1 | 1 | 0 | 0 | 2 | 0 | Include new, expanded or reduced compliance requirements. | 10 | bar: 1 to 10
| Penalties | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Do not involve penalties. | 0
| Regulatory program | [6 empty] | Y | [12 empty] | 1 | 0 | 1 | 0 | 2 | 0 | Include a new, expanded or reduced regulatory program. | 10 | bar: 1 to 10
Topic discussion | [27 empty] | #REF! | #REF!
No additional discussion
9. Permits, certifications, licenses, registrations | [20 empty] | SectionSum | ExecSum
The proposed rules INCLUDE new or expanded 'Air quality' permit, licence, certification or registration requirements. | [20 empty] | The proposed rules affect Air quality permit, licence, certification or registration requirements. | The proposed rules INCLUDE new or expanded 'Air quality' permit, licence, certification or registration requirements.
| Air quality | [8 empty] | 1: New; 5: Expanded; 10: Reduced |  | Involved | New.expanded |  |  | score |  |  | Days Added
[8 empty] | Involved |  | 1: Requirements
| Asbestos License | [19 empty] | 0 | 0 | 0 | 0 | 0 | Asbestos License |  | 0
| Air Contaminant Discharge Permit | [6 empty] | Y | [12 empty] | 1 | 0 | 1 | 0 | 2 | Air Contaminant Discharge Permit | Includes new, expanded or reduced Air Contaminant Discharge Permit requirements. | 10 | bar: 1 to 10
| Air Quality Registrations | [19 empty] | 0 | 0 | 0 | 0 | 0 | Air Quality Registrations |  | 0
| Open Burning Letter Permit | [19 empty] | 0 | 0 | 0 | 0 | 0 | Open Burning Letter Permit |  | 0
| Tanker Certification | [19 empty] | 0 | 0 | 0 | 0 | 0 | Tanker Certification |  | 0
| Ttle V permit | [19 empty] | 0 | 0 | 0 | 0 | 0 | Ttle V permit |  | 0
| Vehicle Emissions Certification | [19 empty] | 0 | 0 | 0 | 0 | 0 | Vehicle Emissions Certification |  | 0
| NESHAP | [6 empty] | Y | [12 empty] | 1 | 0 | 1 | 0 | 2 | NESHAP | Includes new, expanded or reduced NESHAP requirements. | 10 | bar: 1 to 10
| NSPS | [6 empty] | Y | [12 empty] | 1 | 0 | 1 | 0 | 2 | NSPS | Includes new, expanded or reduced NSPS requirements. | 10 | bar: 1 to 10
| Add new or missing title here | [19 empty] | 0 | 0 | 0 | 0 | 0 | Add new or missing title here |  | 0
Topic discussion | [24 empty] | 7 |  |  | 30 | 30
0
3
10. Fees
The proposed rules do not affect fees. | [20 empty] | The proposed rules do not affect fees. | no fee involvement
Draft or review Proposal¦Fee | [20 empty] | sentence 1 | [6 empty] | Days added to schedule
| The proposed rules… |  |  |  |  | The proposed fees… | [14 empty] | The proposed rules do not affect fees.
| Do not affect fees |  |  |  | 1899-12-31 |  | Does not apply | [12 empty] | 1899-12-31 | 0 | 1 | [5 empty] | 0
| Would establish new fees | [5 empty] | Require DAS approval | [15 empty] | 0 |  |  |  |  | 0
| Would increase existing fees | [5 empty] | Are exempt from DAS approval ORS 291.55(2)(d) | [20 empty] | 0 | 0
| Would decrease existing fees | [5 empty] | Are exempt from DAS approval ORS 291.55(2)(m)
Invoicing system
| No invoicing system involved | [5 empty] | HazWaste Invoicing | [13 empty] | The team indicated an invoicing system is involved with this ruleamking. Please consult with resource early in the rulemaking process.
| Develop new | [5 empty] | SWIFT
| Access database | [5 empty] | TRAACS | [12 empty] | 1899-12-31
| Access template | [5 empty] | UST Invoice.new
| CHRIS | [5 empty] | WQSIS
| Add missing option here | [5 empty] | Add missing option here
Topic discussion
There is an existing database and invoicing processes.
11. Regulated party | [20 empty] | The proposed rules do not involve previously unregulated parties. | [6 empty] | Days added to schedule
[8 empty] | Involved |  | 5: Previously unregulated
| Business | [6 empty] | 1899-12-31 |  | 5: 1899-12-31 |  | 0 | 0 |  |  | 0 |  |  | 0
| Manufacturing | [6 empty] | 1899-12-31 |  | 5: 1899-12-31 |  | 0 | 0 |  |  | 0 |  |  | 0
| City/county/state | [6 empty] | 1899-12-31 |  | 5: 1899-12-31 |  | 0 | 0 |  |  | 0 |  |  | 0
| Individuals | [19 empty] | 0 | 0 |  |  | 0 |  |  | 0
| Enter custom regulated party here | [19 empty] | 0 | 0 |  |  | 0 |  |  | 0
| Enter custom regulated party here | [19 empty] | 0 | 0 |  |  | 0 |  |  | 0
0
Topic discussion
No additional discussion
12. Support for proposal | [27 empty] | Days added to schedule
| Group |  |  |  | Degree of support |  |  |  |  | 1: Riskometer
| EQC |  |  |  | somewhat supportive |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3 | [6 empty] | 0
| EMT |  |  |  | unknown or neutral |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 6 | [6 empty] | 3
| other DEQ programs |  |  |  | unknown or neutral |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 6 | [6 empty] | 3
| program management |  |  |  | somewhat supportive |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3 |  |  |  |  | ExSum |  | 0
| regional staff |  |  |  | unknown or neutral |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 6 | 4.8 |  |  | medium | Risks associated with support for the proposed rules is medium within DEQ, medium for the private stakeholders and medium for public stakeholders. |  | 3
| regulated community |  |  |  | unknown or neutral |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 6 | [6 empty] | 3
| business and industry |  |  |  | unknown or neutral |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 6 | [6 empty] | 3
| environmental groups |  |  |  | unknown or neutral |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 6 | [6 empty] | 3
| public |  |  |  | unknown or neutral |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 6 | 6 |  |  | medium |  |  | 3
| state legislators |  |  |  | unknown or neutral |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 6 | [6 empty] | 3
| federal environmental regulators |  |  |  | somewhat supportive |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3 | [6 empty] | 0
| other state and federal agencies |  |  |  | unknown or neutral |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 6 | [6 empty] | 3
| tribal nations |  |  |  | does not apply |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | [6 empty] | 0
| local governments |  |  |  | unknown or neutral |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 6 | 5.25 |  |  | medium |  |  | 3
[7 empty] | Average |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 5.3077 | medium | [5 empty] | 30 | 29
0
Topic discussion
No additional discussion
Process improvement
Public involvement
"The Legislative Assembly finds and declares that it is the policy of this state that whenever possible the public be involved in the development of public policy by agencies and in the drafting of rules. The Legislative Assembly encourages agencies to seek public input to the maximum extent possible before giving notice of intent to adopt a rule. The agency may appoint an advisory committee that will represent the interests of persons likely to be affected by the rule, or use any other means of obtaining public views that will assist the agency in drafting the rule."
1. Advisory committee involvement
Guide |  |  |  |  | Bold topics are part of the advisory committee charter. | [15 empty] | 0 | 0
| No plans to convene a committee |  |  |  | 1899-12-31 |  | Program |  |  | 3: Environmental
| Use a standing committee | [5 empty] | Technology |  |  | 3: Fiscal
| Reconvene a committee | [5 empty] | Timing |  |  | 3: Legal
| Convene a new committee | [5 empty] | Policy |  |  | 3: Political
| Estimated number of meetings |  |  |  | 0 |  | Estimated days between meetings |  |  | 10: 0 | [7 empty] | 0 |  | 0
Topic discussion | [20 empty] | #REF! | #REF! |  |  |  |  | 0 | 0
No additional discussion | [20 empty] | #REF! | #REF! | [5 empty] | 0 | 0
1. The Oregon Administrative Procedures Act requires DEQ to seek the committee’s recommendations about:
(a) Whether the rule will have a fiscal impact;
(b) What the extent of that impact will be;
(c) Whether the rule will have a significant adverse impact on small businesses.
If the committee determines there will be a significant adverse impact on small businesses, DEQ must seek the committee’s recommendations on how to reduce the economic impact of the rule on small business, to the extent consistent with the public health and safety purpose of the rule, by:
o Establishing differing compliance or reporting requirements or time tables for small business;
o Clarifying, consolidating or simplifying the compliance and reporting requirements under the rule for small business;
o Utilizing objective criteria for standards;
o Exempting small businesses from any or all requirements of the rule; or
o Otherwise establishing less intrusive or less costly alternatives applicable to small business.
2. If DEQ convenes a rulemaking advisory committee, but does not seek the committee’s recommendations as described above, there is a risk that the entire rulemaking could later be invalidated by a court for failure to comply with procedural rulemaking requirements under the Oregon Administrative Procedures Act.
| 3. If DEQ does not convene a rulemaking advisory committee regarding a proposed permanent rule, then persons or organizations likely to be affected by the proposed rule may object to DEQ’s fiscal impact statement. Such an objection requires DEQ to appoint a fiscal impact advisory committee to provide recommendations on whether the proposed rule will have a fiscal impact and what the extent of that impact will be. This can significantly delay a rulemaking. | [19 empty] | is there an alternative
2. Information meetings and hearings | [9 empty] | 8: ORS 183.333 |  | =IF(AND(AE235=TRUE,OR(AE236=TRUE,AE237=TRUE,AF235=TRUE,ScopeHearingInvolved=TRUE,AF237=TRUE)),"Change 'Does not apply' to blank.","") | [6 empty] | Days Added to schedule
| Does not apply | [6 empty] | Public notice without hearing | [12 empty] | FALSE | FALSE |  |  | 0 | 0 | 0 | 15
| Portland area information meeting |  |  |  | 1899-12-31 |  |  | Public notice with hearing | [11 empty] | 1899-12-31 | TRUE | TRUE |  |  | 10 | 15 | 25 | 15
| Regional information meeting | [6 empty] | Re-notice | [12 empty] | FALSE | FALSE |  |  | 0 | 0 | 0 | 10
| Estimate number of meetings |  |  |  | 1 |  | Estimate number of hearings | [12 empty] | 1 | Estimated number of meetings: | Estimated number of hearings: |  |  |  |  | 0 |  | 0
Topic discussion | [20 empty] | 1899-12-31 | 1899-12-31 |  |  |  |  | 25 | 0
[21 empty] | 1899-12-31 | There will be stakeholder involvement. | [5 empty] | 40 | 40
Process improvement
Considerations
#REF!
1. Program considerations
|  | Complexity rating |  |  | potential for minor complexity |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3 | [6 empty] | 3
Subject program
Large numbers of businesses that dispense gasoline into non-road vehicles and non-road engines are potentially affected by the amended gasoline dispensing facility NESHAP. Many of these businesses have not previously been subject to air quality regulations. Initially, there may be compliance issues with these businesses, placing a burden on DEQ's Office of Compliance and Enforcement. Compliance rates should improve and therefore the burden on OCE should reduce over time.
Other DEQ programs
Incorporating federal changes to the gasoline dispensing facility NESHAP will result in expansion to facilities that dispense gasoline into non-road vehicles and non-road engines. This will require the UST Program to incorporate the NESHAP requirements into additional inspections. DEQ is implementing the gasoline dispensing facility NESHAP in a joint effort of the Air Quality Division and the Underground Storage Tank Program. The UST program has incorporated the NESHAP requirements into their current inspection program. This leveraging of UST Program resources has allowed the Air Quality Division to reduce implementation costs and establish two lower cost General ACDP fee classes for gasoline dispensing facilities. The generated revenue pays for the NESHAP portion of the UST Program inspection. However, affected businesses aren’t likely to have throughputs that would trigger control requirements or permitting. Therefore, the increase in workload on the UST Program is not expected to be significant. Revenue generated by permitting additional businesses will be used to pay for this increased workload.
[21 empty] | N | N | Y
Include description in: |  |  |  | Committee charter |  |  | Message Map |  | Y | 1: Proposal |  | 1899-12-31 | 0 | 1899-12-31
Topic discussion
No additional discussion
2. Technology considerations
|  | Complexity rating |  |  | potential for minor complexity |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3 | [6 empty] | 3
Describe this consideration
Existing UST and AQ databases will support implementation of this rulemaking.
[21 empty] | N | N | N
Include description in: |  |  |  | Committee charter |  |  | Message Map |  |  | 1: Proposal |  | 1899-12-31 | 0 | 0
Topic discussion
No additional discussion
3. Timing considerations
|  | Criticality rating |  |  | moderate criticality |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 6 | [6 empty] | 10
Describe this consideration
DEQ's 2010-2012 Performance Partnership Agreement with EPA stipulates that DEQ adopt NESHAPs and NSPSs and request delegation at least every two years. States are required to submit a plan that meets the requirements of the amended emission guidelines for commercial and industrial solid waste incinerators by one year after promulgation of the emission guidelines. EPA expects to publish the amended emission guidelines in May of this year. Therefore, state plans will be due in May of 2013. If a state does not submit an approvable plan, EPA is required to develop a Federal plan for Commercial and Industrial Solid Waste Incinerators located in that state within 2 years after promulgation of the emission guidelines.
• Existing gold mine ore processing and production facilities are required to comply with the new NESHAP by February 17, 2014. • Existing gasoline dispensing facilities that dispense gasoline into the fuel tank of "non-road vehicles" or "non-road engines" are required to comply with the amended gasoline dispensing facility NESHAP by January 24, 2014. • Existing commercial, institutional, and industrial boilers are required to be tune-up by March 21, 2013. • Owners of larger commercial, institutional, and industrial boilers are required to have an energy assessment performed by March 21, 2014. • Existing coal- and oil-fired electric utility boilers are required to comply with the new utility NESHAP by April 16, 2015.
Rule changes are necessary now in order to delay implementation of the NESHAP and NSPS standards for stationary engines. Air Quality managers have decided to delay implementation of these standards because of potential workload increases. Air Quality managers want a comprehensive implementation plan and to know how many facilities would be affected before proceeding. Oregon's current rules require DEQ to implement federal standards for currently permitted facilities when they are adopted by EPA, not when they are adopted by the EQC. Oregon's rules also require facilities affected by new NSPSs to obtain a permit when an NSPS is adopted by EPA, not when it is adopted by the EQC. On January 5, 2010, EPA promulgated the Prepared Feeds NESHAP. The NESHAP contained a requirement that facilities, with an average daily feed production level exceeding 50 tons per day, capture and route emissions to a cyclone designed to reduce particulate emissions by 95 percent. The compliance date for this requirement was January 5, 2012. On December 23, 2011, EPA promulgated amendments to the NESHAP that removed the 95 % control requirement for cyclones at existing facilities and retained the compliance date of January 5, 2012. This rulemaking would adopt the revised NESHAP. In the meantime, affected facilities are out of compliance with the version of the NESHAP previously adopted by the EQC. After the rules are adopted, DEQ will revise the prepared feed general ACDP and reassign affected facilities to the revised permit.
[21 empty] | N | N | Y
Include description in: |  |  |  | Committee charter |  |  | Message Map |  | Y | 1: Proposal |  | 0 | 0 | 1899-12-31
Topic discussion
No additional discussion
4. Policy considerations
|  | Complexity rating |  |  | does not apply |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | [6 empty] | 0
Describe this consideration
[21 empty] | N | N | N
Include description in: |  |  |  | Committee charter |  |  | Message Map |  |  | 1: Proposal |  | 0 | 0 | 0
Topic discussion
5. Environmental considerations
|  | Complexity rating |  |  | unknown |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 5 | [6 empty] | 0
The proposed rule |  |  | has no direct correlation to the environment. | [17 empty] | 3
Describe this consideration
EPA has identified gasoline dispensing facilities, gold mine ore processing and production operations, and boilers as emitters of one or more of the 33 hazardous air pollutants that pose the greatest risk to public health in urban areas. Many of these hazardous air pollutants are also of particular concern in Oregon. For instance, gasoline vapors contain benzene, a known cancer-causing chemical. Because benzene concentrations in many Oregon communities are significantly above levels protective of human health, reducing benzene is a priority for DEQ. Boilers and gold mine ore processing and production operations emit mercury which can impair neurological development and cause neurological damage, and is a toxic of concern in Oregon.
[21 empty] | N | N | Y
Include description in: |  |  |  | Committee charter |  |  | Message Map |  | Y | 1: Proposal |  | 0 | 0 | 1899-12-31
Topic discussion
No additional discussion
6. Fiscal considerations
|  | Complexity rating |  |  | does not apply |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | [6 empty] | 0
| Fiscal impact on: |  |  |  | Impact |  |  |  |  | 1: Riskometer
| regulated community |  |  |  | moderate cost increase |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 8
| small business (50 emp or less) |  |  |  | moderate cost increase |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 8
| business and industry |  |  |  | moderate cost increase |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 8
| local governments |  |  |  | no fiscal impacts |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0
| other state or federal agencies |  |  |  | no fiscal impacts |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0
| public |  |  |  | no fiscal impacts |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0
| DEQ |  |  |  | no fiscal impacts |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0
| other |  |  |  | unknown |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 6
[5 empty] | Fiscal impact average |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 7.5 | high
Describe this consideration
No additional discription at this time
Text
Text
Text
Text
Text
Text
[21 empty] | N | N | N
Include description in: |  |  |  | Committee charter |  |  | Message Map |  |  | 1: Proposal |  | 0 | 0 | 0
Topic discussion
No additional discussion
7. Legal considerations
|  | Complexity rating |  |  | potential for moderate complexity |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 6 | [6 empty] | 10
Describe this consideration
No additional description at this time
[21 empty] | N | N | N
Include description in: |  |  |  | Committee charter |  |  | Message Map |  |  | 1: Proposal |  | 0 | 0 | 0
Topic discussion
No additional discussion
8. Political considerations
|  | Controversy rating |  |  | potential for moderate controversy |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 6 | [6 empty] | 10
Describe this consideration
Large numbers of businesses that dispense gasoline into non-road vehicles and non-road engines are potentially affected by the gasoline dispensing facility NESHAP. Many of these businesses have not previously been subject to air quality regulations, are opposed to permitting and fees, and may contact their legislators. However, these businesses aren’t likely to have throughputs that would not trigger the more significant control requirements or permitting. In a 2009 mailing, DEQ informed businesses that dispense gasoline into non-road vehicles and non-road engines that they were exempt from the gasoline dispensing NESHAP, knowing that in the future it would likely have to inform these same businesses that they are subject to the NESHAP.
[21 empty] | N | N | N
Include description in: |  |  |  | Committee charter |  |  | Message Map |  |  | 1: Proposal |  | 0 | 0 | 0
Topic discussion
No additional discussion
9. Implementation considerations
|  | Complexity rating |  |  | potential for minor complexity |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3 | [6 empty] | 3
Describe this consideration
No additional description at this time
[21 empty] | N | N | N
Include description in: |  |  |  | Committee charter |  |  | Message Map |  |  | 1: Proposal |  | 0 | 0 | 0
Topic discussion
No additional discussion
Process improvement
Formulas:
Involved = IF([Object]="Y",TRUE(),FALSE())
New.expanded = IF([Quarter, row below]<>TRUE(),TRUE(),FALSE())
Note on A209: ADVISORY COMMITTEE BEST PRACTICE ORS 183.333 See also Proposal tab, Fiscal Impact section 1. If DEQ convenes a rulemaking advisory committee, the Oregon Administrative Procedures Act requires DEQ to seek the committee’s recommendations about: (a) Whether the rule will have a fiscal impact; (b) What the extent of that impact will be; (c) Whether the rule will have a significant adverse impact on small businesses. If the committee determines there will be a significant adverse impact on small businesses, DEQ must seek the committee’s recommendations on how to reduce the economic impact of the rule on small business, to the extent consistent with the public health and safety purpose of the rule, by:  Establishing differing compliance or reporting requirements or time tables for small business;  Clarifying, consolidating or simplifying the compliance and reporting requirements under the rule for small business;  Utilizing objective criteria for standards;  Exempting small businesses from any or all requirements of the rule; or 2. If DEQ convenes a rulemaking advisory committee, but does not seek the committee’s recommendations as described above, there is a risk that the entire rulemaking could later be invalidated by a court for failure to comply with procedural rulemaking requirements under the Oregon Administrative Procedures Act. 3. If DEQ does not convene a rulemaking advisory committee regarding a proposed permanent rule, then persons or organizations likely to be affected by the proposed rule may object to DEQ’s fiscal impact statement. Such an objection requires DEQ to appoint a fiscal impact advisory committee to provide recommendations on whether the proposed rule will have a fiscal impact and what the extent of that impact will be. This can significantly delay a rulemaking. ORS 183.333(5)
Note on A232: DOJ response to question about when a stakeholder group becomes an advisory committee To: VANDEHEY Maggie From: Logan Paul S [mailto:paul.s.logan@state.or.us] Sent: Thursday, September 29, 2011 1:12 PM To: VANDEHEY Maggie Subject: RE: advisory committees Maggie, From a brief review, Oregon law is very vague on what constitutes an “advisory committee,” and as a result I cannot give you extremely precise guidance. On the other hand, though, it is quite clear that agencies have broad discretion to obtain public views on proposed rulemakings through any means they choose – advisory committees or otherwise. As a result, and as explained further below, I’d suggest that as a practical matter DEQ should comply with advisory committee requirements under ORS 183.333 when it appoints individual members to a group representing multiple interests likely to be affected by the proposed rulemaking, and seeks comments from the group as a whole on the proposed rulemaking. In contrast, if DEQ does not appoint individual members to a group but rather invites input from interest groups more generally, and especially if DEQ does not convene the different interest groups together in a single meeting, DEQ probably does not have to comply with advisory committee requirements. I have to caution, though, that we are operating in a gray area in this matter due to some of the vagueness of the Oregon statute at issue. But if DEQ follows these general guidelines, it should minimize the risk of unintentionally appointing an “advisory committee” that triggers certain requirements under Oregon law. As background, ORS 183.333(1) states that “[t]he agency may appoint an advisory committee that will represent the interests of persons likely to be affected by the rule, or use any other means of obtaining public views that will assist the agency in drafting the rule.” As a threshold matter, therefore, a group must be appointed by DEQ to be considered an advisory committee. On the other hand, even if DEQ invites a number of different stakeholder groups to a single meeting, and seeks comments from the group as a whole, that group begins to look like an advisory committee – even though DEQ hasn’t appointed individual members – and there is a risk that DEQ has effectively “appointed” an advisory committee. In addition to advisory committees, the statute is quite clear that an agency may use “any other means” of obtaining public views, and for example provides that “[a]ny agency in its discretion may develop a list of interested parties and inform those parties of any issue that may be the subject of rulemaking and invite the parties to make comments on the issue.” ORS 183.333(2). Thus it appears that DEQ could “invite” particular parties to comment on a rulemaking issue without triggering the requirements of an advisory committee. There is less risk if DEQ invites those parties to comment separately, rather than together as a single group, which would more closely resemble a committee, and therefore might be construed to be an advisory committee. The analysis above demonstrates that it is not possible, on the basis of the statute’s text, to make a bright line distinction between what constitutes an advisory committee and what does not. If you wish, I could research this issue further by following the analytical methodology for interpreting statutes followed by Oregon courts. That would involve reviewing dictionary definitions of “appoint,” “advisory” and “committee,” and reviewing legislative history. But my instinct is that that type of research is unlikely to give you much more certainty.
Note on D150: DAS FEE APPROVAL Requirement (1) Notwithstanding any other law that grants to a state agency the authority to establish fees, all new state agency fees or fee increases adopted after July 1 of any odd-numbered year: (a) Are not effective for agencies in the executive department of government unless approved in writing by the Director of the Oregon Department of Administrative Services; ... (d) Shall be reported by the state agency to the Oregon Department of Administrative Services within 10 days of their adoption; and (e) Are rescinded on July 1 of the next following odd-numbered year, or on adjournment sine die of the regular session of the Legislative Assembly meeting in that year, whichever is later, unless otherwise authorized by enabling legislation setting forth the approved fees. ORS 291.055
Note on J152: Requirement For fees to become effective, DEQ must obtain approval of all NEW or INCREASED fees from the Director of the Oregon Department of Administrative Services. There are several exemptions. Exemptions that generally apply to DEQ are below.
Note on J153: ORS 291.055 (2)(d) Fees created or authorized by statute that have no established rate or amount but are calculated for each separate instance for each fee payer and are based on actual cost of services provided.
Note on J154: ORS 291.055 (2)(m) New or increased fees that are anticipated in the legislative budgeting process for an agency, revenues from which are included, explicitly or implicitly, in the legislatively adopted budget for the agency.
Note on AB2: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB31: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB47: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB95: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB114: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB147: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB179: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB206: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB217: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB239: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB258: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB268: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB280: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB289: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB301: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB331: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB341: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB351: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB357: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AE166: Added to executive Summary
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message

## Resources
[19 empty] | Movable Messages |  | Resources Formulas
DEQ Rulemaking | [7 empty] | 2026-08-04 | [10 empty] | New message pad | Retired messages | Protect Column BA
Resources | [18 empty] | Click on message pad and move to subject location.
Update Oregon rules to address federal air quality regulations
Table of Content |  | Overview
Rulemaking resources
Review resources
| Workflow | >
| DOJ rulewriting training | >
| Review DOJ Model Rules | >
| APA | ORS 183
| DAS rules on Rulemaking | 137
| DAS rules on Rulemaking | 291.055(1)(a)
| DEQ | http://www.leg.state.or.us/ors/183.html
in HB 2788 i
Project accounting and rulemaking record
The agency rules group has reserved the following for this proposal
Has reserved the following for this proposal:
| Time accounting code for work related to rulemaking | [5 empty] | #####: RM-NESHAP/NSPS
| Project number for expenditures related to this rulemaking | [5 empty] | P##### RM-NESHAP/NSPS
| RM Identifier for email Subject line | [5 empty] | RM-NESHAP/NSPS
| Rule design team email group | [5 empty] | RM-NESHAP/NSPS@deq.state.or.us
| Advisory Committee email group | [5 empty] | None
| Public comment email box | [5 empty] | Comment-NESHAP/NSPS@deq.start.or.us
| Electronic record |  |  |  | RM-NESHAP/NSPSSharePoint
RM-NESHAP/NSPSArchive
| Email folder |  |  |  | RM-NESHAP/NSPS2012
| Email archives |  |  |  | RM-NESHAP/NSPS.pst
Physical record | Physical record |  |  | Pre filing
|  |  |  | Post filing | Central rulemaking cabinet for 5-years then SOS Archives
Core team
Lead DA |  | Andy Ginsburg |  |  |  | =>20 <30 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 4
The lead division administrator: • ensures the program manager and the team has adequate and appropriate resources • raises potential issues to the executive management team • advises the team on Considerations, Resources and Schedules as needed • reviews and approves the draft and final release of the Proposal at: - Presentation to EMT - Public notice - EQC
Lead manager |  | Tom Roick |  |  |  | =>40 <80 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 6
The lead manager is a contributing member on the rule design team who: • ensures the team has adequate and appropriate resources • raises potential issues to the lead division administrator • reviews and advises the team on Considerations, Resources and Schedules • reviews and approves the draft and final release of the Proposal at: - fee notification or approval requests - Public notice - EQC
Project expert |  | Nicole Vick |  |  |  | =>30 <40 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 5
The project lead is the expert on the rulemaking process and writing for the proposed rule. The project lead is responsible for: • Developing, maintaining and keeping the: - Blueprint and SharePoint site - Schedule • Engaging identified resources in collaboration activities • Writing all rulemaking materials using: - plain English - DEQ Style Guide • Ensuring the proposal has all required reviews and approvals before: - Releasing the blueprint beyond the rule design team - Publishing the proposal external to DEQ
Subject expert |  | Jerry Ebersole |  |  |  | =>200 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 10
Process assistant |  | Carol Thornberg |  |  |  | =>2 <10 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 2
Handles meeting logistics including iLinc and conference call-in numbers. Mailings, GovDelivery
Facilitator | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
Rule contact |  | Jerry Ebersole |  |  |  | =>10 <20 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 3
|  | Address | Jerry Ebersole |  |  |  | Phone |  | 1: (503) 229-6974
811 SW 6th Ave
Portland, OR 97204-1390
NESHAP Implementation Plan Team exists and will be used to support communication and implementation.
Section process improvement
Advisors
DOJ |  | Paul Logan |  |  |  | =>10 <20 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 3
Makes sure all legal issues are adequately resolved, and the proposed rules are legally sufficient (within authority, consistent with statute, enforceable).
ARC |  | Maggie Vandehey |  |  |  | =>10 <20 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 3
Checks that the package meets the procedural requirements and is satisfactory for notice and filing.
SIP Coordinator |  | Nicole Vick |  |  |  | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
Section process improvement
Interested staff
Enter custom name | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
Enter custom name | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
Enter custom name | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
Section process improvement
Regions and other divisions |  |  |  |  | (See sections below for the lab and MSD) | [15 empty] | The proposed rules involve regional resources.
Eastern |  | Mark Fisher |  |  |  | =>10 <20 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 3
| rulemaking | Reviews the permitting rules and rules that implement the federal emissions guidelines for commercial and industrial solid waste incinerators.
implementation
Northwest |  | Johnny Baumgartner |  |  |  | =>10 <20 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 3
| rulemaking | Reviews the gasoline dispensing rule amendments.
implementation
Western |  | Steve Croucher |  |  |  | =>10 <20 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 3
| rulemaking | Reviews the gasoline dispensing rule amendments.
implementation
Land Quality |  | Andree Pollock |  |  |  | =>10 <20 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 3
| rulemaking | Reviews the gasoline dispensing rule amendments.
implementation
Air Quality |  | Rebecca Hillwig |  |  |  | =>10 <20 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 3
| rulemaking | Reviews rules for impacts on small businesses. Reviews rules for impacts on small businesses.
implementation
Water Quality |  | Enter email |  |  |  | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Section process improvement
Financial services | [5 empty] | The proposed rules involve financial services resources. | [14 empty] | The proposed rules involve financial services resources.
Budget |  | Robin Williams |  |  |  | =>10 <20 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 3
Review and approve statement of need and fiscal impact statement
Accounting |  | Richard Lawrence |  |  |  | >0 <2 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 1
Though this does not involve fees and invoicing, would still like him to be aware of the rule changes.
The team indicated an invoicing system is involved with this ruleamking. Please consult with resource early in the rulemaking process.
Contracts |  | Debra Owen |  |  |  | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
Section process improvement
Communications and Outreach | [5 empty] | The proposed rules involve OCO resources. | [14 empty] | The proposed rules involve OCO resources.
Edits |  | William Knight |  |  |  | =>2 <10 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 2
Edit Proposal tab: • Notice sections and announcement before SOS release • All other sections before EQC release
Messaging |  | William Knight |  |  |  | =>2 <10 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 2
Reviews messaging indicated on Considerations tab. Reviews Announcement tab and display ad section of MeetingMecanics tab.
Media |  | William Knight |  |  |  | =>2 <10 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 2
rulemaking
implementation
Web services |  | Emma Snodgrass |  |  |  | =>10 <20 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 3
rulemaking
implementation
Organization services | [5 empty] | The proposed rules do not involve organizational services. | [14 empty] | The proposed rules do not involve organizational services.
Health and safety | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Human resources | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Policies and procedures | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Training |  | Jill Corona |  |  |  | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Facilities | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Section process improvement
Technical services | [5 empty] | The proposed rules do not involve technical services. | [14 empty] | The proposed rules do not involve technical services.
Divisional | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
IT |  | Rebecca Kirk |  |  |  | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
The team indicated an invoicing system is involved with this ruleamking. Please consult with resource early in the rulemaking process.
BSD |  | Sohng Shin |  |  |  | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
The team indicated an invoicing system is involved with this ruleamking. Please consult with resource early in the rulemaking process.
Section process improvement
Compliance and Enforcement | [5 empty] | The proposed rules would involve OCE resources. | [14 empty] | The proposed rules would involve OCE resources.
OCE |  | Jenny Root |  |  |  | =>10 <20 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 3
| rulemaking | Reviews proposed rules to ensure enforcement issues are addressed.
implementation
Section process improvement
Laboratory | [5 empty] | The proposed rules do not involve the laboratory. | [14 empty] | The proposed rules do not involve the laboratory.
Monitoring | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Analytical testing | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Quality assurance | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Intergovernmental | [5 empty] | The proposed rules do not involve intergovernmental entities. | [14 empty] | The proposed rules do not involve intergovernmental entities.
Tribal nations | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
EPA | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
LRAPA | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Municipalities | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Counties | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Special districts | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Other state agencies | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Section process improvement
Note on A29: COMMENT BOX PERMISSIONS The project lead, rules coordinator and assistant have access to the Comment box
Note on AB4: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB20: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB37: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB47: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB75: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB93: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB111: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB147: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB166: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB186: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB217: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message

## Proposal (hidden)
|  | This worksheet is in PERMANENT NOTICE view. | [11 empty] | Proposal Formulas |  | Working in views
[13 empty] | Table of Content | Protect bright yellow columns |  | View | RMType | Banner
|  | Oregon Department of Environmental Quality | [10 empty] | Overview
[13 empty] | Views | Permanent rule proposal for: |  | 7 | PERMANENT | This worksheet is in PERMANENT NOTICE view.
|  | Permanent rule proposal for: | [10 empty] | NOTICE
|  | Update Oregon rules to address federal air quality regulations | [10 empty] | Message box
Update Oregon rules to address federal air quality regulations
|  | DEQ recommendation to the EQC |  |  |  |  | Agenda item |  |  | A
DEQ recommends that the Environmental Quality Commission:
|  | Amend the proposed permanent rules in attachement A as part of chapter 340 of the Oregon Administrative Rules. Approve incorporating these proposed permanent rule amendments into the Oregon Clean Air Act Implementation Plan under OAR 340-200-0040. | [11 empty] | Amend the proposed permanent rules in attachement A as part of chapter 340 of the Oregon Administrative Rules. Approve incorporating these proposed permanent rule amendments into the Oregon Clean Air Act Implementation Plan under OAR 340-200-0040.
Attachment A: Proposed rules
Director's electronic signature
Overview
i |  | Rule caption
Update Oregon rules to address federal air quality regulations
|  | Regulated parties | [11 empty] | Regulated parties
|  | Summary of proposed rules | [11 empty] | Summary of proposed rules
|  | Brief history | [11 empty] | Summary of proposed rules
|  | Statement of need | [11 empty] | Statement of need
What problem is DEQ trying to solve?
How would the proposed rule solve the problem?
How will DEQ know the problem has been solved?
What alternatives did DEQ consider?
Request for other options
i |  | During the public comment period, DEQ requests public comment on whether to consider other options for achieving the rule's substantive goals while reducing negative economic impact of the rule on business. | [11 empty] | During the public comment period, DEQ requests public comment on whether to consider other options for achieving the rule's substantive goals while reducing negative economic impact of the rule on business. | requests
Considerations
Enter your freeform title here
Federal relationship
Ä
ORS 183.332
OAR 340-011-0029
|  | "It is the policy of this state that agencies shall seek to retain and promote the unique identity of Oregon by considering local conditions when an agency adopts policies and rules. However, since there are many federal laws and regulations that apply to activities that are also regulated by the state, it is also the policy of this state that agencies attempt to adopt rules that correspond with equivalent federal laws and rules..." | [11 empty] | Oregon Title V Operating Permit Fees under OAR 340 Division 220
|  | The proposal adopts the federal requirement verbatim or by reference. | [6 empty] | FALSE |  | ORS 468A.327 | DDL
Describe federal requirement
This rule proposal is different from or in addition to federal requirements. The following exemption from adopting rules that correspond with equivalent federal laws and rules applies to this proposal.
|  | There is no corresponding federal regulation. ORS 183.332 (6) | [9 empty] | DDL
Discuss HOW the proposal is different from or in addition to federal requirements.
Discuss WHY the proposal is different from or in addition to federal requirements.
|  | Rules affected, authorities, supporting documents | [11 empty] | Rules affected, authorities, supporting documents
| Lead division |  |  |  |  | Program or activity
|  | Land Quality |  |  |  | Oregon's product stewardship program | [8 empty] | #N/A
|  | Chapter 340 action | Div | Rule | Title | [5 empty] | SIP/Land use* |  |  | SIP/Land use* | Adopt | Amend | Renumber | Repeal | Suspend
i |  | adopt | 90 | 9999 | Applicability | [6 empty] | DDL |  | 340-090-9999 | 340-090-9999
i |  | amend | 90 | 9999 | Definitions | [8 empty] | 340-090-9999 |  | 340-090-9999
|  | adopt | 90 | 9999 | Target revenue processes | [8 empty] | 340-090-9999 | 340-090-9999
|  | adopt | 90 | 9999 | Fee structure | [8 empty] | 340-090-9999 | 340-090-9999
|  | amend | 0 | 0 | [9 empty] | 340-000-0000 |  | 340-000-0000
|  | repeal | 0 | 0 | [9 empty] | 340-000-0000 |  |  |  | 340-000-0000
|  | amend | 0 | 0 | [9 empty] | 340-000-0000 |  | 340-000-0000
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  | * SIP means State Implementation Plan. | [11 empty] | * SIP means State Implementation Plan. | 340-090-9999 340-090-9999 340-090-9999 | 340-090-9999 340-000-0000 340-000-0000 |  | 340-000-0000
|  | * Land use means the DEQ State Agency Coordination Program considers this rule, program or activity is a land use program. | [11 empty] | * Land use means the DEQ State Agency Coordination Program considers this rule, program or activity is a land use program.
|  | Statute implemented | [5 empty] | Legislation |  |  | Year
|  | ORS 459A.315 | [5 empty] | HB 2626 |  |  | 2007
Statutory or other legal authority
ORS 468.020, 468.065, 459A.345
Other Authority
[5 empty] | Relied on for fiscal statement | [5 empty] | ORS 183.335(2)(b)(C)
|  | Supporting document title |  |  |  |  | To view document | [6 empty] | Relied on for fiscal statement
Fiscal impact statement
Fiscal and economic impact
|  | The fiscal impact on large businesses and tribal nations would be similar to the impact described under 2 below. | [11 empty] | fee decrease
Statement of Cost of Compliance
|  | 1. Impact on state agencies, units of local government and the public. | [8 empty] | ORS 183.335(2)(b)(E)
The proposed rules do not impact state agencies, units of local governments or the public unless they are manufacturers of electronic devices covered under the E-Cycles program. Any registration fees passed onto consumers as cost increases in covered electronic devices would be negligible.
|  | 2. Cost of compliance on small businesses with 50 or fewer employees. | [6 empty] | ORS 183.336(10)
|  | a) Estimated number of small businesses and types of businesses and industries with small businesses subject to proposed rule. | [11 empty] | Approximately ## small businesses in Oregon are subject to the current fees and would be subject to the proposed fees.
|  | b) Projected reporting, recordkeeping and other administrative activities, including costs of professional services, required for small businesses to comply with the proposed rule. | [11 empty] | No additional activities are required for compliance with the proposed rules.
|  | c) Projected equipment, supplies, labor and increased administration required for small businesses to comply with the proposed rule. | [11 empty] | No additional resources are required for compliance with the proposed rules.
d) Describe how DEQ involved small businesses in developing this proposed rule.
Housing Cost
DEQ determined the proposed rulemaking will have no effect on the development cost of a 6,000-square-foot parcel and construction of a 1,200-square-foot detached single family dwelling on that parcel. The proposed fee affects only manufacturers of electronic devices sold in or into Oregon.
|  | Fees | The proposed rules do not affect fees | [10 empty] | The proposed rules do not affect fees
|  | ORS 459A.315 (2) | is the Environmental Quality Commission authority to adopt the proposed fees. | [10 empty] | The statutory authority for the proposed no fee involvement is
1. Reason for proposing fee change
costs exceed estimate
Please explain.
2. Reason for proposing fee change
change in fee payer mix
Provide trend information.
3. Reason for proposing fee change
text
4. Reason for proposing fee change
text
Brief description of proposed fee
Fee proposal alternatives considered
Affected parties
Affected party involvement in fee setting process
(For more information, see http://www.deq.state.or.us/lq/ecycle/rulemaking.htm, web page.)
All Oregon regulated electronics manufacturers, 157 registered for 2012, will be invited to comment during the public hearing process.
Summary of impacts
Even under the current fee structure, a manufacturer’s fee may change from year to year if its market share changes. In order to measure the impact of the proposed fee change on manufacturers, DEQ calculated each manufacturer’s fee under the proposed fee structure and target revenue using 2011 manufacturer and market share data and compared that fee to the 2011 fee under the current fee structure. The result is that fees are increased by $20,000 for nine Tier 1 manufacturers, reduced $2,500 for five Tier 2 manufacturers, reduced $3,000 for fifteen Tier 3 manufacturers, and increased $64 for nine Tier 4 manufacturers. Thirteen manufacturers in Tier 5 keep the same fee of $200. About 120 manufacturers in Tier 6 would see an increase of $160.
|  | Fee payer agreement with fee change |  |  |  | Link to documents supporting the proposed fee
expect support
Current fee structure
How long will current fee sustain program?
Current fee is not sustaining the program. Based on the first two years of revenue, the Legislative Adopted Budget assumed annual revenue of $360,000, but receipts have declined each year and 2011 revenue was only $287,000. The 2011-2013 LAB expenditure budget, including agency indirect, was $687,000, but wage increases have increased costs to $720,000, or $360,000 a year. In addition, the solid waste disposal fee must be reimbursed to the extent possible for funds borrowed to support E-Cycles program operations and database development. It is not certain what future market share distributions will be; it is possible revenue could go back up or continue to decline under the existing schedule. The uncertainty is a major issue for the program.
|  | Program costs covered by fees |  |  |  | 360000 |  |  | 100% | *
|  | Program costs covered by General Fund |  |  |  | 0 |  |  | 0%
|  | Fee last changed |  |  |  | 2007-10-01
* Plus additional $193,000 from database development in 2011-2013.
Proposed fee structure
How long will proposed fee sustain program?
|  | Expected change in revenue (+/-) |  |  |  | 75000 |  |  | 21% | *
|  | Min GF required by statue/rule to fund program |  |  |  | 0 |  |  | 100%
|  | Proposed fee allows General Fund replacement |  |  |  | 0 |  |  | 100%
|  | Expected effective date |  |  |  | 2012-06-26
* Stated as a percentage of Legislatively Adopted Budget estimated revenue. It is a 29% increase over the four year average (of $338,337) and a 52% increase over the reduced amount generated in 2011 ($287,000).
[6 empty] | Number of | Impact on revenue |  |  | Total revenue
[6 empty] | transactions | (+/-) |  |  | (+/-)
|  |  | Current biennium |  |  | 170 | 75000 |  |  | 722000
|  |  | Next biennium |  |  | 340 | 150000 |  |  | 870000
Fee Schedule
In both the current and proposed fee structures, DEQ determines the market share for each registered manufacturer and assigns each to the appropriate tier schedule based on that market share. The proposed fee structure changes the existing market share tiers by adding two tiers and revising the market share percentages in all but the lowest tier. In addition, instead of establishing a set fee/tier, under the proposed model, DEQ will determine the fee for each tier listed below as follows:
|  |  | Market Share Tiers |  |  |  | Manufacture's Market Shares
|  |  | Tier 1 |  |  |  | 5% or greater
|  |  | Tier 2 |  |  |  | 1% to < 5%
|  |  | Tier 3 |  |  |  | 0.1% to < 1%
|  |  | Tier 4 |  |  |  | 0.03% to < 0.1%
|  |  | Tier 5 |  |  |  | 0.01% to < 0.03%
|  |  | Tier 6 |  |  |  | < 0.01%
To determine the fees for each tier, the individual market shares for the manufacturers in each tier are totaled. This total market share of each tier is multiplied by the total target revenue, which is $435,000 for 2012-2013, as described in the "Proposed Fee Structure, How long will proposed fee sustain program?" section above. Then, each tier's total revenue amount is divided by the number of manufacturers in that tier to obtain the fee for each manufacturer in that tier. After this first calculation, any Tier for which the calculated fee is less than the $200 minimum, the fee is set to $200. The total target revenue is reduced by the total amount paid by the minimum fee payers each year. This is $26,000 paid by Tier 5 & 6 using the 2011 market share sample fee model calculations.
Once the Tier fees are determined, any amount of the individual manufacturers fees over the $40,000 cap are added to the lower tier’s fees. If this addition raises any fees in the next tier over the cap, this new overage is again added to the fees of the manufacturers in the lower tiers. This process continues until all fees are at the cap or below.
Land use evaluation
|  | “It is the Commission's policy to coordinate the Department's programs, rules and actions that affect land use with local acknowledged plans to the fullest degree possible.” | [8 empty] | ORS 197.180
OAR 340-018
OAR 660-030-0005
|  | The proposed rules identified under the 'Chapter 340 Action' section above do not affect existing rules, programs or activities that are considered land use programs in the DEQ State Agency Coordination (SAC) Program. | [9 empty] | SAC |  | The proposed rules identified under the 'Chapter 340 Action' section above do not affect existing rules, programs or activities that are considered land use programs in the DEQ State Agency Coordination (SAC) Program.
|  | OAR 340-018-0030 does not include programs or actions that relate to the proposed rules. | [11 empty] | OAR 340-018-0030 does not include programs or actions that relate to the proposed rules.
DDL
DDL
|  | Existing statewide goal compliance and local plan compatibility procedures adequately cover the proposed rules. | [9 empty] | DDL
|  | Please explain | [9 empty] | Input |  | 1
To determine whether the rules involve programs or actions that are considered a land-use program, DEQ reviewed the statewide planning goals for specific references. Though not considered a land-use program, section III, subsection 2 of the SAC document identifies the following statewide goal that relates to DEQ's authority:
|  | Goal 6 - Air, Water and Land Resources Quality | [9 empty] | DDL
DEQ reasonably expects the program, rules or actions to have:
0
0
If the proposed rules have been determined a land use program above, but are not subject to existing land use compliance and compatibility procedures, explain the new procedures the Department will use to ensure compliance and compatibility.
Implementation
Public involvement
Workgroups and advisory committees
Committee charter
include section here that describes key public involvement dates.
|  | Committee members |  |  |  | Affiliation
>
Committee recommendation
|  | The EQC requested the following involvement with this rulemaking. | [11 empty] | The EQC requested the following involvement with this rulemaking.
|  | Facilitated hearing |  |  | Information item on agenda |  |  |  | In the Director's Dialog
|  | 2012-12-12 | [11 empty] | EQC - facilitated hearing not request | EQC - Information Item not requested | EQC - Director's Dialog not request
|  | Public Notice | [11 empty] | 0 | 0 | 0
Notice posted on DEQ webpage
http://www.deq.state.or.us/regulations/proposedrules.htm
Emailed notice to:
GovDelivery list of interested parties
Stakeholders
|  | Email notice to key legislators | [7 empty] | ORS 183.335
Jackie Dingfelder, Chair, Senate Environment and Natural Resources Committee
>
Mailed notice by U.S. Postal Service
Sent notice to EPA
|  | Notice published in SOS Bulletin |  |  | 2012-04-01
|  | Public comment period closed |  |  | 2012-06-26
Summary of comments and DEQ responses
|  | Comment summary | 1
Response
|  | Comment summary | 2
Response
|  | Comment summary | 3
Response
|  | Comment summary | 4
Response
|  | Comment summary | 5
Response
|  | Comment summary | 6
Response
|  | Comment summary | 7
Response
|  | Comment summary | 8
Response
|  | Comment summary | 9
Response
|  | Comment summary | 10
Response
|  | Comment summary | 11
Response
|  | Comment summary | 12
Response
|  | Comment summary | 13
Response
|  | Comment summary | 14
Response
|  | Comment summary | 15
Response
|  | Comment summary | 16
Response
|  | Comment summary | 17
Response
|  | Comment summary | 18
Response
|  | Comment summary | 19
Response
|  | Comment summary | 20
Response
|  | Comment summary | 21
Response
|  | Comment summary | 22
Response
|  | Comment summary | 23
Response
|  | Comment summary | 24
Response
|  | Comment summary | 25
Response
|  | Comment summary | 26
Response
|  | Comment summary | 27
Response
|  | Comment summary | 28
Response
|  | Comment summary | 29
Response
|  | Comment summary | 30
Response
|  | Comment summary | 31
Response
|  | Comment summary | 32
Response
Commenters
|  | Commenter ID | 1
=IF(L369>KDClosePubComment, "DEQ received comment after the public record closed and regulations prohibit considering it in the final recommendation.","")
|  | Commenter ID | 2
UNDER CONSTRUCTION
Note on A29: Statement of Need and Justification A "Statement of Need and Justification" explains the need for a temporary rulemaking action and the justification for submitting the changes as a temporary rule rather than using the permanent rule process. The Statement of Need and Justification form accompanies the Certificate and Order for Filing Temporary Rules. OAR 166-500-0010 (23) The APA "requires that an agency “take appropriate measures to make the temporary rules known to persons who may be affected by them.” This includes interested parties, organizations and agencies on the agency’s interested party mailing list, as well as and others who may be affected." ORS 183.355(2)(b) Where used:  Proposal - this section part of the EQC recommendation  Certificate and Order for Filing Temporary Rules
Note on A31: Statement of Need and Justification A "Statement of Need and Justification" explains the need for a temporary rulemaking action and the justification for submitting the changes as a temporary rule rather than using the permanent rule process. The Statement of Need and Justification form accompanies the Certificate and Order for Filing Temporary Rules. OAR 166-500-0010 (23) The APA "requires that an agency “take appropriate measures to make the temporary rules known to persons who may be affected by them.” This includes interested parties, organizations and agencies on the agency’s interested party mailing list, as well as and others who may be affected." ORS 183.355(2)(b) Where used:  Proposal - this section part of the EQC recommendation  Certificate and Order for Filing Temporary Rules
Note on A32: OBJECTIVE "An objective, simple and understandable statement summarizing the subject matter and purpose of the intended action in sufficient detail to inform a person that the person’s interests may be affected..."ORS 183.335(2)(a)(B) Use plain language that avoids complicated sentence and paragraph structures.
Note on A57: Federal relationship Requirement This section includes elements required to meet the following requirements. ORS 183.332 For policy statement and exemptions for adopting rules that correspond with equivalent federal laws. OAR 468A.321 (1) For facilities required to pay fees under ORS 468A.315 (emission fees for major sources) OAR 340-011-0029 For DEQ rules adopted in response to Senate Bill 107, section 3, 2007 session that apply to Oregon Title V Operating Permit Fees under OAR 340 Division 220. Processing note: The tense used in the phrase in the cell to the right changes as the rulemaking progresses. Where used:  Notice  Proposal
Note on A111: STATUTE IMPLEMENTED Definition Statutes ("Stats.") Implemented is the statute(s), bill(s) or federal legislation that an agency implements through the rulemaking process. OAR 166-500-0010 (25) Requirement The notice must include a citation of the statute or other law the rule is intended to implement. ORS 183.335(2)(b)(B) The project lead is responsible for verifying that all statutes entered into this cell are valid and accurate. Do not simply accept what was entered into the previously filed rules. Where used The statutes entered to the left are used on the:  notice  certificate of order and filing
Note on A114: STATUTORY AND OTHER LEAGAL AUTHORITY Definition Statutory Authority ("Stat. Auth.") is an agency's authority to make rules granted by Oregon Revised Statutes. OAR 166-500-0010 (24) Requirement The notice must include a citation of the statutory or other legal authority for the agency's rulemaking. ORS 183.335(2)(b)(A) The project lead is responsible for verifying that the statutory authorities entered into this cell are valid and accurate. Do not simply accept what was in the previously filed rules. All rules must include the EQC authority to adopt rules under ORS 468.020. If the proposed rule is a Title V rule, this cell must also include ORS 468A.020. Additionally, this cell must include any statutory authority to adopt these proposed rules. Cite ORS 468.020 for the EQC's general authority to adopt rules, ORS 468.065 if the proposed rules have to do with permits and fees. Where used The statutes entered to the right are used on the:  notice  certificate of order and filing
Note on A119: STATUTORY AND OTHER LEAGAL AUTHORITY Definition Requirement The notice must include a citation of the statutory or other legal authority for the agency's rulemaking. ORS 183.335(2)(b)(C) Where used The statutes entered to the left are used on the:  notice  certificate of order and filing
Note on A129: ADVISORY COMMITTEE Definition Requirement The notice must include a citation of the statutory or other legal authority for the agency's rulemaking. ORS 183.335(2)(b)(C) Where used The statutes entered to the left are used on the:  notice  certificate of order and filing
Note on A223: STATEWIDE GOALS The proposed rule is a land use rule if the SAC Program specifically references the rule, program, activity or action. Of the 19 statewide land use goals, goal 6 is the primary goal that relates to DEQ programs. The implementation of goals 5, 11, 16 and 19 may also relate to our programs because the goals consider the carrying capacity and protection of air and water resources. • Goal 6 - Air, Water and Land Resources • Goal 5 - Open Spaces, Scenic and Historic Areas, and Natural Resources • Goal 11 - Public Facilities and Services • Goal 16 - Estuarine Resources • Goal 19 - Ocean Resources
Note on A226: STATEWIDE GOALS The proposed rule is a land use rule if it relates to statewide land use goals that we reasonably expect to have a significant effect on: a. resources, objectives or areas identified in the statewide planning goals, or b. present or future land uses identified in acknowledged comprehensive plans. The land use responsibilities of a rule, program, action or activity that involved more than one agency are the responsibilities of the agency with primary authority. DEQ must consider our mandate to protect public health and safety and the environment when determining the land use significance.
Note on O8: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the perimeter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
mm/dd/yy
Subject
Your name
Your message
3/9/12
Open text in Word
Maggie
Most cells have Word functionality. To work in Word, double click over text.
Don't be concerned with the font size or page breaks since this will be normalized at publication.

## ScheduleTasks (hidden)
[8 empty] | GoToAHG |  |  | >
Schedule tasks |  | To restore cells in columns I and J to default, enter =AH followed by the current cell column and row. | [885 empty] | 1899-12-31 |  |  |  | EMT plan approval | 2011-11-17
Paced |  | Task complete |  |  |  |  | locked | DEQ closed |  |  | 0 |  |  | Action days | Weekend | DEQ closed | [10 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [6 empty] | Action days | Weekend | DEQ closed | [9 empty] | Action days | Weekend | DEQ closed |  |  |  |  | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [10 empty] | Action days | Weekend | DEQ closed | [12 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [12 empty] | Action days | Weekend | DEQ closed | [10 empty] | Action days | Weekend | DEQ closed | [18 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed |  |  |  |  | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed
|  |  | Workdays |  | Calendar Days | [882 empty] | add least amount of time - leisurely | time axis 2026-08-04 to 2028-12-27
Task |  | Owner | Task | Left | Task | Left | Start | End | [882 empty] | Column B Insert | time axis 2026-08-04 to 2028-12-27
Overview of key dates | [6 empty] | 2011-11-17 | 2012-08-10 | T | t | [877 empty] | 2011-11-17 | 2012-08-10
[9 empty] | Y | y
Select target EQC date |  | RDT |  | -3684 |  | -5157 | 2012-06-21 | 2012-06-21 | [879 empty] | 2012-06-21 | 2012-06-21
State Implementation Plan not involved |  | PE |  | -3730 |  | -5255 | 2012-03-15 | 2012-03-15 | S | [878 empty] | 2012-03-15 | 2012-03-15 | 4 | State Implementation Plan not involved
Fees not involved | > | RDT,RG | 125 | -3628 | 179 | -5107 | 2012-02-13 | 2012-08-10 | F | [878 empty] | 2012-08-10 | 2012-08-10 | 0 | Fees not involved
Submit/publish notice in SOS Bulletin | > | RG | 11 | -3719 | 17 | -5238 | 2012-03-15 | 2012-04-01 | N | [878 empty] | 2012-03-15 | 2012-04-01 | 60 | Submit/publish notice in SOS Bulletin
Hold first public hearing |  | RDT | 1 | -3709 | 0 | -5223 | 2012-04-16 | 2012-04-16 | H | [878 empty] | 2012-04-16 | 2012-04-16 |  | Hold first public hearing
Hold last public hearing |  | RDT | 1 | -3709 | 0 | -5223 | 2012-04-16 | 2012-04-16 | H | [878 empty] | 2012-04-16 | 2012-04-16 |  | Hold last public hearing
Close public comment |  | RG | 1 | -3706 | 0 | -5220 | 2012-04-19 | 2012-04-19 | N | [878 empty] | 2012-04-19 | 2012-04-19
Submit/attend EQC action meeting | > | PE,LM | 28 | -3663 | 41 | -5157 | 2012-05-11 | 2012-06-21 | E | [878 empty] | 2012-05-11 | 2012-06-21
Effective |  |  | 1 | -3660 | 0 | -5152 | 2012-06-26 | 2012-06-26 | [879 empty] | 2012-06-26 | 2012-06-26
Concept | [6 empty] | 2011-06-21 | 2011-11-17 | T | t | [877 empty] | 2011-06-21 | 2011-11-17
[9 empty] | Y | y
Develop concept annual DEQ Rulemaking Plan | [8 empty] | P
Solicite potential rulemaking proposals |  | ARC,LDA,LM | 11 | -3936 | 14 | -5509 | 2011-06-21 | 2011-07-05 | P | [878 empty] | 2011-06-21 | 2011-07-05
Conduct lead manager (LM) meeting |  | RG | 8 | -3928 | 9 | -5499 | 2011-07-06 | 2011-07-15 | P | [878 empty] | 2011-07-06 | 2011-07-15
Assign process expert (PE) |  | ARC | 1 | -3946 | 0 | -5523 | 2011-06-21 | 2011-06-21 | P | [878 empty] | 2011-06-21 | 2011-06-21
Identify & notify subject expert (SE) |  | LM,PE | 1 | -3946 | 0 | -5523 | 2011-06-21 | 2011-06-21 | P | [878 empty] | 2011-06-21 | 2011-06-21
Conduct SE training |  | RG | 1 | -3946 | 0 | -5523 | 2011-06-21 | 2011-06-21 | P | [878 empty] | 2011-06-21 | 2011-06-21
Draft what is known now on: | [8 empty] | P
Considerations | > | SE,PE,LM | 11 | -3936 | 14 | -5509 | 2011-06-21 | 2011-07-05 | P | [878 empty] | 2011-06-21 | 2011-07-05
Resources | > | SE,PE,LM | 8 | -3928 | 9 | -5499 | 2011-07-06 | 2011-07-15 | P | [878 empty] | 2011-07-06 | 2011-07-15
Plan view of ScheduleTasks | > | SE,PE,LM | 1 | -3946 | 0 | -5523 | 2011-06-21 | 2011-06-21 | P | [878 empty] | 2011-06-21 | 2011-06-21
Loop as needed | [8 empty] | P
Approve content |  | LM | 11 | -3925 | 14 | -5494 | 2011-07-06 | 2011-07-20 | P | [878 empty] | 2011-07-06 | 2011-07-20
Brief lead divion administrator |  | LM,SE,PE | 8 | -3917 | 11 | -5482 | 2011-07-21 | 2011-08-01 | P | [878 empty] | 2011-07-21 | 2011-08-01
Review |  | LDA | 1 | -3946 | 0 | -5523 | 2011-06-21 | 2011-06-21 | P | [878 empty] | 2011-06-21 | 2011-06-21
Loop as needed |  | RDT | [6 empty] | P
Approve content |  | LDA | 11 | -3914 | 14 | -5479 | 2011-07-21 | 2011-08-04 | P | [878 empty] | 2011-07-21 | 2011-08-04
Check in concept approved |  | PE | 8 | -3906 | 11 | -5467 | 2011-08-05 | 2011-08-16 | P | [878 empty] | 2011-08-05 | 2011-08-16
Draft consolidated annual DEQ Rulemaking Plan |  | ARC | 1 | -3990 | 0 | -5585 | 2011-04-20 | 2011-04-20 | P | [878 empty] | 2011-04-20 | 2011-04-20
Review and modify draft |  | RG | 8 | -3982 | 11 | -5573 | 2011-04-21 | 2011-05-02 | P | [878 empty] | 2011-04-21 | 2011-05-02
Consensus review of draft |  | LMs,LDAs | 1 | -3946 | 0 | -5523 | 2011-06-21 | 2011-06-21 | P | [878 empty] | 2011-06-21 | 2011-06-21
Loop as needed | [8 empty] | P
Prepare EMT presentation |  | ARC,LDA | 1 | -3946 | 0 | -5523 | 2011-06-21 | 2011-06-21 | P | [878 empty] | 2011-06-21 | 2011-06-21
EMT MEETING |  |  | 4 | -3839 | 3 | -5374 | 2011-11-14 | 2011-11-17 | P | [878 empty] | 2011-11-14 | 2011-11-17
Archive version 1.0 of the blueprint |  | RG | [6 empty] | Y
Start rulemaking | [6 empty] | 2011-11-18 | 2012-03-15 | T | t | [877 empty] | 2011-11-18 | 2012-03-15
[9 empty] | Y | y
Start rulemaking time horizon |  |  | 79 | -3754 | 118 | -5255 | 2011-11-18 | 2012-03-15 | SR | [878 empty] | 2011-11-18 | 2012-03-15
Identify core rule design team | > | LM,SE,PE |  |  |  |  | 2011-11-18 | 2011-11-23 | [879 empty] | 2011-11-18 | 2011-11-23
Develop team SharePoint |  | PE | 79 | -3754 | 118 | -5255 | 2011-11-18 | 2012-03-15 | SR | [878 empty] | 2011-11-18 | 2012-03-15
Rough draft what is known now on: | [8 empty] | SR
Considerations | > | SE,PE,LM | 79 | -3754 | 118 | -5255 | 2011-11-18 | 2012-03-15 | SR | [878 empty] | 2011-11-18 | 2012-03-15
Resources | > | SE,PE,LM | 79 | -3754 | 118 | -5255 | 2011-11-18 | 2012-03-15 | SR | [878 empty] | 2011-11-18 | 2012-03-15
ScheduleTasks - this worksheet | > | SE,PE,LM | 79 | -3754 | 118 | -5255 | 2011-11-18 | 2012-03-15 | SR | [878 empty] | 2011-11-18 | 2012-03-15
Proposal | > | SE,PE,LM | 79 | -3754 | 118 | -5255 | 2011-11-18 | 2012-03-15 | SR | [878 empty] | 2011-11-18 | 2012-03-15
Notify team members |  | LM | 77 | -3754 | 114 | -5255 | 2011-11-22 | 2012-03-15 | SR | [878 empty] | 2011-11-22 | 2012-03-15
Review workflow | > | RDT | 77 | -3754 | 114 | -5255 | 2011-11-22 | 2012-03-15 | SR | [878 empty] | 2011-11-22 | 2012-03-15
Team kickoff meeting |  | PE,LDA,RDT | -4 | -3754 | -5 | -5255 | 2012-03-20 | 2012-03-15 | SR | [878 empty] | 2012-03-20 | 2012-03-15
Schedule recurring team meetings |  | PE,RDT | -4 | -3754 | -5 | -5255 | 2012-03-20 | 2012-03-15 | SR | [878 empty] | 2012-03-20 | 2012-03-15
Draft Meeting Manager |  | PE | 80 | -3754 | 119 | -5255 | 2011-11-17 | 2012-03-15 | SR | [878 empty] | 2011-11-17 | 2012-03-15
Start draft rules | [8 empty] | SR
Contact ARC for new division/rule numbers |  | PE | 1 | -3753 | 0 | -5254 | 2012-03-16 | 2012-03-16 | SR | [878 empty] | 2012-03-16 | 2012-03-16
Check out/post current OAR compilation |  | PE | 1 | -3753 | 0 | -5254 | 2012-03-16 | 2012-03-16 | SR | [878 empty] | 2012-03-16 | 2012-03-16
Go to SIP section |  | PE | 10 | -3743 | 14 | -5240 | 2012-03-16 | 2012-03-30 | SR | [878 empty] | 2012-03-16 | 2012-03-30 | Go to SIP section
No advisory committee convened | [6 empty] | 2011-11-18 | 2012-08-10 | T | t | [877 empty] | 2011-11-18 | 2012-08-10 |  | No advisory committee convened
[9 empty] | Y | y
Advisory committee time horizon |  | RDT | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Advisory Committee Guide |  | RDT | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Considerations tab for involvement |  | RDT | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Identify potential committee members |  | RDT | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Identify charter consideration |  | RDT | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Review and refine charter considerations |  | RDT | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Approve charter considerations |  | LA | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Set potential meeting dates and venues |  | RDT |  |  |  |  | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Reserve potential venues |  | PA |  |  |  |  | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Develop committee communications |  | PE | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Script initial voice contact | [887 empty] | 2011-11-18 | 2012-08-10
Draft committee invitation |  | PE | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Draft committee website content |  | PE |  |  |  |  | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Review script, inviation and web content |  | RDT |  |  |  |  | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Loop as needed | [8 empty] | AC
Approve script, invitation and web content |  | LA | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Initial voice contact |  | RDT | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Post web content |  | PA | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Send invitation |  | PA | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Maintain web content |  | PE, PA | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Finalize meeting dates |  | RDT | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Release unneeded venues |  | PA |  |  |  |  | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Meeting 1 |  | PE | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Meeting mechanics tab |  | PA | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Identify meeting roles |  | RDT |  |  |  |  | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Invite stakeholder presenters, if any |  | PE |  |  |  |  | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Meeting preparation | [8 empty] | AC
Task 1 |  | Assign | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Task 2 |  | Assign | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Taks 3 |  | Assign | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Task 4 |  | Assign | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Task 5 |  | Assign | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Task 6 |  | Assign | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Task 7 |  | Assign | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Task 8 |  | Assign | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Notification | ` | PE | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Presentation |  | PE, RDT | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Loop as needed | [8 empty] | AC
Approve materials |  | PM | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Post materials on committee webpage |  | PA |  |  |  |  | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Send meeting notice with link to webpage |  | PA |  |  |  |  | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Presentation practice |  | RDT |  |  |  |  | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Hold meeting |  | RDT |  |  |  |  | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Draft minutes |  | PE | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Debrief conference |  | RDT | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Post draft minutes on website |  | PA | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Meeting 2 |  | PE | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Meeting mechanics tab |  | PA | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Identify meeting roles |  | RDT |  |  |  |  | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Invite stakeholder presenters, if any |  | PE |  |  |  |  | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Meeting preparation | [8 empty] | AC
Task 1 |  | Assign | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Task 2 |  | Assign | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Taks 3 |  | Assign | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Task 4 |  | Assign | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Task 5 |  | Assign | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Task 6 |  | Assign | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Task 7 |  | Assign | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Task 8 |  | Assign | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Notification | ` | PE | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Presentation |  | PE, RDT | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Loop as needed | [8 empty] | AC
Approve materials |  | PM | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Post materials on committee webpage |  | PA | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Send meeting notice with link to webpage |  | PA | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Presentation practice |  | RDT | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Hold meeting |  | RDT | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Draft minutes |  | PE | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Debrief conference |  | RDT | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Post draft minutes on website |  | PA | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Meeting 3 |  | PE | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Meeting mechanics tab |  | PA | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Identify meeting roles |  | RDT | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Invite stakeholder presenters, if any |  | PE | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Meeting preparation | [8 empty] | AC
Task 1 |  | Assign | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Task 2 |  | Assign | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Taks 3 |  | Assign | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Task 4 |  | Assign | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Task 5 |  | Assign | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Task 6 |  | Assign | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Task 7 |  | Assign | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Task 8 |  | Assign | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Notification | ` | PE | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Presentation |  | PE, RDT | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Loop as needed | [8 empty] | AC
Approve materials |  | PM | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Post materials on committee webpage |  | PA | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Send meeting notice with link to webpage |  | PA | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Dress rehersal |  | RDT | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Hold meeting |  | RDT | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Draft minutes |  | PE | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Debrief conference |  | RDT | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
Post draft minutes on website |  | PA | 181 | -3648 | 266 | -5107 | 2011-11-18 | 2012-08-10 | AC | [878 empty] | 2011-11-18 | 2012-08-10
State Implementation Plan | [6 empty] | 2012-01-13 | 2012-08-10 | T | t | [877 empty] | 2012-01-13 | 2012-08-10 |  | State Implementation Plan
[9 empty] | Y | y
Yada | [8 empty] | S
If idicator | [8 empty] | S | [878 empty] | 2012-01-13 | 2012-08-10
Yada |  | RDT | 145 | -3648 | 210 | -5107 | 2012-01-13 | 2012-08-10 | S | [878 empty] | 2012-01-13 | 2012-08-10
Yada yada | [8 empty] | S | [878 empty] | 2012-01-13 | 2012-08-10
yada | [8 empty] | S | [878 empty] | 2012-01-13 | 2012-08-10
yada yada yada | [8 empty] | S
yada yada yada | [8 empty] | S
Release Yada to EPA |  | LM | 0 | -33027 | 0 | -46238 | 0 | 0 | S
Fees not involved | [6 empty] | 2012-01-13 | 2012-08-10 | T | t | [877 empty] | 2012-01-13 | 2012-08-10 |  | Fees not involved
[9 empty] | Y | y
Fee approval horizon |  | RDT | 145 | -3648 | 210 | -5107 | 2012-01-13 | 2012-08-10 | F | [878 empty] | 2012-01-13 | 2012-08-10
Finalize Considerations: Fees | > | RDT | 145 | -3648 | 210 | -5107 | 2012-01-13 | 2012-08-10 | F | [878 empty] | 2012-01-13 | 2012-08-10
If DAS approval required | [8 empty] | F
Devlope fee approval packet |  | RDT | 145 | -3648 | 210 | -5107 | 2012-01-13 | 2012-08-10 | F | [878 empty] | 2012-01-13 | 2012-08-10
Considerations: fees | > |  | 145 | -3648 | 210 | -5107 | 2012-01-13 | 2012-08-10 | F | [878 empty] | 2012-01-13 | 2012-08-10
Proposal: fees | > |  | 145 | -3648 | 210 | -5107 | 2012-01-13 | 2012-08-10 | F | [878 empty] | 2012-01-13 | 2012-08-10
Fee schedule |  |  | 145 | -3648 | 210 | -5107 | 2012-01-13 | 2012-08-10 | F | [878 empty] | 2012-01-13 | 2012-08-10
Fee analysis | [6 empty] | 2012-01-13 | 2012-08-10 | F | [878 empty] | 2012-01-13 | 2012-08-10
Finalize packet |  |  | 145 | -3648 | 210 | -5107 | 2012-01-13 | 2012-08-10 | F | [878 empty] | 2012-01-13 | 2012-08-10
OPTION | [8 empty] | F
Email packet to DAS for informal review |  | PE | 145 | -3648 | 210 | -5107 | 2012-01-13 | 2012-08-10 | F | [878 empty] | 2012-01-13 | 2012-08-10
Address DAS concerns |  | PE, RDT | 145 | -3648 | 210 | -5107 | 2012-01-13 | 2012-08-10 | F | [878 empty] | 2012-01-13 | 2012-08-10
END OPTION | [8 empty] | F
Approve release of fee approval packet |  | LM | 145 | -3648 | 210 | -5107 | 2012-01-13 | 2012-08-10 | F | [878 empty] | 2012-01-13 | 2012-08-10
Agency rules coordinator cycle and submittal | [8 empty] | F | [878 empty] | 2012-01-13 | 2012-08-10
Plain English and style guide edit |  | ARC, OCO | 145 | -3648 | 210 | -5107 | 2012-01-13 | 2012-08-10 | F | [878 empty] | 2012-01-13 | 2012-08-10
Prepare submittal |  | ARC, RG | 145 | -3648 | 210 | -5107 | 2012-01-13 | 2012-08-10 | F | [878 empty] | 2012-01-13 | 2012-08-10
Email packet to DAS Director |  | DepDir | 145 | -3648 | 210 | -5107 | 2012-01-13 | 2012-08-10 | F | [878 empty] | 2012-01-13 | 2012-08-10
Lock fee approval: | > | ARC, RG | 145 | -3648 | 210 | -5107 | 2012-01-13 | 2012-08-10 | F | [878 empty] | 2012-01-13 | 2012-08-10
Considerations - fees | > | [7 empty] | F | [878 empty] | 2012-01-13 | 2012-08-10
Proposal - fees | > | [7 empty] | F | [878 empty] | 2012-01-13 | 2012-08-10
Archive blueprint |  | ARC, RG | [6 empty] | Y
Follow up for status |  | PE | 145 | -3648 | 210 | -5107 | 2012-01-13 | 2012-08-10 | F | [878 empty] | 2012-01-13 | 2012-08-10
If DAS denies - decide on action |  | PE, RDT | 145 | -3648 | 210 | -5107 | 2012-01-13 | 2012-08-10 | F | [878 empty] | 2012-01-13 | 2012-08-10
Loop as needed | [8 empty] | F
If DAS approves - retain for post-EQC process |  | PA | 1 | -3648 | 0 | -5107 | 2012-08-10 | 2012-08-10 | F | [878 empty] | 2012-08-10 | 2012-08-10
Public notice | [6 empty] | 2011-11-17 | 2012-04-19 | T | t | [877 empty] | 2011-11-17 | 2012-04-19 |  | Public notice | 119
[9 empty] | Y | y
Public notice time horizon |  | RDT | 48 | -3787 | 74 | -5300 | 2011-11-17 | 2012-01-30 | N | [878 empty] | 2011-11-17 | 2012-01-30
Schedule the following: | [6 empty] | Option 1 | Option 2 | O
EQC - Director's Dialog not request |  | PE,PA,RDT | -87 | -3774 | -126 | -5283 | 2012-06-21 | 2012-02-16 | O | [878 empty] | 2012-02-16 | 2012-02-16 |  | EQC - Director's Dialog not request
EQC - Information Item not requested |  | PE,PA,RDT | 1 | -3774 | 0 | -5283 | 2012-02-16 | 2012-02-16 | O | [878 empty] | 2012-02-16 | 2012-02-16 |  | EQC - Information Item not requested
EQC - facilitated hearing not request |  | PE,PA,RDT | 1 | -3774 | 0 | -5283 | 2012-02-16 | 2012-02-16 | O | [878 empty] | 2012-02-16 | 2012-02-16 |  | EQC - facilitated hearing not request
Reserve venues, equipment, supplies for:
Info meeting & hearings planned - FIRST |  | PE,PA,RDT | 1 | -3732 | 0 | -5223 | 2012-04-16 | 2012-04-16 | H | [878 empty] | 2012-04-16 | 2012-04-16 |  | Info meeting & hearings planned - FIRST
Hearings planned - next hearing |  | PE,PA,RDT | 1 | -3732 | 0 | -5223 | 2012-04-16 | 2012-04-16 | [879 empty] | 2012-04-16 | 2012-04-16 |  | Hearings planned - next hearing |  |  | SIP | 0
Hearings planned - next hearing |  | PE,PA,RDT | 1 | -3732 | 0 | -5223 | 2012-04-16 | 2012-04-16 | [879 empty] | 2012-04-16 | 2012-04-16 |  | Hearings planned - next hearing |  |  | Fees
Hearings planned - next hearing |  | PE,PA,RDT | 1 | -3732 | 0 | -5223 | 2012-04-16 | 2012-04-16 | [879 empty] | 2012-04-16 | 2012-04-16 |  | Hearings planned - next hearing |  |  | Public notice
Hearings planned - next hearing |  | PE,PA,RDT | 1 | -3732 | 0 | -5223 | 2012-04-16 | 2012-04-16 | [879 empty] | 2012-04-16 | 2012-04-16 |  | Hearings planned - next hearing |  |  | Info meeting
Hearings planned - next hearing |  | PE,PA,RDT | 1 | -3732 | 0 | -5223 | 2012-04-16 | 2012-04-16 | [879 empty] | 2012-04-16 | 2012-04-16 |  | Hearings planned - next hearing
Hearings planned - next hearing |  | PE,PA,RDT | 1 | -3732 | 0 | -5223 | 2012-04-16 | 2012-04-16 | [879 empty] | 2012-04-16 | 2012-04-16 |  | Hearings planned - next hearing
Hearings planned - LAST hearing |  | PE,PA,RDT | 1 | -3732 | 0 | -5223 | 2012-04-16 | 2012-04-16 | H | [878 empty] | 2012-04-16 | 2012-04-16 |  | Hearings planned - LAST hearing
OPTION | [8 empty] | N
Draft program webpage |  | PE, RDT | 80 | -3754 | 119 | -5255 | 2011-11-17 | 2012-03-15 | N | [878 empty] | 2011-11-17 | 2012-03-15 |  | 2012-03-15
Contribute and review |  | SE, RDT | 80 | -3754 | 119 | -5255 | 2011-11-17 | 2012-03-15 | N | [878 empty] | 2011-11-17 | 2012-03-15
Messaging, plain English review |  | OCO | 80 | -3754 | 119 | -5255 | 2011-11-17 | 2012-03-15 | N | [878 empty] | 2011-11-17 | 2012-03-15
Loop as needed | [8 empty] | N
Approve webpage |  | PM | 80 | -3754 | 119 | -5255 | 2011-11-17 | 2012-03-15 | N | [878 empty] | 2011-11-17 | 2012-03-15
END OPTION | [8 empty] | N
Lead drafting effort for Notice Packet: |  | PE | 80 | -3754 | 119 | -5255 | 2011-11-17 | 2012-03-15 | N | [878 empty] | 2011-11-17 | 2012-03-15 |  |  | 8
Announcement |  | RDT | 80 | -3754 | 119 | -5255 | 2011-11-17 | 2012-03-15 | N | [878 empty] | 2011-11-17 | 2012-03-15 |  |  | 8
Rules - verify team is using current compilation |  | PE | 80 | -3754 | 119 | -5255 | 2011-11-17 | 2012-03-15 | N | [878 empty] | 2011-11-17 | 2012-03-15 |  |  | 8
Overview | > | RDT | 80 | -3754 | 119 | -5255 | 2011-11-17 | 2012-03-15 | N | [878 empty] | 2011-11-17 | 2012-03-15 |  |  | 8
Statement of need | > | RDT | 80 | -3754 | 119 | -5255 | 2011-11-17 | 2012-03-15 | N | [878 empty] | 2011-11-17 | 2012-03-15 |  |  | 8
Freeform section | > | RDT | 80 | -3754 | 119 | -5255 | 2011-11-17 | 2012-03-15 | N | [878 empty] | 2011-11-17 | 2012-03-15 |  |  | 8
Federal relationships | > | RDT | 80 | -3754 | 119 | -5255 | 2011-11-17 | 2012-03-15 | N | [878 empty] | 2011-11-17 | 2012-03-15 |  |  | 8
Chapter 340 rules affected | > | RDT | 80 | -3754 | 119 | -5255 | 2011-11-17 | 2012-03-15 | N | [878 empty] | 2011-11-17 | 2012-03-15 |  |  | 8
Fiscal impact statement | > | RDT | 80 | -3754 | 119 | -5255 | 2011-11-17 | 2012-03-15 | N | [878 empty] | 2011-11-17 | 2012-03-15 |  |  | 8
Fees not involved | > | RDT | 80 | -3754 | 119 | -5255 | 2011-11-17 | 2012-03-15 | N | [878 empty] | 2011-11-17 | 2012-03-15 |  | Fees not involved | 8
Land Use | > | RDT | 80 | -3754 | 119 | -5255 | 2011-11-17 | 2012-03-15 | N | [878 empty] | 2011-11-17 | 2012-03-15 |  |  | 8
SIP not involved |  | SIPCo | 80 | -3754 | 119 | -5255 | 2011-11-17 | 2012-03-15 | N | [878 empty] | 2011-11-17 | 2012-03-15 |  | SIP not involved | 8
Supporting documents |  | RDT | 80 | -3754 | 119 | -5255 | 2011-11-17 | 2012-03-15 | N | [878 empty] | 2011-11-17 | 2012-03-15 |  |  | 8
Display advertisements |  | PE | 80 | -3754 | 119 | -5255 | 2012-01-27 | 2012-01-27 | N | [878 empty] | 2011-11-17 | 2012-03-15 |  | Display advertisements | 8
Obtain input from resources, specifically | > | PE | 41 | -3754 | 57 | -5255 | 2012-01-27 | 2012-01-27 | N | [878 empty] | 2012-01-18 | 2012-03-15 |  |  | 8
Advisory committee not involved | > | Committee | 41 | -3754 | 57 | -5255 | 2012-01-27 | 2012-02-01 | N | [878 empty] | 2012-01-18 | 2012-03-15 |  | Advisory committee not involved | 8
Fiscal impact statement | > | Budget | 80 | -3754 | 119 | -5255 |  |  | N | [878 empty] | 2012-01-18 | 2012-03-15 |  | Fiscal impact statement | 8
Proposal, announcement, notice, display ads |  | OCO | 80 | -3754 | 119 | -5255 | 2012-02-02 | 2012-02-02 | N | [878 empty] | 2012-01-18 | 2012-03-15 |  | Proposal, announcement, notice, display ads | 8
Proposal and rule review if needed |  | DOJ | 80 | -3754 | 119 | -5255 | 2012-02-02 | 2012-02-06 | N | [878 empty] | 2012-01-18 | 2012-03-15 |  | Proposal and rule review if needed | 8
Blueprint |  | ARC | 80 | -3754 | 119 | -5255 | 2012-02-07 | 2012-02-13 | N | [878 empty] | 2012-01-13 | 2012-03-15 |  |  | 10
Loop as needed | [8 empty] | N
Schedule LDA briefing meeting |  | PE | 3 | -3782 | 4 | -5293 | 2012-02-13 | 2012-02-13 | N | [878 empty] | 2012-01-27 | 2012-01-27
Meet for Notice Packet - final review |  | RDT | 1 | -3784 | 0 | -5297 |  |  | N | [878 empty] | 2012-01-27 | 2012-01-27
Approve Notice Packet release to LDA |  | LM | 4 | -3785 | 5 | -5298 |  |  | N | [878 empty] | 2012-01-27 | 2012-02-01 |  |  | 4
Archive blueprint | [6 empty] | 2012-02-14 | 2012-02-28 | Y
Brief lead division administrator |  | RDT | 1 | -3784 | 0 | -5297 | 2012-02-14 | 2012-02-28 | N | [878 empty] | 2012-02-02 | 2012-02-02 |  |  | 10
Lead division administrator review |  | LDA | 3 | -3782 | 4 | -5293 |  |  | N | [878 empty] | 2012-02-02 | 2012-02-06 |  |  | 10
Address LDA comments |  | RDT | 5 | -3777 | 6 | -5286 | 2012-02-29 | 2012-03-05 | N | [878 empty] | 2012-02-07 | 2012-02-13 |  |  | 5
Loop as needed | [6 empty] | 2012-02-29 | 2012-03-05 | N
Approve Notice Packet |  | LDA | 1 | -3777 | 0 | -5286 | 2012-03-06 | 2012-03-06 | N | [878 empty] | 2012-02-13 | 2012-02-13
Archive Notice Packet | [6 empty] | 2012-03-06 | 2012-03-08 | Y
OPEN PREVIEW PERIOD | [8 empty] | N
Notify EMT |  | LDA | 10 | -3766 | 14 | -5271 | 2012-03-09 | 2012-03-09 | N | [878 empty] | 2012-02-14 | 2012-02-28 |  |  | 14
DEQ Staff, specifically contributing resources |  | PE | 10 | -3766 | 14 | -5271 | 2012-03-09 | 2012-03-09 | N | [878 empty] | 2012-02-14 | 2012-02-28 |  |  | 14
CLOSE PREVIEW PERIOD | [6 empty] | 2012-03-09 | 2012-03-09 | N
Decide how to address any preview feedback |  | RDT | 4 | -3762 | 5 | -5265 | 2012-03-09 | 2012-03-09 | N | [878 empty] | 2012-02-29 | 2012-03-05
Modify notice documents as needed |  | PE | 4 | -3762 | 5 | -5265 | 2012-03-09 | 2012-03-14 | N | [878 empty] | 2012-02-29 | 2012-03-05 |  |  | 5
Verify rules use latest rule compilation |  | PE | 1 | -3761 | 0 | -5264 | 2012-03-09 | 2012-03-14 | N | [878 empty] | 2012-03-06 | 2012-03-06
Approve Notice Packet release |  | LM | 3 | -3759 | 2 | -5262 |  |  | N | [878 empty] | 2012-03-06 | 2012-03-08 |  |  | 2
Archive Notice Packet if changed | > | [5 empty] | 2012-03-15 | 2012-03-15 | Y
Submit SIP & DOJ approval to EPA |  | SIPCo | 1 | -3758 | 0 | -5261 |  |  | S | [878 empty] | 2012-03-09 | 2012-03-09 |  | SIP not involved, no EPA submittal required | 5
Notify ARC that Notice Packet is complete |  | PE | 1 | -3758 | 0 | -5261 | 2012-03-15 | 2012-03-15 | N | [878 empty] | 2012-03-09 | 2012-03-09 |  |  | 5
Activate public comment box | > | PA | 1 | -3758 | 0 | -5261 | 2012-03-15 | 2012-03-15 | N | [878 empty] | 2012-03-09 | 2012-03-09 |  |  | 5
Notify EQC Asssistant of potential EQC date |  | PA | 1 | -3758 | 0 | -5261 | 2012-03-15 | 2012-03-15 | N | [878 empty] | 2012-03-09 | 2012-03-09 |  |  | 5
Obtain electronic signoff from budget |  | PE | 4 | -3755 | 5 | -5256 | 2012-03-15 | 2012-03-15 | N | [878 empty] | 2012-03-09 | 2012-03-14 |  |  | 5 | 6
Perform final plain English review |  | ARC,OCO | 4 | -3755 | 5 | -5256 | 2012-03-15 | 2012-03-15 | N | [878 empty] | 2012-03-09 | 2012-03-14 |  |  | 5 | 6
Noticing sequence | [6 empty] | 2012-03-15 | 2012-03-15 | N
Post Notice to SOS |  | ARC | 1 | -3754 | 0 | -5255 |  |  | N | [878 empty] | 2012-03-15 | 2012-03-15
Save evidence to Archive | > | [5 empty] | 2012-03-15 | 2012-03-15 | N
Send packet to rules webrep |  | PA | 1 | -3754 | 0 | -5255 |  |  | N | [878 empty] | 2012-03-15 | 2012-03-15
Post packet to rules webpage |  | Webrep | 1 | -3754 | 0 | -5255 | 2012-03-15 | 2012-03-15 | N | [878 empty] | 2012-03-15 | 2012-03-15
Notify agency rulemaking list |  | PA | 1 | -3754 | 0 | -5255 |  |  | N | [878 empty] | 2012-03-15 | 2012-03-15
GovDelivery |  | PA | 1 | -3754 | 0 | -5255 | 2012-03-15 | 2012-03-15 | N | [878 empty] | 2012-03-15 | 2012-03-15
Program list not on GovDelivery |  | PA | 1 | -3754 | 0 | -5255 | 2011-11-17 | 2012-03-15 | N | [878 empty] | 2012-03-15 | 2012-03-15
Committee members not on GovDelivery |  | PA | 1 | -3754 | 0 | -5255 | 2011-11-17 | 2012-03-15 | N | [878 empty] | 2012-03-15 | 2012-03-15
Save evidence to Archive | > | [5 empty] | 2011-11-17 | 2012-03-15 | N
Notify key legislators by email | > | PE | 1 | -3754 | 0 | -5255 | 2011-11-17 | 2012-03-15 | N | [878 empty] | 2012-03-15 | 2012-03-15
Save evidence to Archive | > | [5 empty] | 2011-11-17 | 2012-03-15 | N
Post notice on Oregon Transparency |  | RG | 1 | -3754 | 0 | -5255 | 2011-11-17 | 2012-03-15 | N | [878 empty] | 2012-03-15 | 2012-03-15 |  | Post on Oregon Transparency
Save evidence to Archive | > | [5 empty] | 2012-01-18 | 2012-03-15 | N
Publish in local newspapers if required |  | PE,PA | 1 | -3754 | 0 | -5255 | 2012-01-18 | 2012-03-15 | N | [878 empty] | 2012-03-15 | 2012-03-15
Save evidence to Archive | > | [7 empty] | N
Verify notice published accurately in Bulletin |  | PE | 1 | -3743 | 0 | -5240 | 2012-03-30 | 2012-03-30 | N | [878 empty] | 2012-03-30 | 2012-03-30 |  |  | 1
Save Bulletin excerpt to Archive |  | PA | 1 | -3742 | 0 | -5237 | 2012-04-02 | 2012-04-02 | N | [878 empty] | 2012-04-02 | 2012-04-02 |  |  | 1
CLOSE PUBLIC COMMENT |  |  | 1 | -3729 | 0 | -5220 | 2012-04-19 | 2012-04-19 | N | [878 empty] | 2012-04-19 | 2012-04-19
Public hearings, comment, response | [8 empty] | T | t
[9 empty] | Y | y
Identify source of information |  |  | 0 | #REF! | -0.33333 |  | 2012-08-18 08:00 | 2012-08-18 | H
Identify research method (primary or secondary) |  |  | #VALUE! | #REF! | #VALUE! |  | 2012-08-19 08:00 |  | H
|  |  | #REF! | #REF! | #REF! |  |  |  | H
Close of public comment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | H
|  |  | #REF! | #REF! | #REF! |  |  |  | H
|  |  | #REF! | #REF! | #REF! |  |  |  | H
|  |  | #REF! | #REF! | #REF! |  |  |  | H
|  |  | #REF! | #REF! | #REF! |  |  |  | H
EQC preparation | [8 empty] | T | t
[9 empty] | Y | y
Verify rules use lateset compilation |  | PE, ARC | #VALUE! | #REF! | #VALUE! |  | 2012-08-25 08:00
Develop research information gathering tool |  |  | 0 | #REF! | -0.33333 |  | 2012-08-26 08:00 | 2012-08-26
Post EQC | [8 empty] | T | t
[9 empty] | Y | y
Verify and prepare filing |  |  | #VALUE! | #REF! | #VALUE! |  | 2012-09-13 08:00
Cover letter |  |  | #REF! | #REF! | #REF!
Certificate of order and filing |  |  | #REF! | #REF! | #REF!
Rules as adopted or amended |  |  | #REF! | #REF! | #REF!
Rules in redline/strickout |  |  | #REF! | #REF! | #REF!
Tables |  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
For exempt fees, DAS notification |  |  | #REF! | #REF! | #REF!
For non-exempt fees: |  |  | #REF! | #REF! | #REF!
Develop Part 2 cover letter |  |  | #REF! | #REF! | #REF!
Complete retained Fee Approval Form |  |  | #REF! | #REF! | #REF!
Distribute Part 2 documents |  |  | #REF! | #REF! | #REF!
Notify stakeholders and feepayers |  |  | #REF! | #REF! | #REF!
Lead administrator to notify legislators |  |  | #REF! | #REF! | #REF!
Thank you letters and survey to Advisory Committee |  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! |  | 2012-09-20 08:00 | 2012-06-26
Note on A7: ABOUT KEY DATES This section includes key dates. These dates meet Oregon's rulemaking requirements, avoid weekends, Oregon holidays and fulough days. They do not consider personal holidays, furlough days or the Governor's leave. The sections below the Key dates section provide the tasks to meet these dates.
Note on A12: SECRETARY OF STATE BULLETIN Requirement Before adopting amending or repealing any permanent rule, DEQ must give notice of our intended action in the Secretary of State Bulletin at least 14 days before the first hearing and 21 days before the effective date. ORS 183.335 (1) Administrative Procedures Act notice requirement ORS 183.341 (4) APA requirement to adopt agency noticing rules OAR 340-011-0002 (a) DEQ noticing rule ORS 468A.327 Facilities required to pay fees under ORS 468A.315 (emission fees for major sources) ORS 183.360 About Secretary of State's Bulletin Default The Bulletin publishes on the first of every month regardless of weekends or holidays. The blueprint calculates the date for publishing in the earliest Secretary of State Bulletin that allows 49 full days before the effective date for legislator notification under ORS 183.335 (15) and a minimum of 14 full days before the first hearing date under OAR 340-011-0002 (a). Where used The blueprint will use to default date and the adjustment days to: • Calculate other dates on the Schedule task tab, and • Report on the Proposal tab.
Note on A272: NOTIFY KEY LEGISLATORS DEQ best practice Though the law requires agencies notify key legislators based on the effective date of the proposed rule, DEQ best practice is to notify them when we post the notice on our rulemaking website. This allows legislators the opportunity to comment during public notice. The legislative team will help identify the key legislators described below. Depending on the subject matter, the lead division administrator or legislative team member may want to call the legislators. This Schedule tab provides reminders. Requirments Legislation passed in 2011 legislation, requires us to provide the notice electronically. Forty nine (49) days before the effective dated of the adopted, amended or repealed rule, DEQ must notify the key legislators of our intended action. ORS 183.335(1)(d) If the proposed adoption, amendment or repeal: • Results from legislation that was passed within two years beforegiving notice under ORS 183.335(1), DEQ must notify the: -- Legislator who introduced the bill -- Chair or co-chairs of all committees that reported the bill out except for those committees whose sole action on the bill was referral to another committee. • Does not result from legislation that was passed within two years before giving notice under ORS 183.335(1), DEQ must notify the chair or co-chairs of any interim or session committee with authority over the subject matter of the rule. If DEQ is unable to notify the legislators above, we must notify the Speaker of the House of Representatives and the President of the Senate who are in office on the notice date. ORS 183.335(15) Where used Calculate some dates on the Schedule tasks tab, Legislators’ listed on the Proposal tab Legislators’ email tab
Note on A277: NOTIFY AGENCY MAILING LIST Requirement Before adopting amending or repealing any permanent rule, DEQ must give notice of our intended action to the agency mailing list least 14 days before the first hearing but no later than 21 days before the effective date. This discussion does not address requests to hold an oral hearing by 10 or more persons under ORS 183.335(3) to before the Commission under OAR 340-011-0029(3). ORS 183.335 (8) Administrative Procedures Act mailing list requirement ORS 183.330(2) APA requirement for agency rules coordinator to maintain and make available the mailing list. OAR 340-011-0002 (b) DEQ rule requiring notifying persons on the department’s mailing list Default The blueprint calculates the date for notifying the agency mailing list as the same day that we send notification to legislators and at least 14 full days before the first hearing date under. Where used The blueprint will use to default date and the adjustment days to: • Calculate some dates on the Schedule tasks tab, and • Report on the Proposal tab.
Note on A282: NOTIFY KEY LEGISLATORS DEQ best practice Though the law requires agencies notify key legislators based on the effective date of the proposed rule, DEQ best practice is to notify them when we post the notice on our rulemaking website. This allows legislators the opportunity to comment during public notice. The legislative team will help identify the key legislators described below. Depending on the subject matter, the lead division administrator or legislative team member may want to call the legislators. This Schedule tab provides reminders. Requirments Legislation passed in 2011 legislation, requires us to provide the notice electronically. Forty nine (49) days before the effective dated of the adopted, amended or repealed rule, DEQ must notify the key legislators of our intended action. ORS 183.335(1)(d) If the proposed adoption, amendment or repeal: • Results from legislation that was passed within two years beforegiving notice under ORS 183.335(1), DEQ must notify the: -- Legislator who introduced the bill -- Chair or co-chairs of all committees that reported the bill out except for those committees whose sole action on the bill was referral to another committee. • Does not result from legislation that was passed within two years before giving notice under ORS 183.335(1), DEQ must notify the chair or co-chairs of any interim or session committee with authority over the subject matter of the rule. If DEQ is unable to notify the legislators above, we must notify the Speaker of the House of Representatives and the President of the Senate who are in office on the notice date. ORS 183.335(15) Where used Calculate some dates on the Schedule tasks tab, Legislators’ listed on the Proposal tab Legislators’ email tab
Note on A284: OREGON TRANSPARENCY POSTING Requirement In addition to the information described in subsection (3) of this section, each state agency shall post on the Oregon transparency website notices of public meetings required to be provided by the state agency under ORS 192.640. ORS 184.483 (4) Background The passage of HB 2788 in 2011 adds an additional step to noticing public hearings for rulemaking. This includes all rulemaking hearings. The bill amends ORS 184.480, which defines “state agency” and 184.483(4), which directs all agencies to post notices of: • public meeting required under ORS 192.640, • on the Oregon transparency website, and • starting January 1, 2012.
Note on D6: DC DAS contact for fees LDA Lead divisiion administrator LM Lead manager PE Project assistant PL Process lead RDT Rule design team RG Rules Group TL Technical lead
mm/dd/yy
Subject
Your name
Your message

## InterestedParties (hidden)
Interested parties | [6 empty] | Learn more about the participant |  |  | Phones |  | Mailing information | [8 empty] | Help establishing the committee
Affiliation | Name | Participation | Email | 1.29.12 meeting | 1.26.12 meeting | 3nd meeting | Category | Expertise | Weblink | Preferred | Alternate | Salutation | Last name | First name | Title | Address 1 | Address 2 | City | State | Zip | Staff to Contact | InvitationNotes | Appointment
Marion county | Payne Bailey | advisory committee | bpayne@co.marion.or.us | in person | phone | [6 empty] | Ms | Payne | Bailey
Electronics Unlimited | Jarvis Beckey | advisory committee | becky@eucomputers.net | in person | [7 empty] | Ms | Jarvis | Beckey
Electronic Manufacturers Recycling Managment | Patton Betty | advisory committee | BPatton@EnvironmentalPractices.com | in person | [7 empty] | Ms | Patton | Betty
Total Reclaim | Lorch Craig | advisory committee | clorch@totalreclaim.com | in person | [7 empty] | Mr | Lorch | Craig
Computer Technology Link | Stromquist Erik | advisory committee | estromquist@ctlcorp.com | [8 empty] | Mr | Stromquist | Erik
Planar | Zuro Gail | advisory committee | gail.zuro@planar.com |  | in person | [6 empty] | Ms | Zuro | Gail
NCER | Linnell Jason | advisory committee | jlinnell@electronicsrecycling.org | in person | phone | [6 empty] | Mr | Linnell | Jason
Hewlett Packard | Kuypers Jeff | advisory committee | jeff.kuypers@hp.com | in person | [7 empty] | Mr | Kuypers | Jeff
TechAmerica | Craven Jim | advisory committee | jimcravenconsulting@gmail.com | in person | phone | [6 empty] | Mr | Craven | Jim
ORRA | Fortier Lee | advisory committee | lfortier@roguedisposal.com | [9 empty] | Fortier | Lee
Lenovo (US) | Jacques Mary | advisory committee | maryjacques@lenovo.com | in person | phone | [6 empty] | Ms | Jacques | Mary
Samsung Electronics | Moss Michael | advisory committee | mikem@sea.samsung.com | [8 empty] | Mr | Moss | Michael
Dell Marketing (USA) | Watson Mike | advisory committee | mike_watson@dell.com |  | phone | [6 empty] | Mr | Watson | Mike
Portland Metro Regional Government | Klag Scott | advisory committee | Scott.Klag@oregonmetro.gov | in person | in person | [6 empty] | Mr | Klag | Scott
Garten Foundation | Rocak Tim | advisory committee | trocak@garten.org | in person | [7 empty] | Mr | Rocak | Tim
Sanyo | Manley Craig | stakeholder | cmanley@sanyotv.com |  | phone | [6 empty] | Mr | Manley | Craig
Panasonic | Vernam Rick | stakeholder | vernamr@us.panasonic.com | in person | [7 empty] | Mr | Vernam | Rick
MRM | Conroy Tricia | stakeholder | Tricia@mrmrecycling.com |  | phone | [6 empty] | Ms | Conroy | Tricia
MRM | Marella Frank | stakeholder | mrmnj@hotmail.com |  | phone | [7 empty] | Marella | Frank
Tektronix | Fretwell Katt | stakeholder | katt.fretwell@tek.com |  | phone | [7 empty] | Fretwell | Katt
| Spivey Curt | stakeholder | cspivey@ecsrefining.com | [9 empty] | Spivey | Curt
Habitat for Humanity | Henry Beau | stakeholder | bhenry@bentonhabitat.org | [9 empty] | Henry | Beau
Consumer Electronics | Acorn Walter | stakeholder | walcorn@ce.org | in person | phone | [7 empty] | Acorn | Walter
| Kumar Dinesh | stakeholder | dkumar@warren-news.com | [9 empty] | Kumar | Dinesh
TRI | Irvine Todd | stakeholder | tirvine@totalreclaim.com | in person | in person | [7 empty] | Irvine | Todd
|  | stakeholder | paulpony4@hotmail.com
IMS | Peterson Bill | stakeholder | bpeterson@universalrecyclers.com | in person | [8 empty] | Peterson | Bill
Funai | Chason Gregg | stakeholder | gregg.chason@pnf-usa.com | in person | [8 empty] | Chason | Gregg
URT | Diaz Devon | stakeholder | ddiaz@universalrecyclers.com | in person | in person | [7 empty] | Diaz | Devon
IPR | Eudis Aaron | stakeholder | aeudis@wm.com |  | in person | [7 empty] | Eudis | Aaron
DEQ | Boudouris Abby | committee adjunct | boudouris.abby@deq.state.or.us |  | in person | [7 empty] | Boudouris | Abby
DEQ | Nuttall Christie | DEQ staff | Nuttall.christie@deq.state.or.us | in person | in person | [7 empty] | Nuttall | Christie
DEQ | Palmeri Jordan | committee adjunct | palmeri.jordan@deq.state.or.us | in person | [8 empty] | Palmeri | Jordan
DEQ | Perry Mary Lou | committee adjunct | perry.marylou@deq.state.or.us |  | in person | [7 empty] | Perry | Mary Lou
DEQ | Pickerell Loretta | committee adjunct | pickerell.loretta@deq.state.or.us | in person | [8 empty] | Pickerell | Loretta
DEQ | Shepperd Michele | DEQ staff | shepperd.michele@deq.state.or.us |  | in person | [7 empty] | Shepperd | Michele
DEQ | Vandehey Maggie | DEQ staff | vandehy.maggie@deq.state.or.us | in person | [8 empty] | Vandehey | Maggie
DEQ | Woodrow Beth | committee adjunct | woodrow.beth@deq.state.or.us | in person | [8 empty] | Woodrow | Beth
DEQ | Pollock Andre | DEQ staff | pollock.andre@deq.state.or.us |  | in person | [7 empty] | Pollock | Andre
DEQ | Kiwala Kathy | DEQ staff |  | in person | [8 empty] | Kiwala | Kathy
DEQ | Wiles Wendy | DEQ staff | wiles.wendy@deq.state.or.us | in person | [8 empty] | Wiles | Wendy
DEQ | Pickens Chris | committee adjunct | pickens.chris@deq.state.or.us |  | in person | [7 empty] | Pickens | Chris
Note on B1: This is a concatenation of the first and last name of the participant entered under Mailing Information to the right.
Note on C1: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on D1: EMAIL ADDRESS To enter an email address: • Right mouse click • Select Hyperlink • Select E-mail Address • Enter Person’s name in Text to display: • Enter Person’s email address in E-mail address:
mm/dd/yy
Subject
Your name
Your message

## FeeApprovalForm (hidden)
Fee Approval Form |  |  | Request for fee no fee involvement |  |  | Original Fee Approval Form 107BF21 (aka 333)
Part 1
#NAME? | [5 empty] | Original Fee Change Detail Form 107BF22
Update Oregon rules to address federal air quality regulations
Agency |  |  |  | Date DAS Received:
Department of Environmental Quality
Agency number |  | Chapter
34000 |  | 340
Program
Land Quality
Brief description of fee change
0
| Anticipated rule adoption date |  | Anticipated SOS rule filing |  | Fee effective date
| 2012-06-21 |  | 2012-06-26 |  | 2012-06-26
| Proposed E-Board action |  | Contact |  | Phone number
| does not apply |  | Jerry Ebersole |  | (503) 229-6974
DAS Signature Box
| Approve |  |  | Deny
| Reviewer |  |  |  | Date
| Director, Department of Administrative Services |  |  |  | Date
Note: | Approval good only through July 1 of the next odd-numbered year or sine die, whichever is later, unless approved in legislation by the Regular Session of the Legislative Assembly.
Part 2
Administrative Rule Reference
| Actual fee amount(s) adopted |  | Date fee adopted or effective
| Agency Rule Coordinator |  |  |  | Date
Data Classification: Level 1 – Published |  |  |  | FeeApprovalForm
Fee Change Detail |  |  |  | Form Purpose
Administrative Rule
|  |  |  | Concept # | Policy Package #
|  |  |  | -0.1 | -0.1
Rule Caption
Update Oregon rules to address federal air quality regulations
Rule Title
0
Brief description of rule
#NAME? | [5 empty] | You have identified the purpose of this form as Administrative Rule. The orange instructions below are unique to the form selected.
Submit form (107BF22) to DAS with Fee Approval Form(107BF21) when changing fees administratively.
Reason for Fee Change
costs exceed estimate |  |  | #NAME?
change in fee payer mix |  |  | #NAME?
#NAME?
#NAME?
Program Funding Summary
|  | Date of last change | Current program costs covered by fee revenues.
Current |  | 2007-10-01 | 360000 |  | 100%
Fees | How long will fee sustain program? |  | Current program costs covered by General Fund
|  |  | 360000 |  | 0%
New Fees | How long will fee sustain program? |  | Minimum GF portion required by statute/rule to fund program.
|  |  | 0 |  | 0%
Proposed fee allows General Fund replacement.
|  |  | 0 |  | 0%
Biennium |  | Number of transactions | Impact on revenue (+/-). |  | Total revenue (+/-).
Current
Next |  |  | 0 |  | 0
Alternatives Considered | [5 empty] | ...proposes changes to more than one program, make another copy of the Fee Change Detail worksheet.
#NAME?
Affected Parties
Who pays the fees | [5 empty] | ...is based on a sliding scale provide a spreadsheet showing calculations.
Program stakeholders
Line 36 is only available if the Form Purpose is Administrative Rule.
Fee payer and stakeholder involvement in fee setting process
#NAME?
Summarize stakeholder opposition comments
Summary of impacts
Data Classification: Level 1 – Published |  |  |  | FeeChangeDetail
Note on A3: PART 1 Part 1 of this form originates on the Proposal. The shaded area is reserved for DAS date-stamp.
Note on A22: DAS SIGNATURE BOX The shaded area to the right is reserved for DAS signatures. DAS will return the signed form. The signed form will be kept behind the FeeCoversheet in the rulemaking record until after EQC adopts fee. See FeeCoversheet tab.
Note on A30: DAS SIGNATURE BOX After the fees are adopted, complete Part 2 on the hard copy of the approved version with DAS original signature retained bewhind the Fee Approval and Notification cover sheet with other fee approval documents

## FEELetterPart1 (hidden)
Michael Jordan, Director |  |  | Please print on agency letterhead
Budget and Management Division
Department of Administrative Services
155 Cottage St NE, U10
Salem, OR 97301-3965
2026-08-04
RE: | Request for Fee Approval
Update Oregon rules to address federal air quality regulations
Dear Mr. Jordan:
The Department of Environmental Quality is planning a rulemaking that would adopt fees requiring Department of Administrative Service approval described on the enclosured Fee Approval Form and DEQ's equivelent to the fee detail form.
Please contact the following person if you have questions or need additional information.
| Jerry Ebersole | barrows.bob@deq.state.or.us
| Department of Environmental Quality | (503) 229-6974
Jerry Ebersole
Portland, OR 97204-1390
After signing the form, please return it to the contact above. Thank you for helping meet the deadlines on the fee approval form.
Sincerely,
Joni Hammond
Deputy Director
Enclosures
Cc: | Ken Rocco, Legislative Fiscal Office
Palmer Mason, Interim Government Relations Manager, DEQ
Jim Roys, MSD-Financial Srvices, DEQ
Wendy Wiles, Land Quality Division Administrator, DEQ
Loretta Pikerell, Land Quality, DEQ
Retain 10 years after repeal of entire rule |  | P1CoverLetter

## SIPLetter (hidden)
2012-01-24
Dennis McLarran, Regional Administrator | [5 empty] | Please print on agency letterhead
U.S. Environmental Protection Agency, Region 10
Department of Administrative Services
1200 Sixth Avenue
Seattle, WA 98101
RE: | Revision to the Oregon State Implementation Plan
Update Oregon rules to address federal air quality regulations
Dear Mr. McLerran:
The Oregon Department of Environmental Quality requests approval of revisions to the Oregon State Implementation Plan from the Office of Air, Waste, and Toxics, State and Tribal Air Programs Unit of the U.S. EPA, Region 10. DEQ transmits this letter and its attachments as provided in 40 CFR 51.104.
I certify that the:
1. | Oregon Environmental Quality Commission:
| a. Amended "&"Name of Rules on " | 2012-06-21
b. As a modification to the Oregon State Implementation Plan under OAR 340-200-0040.
2. | DEQ notified the public about the proposed rule amendments through the following publications. The following notices included a statement that the rule amendments would revise the State Implementation Plan:
| a. The Oregonian, a newspaper of general circulation, on |  | =KDSIPNotice
| b. The Secretary of State’s Bulletin |  | 2012-04-01
3. | DEQ held the following public hearings.
| =H1City&" hearing" |  | 2012-04-16
| =H2City&" hearing" |  | =KDHearing2
| =H3City&" hearing" |  | =KDHearing3
| =H4City&" hearing" |  | =KDHearing4
Thank you for EPA’s coordination with our agency during the rule development process and for your consideration of these revision to Oregon’s SIP. Please contact the following people for questions about:
| The enclosed rules | =Contact name | =Contact phone
| This SIP submission | Nicole Vick | (503) 229-5946
Sincerely,
Joni Hammond
Deputy Director
cc: | Donna Deneen, EPA, Region 10 | (3) complete sets | (2) redline rules | (1) Attachment 3
Paul Koprowski, EPA OR Operations office
Andrew Ginsburg, DEQ AQ Administrator
Nicole Vick, DEQ AQ SIP Coordinator
Data Classification: Level 1 – Published |  |  |  |  | SIPCoverLetter
affidavit

## SIP_Submittal (hidden)
ATTACHMENTS
Attachment
1 | Evidence the state has adopted the revision
| 1.1 | Staff Report, Agenda Item |  | A for the | 2012-06-21 |  | EQC meeting
See also, Certificate and Order for Filing Permanent Administrative Rules in Attachment 4.2.
2 | Evidence that the state has the necessary legal authority
| See "Commission Authority" on page number |  |  |  | # | of the Staff Report in Attachment 1.1.
|  | Staff Report, Agenda Item |  | A for the | 2012-06-21 |  | EQC meeting
3 | Provisions submitted for approval | [6 empty] | Attachment 1.1
| 3.1 | Adopted and amended rules submitted to Secretary of State
|  | 3.1a | General Air Pollution Procedures and Definitions 340-200-0040
|  | 3.1b | Rule title, 340-&Div1&Rule1, &Rule2, &Rule3, &Rule4
|  | 3.1c | Rule title, 340-&Div2&Rule1, &Rule2, &Rule3, &Rule4
|  | 3.1d | Rule title, 340-&Div3&Rule1, &Rule2, &Rule3, &Rule4
|  | 3.1e | Rule title, 340-&Div4&Rule1, &Rule2, &Rule3, &Rule4
| 3.2 | Redline/strikeout version of adopted and amended rules submitted to Secretary of State
4 | Evidence that the state followed the Administrative Procedures Act
| 4.1 | Public notice in the Secretary of State's Oregon Bulletin: | [5 empty] | 2012-04-01
| 4.2 | Certificate and Order for Filing Permanent Administrative Rules: | [5 empty] | 2012-06-26
filed and effective
5 | Evidence of adequate public notice
| 5.1 | Affidavit of Publication:
|  |  |  | publication |  |  |  | notice date
| 5.2 | Affidavit of Publication:
|  |  |  | publication |  |  |  | notice date
6 | Certification of public hearing
See paragraph #3 of cover letter and Attachment 7.1
7 | Compilation of public comments and department's response
| 7.1 | Presiding Officer's Report |  |  |  | for hearing held on
|  |  |  | report date |  |  |  | rulemaking hearing date
| 7.2 | Summary of public comment and agency response
response date
Data Classification: Level 1 - Published | [8 empty] | CoverAttachments
1/24/12
Maggie asks
Why not list it here rather the cover letter?
1/24/12
Maggie asks
Why not take this out of the cover letter and leave it here?
1/24/12
Maggie asks
Why duplicate the staff report information? Just reference 1.1 and page number.

## CertOfFilingPerm (hidden)
Secretary of State
Certificate and Order for Filing
PERMANENT ADMINISTRATIVE RULES
A Statement of Need and Justification accompanies this form. | [6 empty] | F
I certify the attached copies* are true, full and correct copies of the PERMANENT Rule(s) adopted on
2012-06-21
Oregon Department of Environmental Quality, Land Quality |  |  |  |  | 340
Agency and Division |  |  |  | Administrative Rules Chapter Number
Maggie Vandehey |  | 811 SW Sixth Avenue. Portland OR 97204-1390 |  |  |  | (503) 229-6878
Rules Coordinator |  | Address |  |  |  | Telephone
| 2012-06-26 |  |  | 2011-12-01
| to become effective |  |  | Rulemaking Notice published in the Oregon Bulletin
RULE CAPTION
Update Oregon rules to address federal air quality regulations
Not more than 15 words that reasonably identifies the subject matter of the agency’s intended action.
RULEMAKING ACTION
List each rule number separately, 000-000-0000.
Secure approval of new rule numbers (Adopted rules) with the Administrative Rules Unit prior to filing
ADOPT: | OAR 340-090-9999 340-090-9999 340-090-9999
AMEND: | OAR 340-090-9999 340-000-0000 340-000-0000
REPEAL: | OAR 340-000-0000
RENUMBER:
Stat. Auth.: | ORS 468.020, 468.065, 459A.345
Other Auth.:
Stats. Implemented: ORS | ORS 459A.315
RULE SUMMARY | #NAME?
|  |  | Maggie Vandehey |  | 2012-06-26
Authorized Signer
*With this original, file one photocopy of certificate, one paper copy of rules listed in Rulemaking Actions, and electronic copy of rules. **The Oregon Bulletin is published the 1st of each month and updates rules found in the OAR Compilation.

## DASEMAIL (hidden)
EMAIL
RECIPIENTS
TO… JORDAN Michael J * DO EXEC
Cc… PEARSON Lisa * BAM Analysts; PERRY Marylou; MASON Palmer; ROYS Jim; WILES Wendy; PICKERELL Loretta; VANDEHEY Maggie
TRACKING OPTIONS
Under tracking options, please check Request a Delivery Receipt and Request a Read Receipt. Forward receipts to Mary Lou Perry.
START EMAIL
Dear Mr. Jordan:
The Department of Environmental Quality is planning a rulemaking that would increase E-Cycles registration fees that require Department of Administrative Service approval. DEQ plans to submit the Notice of Proposed Rulemaking to Secretary of State on March 15, 2012. Our best practice is to have DAS approval before we go out for public notice.
The fee approval documents in the attachment include:
· DEQ’s system-generated Fee Approval Form that simulates DAS form 107BF22.
· DEQ's system-generated Fee Detail form that captures information requested on form 107BF22, it’s instructions and the instructions for the cover letter.
· Sample fee calculations using DEQ proposed registration fee model
· Fee Structures Used For Calculations
Please contact the following person if you have questions or need additional information about the fees.
| Marylou Perry | perry.marylou@deq.state.or.us
| Department of Environmental Quality | (503) 229-5731
811 SW Sixth Avenue
Portland, OR 97204-1390
If you have any questions about DEQ’s new rulemaking system or the format, please contact Maggie Vandehey at (503) 228-6878 or Maggie.vandehey@deq.state.or.us.
Joni Hammond
Deputy Director
END EMAIL
Thank you.
Maggie Vandehey
ext. 6878

## Sheet1 (hidden)
PEARSON Lisa * BAM Analysts; ROCCO Ken G
MASON Palmer; WESTBROOK Esther; ROICK Tom; GINSBURG Andy; OLIPHANT Margaret; ROYS Jim; LAWRENCE Richard; SHIN Sohng; STEVENS-SCHWENGER Joanie

## ACThankYou (hidden)
<<Date>>
<<ACMember_Name>>, <<ACMember_Title>>
<<ACMember_Company>>
<<ACMember_Add1>>
<<ACMember_Add2>>
<<ACMember_City>>, <<ACMember_State>>, <<ACMember_Zip>>
RE:
Dear <<ACMember_Salutaion>>, <<ACMember_LastName>>,
Thank you for serving on the <name of rulemaking> Advisory Committee. I understand your ideas, enthusiasm and commitment helped staff develop what we anticipate will be an effective <name program>. The Environmental Quality Commission adopted the evidence of your <Name of rulemaking> work on <adoption date>.
<Mr./Ms> <Contact Last Name>, I would like to know about your experience serving on the committee. The <Name of rulemaking> survey should take under 10 minutes. Staff will use survey responses to better support our citizen advisory committees.
I view stakeholder involvement essential in developing equitable rules to guide DEQ administration of Oregon’s environmental laws. We could not do our part without you. Thank you.
Gratefully yours,
Dick Pedersen, Director DEQ

## DDLs (hidden)
DDLs called from Considerations
DDL_BrainstormingAction
align
carry out
create
expand
eliminate
implement
improve
incorporate
maintain
prevent
reduce
solve
simplify
support
streamline
resolve conflict
Called from Considerations
DDL_BrainstormingObject
Oregon law
a commitment in PPA
science applicable to Oregon
new legislation
a court order
DEQ business process
an external process
a known environmental problem
a suspected environmental problem
advisory committee recommendation
EQC directions
DEQ strategic directions
workload
existing regulatory program
insufficient funding
new regulatory program
rules for obsolete program
cross program coordination
Called from Considerations
DDL_BrainstormingDriver
Oregon law
new legislation
court order
federal regulations
regulated community
scientific community
environmental group
stable funding source
EPA direction
EQC direction
program business decision
Sustainable funding model
DEQ business decision
Called from Considerations
DDL_PermitType | Air quality | Onsite | Solid waste | Water quality
Air quality | Asbestos License | Onsite Installers and Maintenance Provider Certification | Closure Permit | National Pollutant Discharge Elimination System permit
Onsite | Air Contaminant Discharge Permit | Construction-installation Permit | Composting Facility Permit or Registration | Sewage Disposal Service Business Licensing
Solid waste | Air Quality Registrations | Sewage Disposal Service Licences | Energy Recovery Facility Permit | Stormwater Discharge permit
Water quality | Open Burning Letter Permit | Product Approvals | Incineration Facility Permit | Underground Injection Control registration/permits
Called from Considerations | Tanker Certification | Water Pollution Control Facilities Permit | Land Disposal Site Permit | WastewaterSystem Operator Certification
| Ttle V permit | Site Evaluation | Solid Waste Disposal Permit | Water Pollution Control Facilities Permit
| Vehicle Emissions Certification | Authorization Notice | Solid Waste Letter Authorization Permit | Water Quality Permit Program
| NESHAP | Existing System Evaluation | Solid Waste Treatment Facility Permit
| NSPS | Variance | Transfer Station/Material Recovery Facility Permit
DDL_ControversyRating | VL_ControversyRating
does not apply | 0
definitely not controversial | 1
potential for minor controversy | 3
unknown | 5
potential for moderate controversy | 6
potential for major controversy | 8
definitely controversial | 10
Called from Considerations
DDL_ComplexityRating | VL_ComplexityRating
does not apply | 0
definitely not complex | 1
potential for minor complexity | 3
unknown | 5
potential for moderate complexity | 6
potential for major complexity | 8
definitely complex | 10
Called from Considerations
DDL_CriticalityRating | VL_CriticalityRating
does not apply | 0
definitely not critical | 1
minor criticality | 3
unknown | 5
moderate criticality | 6
high criticality | 8
definitely critical | 10
Called from Considerations
DDL_EnvironmentalProblem
has no direct correlation to the environment.
addresses an environmental problem directly.
addresses an environmental problem indirectly.
prevents a known problem.
solves a known problem.
prevents a suspected problem.
solves a suspected problem.
Called from Considerations
DDL_RiskOfRejectingConcept
loss of delegation
noncompliance
rule does not align with law
advisory committee commitment
science not applicable to Oregon
loss of federal funding
loss of program funding
loss of reputation
increased difficulty doing business
failure to keep commitment
a problem we suspect will occur
Called from Considerations
DDL_Media
air
cross media
land
water
Called from Considerations
Risk evaluation DDLs on Considerations
DDL_FiscalComplexityRating | VL_FiscalComplexityRating
does not apply | 0
definitely not complex | 1
potential for minor complexity | 3
unknown | 5
potential for moderate complexity | 6
potential for major complexity | 8
definitely complex | 10
Called from Considerations
DDL_ScopeOfRule | VL_ScopeOfRule
does not apply | 0
definitely true | 1
somewhat true | 3
unknown | 6
somewhat false | 8
definitely false | 10
Called from Considerations
DDL_SupportForRule | VL_SupportForRule
does not apply | 0
definitely supportive | 1
somewhat supportive | 3
unknown or neutral | 6
somewhat opposed | 8
definitely opposed | 10
Called from Considerations
DDL_FiscalImpacts | VL_FiscalImpacts
no fiscal impacts | 0
significant cost decrease | 1
moderate cost decrease | 3
unknown | 6
moderate cost increase | 8
significant cost increase | 10
Called from Considerations
DDLs called from InterestedParties
DDL_MeetingAttendance
by phone
in person
Called from InterestedParties
DDL_RepresentativeOf - InterestedParties
business
environmental group
government
industry
producers
regulated parties
retailer
small business
tribal nations
Called from InterestedParties
DDL_Participation Used on InterestedParties
Advisor
Advisory committee member
Committee adjunct
DEQ staff
Fiscal advisor
Called from InterestedParties
Logical DDLs
DDL_YN
Y
DDL_TrueFalse
1899-12-31
DDL_YesNo
?
regulatory streamlining
policy change
Called from Proposal
DDLs called from Proposal
DDL_FeeChangeReason | VL_FeeChangeReason
regulatory streamlining | Please explain.
policy change | Please explain.
new fee created by statute | Identify session, bill number and interested legislators.
fee allowed in statute | Optional - provide useful information.
change in federal revenue | Optional - provide useful information.
change in Other Funds revenues | Optional - provide useful information.
increase in program costs | Provide overview of the increased costs.
increase in systems costs | Please explain.
change in transaction volume | Provide trend information and FTE workload statistics.
changed number of fee payers | Provide trend information and FTE workload statistics.
change in fee payer mix | Provide trend information.
response to legislative concerns | Optional - provide useful information.
underestimated operating costs | Please explain.
underestimated business systems development costs | Please explain.
overestimated operating costs | Please explain.
costs exceed estimate | Please explain.
response to legislative concerns | Identify session, committees, legislators and concerns.
Called from Proposal
DDL_FedConnection
has no corresponding federal regulation.
would achieve goals of federal law with least impact on public and private resources.
would have effect of clarifying the federal rules, standards, procedures or requirements.
would address local or special conditions that warrant a different rule.
has a federal waiver that warrants a different rule.
has specific statutory direction authorizes adoption.
would align Oregon rules with federal requirements.
would maintain federal delegation.
would maintain commitment in PPA.
would align with science applicable to Oregon.
would address public health issues in Oregon.
would address economic conditions in Oregon.
would incorporate technological advancement.
would incorporate administrative advancement.
would keep an advisory committee commitment.
would maintain federal funding.
would ensure program funding.
would ensure program support.
would ensure compliance.
would keep an EQC commitment.
would keep a stakeholder commitment.
reduce difficulty in doing business.
Called from Proposal
DDL_FedReqExceptions
ORS 183.332 does not list an exemption.
There is specific statutory direction to the agency that authorizes the adoption of the rule. ORS 183.332 (1)
A federal waiver has been granted that authorizes the adoption of the rule. ORS 183.332 (2)
Local or special conditions exist in this state that warrant a different rule; ORS 183.332 (3)
The state rule has the effect of clarifying the federal rules, standards, procedures or requirements. ORS 183.332 (4)
The state rule achieves the goals of the federal and state law with the least impact on public and private resources; ORS 183.332 (5)
There is no corresponding federal regulation. ORS 183.332 (6)
Called from Proposal
DDL_LandUseProceduresAdequate
Existing statewide goal compliance and local plan compatibility procedures adequately cover the proposed rules.
Existing statewide goal compliance and local plan compatibility procedures do not adequately cover the proposed rules.
Called from Proposal
DDL_SAC
(1)(a) Approval of Noise Impact Boundaries for Motor Racing Facilities
(1)(b) Approval of Airport Noise Abatement Program and Noise Impact Boundaries
(1)(c) Approval of Notice of Construction
(1)(d) Issuance of Air Contaminant Discharge Permit
(1)(e) Issuance of Indirect Source Construction Permit
(1)(f) Approval of Parking and Traffic Circulation Plan
(1)(g) Employee Commute Options
(2) Environmental Cleanup Division: Issuance of Environmental Hazard Notice
(3)(a) Issuance of Solid Waste Disposal Permit
(3)(b) Issuance of Waste Tire Storage Permit
(3)(c) Issuance of Hazardous Waste and PCB Storage, Treatment and Disposal Permit
(4) Management Services Division: Approval of Pollution Control Bond Fund Application
(5)(a) Approval of Wastewater System and Facility Plans
(5)(b) Approval of State Revolving Loan Application
(5)(c) Issuance of On-site Sewer Permit
(5)(d) Issuance of NPDES and WPCF Permits
(5)(e) Development of Water Quality Wetland Protection Criteria
(5)(f) Requirement of an Implementation Plan to Meet Restrictions for Waste Load Allocations on Water Quality Limited Waterways (TMDLS)
(5)(g) Certification of Water Quality Standards for Federal Permits, Licenses
(5)(h) Development of Action Plan for Declared Ground Water Management Area
(5)(i) Development of Nonpoint Source Management Plan
(5)(j) Development of Estuary Plans
Called from Proposal
DDL_LandUseGoals
Goal 6 - Air, Water and Land Resources Quality | requires that all waste and process discharges from development comply with state and federal environmental quality standards.
Goal 5 - Open Spaces, Scenic and Historic Areas, and Natural Resources
Goal 11 - Public Facilities and Services
Goal 16 - Estuarian resources
Goal 19 - Ocean Resources
Called from Proposal
DDL_EQCDirDilaog
Information through Director's Dialog.
No Director's Dialog
Called from Proposal
DDLs called from Resources
DDL_DEQResourcesInvolved | VL_DEQResourcesInvolved
0 hours | 0
>0 <2 hours | 1
=>2 <10 hours | 2
=>10 <20 hours | 3
=>20 <30 hours | 4
=>30 <40 hours | 5
=>40 <80 hours | 6
=>80 <120 hours | 7
=>120 <160 hours | 8
=>160 <200 hours | 9
=>200 hours | 10
Called from Resources
DDLs called from ScheduleTasks
DDL_EQCMeeting | EQCStaffRptDue | EQCMaterialsDue | VL_EQCActivities
2012-02-16 | 2012-01-12
2012-04-26 | 2012-03-16 | 2012-03-26
2012-06-21 | 2012-05-11 | 2012-05-28
2012-08-23 | 2012-07-13 | 2012-07-30
2012-10-25 | 2012-09-14 | 2012-10-01
2012-12-13 | 2012-11-02 | 2012-11-19
2013-02-21 | 2013-01-14
2013-04-18 | 2013-03-11 |  | Estimate
2013-06-20 | 2013-05-13 |  | Estimate
2013-08-22 | 2013-07-15 |  | Estimate
2013-10-24 | 2013-09-16 |  | Estimate
2013-12-12 | 2013-11-04 |  | Estimate
2014-02-20 | 2014-01-13 |  | Estimate
Called from ScheduleTasks
Holidays
2011-11-11 | Veterans
2011-11-24 | Thanksgiving
2011-11-25 | furlough
2011-12-25 | Christmas
2011-12-26 | State Observed Christmas
2012-01-01 | New Year
2012-01-02 | State Observed New Year 2012
2012-01-16 | MLK Jr.
2012-02-20 | Presidents
2012-03-23 | furlough
2012-05-25 | furlough
2012-05-28 | Memorial
2012-07-04 | Independence
2012-08-17 | furlough
2012-09-03 | Labor
2012-10-19 | furlough
2012-11-11 | Veterans
2012-11-12 | State Observed Veterans
2012-11-22 | Thanksgiving
2012-11-23 | furlough
2012-12-25 | Christmas
2013-01-01 | New Year
2013-01-18 | furlough
2013-01-21 | MLK Jr.
2013-02-18 | Presidents
2013-04-19 | furlough
2013-05-24 | furlough
2013-05-27 | Memorial
2013-07-04 | Independence
2013-09-02 | Labor
2013-11-11 | Veterans
2013-11-28 | Thanksgiving
2013-12-25 | Christmas
2014-01-01 | New Year
Called from ScheduleTasks
DDL_Bulletin | VL_Bulletin
2011-12-01 | 2011-11-15 | 2011-11-15 | 0
2012-01-01 | 2011-12-15 | 2011-12-15 | 0
2012-02-01 | 2012-01-13 | 2012-01-13 | 0
2012-03-01 | 2012-02-15 | 2012-02-15 | 0
2012-04-01 | 2012-03-15 | 2012-03-15 | 0
2012-05-01 | 2012-04-13 | 2012-04-13 | 0
2012-06-01 | 2012-05-15 | 2012-05-15 | 0
2012-07-01 | 2012-06-15 | 2012-06-15 | 0
2012-08-01 | 2012-07-13 | 2012-07-13 | 0
2012-09-01 | 2012-08-15 | 2012-08-15 | 0
2012-10-01 | 2012-09-14 | 2012-09-14 | 0
2012-11-01 | 2012-10-15 | 2012-10-15 | 0
2012-12-01 | 2012-11-15 | 2012-11-15 | 0
2013-01-01 | 2012-12-14 | 2012-12-14 | 0
2013-02-01 | 2013-01-15 | 2013-01-15 | 0
2013-03-01 | 2013-02-15 | 2013-02-15 | 0
2013-04-01 | 2013-03-15 | 2013-03-15 | 0
2013-05-01 | 2013-04-15 | 2013-04-15 | 0
2013-06-01 | 2013-05-15 | 2013-05-15 | 0
2013-07-01 | 2013-06-14 | 2013-06-14 | 0
2013-08-01 | 2013-07-15 | 2013-07-15 | 0
2013-09-01 | 2013-08-15 | 2013-08-15 | 0
2013-10-01 | 2013-09-13 | 2013-09-13 | 0
2013-11-01 | 2013-10-15 | 2013-10-15 | 0
2013-12-01 | 2013-11-15 | 2013-11-15 | 0
2014-01-01 | 2013-12-13 | 2013-12-13 | 0
2014-02-01 | 2014-01-15 | 2014-01-15 | 0
2014-03-01 | 2014-02-14 | 2014-02-14 | 0
2014-04-01 | 2014-03-14 | 2014-03-14 | 0
2014-05-01 | 2014-04-15 | 2014-04-15 | 0
2014-06-01 | 2014-05-15 | 2014-05-15 | 0
2014-07-01 | 2014-06-13 | 2014-06-13 | 0
2014-08-01 | 2014-07-15 | 2014-07-15 | 0
2014-09-01 | 2014-08-15 | 2014-08-15 | 0
2014-10-01 | 2014-09-15 | 2014-09-15 | 0
2014-11-01 | 2014-10-15 | 2014-10-15 | 0
2014-12-01 | 2014-11-14 | 2014-11-14 | 0
2015-01-01 | 2014-12-15 | 2014-12-15 | 0
2015-02-01 | 2015-01-15 | 2015-01-15 | 0
2015-03-01 | 2015-02-13 | 2015-02-13 | 0
2015-04-01 | 2015-03-13 | 2015-03-13 | 0
2015-05-01 | 2015-04-15 | 2015-04-15 | 0
2015-06-01 | 2015-05-15 | 2015-05-15 | 0
2015-07-01 | 2015-06-15 | 2015-06-15 | 0
2015-08-01 | 2015-07-15 | 2015-07-15 | 0
2015-09-01 | 2015-08-15 | 2015-08-15 | 0
2015-10-01 | 2015-09-15 | 2015-09-15 | 0
2015-11-01 | 2015-10-15 | 2015-10-15 | 0
2015-12-01 | 2015-11-13 | 2015-11-13 | 0
2016-01-01 | 2015-12-15 | 2015-12-15 | 0
2016-02-01 | 2016-01-15 | 2016-01-15 | 0
2016-03-01 | 2016-02-15 | 2016-02-15 | 0
2016-04-01 | 2016-03-15 | 2016-03-15 | 0
2016-05-01 | 2016-04-15 | 2016-04-15 | 0
2016-06-01 | 2016-05-13 | 2016-05-13 | 0
2016-07-01 | 2016-06-15 | 2016-06-15 | 0
2016-08-01 | 2016-07-15 | 2016-07-15 | 0
2016-09-01 | 2016-08-15 | 2016-08-15 | 0
2016-10-01 | 2016-09-15 | 2016-09-15 | 0
2016-11-01 | 2016-10-14 | 2016-10-14 | 0
2016-12-01 | 2016-11-15 | 2016-11-15 | 0
2017-01-01 | 2016-12-15 | 2016-12-15 | 0
2017-02-01 | 2017-01-13 | 2017-01-13 | 0
2017-03-01 | 2017-02-15 | 2017-02-15 | 0
2017-04-01 | 2017-03-15 | 2017-03-15 | 0
2017-05-01 | 2017-04-14 | 2017-04-14 | 0
2017-06-01 | 2017-05-15 | 2017-05-15 | 0
2017-07-01 | 2017-06-15 | 2017-06-15 | 0
2017-08-01 | 2017-07-14 | 2017-07-14 | 0
2017-09-01 | 2017-08-15 | 2017-08-15 | 0
2017-10-01 | 2017-09-15 | 2017-09-15 | 0
2017-11-01 | 2017-10-13 | 2017-10-13 | 0
2017-12-01 | 2017-11-15 | 2017-11-15 | 0
2018-01-01 | 2017-12-15 | 2017-12-15 | 0
2018-02-01 | 2018-01-15 | 2018-01-15 | 0
2018-03-01 | 2018-02-15 | 2018-02-15 | 0
2018-04-01 | 2018-03-14 | 2018-03-14 | 0
2018-05-01 | 2018-04-13 | 2018-04-13 | 0
2018-06-01 | 2018-05-15 | 2018-05-15 | 0
2018-07-01 | 2018-06-15 | 2018-06-15 | 0
2018-08-01 | 2018-07-13 | 2018-07-13 | 0
2018-09-01 | 2018-08-15 | 2018-08-15 | 0
2018-10-01 | 2018-09-14 | 2018-09-14 | 0
2018-11-01 | 2018-10-15 | 2018-10-15 | 0
2018-12-01 | 2018-11-15 | 2018-11-15 | 0
2019-01-01 | 2018-12-14 | 2018-12-14 | 0
2019-02-01 | 2019-01-15 | 2019-01-15 | 0
2019-03-01 | 2019-02-15 | 2019-02-15 | 0
2019-04-01 | 2019-03-15 | 2019-03-15 | 0
2019-05-01 | 2019-04-15 | 2019-04-15 | 0
2019-06-01 | 2019-05-15 | 2019-05-15 | 0
2019-07-01 | 2019-06-14 | 2019-06-14 | 0
2019-08-01 | 2019-07-15 | 2019-07-15 | 0
2019-09-01 | 2019-08-15 | 2019-08-15 | 0
2019-10-01 | 2019-09-13 | 2019-09-13 | 0
2019-11-01 | 2019-10-15 | 2019-10-15 | 0
2019-12-01 | 2019-11-15 | 2019-11-15 | 0
2020-01-01 | 2019-12-13 | 2019-12-13 | 0
2020-02-01 | 2020-01-15 | 2020-01-15 | 0
2020-03-01 | 2020-02-14 | 2020-02-14 | 0
2020-04-01 | 2020-03-13 | 2020-03-13 | 0
2020-05-01 | 2020-04-15 | 2020-04-15 | 0
2020-06-01 | 2020-05-15 | 2020-05-15 | 0
2020-07-01 | 2020-06-15 | 2020-06-15 | 0
2020-08-01 | 2020-07-15 | 2020-07-15 | 0
2020-09-01 | 2020-08-14 | 2020-08-14 | 0
2020-10-01 | 2020-09-15 | 2020-09-15 | 0
2020-11-01 | 2020-10-15 | 2020-10-15 | 0
2020-12-01 | 2020-11-13 | 2020-11-13 | 0
2021-01-01 | 2020-12-15 | 2020-12-15 | 0
2021-02-01 | 2021-01-15 | 2021-01-15 | 0
2021-03-01 | 2021-02-15 | 2021-02-15 | 0
2021-04-01 | 2021-03-15 | 2021-03-15 | 0
2021-05-01 | 2021-04-15 | 2021-04-15 | 0
2021-06-01 | 2021-05-14 | 2021-05-14 | 0
2021-07-01 | 2021-06-15 | 2021-06-15 | 0
2021-08-01 | 2021-07-15 | 2021-07-15 | 0
2021-09-01 | 2021-08-13 | 2021-08-13 | 0
2021-10-01 | 2021-09-15 | 2021-09-15 | 0
2021-11-01 | 2021-10-15 | 2021-10-15 | 0
2021-12-01 | 2021-11-15 | 2021-11-15 | 0
Called from ScheduleTasks
DDL_Pace
Rushed
Paced
Leisurely
Called from ScheduleTasks
Formulas:
Air quality = WORKDAY([DDL_PermitType]-40,1,Holidays)
Onsite = WORKDAY([Air quality],0,Holidays)