## Orientation (hidden)
This Excel workbook is part of the blueprint for your rulemaking
It helps manage the new rulemaking process
| z | Tailor rulemaking tasks to risks and complexity
| z | Reduce the number of edits
| z | Eliminate disconnected instructions and guidance
| z | Eliminate duplication and multiple forms
| z | Help capture the actual cost of rulemaking
Helps create the work product
| z | Fee approval
| z | Notice
| z | EQC
| z | Supporting materials
|  | O | Letters
|  | O | Forms
|  | O | Certificates
Stimulates early and ongoing thinking about:
| z | Risks to the success of the rulemaking and implementation
| z | Rulemaking scope and issues
| z | Stakeholder involvement
| z | Resources needed for rulemaking and implementation
Provides help and opportunity for input
| z | Process improvement
| z | Movable messages
| z | In cell prompts
| z | Guidance
The GO-TO place to review:
| z | Schedule
| z | The work product
Records management
| z | Archiving copies of the blueprint at decision points
| z | Documents have retention schedule and name
| z | Hardcopy cover sheets
What is the blueprint?

## WorkFlow (hidden)
DEQ Rulemaking | [10 empty] | Under construction
| Concept | [9 empty] | Start rulemaking |  | Advisory Committee |  | SIP | Fee Approval | [10 empty] | Notice | [7 empty] | Public comment and response | [6 empty] | EQC | [6 empty] | Post EQC
|  |  | Identify |  | Develop |  |  | Review |  | Decide | [7 empty] | Identify |  |  | Develop |  |  | Review |  | Decide |  | Identify | Develop |  | Review |  | Decide |  |  | Identify | Develop |  | Review | Decide |  |  | Identify | Develop |  | Review | Decide |  |  | Identify | Develop |  | Review | Decide
|  | LDA and Core Rule Design Team |  | Draft rulemaking concept |  |  | Concept signoff |  | Prepare draft concept for EMT | [7 empty] | Requirement for DAS fee approval |  |  | Fee approval documents |  |  | Fee submittal signoff |  | Prepare draft concept for EMT | [6 empty] | Prepare draft concept for EMT
Click on:
o to go to Overview |  |  | Lead division administrator |  | Considerations worksheet | o |  | RDT-LM keeps LDA informed about concept |  | LDA approves concept |  | o |  | o |  |  |  | Determine DAS fee approval requirement |  |  | Considerations worksheet - fee section | o |  | RDT-LM keeps LDA informed about fees |  | Deputy director emails submittal to DAS
t to go to Table of Content | [5 empty] | t | [5 empty] | t |  | t |  |  |  |  | Y |  |  | t
s to go to Schedule | [5 empty] | s | [5 empty] | s |  | s | [7 empty] | s
w to go to Worksheet | [5 empty] | w | [5 empty] | w |  | w | [7 empty] | w
| Deliverables | [9 empty] | Deliverables |  | Deliverables |  | Deliverables | Deliverables |  | N | [8 empty] | Deliverables | [7 empty] | Deliverables | [6 empty] | Deliverables | [6 empty] | Deliverables
| 2012 plan | [9 empty] | Contact list |  | Contact list |  | EPA letter | DAS emails | [10 empty] | ALL notice documents | [7 empty] | List of respondents | [6 empty] | Staff report | [6 empty] | Notice of filing
| EQC Involvement |  | RDT: program manager |  | Resources | o |  | RDT completes draft concept |  | Rules group consolidates agency concepts | Charter |  | Charter |  | EPA SIP Insert | DAS submittal |  | Email DAS when submitting Notice to SOS |  |  | Proposal worksheet - fee section | o |  | RDT completes fee approval |  | Follow up with DAS | SOS submittal | [7 empty] | Comment/response worksheet | [13 empty] | DAS fee notification
[6 empty] | t |  |  |  |  | Website template |  | Website template | [8 empty] | t |  |  |  |  | Announcement
[6 empty] | s |  |  |  |  | Agenda template |  | Agenda template | [8 empty] | s
[6 empty] | w |  |  |  |  | Minutes template |  | Minutes template | [8 empty] | w | [7 empty] | w |  |  |  | w |  |  |  | w |  |  | w |  |  |  | w |  |  | w |  |  |  | w |  |  | w
| Kaizen principals | [9 empty] | Kaizen principals |  | Kaizen principals |  | Kaizen principals | Kaizen principals | [10 empty] | Kaizen principals | [7 empty] | Kaizen principals | [6 empty] | Kaizen principals | [6 empty] | Kaizen principals
| Though developing the annual plan was out of scope, the following principal are incorporated. |  | RDT: process expert |  | Proposal in Plan view | o |  | RDT-LM approves concept release to LDA |  | LDA, LM review/approve consolidated draft annual plan | [7 empty] | Email DAS when filing with SOS |  |  | Supporting documents | o |  | RDT-LM approves release to DAS |  | If DAS approves file Fee Approval form for post-EQC activities | Eliminate duplication
[6 empty] | t | [15 empty] | t |  |  |  |  | Reduce review cycles
[6 empty] | s | [15 empty] | s |  |  |  |  | Provide uniformity
[6 empty] | w | [15 empty] | w |  |  |  |  | Streamline information capture |  |  | w |  |  |  | w |  |  |  | w |  |  | w |  |  |  | w |  |  | w |  |  |  | w |  |  | w
| o Eliminate SRP, incorporate factors into annual planning | [19 empty] | Get input from advisors: fiscal, budget, accounting, BSD | o
|  |  | RDT: subject expert |  | Key dates | o |  | RDT presents draft concept to LDA |  | All LDA, LM, ARC present draft plan to EMT | [11 empty] | t |  |  |  | If DAS denies, RDT decides how to respond
[6 empty] | t | [15 empty] | s
| o Early EMT decision whether to expend resources |  |  |  |  | s | [15 empty] | w
w
o Creates comprehensive rule design team
[8 empty] | LDA reviews concept |  | IF EMT approves - continue rulemaking
o Establishes agency rules group
– Process experts (3)
– Process assistant (1)
– Agency rules coordinator (1)
Note on X9: Go to overview.
Note on X10: Go to table of contents.
Note on X11: Go to schedule.
Note on X12: Go to worksheet.
Note on AL9: Go to overview.
Note on AL10: Go to table of contents.
Note on AL11: Go to schedule.
Note on AL12: Go to worksheet.
Add concept to annual rulemaking plan
Does the proposal nvolve the State Implementation Plan
Does the team plan to convene an advisory committee
Does the rule proposal include fees
Will there be a notice of proposed rulemaking
Did DEQ receive public comment
Is it time to prepare for the EQC
Is it time for Post EQC activities
Does the team plan to convene an advisory committee

## Considerations
Considerations Formulas
| DEQ Rulemaking | [7 empty] | 2026-08-04 | [12 empty] | Protect Orange columns | [6 empty] | Days added to schedule
| Considerations | [20 empty] | Calculations are in pale yellow on the same row where use.
|  | Update Oregon rules to address federal air quality regulations | [19 empty] | Y | [6 empty] | 192
| Executive summary | [20 empty] | Key legislators 49 days before effective date
SOS Bulletin 21 days before
| This section sumarizes the remaining sections of this worksheet. The information is not statice and will change as the Rule Design Team develops the rulemaking concept. | [20 empty] | This section sumarizes the remaining sections of this worksheet. The information is not statice and will change as the Rule Design Team develops the rulemaking concept.
| The Update Oregon rules to address federal air quality regulations is a permanent rule proposal. The proposal does not involve any land use rules but does involve a State Implementation Plan. | [20 empty] | The Update Oregon rules to address federal air quality regulations is a permanent rule proposal. The proposal does not involve any land use rules but does involve a State Implementation Plan.
| Schedule |  | The rule design team plans to start rulemaking in the first quarter of 2012. They plan to recommend that the EQC amend, adopt or repeal the proposed rules in the fourth quarter of 2012 with an effective date in the first quarter of 2013. | [18 empty] | The rule design team plans to start rulemaking in the first quarter of 2012. They plan to recommend that the EQC amend, adopt or repeal the proposed rules in the fourth quarter of 2012 with an effective date in the first quarter of 2013.
| Compliance |  | The rule proposal includes new or expanded compliance requirements. | [18 empty] | The rule proposal includes new or expanded compliance requirements.
| Penalties |  | The proposal does not affect penalties. | [18 empty] | The proposal does not affect penalties.
| Requirements |  | It includes a new or expanded regulatory program. | [18 empty] | It includes a new or expanded regulatory program.
| Permits, Certifications |  | The proposed rules do not affect Air quality permit, licence, certification or registration requirements but not propose new requirements or expande existing requirements. See section 6 below. | [18 empty] | The proposed rules do not affect Air quality permit, licence, certification or registration requirements but not propose new requirements or expande existing requirements. See section 6 below.
| Fees |  | The proposed rules do not affect fees. | [18 empty] | The proposed rules do not affect fees.
| Regulated party |  | The proposed rules would apply to previously unregulated parties. See section 9 below. | [18 empty] | The proposed rules would apply to previously unregulated parties. See section 9 below.
| Risks |  | Risks associated with support for the proposed rules is medium within DEQ, medium for the private stakeholders and medium for public stakeholders. | [7 empty] | Risk rating low → high
[11 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3 | Risks associated with support for the proposed rules is medium within DEQ, medium for the private stakeholders and medium for public stakeholders.
| Considerations | [9 empty] | Risk rating low → high 1: Risk rating low → high
| Program | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3
| Technology | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3
| Timing | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 6
| Policy | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 5
| Environmental | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 5
| Fiscal | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3
| Legal | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 6
| Political | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 6
| Implementation | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 5
| In addition to Considerations, the following parts of the Update Oregon rules to address federal air quality regulations blueprint for rulemaking provide additional information. | [20 empty] | In addition to Considerations, the following parts of the Update Oregon rules to address federal air quality regulations blueprint for rulemaking provide additional information.
|  |  | Resources |  |  | Identifies resources involved in the Update Oregon rules to address federal air quality regulations rulemaking and implemenation.
|  |  | Proposal |  |  | The proposal in its final VIEW is the the EQC staff report that includes the majority of the attachments such as:
|  | About views |  |  |  |  | o | the statement of need
|  | Views, unique to the Proposal tab, show the work products at various stages in the rule design process. |  |  |  |  | o | fee analysis
[7 empty] | o | fiscal impact statement, relationship to federal requirements, land use evaluation, summary of public involvement, public comment and agency response to public comment. Interim forms include: DAS fee detail submittal; notice to Secretary of State, stakeholders and agency lists;
[7 empty] | o | relationship to federal requirements
[7 empty] | o | land use statement
[7 empty] | o | summary of public involvement, public comment and agency response to public comment
Interim VIEWS of the proposal forms includes:
[7 empty] | o | DAS fee detail submittal; notice to Secretary of State, stakeholders and agency lists;
[7 empty] | o | notice to Secretary of State, stakeholders and agency lists
|  |  | ScheduleTasks |  |  | The schedule lists the task for the Update Oregon rules to address federal air quality regulations rulemaking.
Brainstorming
Complete the idea that this rule proposal would…
|  | Action |  | Object | [5 empty] | Driver
| a | align |  | existing regulatory program | [5 empty] | federal regulations
| b | carry out |  | a commitment in PPA | [5 empty] | EPA direction
| c | improve |  | existing regulatory program | [5 empty] | program business decision
| d | expand |  | existing regulatory program | [5 empty] | federal regulations
| e | implement |  | existing regulatory program | [5 empty] | federal regulations
f
g
h
Topic discussion
This rulemaking will address several objectives as listed above.
| Scope | [26 empty] | Days added to schedule
| 1. Proposed rules basics | [22 empty] | ExSum
[6 empty] | permanent | [14 empty] | 60 | permanent | FALSE | The Update Oregon rules to address federal air quality regulations is a permanent rule proposal. |  |  |  | 60 | 59
[6 empty] | temporary | [14 empty] | 5 |  |  | The Update Oregon rules to address federal air quality regulations is a permanent rule proposal. The proposal does not involve any land use rules but does involve a State Implementation Plan. |  |  |  | 5 | 4
ExSum
` | [20 empty] | 0 |  | 0 | The proposal does not involve any land use rules but does involve a State Implementation Plan. |  |  |  | 0 | -1
[21 empty] | 5 | State Implementation Plan rules | 1 |  |  |  |  | 5 | 4
The proposed rule
[6 empty] | Risk option |  |  |  |  | Risk rating low → high 1 1 1 1 1 1 1 1 1: Riskometer
|  | ...had prior public input |  |  |  | somewhat true |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3
|  | ...is backed by science |  |  |  | somewhat true |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3
|  | ...is backed by data |  |  |  | somewhat true |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3
|  | ...will make DEQ's work easier |  |  |  | somewhat true |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3
|  | ...would minimize DEQ costs |  |  |  | somewhat true |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3
|  | ...furthers DEQ priorities |  |  |  | somewhat true |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3 | [5 empty] | Days added to schedule
|  | ...supports strategic directions |  |  |  | somewhat true |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3
|  | ...supports sustainability |  |  |  | somewhat true |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 3 | [5 empty] | 0 | 0
[6 empty] | Risk average |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 0 | 3
| 2. What problem is DEQ trying to solve? | [8 empty] | >
| 3. How would the proposed rule solve the problem? | [8 empty] | >
| 4. How will DEQ know the problem has been solved? | [8 empty] | >
| 5. What alternatives did DEQ considered? | [8 empty] | >
Topic discussion
This rulemaking amends rules contained in DEQ's State Implementation Plan.
6. Out of the scope of this rulemaking.
| Topic | [6 empty] | Reasoning
None
| Include the above in the: |  |  |  | Committee charter |  |  | OCO Review |  |  | 7: Proposal |  | 0 | FALSE | 0
| 7. If the EQC does not amend, adopt or repeal the proposed rules, DEQ risks: | [20 empty] | Column1 | Column2 | Column3
[22 empty] | 1899-12-31 | 0 | 1899-12-31
[22 empty] | 1899-12-31 | 0 | 0
[22 empty] | 0 | 1899-12-31 | 0
[22 empty] | 1899-12-31 | 0 | 1899-12-31
[23 empty] | 1899-12-31 | 1899-12-31
|  | Custom entry | [5 empty] | Custom entry | [14 empty] | 0 | 0
8. Schedule
| The EMT approved this proposal. Information entered on this tab helps tailor the ScheduleTasks worksheet; therefore the team should enter their current knowledge on this, the Considerations worksheet, before spending too much time on the scheduled. | [8 empty] | Quarter | [11 empty] | Error | ExecSum
[9 empty] | Year |  | 1: Q1; 4: Q2; 7: Q3; 10: Q4 |  |  | The rule design team plans to start rulemaking in the first quarter of 2012. They plan to recommend that the EQC amend, adopt or repeal the proposed rules in the fourth quarter of 2012 with an effective date in the first quarter of 2013. | Check Yr & Qtr sequense |  | SectionDialog
[7 empty] | Start |  | 2012 | [12 empty] | ExcSum | FALSE | 1/1/2012 | 2012-01-01 | The EMT approved this proposal. Information entered on this tab helps tailor the ScheduleTasks worksheet; therefore the team should enter their current knowledge on this, the Considerations worksheet, before spending too much time on the scheduled.
[7 empty] | EQC Action |  | 2012 | [12 empty] | The rule design team plans to start rulemaking in the first quarter of 2012. | FALSE | 10/1/2012 | 2012-10-01 | The EMT approved this proposal. Information entered on this tab helps tailor the ScheduleTasks worksheet; therefore the team should enter their current knowledge on this, the Considerations worksheet, before spending too much time on the scheduled.
[7 empty] | Effective |  | 2013 | [12 empty] | They plan to recommend that the EQC amend, adopt or repeal the proposed rules in the fourth quarter of 2012 | FALSE | 1/1/2013 | 2013-01-01 | The schedule to the right provides a rough idea about the progression of this draft rule concept. The rule design team will develop the actual rulemaking schedule if the EMT approves this draft rule concept.)
with an effective date in the first quarter of 2013.
Topic discussion
December 2012 is the target date, but there is no set deadline for this rulemaking.
`
| 9. Compliance, regulatory programs and penalties | [20 empty] | SectionSum
| The proposed rules do not affect compliance, regulatory programs or penalties. | [9 empty] | 3: New or expanded requirements |  | The proposed rules do not affect compliance, regulatory programs or penalties. | The rule proposal includes new or expanded compliance requirements. It includes a new or expanded regulatory program. The proposal does not affect penalties.
[9 empty] | New | Reduced | [11 empty] | ExSum | Involved | New/Expanded | Score |  |  | Days Added
[21 empty] | 10 | The rule proposal includes new or expanded compliance requirements. | 1 | 1 | 2 |  |  | 10
[21 empty] | 10 | It includes a new or expanded regulatory program. | 1 | 1 | 2 |  |  | 10
[21 empty] | 0 | The proposal does not affect penalties. | 0 | 0 | 0 |  |  | 0
| Topic discussion | [19 empty] | 20 | [6 empty] | 20 | 20
| 10. Permits, certifications, licenses, registrations | [9 empty] | 3: New or expanded requirements |  | SectionSum | ExecSum | [6 empty] | PermitTypeTable
| The proposed rules affect Air quality permit, licence, certification or registration requirements. | [20 empty] | The proposed rules affect Air quality permit, licence, certification or registration requirements. | The proposed rules do not affect Air quality permit, licence, certification or registration requirements but not propose new requirements or expande existing requirements. See section 6 below.
|  | Air quality | [19 empty] | Invilved | New.expanded | score |  |  |  | Days Added |  | Air quality | Onsite | Solid waste | Water quality | DDL_PermitType
|  |  | Asbestos License | [17 empty] | 0 | 0 | 0 | 0 | asbestos license |  |  | 0 |  | asbestos license | onsite installers and maintenance provider certification | closure permit | national Pollutant Discharge Elimination System permit | Air quality
P |  |  | Air Contaminant Discharge Permit | [18 empty] | 1 | 1 | 2 | air contaminant discharge permit | Includes new or expanded air contaminant discharge permit requirements. |  | 10 |  | air contaminant discharge permit | construction-installation permit | composting facility permit or registration | sewage disposal service business licensing | Onsite
R |  |  | Air Quality Registrations | [18 empty] | 0 | 0 | 0 | air quality registrations |  |  | 0 |  | air quality registrations | sewage disposal service licences | energy recovery facility permit | stormwater discharge permit | Solid waste
O |  |  | Open Burning Letter Permit | [18 empty] | 0 | 0 | 0 | open burning letter permit |  |  | 0 |  | open burning letter permit | product approvals | incineration facility permit | underground injection control registration/permits | Water quality
T |  |  | Tanker Certification | [18 empty] | 0 | 0 | 0 | tanker certification |  |  | 0 |  | tanker certification | water pollution control facilities permit | land disposal site permit | wastewater system operator certification
E |  |  | Ttle V Permit | [18 empty] | 0 | 0 | 0 | Ttle V permit |  |  | 0 |  | Ttle V permit | site evaluation | solid waste disposal permit | water pollution control facilities permit
C |  |  | Vehicle Emissions Certification | [18 empty] | 0 | 0 | 0 | vehicle emissions certification |  |  | 0 |  | vehicle emissions certification | authorization notice | solid waste letter authorization permit | water quality permit program
T |  |  | Neshap | [18 empty] | 1 | 1 | 2 | NESHAP | Includes new or expanded NESHAP requirements. |  | 10 |  | NESHAP | existing system evaluation | solid waste treatment facility permit
|  |  | Nsps | [18 empty] | 1 | 1 | 2 | nsps | Includes new or expanded nsps requirements. |  | 10 |  | nsps | variance | transfer station/material recovery facility permit
|  |  | Add a new permit category | [18 empty] | 0 | 0 | 0 |  |  |  | 0
30
| Topic discussion | [22 empty] | 7 |  |  |  | 30 | 30
0
3
11. Fees
The proposed rules do not affect fees.
| Draft or review Proposal¦Fee | [20 empty] | 0 | [5 empty] | Days added to schedule
|  | The proposed rules… |  |  |  |  | The proposed fees… | [14 empty] | The proposed rules do not affect fees.
[21 empty] | 0 | FALSE | The proposed rules do not affect fees. | FALSE |  |  |  | 0
[21 empty] | 0 | The proposed rules do not affect fees. | [5 empty] | 0
[21 empty] | 0 | [6 empty] | 0 | 0
Invoicing system
[22 empty] | 7 | 0
UST Invoice.net
WQSIS
Topic discussion
Existing database and invoicing processes.
| 12. Regulated party | [9 empty] | 7: Previously unregulated | [7 empty] | Days added to schedule
|  |  | Business | [17 empty] | 10 | 1899-12-31 | 1899-12-31 | 2 |  |  |  | 10
|  |  | Manufacturing | [17 empty] | 10 | 1899-12-31 | 1899-12-31 | 2 |  |  |  | 10
|  |  | City/county/state | [17 empty] | 10 | 1899-12-31 | 1899-12-31 | 2 |  |  |  | 10
|  |  | Individuals | [17 empty] | 0 | 0 | 0 | 0 |  |  |  | 0
|  |  | Enter another regulated party here | [17 empty] | 0 | 0 | 0 | 0 |  |  |  | 0
|  |  | Enter another regulated party here | [17 empty] | 0 | 0 | 0 | 0 |  |  |  | 0
[21 empty] | 10 |  |  | The proposed rules would apply to previously unregulated parties. See section 9 below. |  |  |  | 10 | 9
Topic discussion
| 13. Support for proposal | [26 empty] | Days added to schedule
|  | Group |  |  |  | Degree of support |  |  |  |  | 1: Riskometer
|  | EQC |  |  |  | somewhat supportive |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 0 | 3 | [5 empty] | 0
|  | EMT |  |  |  | unknown or neutral |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 3 | 6 | [5 empty] | 3
|  | other DEQ programs |  |  |  | unknown or neutral |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 3 | 6 | [5 empty] | 3
|  | program management |  |  |  | somewhat supportive |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 0 | 3 |  |  | ExSum |  |  | 0
|  | regional staff |  |  |  | unknown or neutral |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 3 | 6 | 4.8 | medium | Risks associated with support for the proposed rules is medium within DEQ, medium for the private stakeholders and medium for public stakeholders. |  |  | 3
|  | regulated community |  |  |  | unknown or neutral |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 3 | 6 | [5 empty] | 3
|  | business and industry |  |  |  | unknown or neutral |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 3 | 6 | [5 empty] | 3
|  | environmental groups |  |  |  | unknown or neutral |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 3 | 6 | [5 empty] | 3
|  | public |  |  |  | unknown or neutral |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 3 | 6 | 6 | medium |  |  |  | 3
|  | state legislators |  |  |  | unknown or neutral |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 3 | 6 | [5 empty] | 3
|  | federal environmental regulators |  |  |  | somewhat supportive |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 0 | 3 | [5 empty] | 0
|  | other state and federal agencies |  |  |  | unknown or neutral |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 3 | 6 | [5 empty] | 3
|  | tribal nations |  |  |  | does not apply |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 0 | 0 | [5 empty] | 0
|  | local governments |  |  |  | unknown or neutral |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 3 | 6 | 5.25 | medium |  |  |  | 3
[8 empty] | Average |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 30 | 5.3077 | medium |  |  |  |  | 30 | 29
Process improvement
Public involvement
"The Legislative Assembly finds and declares that it is the policy of this state that whenever possible the public be involved in the development of public policy by agencies and in the drafting of rules. The Legislative Assembly encourages agencies to seek public input to the maximum extent possible before giving notice of intent to adopt a rule. The agency may appoint an advisory committee that will represent the interests of persons likely to be affected by the rule, or use any other means of obtaining public views that will assist the agency in drafting the rule."
| 1. Information meetings and hearings | [9 empty] | 8: ORS 183.333 | [7 empty] | Days Added to schedule
|  |  | Not required for TEMPORARY rules | [6 empty] | Public notice without hearing | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Notice | 15
|  |  | Portland area information meeting and notice | [6 empty] | Public notice with hearing | [10 empty] | 25 | 1899-12-31 | 1899-12-31 | 10 | 15 | 25 | Hearing | 15
|  |  | Regional information meeting at notice | [6 empty] | Re-notice | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | InfoMeeting | 10
|  | Topic discussion | [18 empty] | 25 | 1899-12-31 | 1899-12-31 |  |  | 25 | Renotice | 0
[22 empty] | 1899-12-31 | There will be stakeholder involvement. |  |  |  |  | 40 | 40
2. Advisory committee involvement
| Guide |  |  |  |  | Bold topics are part of the advisory committee charter. | [15 empty] | FALSE | 0
|  | No plans to convene a committee | [5 empty] | Program |  |  | 3: Environmental
|  | Use a standing committee | [5 empty] | Technology |  |  | 3: Fiscal
|  | Reconvene a committee | [5 empty] | Timing |  |  | 3: Legal
|  | Convene a new committee | [5 empty] | Policy |  |  | 3: Political
[6 empty] | 2 |  |  |  |  | 10: 30 | 0 |  |  |  |  | 0 |  |  | 0
1. The Oregon Administrative Procedures Act requires DEQ to seek the committee’s recommendations about:
(a) Whether the rule will have a fiscal impact;
(b) What the extent of that impact will be;
(c) Whether the rule will have a significant adverse impact on small businesses.
If the committee determines there will be a significant adverse impact on small businesses, DEQ must seek the committee’s recommendations on how to reduce the economic impact of the rule on small business, to the extent consistent with the public health and safety purpose of the rule, by:
o Establishing differing compliance or reporting requirements or time tables for small business;
o Clarifying, consolidating or simplifying the compliance and reporting requirements under the rule for small business;
o Utilizing objective criteria for standards;
o Exempting small businesses from any or all requirements of the rule; or
o Otherwise establishing less intrusive or less costly alternatives applicable to small business.
2. If DEQ convenes a rulemaking advisory committee, but does not seek the committee’s recommendations as described above, there is a risk that the entire rulemaking could later be invalidated by a court for failure to comply with procedural rulemaking requirements under the Oregon Administrative Procedures Act.
|  | 3. If DEQ does not convene a rulemaking advisory committee regarding a proposed permanent rule, then persons or organizations likely to be affected by the proposed rule may object to DEQ’s fiscal impact statement. Such an objection requires DEQ to appoint a fiscal impact advisory committee to provide recommendations on whether the proposed rule will have a fiscal impact and what the extent of that impact will be. This can significantly delay a rulemaking. | [19 empty] | is there an alternative
Process improvement
Program considerations
Aug-04-2026
|  |  | Complexity rating |  |  | potential for minor complexity |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 3 | 3 | [5 empty] | 3
Describe this consideration
Incorporating federal changes to the gasoline dispensing facility NESHAP will result in expansion to facilities that dispense gasoline into non-road vehicles and non-road engines. This will require the UST Program to incorporate the NESHAP requirements into additional inspections. DEQ is implementing the gasoline dispensing facility NESHAP in a joint effort of the Air Quality Division and the Underground Storage Tank Program. The UST program has incorporated the NESHAP requirements into their current inspection program. This leveraging of UST Program resources has allowed the Air Quality Division to reduce implementation costs and establish two lower cost General ACDP fee classes for gasoline dispensing facilities. The generated revenue pays for the NESHAP portion of the UST Program inspection. However, affected businesses aren’t likely to have throughputs that would trigger control requirements or permitting. Therefore, the increase in workload on the UST Program is not expected to be significant. Revenue generated by permitting additional businesses will be used to pay for this increased workload. Large numbers of businesses that dispense gasoline into non-road vehicles and non-road engines are potentially affected by the amended gasoline dispensing facility NESHAP. Many of these businesses have not previously been subject to air quality regulations. Initially, there may be compliance issues with these businesses, placing a burden on DEQ's Office of Compliance and Enforcement. Compliance rates should improve and therefore the burden on OCE should reduce over time.
Text
Text
Text
Text
[22 empty] | N | N | Y
| Include the above in the: |  |  |  | Committee charter |  |  | OCO Review |  |  | 7: Proposal |  | 0 | FALSE | 1899-12-31
Topic discussion
Technology Considerations
|  |  | Complexity rating |  |  | potential for minor complexity |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 3 | 3 | [5 empty] | 3
Describe this consideration
Existing UST and AQ databases will support implementation of this rulemaking.
[22 empty] | N | N | N
| Include the above in the: |  |  | Committee charter |  |  |  | OCO Review |  |  | 7: Proposal |  | 0 | 0 | 0
Topic discussion
Timing Considerations
|  |  | Criticality rating |  |  | moderate criticality |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 10 | 6 | [5 empty] | 10
Describe this consideration
DEQ's 2010-2012 Performance Partnership Agreement with EPA stipulates that DEQ adopt NESHAPs and NSPSs and request delegation at least every two years. States are required to submit a plan that meets the requirements of the amended emission guidelines for commercial and industrial solid waste incinerators by one year after promulgation of the emission guidelines. EPA expects to publish the amended emission guidelines in May of this year. Therefore, state plans will be due in May of 2013. If a state does not submit an approvable plan, EPA is required to develop a Federal plan for Commercial and Industrial Solid Waste Incinerators located in that state within 2 years after promulgation of the emission guidelines. • Existing gold mine ore processing and production facilities are required to comply with the new NESHAP by February 17, 2014. • Existing gasoline dispensing facilities that dispense gasoline into the fuel tank of "non-road vehicles" or "non-road engines" are required to comply with the amended gasoline dispensing facility NESHAP by January 24, 2014. • Existing commercial, institutional, and industrial boilers are required to be tune-up by March 21, 2013. • Owners of larger commercial, institutional, and industrial boilers are required to have an energy assessment performed by March 21, 2014. • Existing coal- and oil-fired electric utility boilers are required to comply with the new utility NESHAP by April 16, 2015.
Rule changes are necessary now in order to delay implementation of the NESHAP and NSPS standards for stationary engines. Air Quality managers have decided to delay implementation of these standards because of potential workload increases. Air Quality managers want a comprehensive implementation plan and to know how many facilities would be affected before proceeding. Oregon's current rules require DEQ to implement federal standards for currently permitted facilities when they are adopted by EPA, not when they are adopted by the EQC. Oregon's rules also require facilities affected by new NSPSs to obtain a permit when an NSPS is adopted by EPA, not when it is adopted by the EQC. On January 5, 2010, EPA promulgated the Prepared Feeds NESHAP. The NESHAP contained a requirement that facilities, with an average daily feed production level exceeding 50 tons per day, capture and route emissions to a cyclone designed to reduce particulate emissions by 95 percent. The compliance date for this requirement was January 5, 2012. On December 23, 2011, EPA promulgated amendments to the NESHAP that removed the 95 % control requirement for cyclones at existing facilities and retained the compliance date of January 5, 2012. This rulemaking would adopt the revised NESHAP. In the meantime, affected facilities are out of compliance with the version of the NESHAP previously adopted by the EQC. After the rules are adopted, DEQ will revise the prepared feed general ACDP and reassign affected facilities to the revised permit.
[22 empty] | N | N | Y
| Include the above in the: |  |  | Committee charter |  |  |  | OCO Review |  |  | 7: Proposal |  | 0 | FALSE | 1899-12-31
Topic discussion
Policy Considerations
|  |  | Complexity rating |  |  | unknown |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 0 | 5 | [5 empty] | 0
Describe this consideration
Text
Text
Text
Text
Text
[22 empty] | N | N | N
| Include the above in the: |  |  | Committee charter |  |  |  | OCO Review |  |  | 7: Proposal |  | 0 | 0 | 0
Topic discussion
Environmental Considerations
|  |  | Complexity rating |  |  | unknown |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 0 | 5 | [5 empty] | 0
| The proposed rule |  |  | addresses an environmental problem directly. | [17 empty] | 3
Describe this consideration
EPA has identified gasoline dispensing facilities, gold mine ore processing and production operations, and boilers as emitters of one or more of the 33 hazardous air pollutants that pose the greatest risk to public health in urban areas. Many of these hazardous air pollutants are also of particular concern in Oregon. For instance, gasoline vapors contain benzene, a known cancer-causing chemical. Because benzene concentrations in many Oregon communities are significantly above levels protective of human health, reducing benzene is a priority for DEQ. Boilers and gold mine ore processing and production operations emit mercury which can impair neurological development and cause neurological damage, and is a toxic of concern in Oregon.
[22 empty] | N | N | Y
| Include the above in the: |  |  | Committee charter |  |  |  | OCO Review |  |  | 7: Proposal |  | 1899-12-31 | 0 | 1899-12-31
Topic discussion
Change 10 above to involve committee.
Fiscal Considerations
|  |  | Fiscal complexity rating |  |  | potential for minor complexity |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 3 | 3 | [5 empty] | 3
|  | Fiscal impact on: |  |  |  | Impact |  |  |  |  | 1: Riskometer
|  | regulated community |  |  |  | moderate cost increase |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 8
|  | small business (50 emp or less) |  |  |  | moderate cost increase |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 8
|  | business and industry |  |  |  | moderate cost increase |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 8
|  | local governments |  |  |  | no fiscal impacts |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0
|  | other state or federal agencies |  |  |  | no fiscal impacts |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0
|  | public |  |  |  | no fiscal impacts |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0
|  | DEQ |  |  |  | no fiscal impacts |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0
|  | other |  |  |  | unknown |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 6
[6 empty] | Fiscal impact average |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 7.5 | high
Describe this consideration
Text
Text
Text
Text
Text
Text
[22 empty] | N | N | N
| Include the above in the: |  |  | Committee charter |  |  |  | OCO Review |  |  | 7: Proposal |  | 0 | FALSE | 0
Topic discussion
Text
Text
Text
Text
Legal Considerations
|  |  | Complexity rating |  |  | potential for moderate complexity |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 10 | 6 | [5 empty] | 10
Describe this consideration
[22 empty] | N | N | N
| Include the above in the: |  |  | Committee charter |  |  |  | OCO Review |  |  | 7: Proposal |  | 0 | 0 | 0
Topic discussion
Political Considerations
|  |  | Controversy rating |  |  | potential for moderate controversy |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 10 | 6 | [5 empty] | 10
Describe this consideration
Large numbers of businesses that dispense gasoline into non-road vehicles and non-road engines are potentially affected by the gasoline dispensing facility NESHAP. Many of these businesses have not previously been subject to air quality regulations, are opposed to permitting and fees, and may contact their legislators. However, these businesses aren’t likely to have throughputs that would not trigger the more significant control requirements or permitting. In a 2009 mailing, DEQ informed businesses that dispense gasoline into non-road vehicles and non-road engines that they were exempt from the gasoline dispensing NESHAP, knowing that in the future it would likely have to inform these same businesses that they are subject to the NESHAP.
[22 empty] | N | N | N
| Include the above in the: |  |  | Committee charter |  |  |  | OCO Review |  |  | 7: Proposal |  | 0 | FALSE | 0
Topic discussion
Implementation Considerations
|  |  | Complexity rating |  |  | potential for minor complexity |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 3 | 3 | [5 empty] | 3
Describe this consideration
Text
Text
Text
Text
Text
Text
[22 empty] | N | N | N
| Include the above in the: |  |  | Committee charter |  |  |  | OCO Review |  |  | 7: Proposal |  | 0 | 0 | 0
Topic discussion
Process improvement
Dropdown lists on Considerations tab
DDL_BrainstormingAction
align
carry out
create
expand
eliminate
implement
improve
incorporate
maintain
prevent
reduce
solve
simplify
support
streamline
resolve conflict
DDL_BrainstormingObject
Oregon law
a commitment in PPA
science applicable to Oregon
new legislation
a court order
DEQ business process
an external process
a known environmental problem
a suspected environmental problem
advisory committee recommendation
EQC directions
DEQ strategic directions
workload
existing regulatory program
insufficient funding
new regulatory program
rules for obsolete program
cross program coordination
DDL_BrainstormingDriver
Oregon law
new legislation
court order
federal regulations
regulated community
scientific community
environmental group
stable funding source
EPA direction
EQC direction
program business decision
DEQ business decision
[22 empty] | DDL_ControversyRating | VL_ControversyRating
[22 empty] | does not apply | 0
[22 empty] | definitely not controversial | 1
[22 empty] | potential for minor controversy | 3
[22 empty] | unknown | 5
[22 empty] | potential for moderate controversy | 6
[22 empty] | potential for major controversy | 8
[22 empty] | definitely controversial | 10
[22 empty] | DDL_ComplexityRating | VL_ComplexityRating
[22 empty] | does not apply | 0
[22 empty] | definitely not complex | 1
[22 empty] | potential for minor complexity | 3
[22 empty] | unknown | 5
[22 empty] | potential for moderate complexity | 6
[22 empty] | potential for major complexity | 8
[22 empty] | definitely complex | 10
[22 empty] | DDL_CriticalityRating | VL_CriticalityRating
[22 empty] | does not apply | 0
[22 empty] | definitely not critical | 1
[22 empty] | minor criticality | 3
[22 empty] | unknown | 5
[22 empty] | moderate criticality | 6
[22 empty] | high criticality | 8
[22 empty] | definitely critical | 10
DDL_EnvironmentalProblem
no direct correlation to the environment.
addresses an environmental problem directly.
addresses an environmental problem indirectly.
prevents a known problem.
solves a known problem.
prevents a suspected problem.
solves a suspected problem.
DDL_RiskOfRejectingConcept
loss of delegation
noncompliance
rule does not align with law
advisory committee commitment
science not applicable to Oregon
loss of federal funding
loss of program funding
loss of reputation
increased difficulty doing business
failure to keep commitment
a problem we suspect will occur
[22 empty] | DDL_FiscalComplexityRating | VL_FiscalComplexityRating
[22 empty] | definitely not complex | 1
[22 empty] | potential for minor complexity | 3
[22 empty] | unknown | 5
[22 empty] | potential for moderate complexity | 6
[22 empty] | potential for major complexity | 8
[22 empty] | definitely complex | 10
Risk evaluations DDLs
[22 empty] | DDL_ScopeOfRule | VL_ScopeOfRule
[22 empty] | does not apply | 0
[22 empty] | definitely true | 1
[22 empty] | somewhat true | 3
[22 empty] | unknown | 6
[22 empty] | somewhat false | 8
[22 empty] | definitely false | 10
[22 empty] | DDL_SupportForRule | VL_SupportForRule
[22 empty] | does not apply | 0
[22 empty] | definitely supportive | 1
[22 empty] | somewhat supportive | 3
[22 empty] | unknown or neutral | 6
[22 empty] | somewhat opposed | 8
[22 empty] | definitely opposed | 10
[22 empty] | DDL_FiscalImpacts | VL_FiscalImpacts
[22 empty] | no fiscal impacts | 0
[22 empty] | significant cost decrease | 1
[22 empty] | moderate cost decrease | 3
[22 empty] | unknown | 6
[22 empty] | moderate cost increase | 8
[22 empty] | significant cost increase | 10
Formulas:
ExSum = IF(OR(AE209,[ExSum, row above])=TRUE(),TRUE())
Involved = IF([ExSum]>1,TRUE(),FALSE())
Note on A206: DOJ response to question about when a stakeholder group becomes an advisory committee To: VANDEHEY Maggie From: Logan Paul S [mailto:paul.s.logan@state.or.us] Sent: Thursday, September 29, 2011 1:12 PM To: VANDEHEY Maggie Subject: RE: advisory committees Maggie, From a brief review, Oregon law is very vague on what constitutes an “advisory committee,” and as a result I cannot give you extremely precise guidance. On the other hand, though, it is quite clear that agencies have broad discretion to obtain public views on proposed rulemakings through any means they choose – advisory committees or otherwise. As a result, and as explained further below, I’d suggest that as a practical matter DEQ should comply with advisory committee requirements under ORS 183.333 when it appoints individual members to a group representing multiple interests likely to be affected by the proposed rulemaking, and seeks comments from the group as a whole on the proposed rulemaking. In contrast, if DEQ does not appoint individual members to a group but rather invites input from interest groups more generally, and especially if DEQ does not convene the different interest groups together in a single meeting, DEQ probably does not have to comply with advisory committee requirements. I have to caution, though, that we are operating in a gray area in this matter due to some of the vagueness of the Oregon statute at issue. But if DEQ follows these general guidelines, it should minimize the risk of unintentionally appointing an “advisory committee” that triggers certain requirements under Oregon law. As background, ORS 183.333(1) states that “[t]he agency may appoint an advisory committee that will represent the interests of persons likely to be affected by the rule, or use any other means of obtaining public views that will assist the agency in drafting the rule.” As a threshold matter, therefore, a group must be appointed by DEQ to be considered an advisory committee. On the other hand, even if DEQ invites a number of different stakeholder groups to a single meeting, and seeks comments from the group as a whole, that group begins to look like an advisory committee – even though DEQ hasn’t appointed individual members – and there is a risk that DEQ has effectively “appointed” an advisory committee. In addition to advisory committees, the statute is quite clear that an agency may use “any other means” of obtaining public views, and for example provides that “[a]ny agency in its discretion may develop a list of interested parties and inform those parties of any issue that may be the subject of rulemaking and invite the parties to make comments on the issue.” ORS 183.333(2). Thus it appears that DEQ could “invite” particular parties to comment on a rulemaking issue without triggering the requirements of an advisory committee. There is less risk if DEQ invites those parties to comment separately, rather than together as a single group, which would more closely resemble a committee, and therefore might be construed to be an advisory committee. The analysis above demonstrates that it is not possible, on the basis of the statute’s text, to make a bright line distinction between what constitutes an advisory committee and what does not. If you wish, I could research this issue further by following the analytical methodology for interpreting statutes followed by Oregon courts. That would involve reviewing dictionary definitions of “appoint,” “advisory” and “committee,” and reviewing legislative history. But my instinct is that that type of research is unlikely to give you much more certainty.
Note on A216: ADVISORY COMMITTEE BEST PRACTICE ORS 183.333 See also Proposal tab, Fiscal Impact section 1. If DEQ convenes a rulemaking advisory committee, the Oregon Administrative Procedures Act requires DEQ to seek the committee’s recommendations about: (a) Whether the rule will have a fiscal impact; (b) What the extent of that impact will be; (c) Whether the rule will have a significant adverse impact on small businesses. If the committee determines there will be a significant adverse impact on small businesses, DEQ must seek the committee’s recommendations on how to reduce the economic impact of the rule on small business, to the extent consistent with the public health and safety purpose of the rule, by:  Establishing differing compliance or reporting requirements or time tables for small business;  Clarifying, consolidating or simplifying the compliance and reporting requirements under the rule for small business;  Utilizing objective criteria for standards;  Exempting small businesses from any or all requirements of the rule; or 2. If DEQ convenes a rulemaking advisory committee, but does not seek the committee’s recommendations as described above, there is a risk that the entire rulemaking could later be invalidated by a court for failure to comply with procedural rulemaking requirements under the Oregon Administrative Procedures Act. 3. If DEQ does not convene a rulemaking advisory committee regarding a proposed permanent rule, then persons or organizations likely to be affected by the proposed rule may object to DEQ’s fiscal impact statement. Such an objection requires DEQ to appoint a fiscal impact advisory committee to provide recommendations on whether the proposed rule will have a fiscal impact and what the extent of that impact will be. This can significantly delay a rulemaking. ORS 183.333(5)
Note on A402: Purpose Provide a creative space for sharing basic information about the rulemaking. This is the space to develop, update and raise any considerations, concerns and issues about the proposed rule and its implementation. Sentence and paragraph structures do not need to be "publication perfect." Goal Share each aspect of the rule proposal that the rule design team has or will be considering. Get started On the first round of this worksheet, add information you know now or that is readily accessible. The rule design may update the information as rulemaking progresses.
Note on D154: DAS FEE APPROVAL Requirement (1) Notwithstanding any other law that grants to a state agency the authority to establish fees, all new state agency fees or fee increases adopted after July 1 of any odd-numbered year: (a) Are not effective for agencies in the executive department of government unless approved in writing by the Director of the Oregon Department of Administrative Services; ... (d) Shall be reported by the state agency to the Oregon Department of Administrative Services within 10 days of their adoption; and (e) Are rescinded on July 1 of the next following odd-numbered year, or on adjournment sine die of the regular session of the Legislative Assembly meeting in that year, whichever is later, unless otherwise authorized by enabling legislation setting forth the approved fees. ORS 291.055
Note on I154: EXEMPT FROM FEE APPROVAL Requirement For fees to become effective, DEQ must obtain approval of all NEW or INCREASED fees from the Director of the Oregon Department of Administrative Services. There are several exemptions. Exemptions that generally apply to DEQ are: o Fees created or authorized by statute that have no established rate or amount but are calculated for each separate instance for each fee payer and are based on actual cost of services provided. ORS 291.055 (2)(d) o New or increased fees that are anticipated in the legislative budgeting process for an agency, revenues from which are included, explicitly or implicitly, in the legislatively adopted budget for the agency. ORS 291.055 (2)(m)
Note on J70: SIP - State Implementation Plan
Note on AA66: SCHEDULE ADJUSTMENT DAYS Temporary = 60 days Permanent = 90 days All numbers found in column Z adjust the initial schedule shown on the ScheduleTasks worksheet. The team may make adjustments on that worksheet.
Note on AA69: SCHEDULE ADJUSTMENT DAYS Temporary = 60 days Permanent = 90 days All numbers found in column Z adjust the initial schedule shown on the ScheduleTasks worksheet. The team may make adjustments on that worksheet.
Note on AA84: SCHEDULE ADJUSTMENT DAYS The MAX number found in column Z will adjust the initial schedule shown on the ScheduleTasks worksheet. The team may make adjustments on that worksheet. Days assigned to risk ratings are: GREEN (does not apply)= 0 days LIME = 0 days YELLOW (unknown) = 0 ORANGE = 10 RED =14 Days assigned to the ratings will change as we capture more data.
Note on AA126: SCHEDULE ADJUSTMENT DAYS All numbers found in column Z adjust the initial schedule shown on the ScheduleTasks worksheet. The team may make adjustments on that worksheet.
Note on AA136: SCHEDULE ADJUSTMENT DAYS All numbers found in column Z adjust the initial schedule shown on the ScheduleTasks worksheet. The team may make adjustments on that worksheet.
Note on AA155: SCHEDULE ADJUSTMENT DAYS All numbers found in column Z adjust the initial schedule shown on the ScheduleTasks worksheet. The team may make adjustments on that worksheet.
Note on AA169: SCHEDULE ADJUSTMENT DAYS All numbers found in column Z adjust the initial schedule shown on the ScheduleTasks worksheet. The team may make adjustments on that worksheet.
Note on AA182: SCHEDULE ADJUSTMENT DAYS All numbers found in column Z adjust the initial schedule shown on the ScheduleTasks worksheet. The team may make adjustments on that worksheet.
Note on AA208: SCHEDULE ADJUSTMENT DAYS All numbers found in column Z adjust the initial schedule shown on the ScheduleTasks worksheet. The team may make adjustments on that worksheet.
Note on AA223: SCHEDULE ADJUSTMENT DAYS All numbers found in column Z adjust the initial schedule shown on the ScheduleTasks worksheet. The team may make adjustments on that worksheet.
Note on AA242: SCHEDULE ADJUSTMENT DAYS The MAX number found in column Z will adjust the initial schedule shown on the ScheduleTasks worksheet. The team may make adjustments on that worksheet. Days assigned to risk ratings are: GREEN (does not apply)= 0 days LIME = 0 days YELLOW (unknown) = 0 ORANGE = 10 RED =14 Days assigned to the ratings will change as we capture more data.
Note on AA272: SCHEDULE ADJUSTMENT DAYS The MAX number found in column Z will adjust the initial schedule shown on the ScheduleTasks worksheet. The team may make adjustments on that worksheet. Days assigned to risk ratings are: GREEN (does not apply)= 0 days LIME = 0 days YELLOW (unknown) = 0 ORANGE = 10 RED =14 Days assigned to the ratings will change as we capture more data.
Note on AA288: SCHEDULE ADJUSTMENT DAYS The MAX number found in column Z will adjust the initial schedule shown on the ScheduleTasks worksheet. The team may make adjustments on that worksheet. Days assigned to risk ratings are: GREEN (does not apply)= 0 days LIME = 0 days YELLOW (unknown) = 0 ORANGE = 10 RED =14 Days assigned to the ratings will change as we capture more data.
Note on AA309: SCHEDULE ADJUSTMENT DAYS The MAX number found in column Z will adjust the initial schedule shown on the ScheduleTasks worksheet. The team may make adjustments on that worksheet. Days assigned to risk ratings are: GREEN (does not apply)= 0 days LIME = 0 days YELLOW (unknown) = 0 ORANGE = 10 RED =14 Days assigned to the ratings will change as we capture more data.
Note on AA327: SCHEDULE ADJUSTMENT DAYS The MAX number found in column Z will adjust the initial schedule shown on the ScheduleTasks worksheet. The team may make adjustments on that worksheet. Days assigned to risk ratings are: GREEN (does not apply)= 0 days LIME = 0 days YELLOW (unknown) = 0 ORANGE = 10 RED =14 Days assigned to the ratings will change as we capture more data.
Note on AA362: SCHEDULE ADJUSTMENT DAYS The MAX number found in column Z will adjust the initial schedule shown on the ScheduleTasks worksheet. The team may make adjustments on that worksheet. Days assigned to risk ratings are: GREEN (does not apply)= 0 days LIME = 0 days YELLOW (unknown) = 0 ORANGE = 10 RED =14 Days assigned to the ratings will change as we capture more data.
Note on AA383: SCHEDULE ADJUSTMENT DAYS The MAX number found in column Z will adjust the initial schedule shown on the ScheduleTasks worksheet. The team may make adjustments on that worksheet. Days assigned to risk ratings are: GREEN (does not apply)= 0 days LIME = 0 days YELLOW (unknown) = 0 ORANGE = 10 RED =14 Days assigned to the ratings will change as we capture more data.
Note on AA404: SCHEDULE ADJUSTMENT DAYS The MAX number found in column Z will adjust the initial schedule shown on the ScheduleTasks worksheet. The team may make adjustments on that worksheet. Days assigned to risk ratings are: GREEN (does not apply)= 0 days LIME = 0 days YELLOW (unknown) = 0 ORANGE = 10 RED =14 Days assigned to the ratings will change as we capture more data.
Note on AB2: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB6: TRoick:
Note on AB47: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB63: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB97: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB123: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB151: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB180: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB203: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB221: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB240: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB259: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB270: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB286: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB307: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB325: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB360: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB381: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB402: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AG175: Added to executive Summary
Note on AO133: Maggie: The names in the white header populate the DDL. CHANGE names here rather than under the DDL.
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
Loss of delegation
Noncompliance
Loss of reputation
Loss of federal funding
Loss of program funding
Rule does not align with law
Failure to keep commitment
Unclear rules
Science does not apply to Oregon
Increased difficulty doing business
Failure to respond to Legislature
The proposed rules include compliance requirements.
The proposed rules involve a regulatory program.
The proposed rules involve penalties.
Failure to comply with CWA or CAA
Delay public health protection
Imposes undue administrative burden
Failure to address costs
Rule type
Do not affect fees
Would establish new fees
Would increase existing fees
Would decreases existing fees
Does not apply
Require Department of Administrative Services approval
Are exempt from DAS approval under ORS 291.055(2)(d)
Develop new
Access database
Access template
CHRIS
HazWaste Invoicing
SWIFT
TRAACS
UST Invoice.net
WQSIS
No invoicing
Are exempt from DAS approval under ORS 291.055(2)(m)
Proposal includes
Land Use Rules
SIP

## Resources
[19 empty] | Movable Messages |  | Resources Formulas | Drop Down Lists
DEQ Rulemaking | [7 empty] | 2026-08-04 | [10 empty] | New message pad | Retired messages | Protect Column BA
Resources | [18 empty] | Click on message pad and move to subject location.
Update Oregon rules to address federal air quality regulations
Rulemaking resources
Review resources
| Workflow | >
| DOJ rulewriting training | >
| Review DOJ Model Rules | >
| APA | ORS 183
| DAS rules on Rulemaking | 137
| DAS rules on Rulemaking | 291.055(1)(a)
| DEQ | http://www.leg.state.or.us/ors/183.html
in HB 2788 i
Project accounting and rulemaking record
The agency rules group has reserved the following for this proposal
| Time accounting code for work related to rulemaking | [5 empty] | #####: RM-NESHAP/NSPS
| Project number for expenditures related to this rulemaking | [5 empty] | P##### RM-NESHAP/NSPS
| RM Identifier for email Subject line | [5 empty] | RM-NESHAP/NSPS
| Rule design team email group | [5 empty] | RM-NESHAP/NSPS@deq.state.or.us
| Advisory Committee email group | [5 empty] | None
| Public comment email box | [5 empty] | Comment-NESHAP/NSPS@deq.start.or.us
| Electronic record |  |  |  | RM-NESHAP/NSPSSharePoint
RM-NESHAP/NSPSArchive
| Email folder |  |  |  | RM-NESHAP/NSPS2012
| Email archives |  |  |  | RM-NESHAP/NSPS.pst
Physical record | Physical record |  |  | Pre filing
|  |  |  | Post filing | Central rulemaking cabinet for 5-years then SOS Archives
Core team
Lead DA |  | Andy Ginsburg |  |  |  | =>20 <30 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 4
The lead division administrator: • ensures the program manager and the team has adequate and appropriate resources • raises potential issues to the executive management team • advises the team on Considerations, Resources and Schedules as needed • reviews and approves the draft and final release of the Proposal at: - Presentation to EMT - Public notice - EQC
Lead manager |  | Tom Roick |  |  |  | =>40 <80 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 6
The lead manager is a contributing member on the rule design team who: • ensures the team has adequate and appropriate resources • raises potential issues to the lead division administrator • reviews and advises the team on Considerations, Resources and Schedules • reviews and approves the draft and final release of the Proposal at: - fee notification or approval requests - Public notice - EQC
Process expert |  | Nicole Vick |  |  |  | =>30 <40 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 5
The project lead is the expert on the rulemaking process and writing for the proposed rule. The project lead is responsible for: • Developing, maintaining and keeping the: - Blueprint and SharePoint site - Schedule • Engaging identified resources in collaboration activities • Writing all rulemaking materials using: - plain English - DEQ Style Guide • Ensuring the proposal has all required reviews and approvals before: - Releasing the blueprint beyond the rule design team - Publishing the proposal external to DEQ
Subject expert |  | Jerry Ebersole |  |  |  | =>200 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 10
Process assistant |  | Carol Thornberg |  |  |  | =>2 <10 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 2
Facilitator |  | Carol Thornberg |  |  |  | =>2 <10 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 2
Handles meeting logistics including iLinc and conference call-in numbers.
Rule contact |  | Jerry Ebersole |  |  |  | =>10 <20 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 3
|  | Address | 811 SW Sixth Avenue |  |  |  | Phone |  | 1: (503) 229-6974
Portland, OR 97204
NESHAP Implementation Plan Team exists and will be used to support communication and implementation.
Section process improvement
Advisors
DOJ |  | Paul Logan |  |  |  | =>10 <20 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 3
Makes sure all legal issues are adequately resolved, and the proposed rules are legally sufficient (within authority, consistent with statute, enforceable).
ARC |  | Maggie Vandehey |  |  |  | =>30 <40 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 5
Checks that the package meets the procedural requirements and is satisfactory for submittal to the SOS.
SIP Coordinator |  | Nicole Vick |  |  |  | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
Section process improvement
Interested staff
Enter custom name | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
Enter custom name | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
Enter custom name | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
Section process improvement
Regions and other divisions | [20 empty] | The proposed rules involve regional resources.
Eastern |  | Mark Fisher |  |  |  | =>10 <20 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 3
| rulemaking | Reviews the permitting rules and rules that implement the federal emissions guidelines for commercial and industrial solid waste incinerators.
implementation
Northwest |  | Johnny Baumgartner |  |  |  | =>10 <20 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 3
| rulemaking | Reviews the gasoline dispensing rule amendments.
implementation
Western |  | Steve Croucher |  |  |  | =>10 <20 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 3
| rulemaking | Reviews the gasoline dispensing rule amendments.
implementation
Land Quality |  | Andree Pollock |  |  |  | =>10 <20 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 3
| rulemaking | Reviews the gasoline dispensing rule amendments.
implementation
Air Quality |  | Rebecca Hillwig |  |  |  | =>10 <20 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 3
| rulemaking | Reviews rules for impacts on small businesses.
implementation
Water Quality | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Section process improvement
Financial services | [5 empty] | The proposed rules involve financial services resources. | [14 empty] | The proposed rules involve financial services resources.
Budget |  | Robin Williams |  |  |  | =>10 <20 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 3
Reviews and approves statement of need and fiscal impact statement.
Accounting |  | Richard Lawrence |  |  |  | =>10 <20 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 3
Reviews for ability to collect fees, changes to invoicing.
Contracts | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
Section process improvement
Communications and Outreach | [5 empty] | The proposed rules involve OCO resources. | [14 empty] | The proposed rules involve OCO resources.
OCO Review |  | William Knight |  |  |  | =>2 <10 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 2
Edit Proposal tab: • Notice sections before SOS release • All other sections before EQC release
Messaging |  | William Knight |  |  |  | =>2 <10 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 2
Reviews messaging indicated on Considerations tab. Reviews Announcement tab and display ad section of MeetingMecanics tab.
Media interactions |  | William Knight |  |  |  | =>2 <10 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 2
rulemaking
implementation
Web services |  | Emma Snodgrass |  |  |  | =>10 <20 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 3
rulemaking
implementation
Organization services | [5 empty] | The proposed rules do not involve organizational services. | [14 empty] | The proposed rules do not involve organizational services.
Health and safety | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Human resources | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Policies, procedures | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Training | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Facilities | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Section process improvement
Technical services | [5 empty] | The proposed rules do not involve technical services. | [14 empty] | The proposed rules do not involve technical services.
Divisional | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
IT | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
BSD | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Section process improvement
Compliance and Enforcement | [5 empty] | The proposed rules would involve OCE resources. | [14 empty] | The proposed rules would involve OCE resources.
OCE |  | Jenny Root |  |  |  | =>10 <20 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 3
| rulemaking | Reviews proposed rules to ensure enforcement issues are addressed.
implementation
Section process improvement
Laboratory | [5 empty] | The proposed rules do not involve the laboratory. | [14 empty] | The proposed rules do not involve the laboratory.
Monitoring | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Analytical testing | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Quality assurance | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Intergovernmental | [5 empty] | The proposed rules do not involve intergovernmental entities. | [14 empty] | The proposed rules do not involve intergovernmental entities.
Tribal nations | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
EPA | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
LRAPA | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Municipalities | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Counties | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Special districts | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Other state agencies | [5 empty] | 0 hours |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | 0
rulemaking
implementation
Section process improvement
[22 empty] | DDL_DEQResourcesInvolved | VL_DEQResourcesInvolved
[22 empty] | 0 hours | 0
[22 empty] | >0 <2 hours | 1
[22 empty] | =>2 <10 hours | 2
[22 empty] | =>10 <20 hours | 3
[22 empty] | =>20 <30 hours | 4
[22 empty] | =>30 <40 hours | 5
[22 empty] | =>40 <80 hours | 6
[22 empty] | =>80 <120 hours | 7
[22 empty] | =>120 <160 hours | 8
[22 empty] | =>160 <200 hours | 9
[22 empty] | =>200 hours | 10
Note on A29: COMMENT BOX PERMISSIONS The project lead, rules coordinator and assistant have access to the Comment box
Note on AB4: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB20: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB37: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB47: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB74: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB92: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB110: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB146: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB164: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB184: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on AB215: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message
mm/dd/yy
Subject
Your name
Your message

## Proposal
|  | This worksheet is in PERMANENT EQC view. | [11 empty] | Proposal Formulas | [5 empty] | Working in views
[13 empty] | Views | Protect bright yellow columns | [5 empty] | View | RMType | Banner
|  | Oregon Department of Environmental Quality | [10 empty] | EQC | 2012-12-13 | [5 empty] | 7 | PERMANENT | This worksheet is in PERMANENT EQC view.
2012-12-13
|  | Environmental Quality Commission Meeting | [20 empty] | Click here to go to Proposal dropdown lists
Environmental Quality Commission Meeting
|  | DEQ recommendation to the EQC |  |  |  |  | Agenda item |  |  | A
DEQ recommends that the Environmental Quality Commission:
|  | Adopt the proposed permanent rules in attachment A as part of chapter 340 of the Oregon Administrative Rules. | [11 empty] | Adopt the proposed permanent rules in attachment A as part of chapter 340 of the Oregon Administrative Rules.
Attachment A: Proposed rules
Director's electronic signature
Overview
Rule caption
Update Oregon rules to address federal air quality regulations
|  | Summary of proposed rules | [11 empty] | Summary of proposed rules
|  | Regulated parties | [11 empty] | Regulated parties
Summary of proposed rules
|  | Statement of need | [11 empty] | Statement of need
What problem is DEQ trying to solve?
How would the proposed rule solve the problem?
How will DEQ know the problem has been solved?
What alternatives did DEQ considered?
Request for other options
|  | During the public comment period, DEQ requested public comment on whether to consider other options for achieving the rule's substantive goals while reducing negative economic impact of the rule on business. | [11 empty] | During the public comment period, DEQ requested public comment on whether to consider other options for achieving the rule's substantive goals while reducing negative economic impact of the rule on business. | requested
Enter your freeform title here
DEQ’s 2006-2011 Strategic Directions include promoting sustainable practices, improving Oregon’s air and water, protecting people and the environment from toxics, and involving Oregonians in solving problems. By providing…
Federal relationship
Ä
ORS 183.332
OAR 340-011-0029
|  | "It is the policy of this state that agencies shall seek to retain and promote the unique identity of Oregon by considering local conditions when an agency adopts policies and rules. However, since there are many federal laws and regulations that apply to activities that are also regulated by the state, it is also the policy of this state that agencies attempt to adopt rules that correspond with equivalent federal laws and rules..." | [11 empty] | Oregon Title V Operating Permit Fees under OAR 340 Division 220
|  | The proposal adopts the federal requirement verbatim or by reference. | [6 empty] | FALSE |  | ORS 468A.327 | DDL
Describe federal requirement
This rule proposal is different from or in addition to federal requirements. The following exemption from adopting rules that correspond with equivalent federal laws and rules applies to this proposal.
|  | Local or special conditions exist in this state that warrant a different rule; ORS 183.332 (3) | [9 empty] | DDL
Discuss HOW the proposal is different from or in addition to federal requirements.
Discuss WHY the proposal is different from or in addition to federal requirements.
|  | Rules affected, authorities, supporting documents | [11 empty] | Rules affected, authorities, supporting documents
| Lead division |  |  |  |  | Program or activity | [7 empty] | Land use
|  | Air Quality |  |  |  | Program Operations section | [7 empty] | SIP | #N/A
|  | Chapter 340 action | Div | Rule | Title | [5 empty] | SIP/Land use* |  |  | SIP/Land use* | Adopt | Amend | Renumber | Repeal | Suspend
|  | amend | 200 | 20 | General Air Quality Definitions | [5 empty] | SIP | DDL |  | 340-200-0020 |  | 340-200-0020
|  | amend | 200 | 40 | State of Oregon Clean Air Act Implementation Plan | [5 empty] | SIP
|  | amend | 216 | 20 | Applicability | [5 empty] | Land use and SIP
|  | amend | 216 | 20 | Table 1 | [5 empty] | Land use and SIP
|  | amend | 216 | 60 | General Air Contaminant Discharge Permits | [5 empty] | Land use and SIP
|  | amend | 216 | 64 | Simple ACDP | [5 empty] | Land use and SIP
|  | amend | 230 | 20 | Applicability
|  | amend | 230 | 30 | Definitions
|  | amend | 232 | 85 | Gasoline Delivery Vessel(s) | [5 empty] | SIP
|  | amend | 238 | 40 | Definitions
|  | amend | 238 | 60 | Federal Regulations Adopted by Reference
|  | amend | 244 | 30 | Definitions
|  | amend | 244 | 210 | Emissions Limitation for Existing Sources
|  | amend | 244 | 220 | Federal Regulations Adopted by Reference
|  | amend | 244 | 234 | Affected Sources | [5 empty] | SIP
|  | amend | 244 | 238 | Compliance Dates | [5 empty] | SIP
|  | amend | 244 | 240 | Work Practice and Submerged Fill Requirements | [5 empty] | SIP
|  | amend | 244 | 244 | Testing and Monitoring Requirements | [5 empty] | SIP
|  | amend | 244 | 246 | Notifications | [5 empty] | SIP
|  | amend | 244 | 248 | Recordkeeping Requirements | [5 empty] | SIP
|  | amend | 244 | 250 | Reporting Requirements | [5 empty] | SIP
|  | adopt | 230 | 500 | Applicability
|  | adopt | 230 | 505 | Compliance Schedule
|  | adopt | 230 | 510 | Increments of Progress Achievement Notifications
|  | adopt | 230 | 515 | Compliance with the Increments of Progress
|  | adopt | 230 | 520 | Waste Management Plan
|  | adopt | 230 | 525 | Operator Training and Qualifications Requirements
|  | adopt | 230 | 530 | Emission Limitations
|  | adopt | 230 | 535 | Operating Limits
|  | adopt | 230 | 540 | Affirmative Defense for Emission Limit Exceedances
|  | adopt | 230 | 550 | Demonstrating Initial Compliance
|  | adopt | 230 | 560 | Demonstrating Continuous Compliance | [8 empty] | 340-230-0565 | 340-230-0565
|  | adopt | 230 | 565 | Monitoring Equipment and Monitoring Parameters | [8 empty] | 340-230-0570 | 340-230-0570
|  | adopt | 230 | 570 | Recordkeeping | [8 empty] | 340-230-0575 | 340-230-0575
|  | adopt | 230 | 575 | Reporting | [8 empty] | 340-230-0580 | 340-230-0580
|  | adopt | 230 | 580 | Title V Operating Permits | [5 empty] | Land use |  |  | 340-244-0239 | 340-244-0239
|  | adopt | 244 | 239 | General Duties to Minimize Emissions | [8 empty] | 340-244-0230 |  |  |  | 340-244-0230
|  | repeal | 244 | 230 | Accidental Release Program
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
[14 empty] | * SIP means State Implementation Plan. | 340-230-0565 340-230-0570 340-230-0575 340-230-0580 340-244-0239 | 340-200-0020 |  | 340-244-0230
|  | * SIP means State Implementation Plan. | [11 empty] | * Land use means the DEQ State Agency Coordination Program considers this rule, program or activity is a land use program.
* Land use means the DEQ State Agency Coordination Program considers this rule, program or activity is a land use program.
|  | Statute implemented | [5 empty] | Legislation |  |  | Year
ORS 468.020, 468A.025, 468A.035, 468A.040 and 468A.310
Statutory or other legal authority
| Other Authority | ORS 468.020, 468A.025, 468A.035, 468A.040 and 468A.310
[5 empty] | Relied on for fiscal statement | [5 empty] | ORS 183.335(2)(b)(C) |  |  | Relied on for fiscal statement
|  | Supporting document title |  |  |  |  | To view document
|  | Code of Federal Regulations |  |  | No |  | Code of Federal Regulations
|  | Federal Register |  |  | No |  | Federal Register
No
Fiscal impact statement
|  | Fiscal and economic impact | [11 empty] | fee decrease
Statement of Cost of Compliance
|  | 1. Impact on state agencies, units of local government and the public. | [8 empty] | ORS 183.335(2)(b)(E)
|  | 2. Cost of compliance on small businesses with 50 or fewer employees. | [6 empty] | ORS 183.336(10)
Approximately ## small businesses in Oregon are subject to the current fees and would be subject to the proposed fees.
a) Estimated number of small businesses and types of businesses and industries with small businesses subject to proposed rule.
No additional activities are required for compliance with the proposed rules.
b) Projected reporting, recordkeeping and other administrative activities, including costs of professional services, required for small businesses to comply with the proposed rule.
No additional resources are required for compliance with the proposed rules.
c) Projected equipment, supplies, labor and increased administration required for small businesses to comply with the proposed rule.
d) Describe how DEQ involved small businesses in developing this proposed rule.
Housing Cost
The proposed rule does not affect fees
|  | Fees | The proposed rule does not affect fees
The statutory authority for the proposed The proposed rules do not affect fees. is
|  | ORS 459A.315 (2) | is the Environmental Quality Commission authority to adopt the proposed fees.
1. Reason for proposing fee change
change in fee payer mix
Provide trend information.
text
2. Reason for proposing fee change
new fee created by statute
Identify session, bill number and interested legislators.
text
3. Reason for proposing fee change
increase in program costs
Provide overview of the increased costs.
text
4. Reason for proposing fee change
Provide overview of the increased costs.
text
Brief description of proposed fee
text
Fee proposal alternatives considered
Affected parties
Affected party involvement in fee setting process
The ##-member Conversion Technology Workgroup met ## times in 2012 for the purpose of developing Oregon's Conversion Technology program. The workgroup provided input on the draft fee rule and the budget and fee structure. DEQ plans involve stakeholders during the public comment period.
Summary of impacts
text
|  | Fee payer agreement with fee change |  |  |  | Link to documents supporting the proposed fee
accepting
Current fee structure
How long will current fee sustain program?
|  | Program costs covered by fees |  |  |  | 0 |  |  | 100%
|  | Program costs covered by General Fund |  |  |  | 0 |  |  | 0%
|  | Fee last changed |  |  |  | 2007-08-01
Proposed fee structure
How long will proposed fee sustain program?
3 to 5 years
|  | Expected change in revenue (+/-) |  |  |  | 0 |  |  | 0%
|  | Min GF required by statue/rule to fund program |  |  |  | 0 |  |  | 100%
|  | Proposed fee allows General Fund replacement |  |  |  | 0 |  |  | 100%
|  | Expected effective date |  |  |  | 2012-12-18
[6 empty] | Number of | Impact on revenue |  |  | Total revenue
[6 empty] | transactions | (+/-) |  |  | (+/-)
|  |  | Current biennium |  |  | 0 | 0 |  |  | 0
|  |  | Next biennium |  |  | 0 | 0 |  |  | 0
Fee Schedule
Land use evaluation
|  | “It is the Commission's policy to coordinate the Department's programs, rules and actions that affect land use with local acknowledged plans to the fullest degree possible.” | [8 empty] | ORS 197.180
OAR 340-018
[11 empty] | OAR 660-030-0005 | SAC |  | The proposed rules identified under the 'Chapter 340 Action' section above do not affect existing rules, programs or activities that are considered land use programs in the DEQ State Agency Coordination (SAC) Program.
|  | The proposed rules identified under the 'Chapter 340 Action' section above do not affect existing rules, programs or activities that are considered land use programs in the DEQ State Agency Coordination (SAC) Program. | [11 empty] | OAR 340-018-0030 does not include programs or actions that relate to the proposed rules.
|  | OAR 340-018-0030 does not include programs or actions that relate to the proposed rules. | [9 empty] | DDL
DDL
DDL
|  | Existing statewide goal compliance and local plan compatibility procedures adequately cover the proposed rules. | [9 empty] | Input |  | 1
Please explain
|  | The land use goal that relates to the proposal is: | [9 empty] | DDL
Goal 5 - Open Spaces, Scenic and Historic Areas, and Natural Resources
Does the program or rules Reasonably expected to have:
a. Significant effects on resources, objectives or areas identified in the statewide planning goals, or
b. Present or future land uses identified in acknowledged comprehensive plans.
If the proposed rules have been determined a land use program under 2. above, but are not subject to existing land use compliance and compatibility procedures, explain the new procedures the Department will use to ensure compliance and compatibility.
Implementation
Public involvement
Workgroups and advisory committees
Committee charter
include section here that describes key public involvement dates.
|  | Committee members |  |  |  | Affiliation
>
Committee recommendation
The EQC requested the following involvement with this rulemaking.
The EQC requested the following involvement with this rulemaking.
|  | Facilitated hearing |  |  | Information item on agenda |  |  |  | In the Director's Dialog |  |  |  |  | EQC - facilitated hearing not request | EQC - Information Item not requested | EQC - Director's Dialog not request
2012-12-12
[14 empty] | 0 | 0 | 0
Public Notice
Notice posted on DEQ webpage
http://www.deq.state.or.us/regulations/proposedrules.htm
Emailed notice to:
GovDelivery list of interested parties
Stakeholders
|  | Email notice to key legislators | [7 empty] | ORS 183.335
> |  | Jackie Dingfelder, Chair, Senate Environment and Natural Resources Committee
Mailed notice by U.S. Postal Service
Sent notice to EPA
|  | Notice published in SOS Bulletin |  |  | 2012-10-01
|  | Public comment period closed |  |  | 2012-12-18
Summary of comments and DEQ responses
|  | Comment summary | 1
Response
|  | Comment summary | 2
Response
|  | Comment summary | 3
Response
|  | Comment summary | 4
Response
|  | Comment summary | 5
Response
|  | Comment summary | 6
Response
|  | Comment summary | 7
Response
|  | Comment summary | 8
Response
|  | Comment summary | 9
Response
|  | Comment summary | 10
Response
|  | Comment summary | 11
Response
|  | Comment summary | 12
Response
|  | Comment summary | 13
Response
|  | Comment summary | 14
Response
|  | Comment summary | 15
Response
|  | Comment summary | 16
Response
|  | Comment summary | 17
Response
|  | Comment summary | 18
Response
|  | Comment summary | 19
Response
|  | Comment summary | 20
Response
|  | Comment summary | 21
Response
|  | Comment summary | 22
Response
|  | Comment summary | 23
Response
|  | Comment summary | 24
Response
|  | Comment summary | 25
Response
|  | Comment summary | 26
Response
|  | Comment summary | 27
Response
|  | Comment summary | 28
Response
|  | Comment summary | 29
Response
|  | Comment summary | 30
Response
|  | Comment summary | 31
Response
|  | Comment summary | 32
Response
Commenters
|  | Commenter ID | 1
=IF(L369>KDClosePubComment, "DEQ received comment after the public record closed and regulations prohibit considering it in the final recommendation.","")
|  | Commenter ID | 2
UNDER CONSTRUCTION
Dropdown lists for proposal tab
[22 empty] | DDL_FeeChangeReason | VL_FeeChangeReason
[22 empty] | regulatory streamlining | Please explain.
[22 empty] | policy change | Please explain.
[22 empty] | new fee created by statute | Identify session, bill number and interested legislators.
[22 empty] | fee allowed in statute | Optional - provide useful information.
[22 empty] | change in federal revenue | Optional - provide useful information.
[22 empty] | change in Other Funds revenues | Optional - provide useful information.
[22 empty] | increase in program costs | Provide overview of the increased costs.
[22 empty] | increase in systems costs | Please explain.
[22 empty] | change in transaction volume | Provide trend information and FTE workload statistics.
[22 empty] | changed number of fee payers | Provide trend information and FTE workload statistics.
[22 empty] | change in fee payer mix | Provide trend information.
[22 empty] | response to legislative concerns | Optional - provide useful information.
[22 empty] | underestimated operating costs | Please explain.
[22 empty] | underestimated business systems development costs | Please explain.
[22 empty] | overestimated operating costs | Please explain.
[22 empty] | response to legislative concerns | Identify session, committees, legislators and concerns.
DDL_FedConnection
has no corresponding federal regulation.
would achieve goals of federal law with least impact on public and private resources.
would have effect of clarifying the federal rules, standards, procedures or requirements.
would address local or special conditions that warrant a different rule.
has a federal waiver that warrants a different rule.
has specific statutory direction authorizes adoption.
would align Oregon rules with federal requirements.
would maintain federal delegation.
would maintain commitment in PPA.
would align with science applicable to Oregon.
would address public health issues in Oregon.
would address economic conditions in Oregon.
would incorporate technological advancement.
would incorporate administrative advancement.
would keep an advisory committee commitment.
would maintain federal funding.
would ensure program funding.
would ensure program support.
would ensure compliance.
would keep an EQC commitment.
would keep a stakeholder commitment.
reduce difficulty in doing business.
DDL_FedReqExceptions
ORS 183.332 does not list an exemption.
There is specific statutory direction to the agency that authorizes the adoption of the rule. ORS 183.332 (1)
A federal waiver has been granted that authorizes the adoption of the rule. ORS 183.332 (2)
Local or special conditions exist in this state that warrant a different rule; ORS 183.332 (3)
The state rule has the effect of clarifying the federal rules, standards, procedures or requirements. ORS 183.332 (4)
The state rule achieves the goals of the federal and state law with the least impact on public and private resources; ORS 183.332 (5)
There is no corresponding federal regulation. ORS 183.332 (6)
DDL_LandUseProceduresAdequate
Existing statewide goal compliance and local plan compatibility procedures adequately cover the proposed rules.
Existing statewide goal compliance and local plan compatibility procedures do not adequately cover the proposed rules.
DDL_SAC
(1)(a) Approval of Noise Impact Boundaries for Motor Racing Facilities
(1)(b) Approval of Airport Noise Abatement Program and Noise Impact Boundaries
(1)(c) Approval of Notice of Construction
(1)(d) Issuance of Air Contaminant Discharge Permit
(1)(e) Issuance of Indirect Source Construction Permit
(1)(f) Approval of Parking and Traffic Circulation Plan
(1)(g) Employee Commute Options
(2) Environmental Cleanup Division: Issuance of Environmental Hazard Notice
(3)(a) Issuance of Solid Waste Disposal Permit
(3)(b) Issuance of Waste Tire Storage Permit
(3)(c) Issuance of Hazardous Waste and PCB Storage, Treatment and Disposal Permit
(4) Management Services Division: Approval of Pollution Control Bond Fund Application
(5)(a) Approval of Wastewater System and Facility Plans
(5)(b) Approval of State Revolving Loan Application
(5)(c) Issuance of On-site Sewer Permit
(5)(d) Issuance of NPDES and WPCF Permits
(5)(e) Development of Water Quality Wetland Protection Criteria
(5)(f) Requirement of an Implementation Plan to Meet Restrictions for Waste Load Allocations on Water Quality Limited Waterways (TMDLS)
(5)(g) Certification of Water Quality Standards for Federal Permits, Licenses
(5)(h) Development of Action Plan for Declared Ground Water Management Area
(5)(i) Development of Nonpoint Source Management Plan
(5)(j) Development of Estuary Plans
DDL_LandUseGoals
[22 empty] | Goal 6 - Air, Water and Land Resources Quality | requires that all waste and process discharges from development comply with state and federal environmental quality standards.
Goal 5 - Open Spaces, Scenic and Historic Areas, and Natural Resources
Goal 11 - Public Facilities and Services
Goal 16 - Estuarian resources
Goal 19 - Ocean Resources
DDL_EQCDirDilaog
Information through Director's Dialog.
No Director's Dialog
Note on A18: CAPTION Oregon law requires a caption that must not exceed 15 words but try not to exceed 8 words or less. The caption must reasonably identify the subject matter of the intended action. ORS 183.335(2)(a)(A) Where used The caption entered to the left is used on all rulemaking documents including the:  annual DEQ rulemaking plan  proposal  announcement  rulemaking web page  notice  certificate of order and filing  reports to legislature including Ways and Means  5-year rule review
Note on A31: Statement of Need and Justification A "Statement of Need and Justification" explains the need for a temporary rulemaking action and the justification for submitting the changes as a temporary rule rather than using the permanent rule process. The Statement of Need and Justification form accompanies the Certificate and Order for Filing Temporary Rules. OAR 166-500-0010 (23) The APA "requires that an agency “take appropriate measures to make the temporary rules known to persons who may be affected by them.” This includes interested parties, organizations and agencies on the agency’s interested party mailing list, as well as and others who may be affected." ORS 183.355(2)(b) Where used:  Proposal - this section part of the EQC recommendation  Certificate and Order for Filing Temporary Rules
Note on A32: Statement of Need Definition A "Statement of Need and Fiscal Impact" explains the need for the proposed rulemaking action and its fiscal impact. The Statement of Need and Fiscal Impact form accompanies the Notice of Proposed Rulemaking Hearing and the Notice of Proposed Rulemaking OAR 166-500-0010 (22) Requirement Before adopting amending or repealing any rule, DEQ must give notice of our intended action that includes a "statement of the need for the rule and a statement of how the rule is intended to meet the need." OAR 183.335(2)(b)(C) The "need" is what DEQ perceives as the need for the proposed rule and it must justify why we are invoking our discretionary rulemaking authority. This statement is intended to be informal and provide sufficient information for an interested party the opportunity to provide information or challenge our assertions. Where used:  Notice  Certificate and Order for Filing Permanent Rules
Note on A40: Statement of Need and Justification A "Statement of Need and Justification" explains the need for a temporary rulemaking action and the justification for submitting the changes as a temporary rule rather than using the permanent rule process. The Statement of Need and Justification form accompanies the Certificate and Order for Filing Temporary Rules. OAR 166-500-0010 (23) The APA "requires that an agency “take appropriate measures to make the temporary rules known to persons who may be affected by them.” This includes interested parties, organizations and agencies on the agency’s interested party mailing list, as well as and others who may be affected." ORS 183.355(2)(b) Where used:  Proposal - this section part of the EQC recommendation  Certificate and Order for Filing Temporary Rules
Note on A41: Statement of Need Definition A "Statement of Need and Fiscal Impact" explains the need for the proposed rulemaking action and its fiscal impact. The Statement of Need and Fiscal Impact form accompanies the Notice of Proposed Rulemaking Hearing and the Notice of Proposed Rulemaking OAR 166-500-0010 (22) Requirement Before adopting amending or repealing any rule, DEQ must give notice of our intended action that includes a "statement of the need for the rule and a statement of how the rule is intended to meet the need." OAR 183.335(2)(b)(C) The "need" is what DEQ perceives as the need for the proposed rule and it must justify why we are invoking our discretionary rulemaking authority. This statement is intended to be informal and provide sufficient information for an interested party the opportunity to provide information or challenge our assertions. Where used:  Notice  Certificate and Order for Filing Permanent Rules
Note on A54: REQUEST FOR OTHER OPTIONS Requirement "A request for public comment on whether other options should be considered for achieving the rule’s substantive goals while reducing the negative economic impact of the rule on business." OAR 183.335(2)(b)(G) Processing note: The tense used in the phrase in the cell to the right changes as the rulemaking progresses. Where used:  Notice  Proposal
Note on A65: Federal relationship Requirement This section includes elements required to meet the following requirements. ORS 183.332 For policy statement and exemptions for adopting rules that correspond with equivalent federal laws. OAR 468A.321 (1) For facilities required to pay fees under ORS 468A.315 (emission fees for major sources) OAR 340-011-0029 For DEQ rules adopted in response to Senate Bill 107, section 3, 2007 session that apply to Oregon Title V Operating Permit Fees under OAR 340 Division 220. Processing note: The tense used in the phrase in the cell to the right changes as the rulemaking progresses. Where used:  Notice  Proposal
Note on A85: CHAPTER 340 ACTIONS Definitions An "Adopted Administrative Rule" is a completely new rule added to an agency's existing body of rules. New rule numbers must be approved by the Administrative Rules Unit prior to filing. OAR 166-500-0010(2) An "Amended Administrative Rule" is an existing rule that is modified by additions or deletions to the rule text under an existing rule number. OAR 166-500-0010(3) A "Renumbered Administrative Rule" is an existing rule that is moved from an existing rule number to a new rule number. OAR 166-500-0010(16) A "Repealed Administrative Rule" is an existing rule that is completely removed from the Oregon Administrative Rule Compilation. OAR 166-500-0010(17) A "Suspended Administrative Rule" is an existing rule that is rendered ineffective for a specified time not to exceed 180 days. See ORS 183.335(6). OAR 166-500-0010(26) Where used The Chapter 3430 Actions entered to the left are used on the:  notice  certificate of order and filing
Note on A149: STATUTE IMPLEMENTED Definition Statutes ("Stats.") Implemented is the statute(s), bill(s) or federal legislation that an agency implements through the rulemaking process. OAR 166-500-0010 (25) Requirement The notice must include a citation of the statute or other law the rule is intended to implement. ORS 183.335(2)(b)(B) The project lead is responsible for verifying that all statutes entered into this cell are valid and accurate. Do not simply accept what was entered into the previously filed rules. Where used The statutes entered to the left are used on the:  notice  certificate of order and filing
Note on A152: STATUTORY AND OTHER LEAGAL AUTHORITY Definition Statutory Authority ("Stat. Auth.") is an agency's authority to make rules granted by Oregon Revised Statutes. OAR 166-500-0010 (24) Requirement The notice must include a citation of the statutory or other legal authority for the agency's rulemaking. ORS 183.335(2)(b)(A) The project lead is responsible for verifying that the statutory authorities entered into this cell are valid and accurate. Do not simply accept what was in the previously filed rules. All rules must include the EQC authority to adopt rules under ORS 468.020. If the proposed rule is a Title V rule, this cell must also include ORS 468A.020. Additionally, this cell must include any statutory authority to adopt these proposed rules. Cite ORS 468.020 for the EQC's general authority to adopt rules, ORS 468.065 if the proposed rules have to do with permits and fees. Where used The statutes entered to the right are used on the:  notice  certificate of order and filing
Note on A157: STATUTORY AND OTHER LEAGAL AUTHORITY Definition Requirement The notice must include a citation of the statutory or other legal authority for the agency's rulemaking. ORS 183.335(2)(b)(C) Where used The statutes entered to the left are used on the:  notice  certificate of order and filing
Note on A167: ADVISORY COMMITTEE Definition Requirement The notice must include a citation of the statutory or other legal authority for the agency's rulemaking. ORS 183.335(2)(b)(C) Where used The statutes entered to the left are used on the:  notice  certificate of order and filing
Note on A251: STATEWIDE GOALS The proposed rule is a land use rule if the SAC Program specifically references the rule, program, activity or action. Of the 19 statewide land use goals, goal 6 is the primary goal that relates to DEQ programs. The implementation of goals 5, 11, 16 and 19 may also relate to our programs because the goals consider the carrying capacity and protection of air and water resources. • Goal 6 - Air, Water and Land Resources • Goal 5 - Open Spaces, Scenic and Historic Areas, and Natural Resources • Goal 11 - Public Facilities and Services • Goal 16 - Estuarine Resources • Goal 19 - Ocean Resources
Note on A254: STATEWIDE GOALS The proposed rule is a land use rule if it relates to statewide land use goals that we reasonably expect to have a significant effect on: a. resources, objectives or areas identified in the statewide planning goals, or b. present or future land uses identified in acknowledged comprehensive plans. The land use responsibilities of a rule, program, action or activity that involved more than one agency are the responsibilities of the agency with primary authority. DEQ must consider our mandate to protect public health and safety and the environment when determining the land use significance.
Note on O6: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the perimeter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
mm/dd/yy
Subject
Your name
Your message
02/28/12
Space
Jerry Ebersole
The entire rule Titles are not visible
02/28/2012
Cell Height
Jerry Ebersole
I can't make the cell height any larger.
Maggie response See section below for examples
I also don't like that Excel doesn't have a Word like spell checker.
Maggie response
Review|Spelling check doesn't work?
I have to export to Word to add new paragraphs (i.e., if you hit the enter key, it sends you to the next cell.
Maggie response If you work in the formula bar, you won't have this problem. There is also a key combination around this but I don't remember it right now.
Jerry response Did not work.
3/5/12
Regulated party
Maggie
The content doesn't name the regulated party. We just need one or two sentences here. Jerry response It is impossible to name the regulated parties, so I describe the regulated parties.
03/09/2012
New Format
Jerry Ebersole
Still a little clumsy, but better. When you are in edit mode, "Reduction of Burden on Business" and "Alignment with Federal Regulations" are underlined. Why are they not underlined when out of edit mode.
Maggie - I don't know why its doing that but I'll try to figure it out.
03/09/2012
New Format
Jerry Ebersole
Same problem, underlining in edit mode, but not out of edit mode.

## ScheduleTasks (hidden)
[9 empty] | GoToAHG |  |  | >
| Schedule tasks |  | To restore cells in columns I and J to default, enter =AH followed by the current cell column and row. | [885 empty] | 1899-12-31 | Protect Yellow columns |  |  | EMT plan approval | 2011-11-17
|  |  | Task complete |  |  |  |  | locked | DEQ closed |  |  | -150 |  |  | Action days | Weekend | DEQ closed | [10 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [6 empty] | Action days | Weekend | DEQ closed | [9 empty] | Action days | Weekend | DEQ closed |  |  |  |  | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [10 empty] | Action days | Weekend | DEQ closed | [12 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [12 empty] | Action days | Weekend | DEQ closed | [10 empty] | Action days | Weekend | DEQ closed | [18 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed |  |  |  |  | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed | [11 empty] | Action days | Weekend | DEQ closed
|  |  |  | Workdays |  | Calendar Days | [882 empty] | add least amount of time - leisurely | time axis 2026-03-07 to 2028-07-30
| Task |  | Owner | Task | Left | Task | Left | Start | End | [882 empty] | Column B Insert | time axis 2026-03-07 to 2028-07-30
| Overview of key dates | [6 empty] | 2011-11-17 | 2013-02-01 | B | t | [877 empty] | 2011-11-17 | 2013-02-01
y
| Select target EQC date |  | RDT |  | -3559 |  | -4982 | 2011-11-17 | 2012-12-13 | [879 empty] | 2012-12-13 | 2012-12-13
| State Implementation Plan not involved |  | PE |  | -3605 |  | -5072 | 2012-09-14 | 2012-09-14 | [879 empty] | 2012-09-14 | 2012-09-14 | 4 | State Implementation Plan not involved
| Fees not involved | > | RDT,RG | 1 | -3513 | 0 | -4932 | 2013-02-01 | 2013-02-01 | [879 empty] | 2013-02-01 | 2013-02-01 | 0 | Fees not involved
| Submit/publish notice in SOS Bulletin | > | RG | 12 | -3594 | 17 | -5055 | 2012-09-14 | 2012-10-01 | [879 empty] | 2012-09-14 | 2012-10-01 | 60 | Submit/publish notice in SOS Bulletin
| Hold first public hearing |  | RDT | 1 | -3583 | 0 | -5040 | 2012-10-16 | 2012-10-16 | [879 empty] | 2012-10-16 | 2012-10-16 |  | Hold first public hearing
| Hold last public hearing |  | RDT | 1 | -3583 | 0 | -5040 | 2012-10-16 | 2012-10-16 | [879 empty] | 2012-10-16 | 2012-10-16 |  | Hold last public hearing
| Close public comment |  | RG | 1 | -3580 | 0 | -5034 | 2012-10-22 | 2012-10-22 | [879 empty] | 2012-10-22 | 2012-10-22
| Submit/attend EQC action meeting | > | PE,LM | 27 | -3545 | 41 | -4982 | 2012-11-02 | 2012-12-13 | [879 empty] | 2012-11-02 | 2012-12-13
| Effective |  |  | 1 | -3542 | 0 | -4977 | 2012-12-18 | 2012-12-18 | [879 empty] | 2012-12-18 | 2012-12-18
| Concept | [6 empty] | 2011-06-21 | 2011-11-17 | B | t | [877 empty] | 2011-06-21 | 2011-11-17
y
Develop concept annual DEQ Rulemaking Plan
| Solicite potential rulemaking proposals |  | ARC,LDA,LM | 11 | -3936 | 14 | -5509 | 2011-06-21 | 2011-07-05 | [879 empty] | 2011-06-21 | 2011-07-05
| Conduct lead manager (LM) meeting |  | RG | 8 | -3928 | 9 | -5499 | 2011-07-06 | 2011-07-15 | [879 empty] | 2011-07-06 | 2011-07-15
| Assign process expert (PE) |  | ARC | 1 | -3946 | 0 | -5523 | 2011-06-21 | 2011-06-21 | [879 empty] | 2011-06-21 | 2011-06-21
| Identify & notify subject expert (SE) |  | LM,PE | 1 | -3946 | 0 | -5523 | 2011-06-21 | 2011-06-21 | [879 empty] | 2011-06-21 | 2011-06-21
| Conduct SE training |  | RG | 1 | -3946 | 0 | -5523 | 2011-06-21 | 2011-06-21 | [879 empty] | 2011-06-21 | 2011-06-21
Draft what is known now on:
| Considerations | > | SE,PE,LM | 11 | -3936 | 14 | -5509 | 2011-06-21 | 2011-07-05 | [879 empty] | 2011-06-21 | 2011-07-05
| Resources | > | SE,PE,LM | 8 | -3928 | 9 | -5499 | 2011-07-06 | 2011-07-15 | [879 empty] | 2011-07-06 | 2011-07-15
| Plan view of ScheduleTasks | > | SE,PE,LM | 1 | -3946 | 0 | -5523 | 2011-06-21 | 2011-06-21 | [879 empty] | 2011-06-21 | 2011-06-21
Loop as needed
| Approve content |  | LM | 11 | -3925 | 14 | -5494 | 2011-07-06 | 2011-07-20 | [879 empty] | 2011-07-06 | 2011-07-20
| Brief lead divion administrator |  | LM,SE,PE | 8 | -3917 | 11 | -5482 | 2011-07-21 | 2011-08-01 | [879 empty] | 2011-07-21 | 2011-08-01
| Review |  | LDA | 1 | -3946 | 0 | -5523 | 2011-06-21 | 2011-06-21 | [879 empty] | 2011-06-21 | 2011-06-21
| Loop as needed |  | RDT
| Approve content |  | LDA | 11 | -3914 | 14 | -5479 | 2011-07-21 | 2011-08-04 | [879 empty] | 2011-07-21 | 2011-08-04
| Check in concept approved |  | PE | 8 | -3906 | 11 | -5467 | 2011-08-05 | 2011-08-16 | [879 empty] | 2011-08-05 | 2011-08-16
| Draft consolidated annual DEQ Rulemaking Plan |  | ARC | 1 | -3990 | 0 | -5585 | 2011-04-20 | 2011-04-20 | [879 empty] | 2011-04-20 | 2011-04-20
| Review and modify draft |  | RG | 8 | -3982 | 11 | -5573 | 2011-04-21 | 2011-05-02 | [879 empty] | 2011-04-21 | 2011-05-02
| Consensus review of draft |  | LMs,LDAs | 1 | -3946 | 0 | -5523 | 2011-06-21 | 2011-06-21 | [879 empty] | 2011-06-21 | 2011-06-21
Loop as needed
| Prepare EMT presentation |  | ARC,LDA | 1 | -3946 | 0 | -5523 | 2011-06-21 | 2011-06-21 | [879 empty] | 2011-06-21 | 2011-06-21
| EMT MEETING |  |  | 4 | -3839 | 3 | -5374 | 2011-11-14 | 2011-11-17 | [879 empty] | 2011-11-14 | 2011-11-17
| Archive version 1.0 of the blueprint |  | RG
| Start rulemaking | [6 empty] | 2012-02-27 | 2012-03-19 | B | t | [877 empty] | 2012-02-27 | 2012-03-19
y
| Identify core rule design team | > | LM,SE,PE | 1 | -3767 | 0 | -5272 | 2012-02-27 | 2012-02-27 | [879 empty] | 2011-11-18 | 2012-02-27
| Develop team SharePoint |  | PE | 15 | -3752 | 20 | -5251 | 2012-02-28 | 2012-03-19 | [879 empty] | 2012-02-28 | 2012-03-19
Rough draft what is known now on:
| Considerations | > | SE,PE,LM | 8 | -3760 | 9 | -5263 | 2012-02-27 | 2012-03-07 | [879 empty] | 2012-02-27 | 2012-03-07
| Resources | > | SE,PE,LM | 8 | -3760 | 9 | -5263 | 2012-02-27 | 2012-03-07 | [879 empty] | 2012-02-27 | 2012-03-07
| ScheduleTasks - this worksheet | > | SE,PE,LM | 8 | -3760 | 9 | -5263 | 2012-02-27 | 2012-03-07 | [879 empty] | 2012-02-27 | 2012-03-07
| Proposal | > | SE,PE,LM | 8 | -3760 | 9 | -5263 | 2012-02-27 | 2012-03-07 | [879 empty] | 2012-02-27 | 2012-03-07
| Notify team members |  | LM | 3 | -3763 | 2 | -5268 | 2012-02-29 | 2012-03-02 | [879 empty] | 2012-02-29 | 2012-03-02
| Review workflow | > | RDT | 6 | -3760 | 7 | -5263 | 2012-02-29 | 2012-03-07 | [879 empty] | 2012-02-29 | 2012-03-07
| Team kickoff meeting |  | PE,LDA,RDT | 1 | -3760 | 0 | -5263 | 2012-03-07 | 2012-03-07 | [879 empty] | 2012-03-07 | 2012-03-07
| Schedule recurring team meetings |  | PE,RDT | 1 | -3760 | 0 | -5263 | 2012-03-07 | 2012-03-07 | [879 empty] | 2012-03-07 | 2012-03-07
| Draft Meeting Manager |  | PE | 231 | -3523 | 340 | -4932 | 2012-02-27 | 2013-02-01 | [879 empty] | 2012-02-27 | 2013-02-01
Start draft rules
| Contact ARC for new division/rule numbers |  | PE | 1 | -3759 | 0 | -5262 | 2012-03-08 | 2012-03-08 | [879 empty] | 2012-03-08 | 2012-03-08
| Check out/post current OAR compilation |  | PE | 1 | -3759 | 0 | -5262 | 2012-03-08 | 2012-03-08 | [879 empty] | 2012-03-08 | 2012-03-08
| Go to SIP section |  | PE | 1 | -3752 | 0 | -5251 | 2012-03-19 | 2012-03-19 | [879 empty] | Go to SIP section | 2012-03-19
| No advisory committee convened | [6 empty] | 2011-11-17 | 2012-12-11 | B | t | [877 empty] | 2011-11-17 | 2013-02-01 |  | No advisory committee convened
y
Review materials
| Advisory Committee Guide |  | RDT | 22 | -3851 | 29 | -5390 | 2011-10-03 | 2011-11-01 | [879 empty] | 2011-11-17
| Considerations tab for involvement |  | RDT | 22 | -3851 | 29 | -5390 | 2011-10-03 | 2011-11-01
| Identify potential committee members |  | RDT | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Identify charter consideration |  | RDT | 78 | -3789 | 115 | -5304 | 2011-10-03 | 2012-01-26 | [879 empty] | 2011-12-27 | 2012-03-30
| Review and refine charter considerations |  | RDT | 22 | -3851 | 29 | -5390 | 2011-10-03 | 2011-11-01
| Approve charter considerations |  | LA | 22 | -3851 | 29 | -5390 | 2011-10-03 | 2011-11-01
| Set potential meeting dates and venues |  | RDT |  |  |  |  | 2011-10-03 | 2011-11-01
| Reserve potential venues |  | PA |  |  |  |  | 2011-10-03 | 2011-11-01
Develop committee communications
| Script initial voice contact |  | PE | 22 | -3851 | 29 | -5390 | 2011-10-03 | 2011-11-01
| Draft committee invitation |  | PE | 22 | -3851 | 29 | -5390 | 2011-10-03 | 2011-11-01
| Draft committee website content |  | PE
| Review script, inviation and web content |  | RDT
Loop as needed
| Approve script, invitation and web content |  | LA | 22 | -3851 | 29 | -5390 | 2011-10-03 | 2011-11-01
| Initial voice contact |  | RDT | 78 | -3789 | 115 | -5304 | 2011-10-03 | 2012-01-26
| Post web content |  | PA | 22 | -3851 | 29 | -5390 | 2011-10-03 | 2011-11-01
| Send invitation |  | PA | 22 | -3851 | 29 | -5390 | 2011-10-03 | 2011-11-01
| Maintain web content |  | PE, PA | 22 | -3851 | 29 | -5390 | 2011-10-03 | 2011-11-01 | [879 empty] | #REF! | 2012-12-13
| Finalize meeting dates |  | RDT | 58 | -3811 | 85 | -5334 | 2011-10-03 | 2011-12-27
| Release unneeded venues |  | PA
| Meeting 1 |  | PE | 1 | -3789 | 0 | -5304 | 2012-01-26 | 2012-01-26 | [879 empty] | 2012-03-30
| Meeting mechanics tab |  | PA | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03 | [880 empty] | 2011-11-08
| Identify meeting roles |  | RDT |  |  |  |  | 2011-10-03 | 2012-01-03
| Invite stakeholder presenters if appropriate |  | PE |  |  |  |  | 2011-10-03 | 2012-01-03
Draft meeting materials
| Notice/email/GovDelivery | ` | PE | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Agenda |  | PE | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Presentation |  | PE, RDT | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
Loop as needed
| Approve materials |  | PM | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Post materials on committee webpage |  | PA |  |  |  |  | 2011-10-03 | 2012-01-03
| Send meeting notice with link to webpage |  | PA
| Presentation practice |  | RDT
| Hold meeting |  | RDT |  |  |  |  | 2011-10-03 | 2011-11-01
| Draft minutes |  | PE | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Debrief conference |  | RDT | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Post draft minutes on website |  | PA | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Meeting 2 |  | PE | 1 | -3789 | 0 | -5304 | 2012-01-26 | 2012-01-26 | [879 empty] | 0
| Meeting mechanics tab |  | PA | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03 | [880 empty] | 2012-02-02
| Identify meeting roles |  | RDT |  |  |  |  | 2011-10-03 | 2012-01-03
| Invite stakeholder presenters if appropriate |  | PE |  |  |  |  | 2011-10-03 | 2012-01-03
Draft meeting materials
| Notice/email/GovDelivery | ` | PE | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Agenda |  | PE | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Presentation |  | PE, RDT | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
Loop as needed
| Approve materials |  | PM | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Post materials on committee webpage |  | PA | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Send meeting notice with link to webpage |  | PA | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Presentation practice |  | RDT | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Hold meeting |  | RDT | 1 | -3789 | 0 | -5304 | 2012-01-26 | 2012-01-26
| Draft minutes |  | PE | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Debrief conference |  | RDT | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Post draft minutes on website |  | PA | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Meeting 3 |  | PE | 1 | -3789 | 0 | -5304 | 2012-01-26 | 2012-01-26 | [879 empty] | 0
| Meeting mechanics tab |  | PA | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03 | [880 empty] | 2012-01-10
| Identify meeting roles |  | RDT | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Invite stakeholder presenters if appropriate |  | PE | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
Draft meeting materials
| Notice/email/GovDelivery | ` | PE | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Agenda |  | PE | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Presentation |  | PE, RDT | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
Loop as needed
| Approve materials |  | PM | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Post materials on committee webpage |  | PA | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Send meeting notice with link to webpage |  | PA | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Dress rehersal |  | RDT | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Hold meeting |  | RDT | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Draft minutes |  | PE | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Debrief conference |  | RDT | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| Post draft minutes on website |  | PA | 62 | -3806 | 92 | -5327 | 2011-10-03 | 2012-01-03
| State Implementation Plan | [6 empty] | 2012-12-31 | 2013-02-01 | B | t | [877 empty] | 2012-12-31 | 2013-02-01 |  | State Implementation Plan
y
Yada
| If idicator | [887 empty] | 2012-12-31 | 2013-02-01
| Yada |  | RDT | 22 | -3523 | 32 | -4932 | 2012-12-31 | 2013-02-01 | [879 empty] | 2012-12-31 | 2013-02-01
| Yada yada | [887 empty] | 2012-12-31 | 2013-02-01
| yada | [887 empty] | 2012-12-31 | 2013-02-01
yada yada yada
yada yada yada
| Release Yada to EPA |  | LM | 0 | -33027 | 0 | -46238 | 0 | 0
| Fees not involved | [6 empty] | 2012-12-31 | 2013-02-01 | B | t | [877 empty] | 2012-12-31 | 2013-02-01 |  | Fees not involved
y
| Finalize Considerations: Fees | > | RDT | 22 | -3523 | 32 | -4932 | 2012-12-31 | 2013-02-01 | [879 empty] | 2012-12-31 | 2013-02-01
If DAS approval required
| Devlope fee approval packet |  | RDT | 22 | -3523 | 32 | -4932 | 2012-12-31 | 2013-02-01 | [879 empty] | 2012-12-31 | 2013-02-01
| Considerations: fees | > |  | 22 | -3523 | 32 | -4932 | 2012-12-31 | 2013-02-01 | [879 empty] | 2012-12-31 | 2013-02-01
| Proposal: fees | > |  | 22 | -3523 | 32 | -4932 | 2012-12-31 | 2013-02-01 | [879 empty] | 2012-12-31 | 2013-02-01
| Fee schedule |  |  | 22 | -3523 | 32 | -4932 | 2012-12-31 | 2013-02-01 | [879 empty] | 2012-12-31 | 2013-02-01
Fee analysis
| Finalize packet |  |  | 22 | -3523 | 32 | -4932 | 2012-12-31 | 2013-02-01 | [879 empty] | 2012-12-31 | 2013-02-01
OPTION
| Email packet to DAS for informal review |  | PE | 22 | -3523 | 32 | -4932 | 2012-12-31 | 2013-02-01 | [879 empty] | 2012-12-31 | 2013-02-01
| Address DAS concerns |  | PE, RDT | 22 | -3523 | 32 | -4932 | 2012-12-31 | 2013-02-01 | [879 empty] | 2012-12-31 | 2013-02-01
END OPTION
| Approve release of fee approval packet |  | LM | 22 | -3523 | 32 | -4932 | 2012-12-31 | 2013-02-01 | [879 empty] | 2012-12-31 | 2013-02-01
| Agency rules coordinator cycle and submittal | [887 empty] | 2012-12-31 | 2013-02-01
| Plain English and style guide edit |  | ARC, OCO | 22 | -3523 | 32 | -4932 | 2012-12-31 | 2013-02-01 | [879 empty] | 2012-12-31 | 2013-02-01
| Prepare submittal |  | ARC, RG | 22 | -3523 | 32 | -4932 | 2012-12-31 | 2013-02-01 | [879 empty] | 2012-12-31 | 2013-02-01
| Email packet to DAS Director |  | DepDir | 22 | -3523 | 32 | -4932 | 2012-12-31 | 2013-02-01 | [879 empty] | 2012-12-31 | 2013-02-01
| Lock fee approval | > | ARC, RG | 22 | -3523 | 32 | -4932 | 2012-12-31 | 2013-02-01 | [879 empty] | 2012-12-31 | 2013-02-01
| Considerations: fees | > | [886 empty] | 2012-12-31 | 2013-02-01
| Proposal: fees | > | [886 empty] | 2012-12-31 | 2013-02-01
| Archive blueprint data |  | ARC, RG
| Follow up for status |  | PE | 22 | -3523 | 32 | -4932 | 2012-12-31 | 2013-02-01 | [879 empty] | 2012-12-31 | 2013-02-01
| If DAS denies - decide on action |  | PE, RDT | 22 | -3523 | 32 | -4932 | 2012-12-31 | 2013-02-01 | [879 empty] | 2012-12-31 | 2013-02-01
Loop as needed
| If DAS approves - retain for post-EQC process |  | PA | 1 | -3523 | 0 | -4932 | 2013-02-01 | 2013-02-01 | [879 empty] | 2013-02-01 | 2013-02-01
| Public notice | [6 empty] | 2012-02-27 | 2012-10-22 | B | t | [877 empty] | 2012-02-27 | 2012-10-22 |  | Public notice | 200
y
| Start notice |  | RDT | 108 | -3656 | 155 | -5117 | 2012-02-27 | 2012-07-31 | [879 empty] | 2012-02-27 | 2012-07-31
| Schedule meetings, reserve venues | [6 empty] | Option 1 | Option 2
| EQC - Director's Dialog not request |  | PE,PA,RDT | 1 | -3684 | 0 | -5157 | 2012-06-21 | 2012-06-21 | [879 empty] | 2012-06-21 | 2012-06-21 |  | EQC - Director's Dialog not request
| EQC - Information Item not requested |  | PE,PA,RDT | 1 | -3684 | 0 | -5157 | 2012-06-21 | 2012-06-21 | [879 empty] | 2012-06-21 | 2012-06-21 |  | EQC - Information Item not requested
| EQC - facilitated hearing not request |  | PE,PA,RDT | 1 | -3684 | 0 | -5157 | 2012-06-21 | 2012-06-21 | [879 empty] | 2012-06-21 | 2012-06-21 |  | EQC - facilitated hearing not request
| Info meeting & hearings planned - FIRST |  | PE,PA,RDT | 1 | -3601 | 0 | -5040 | 2012-10-16 | 2012-10-16 | [879 empty] | 2012-10-16 | 2012-10-16 |  | Info meeting & hearings planned - FIRST |  |  | Committee | 0
| Hearings planned - next hearing |  | PE,PA,RDT | 1 | -3601 | 0 | -5040 | 2012-10-16 | 2012-10-16 | [879 empty] | 2012-10-16 | 2012-10-16 |  | Hearings planned - next hearing |  |  | SIP | 0
| Hearings planned - next hearing |  | PE,PA,RDT | 1 | -3601 | 0 | -5040 | 2012-10-16 | 2012-10-16 | [879 empty] | 2012-10-16 | 2012-10-16 |  | Hearings planned - next hearing |  |  | Fees
| Hearings planned - next hearing |  | PE,PA,RDT | 1 | -3601 | 0 | -5040 | 2012-10-16 | 2012-10-16 | [879 empty] | 2012-10-16 | 2012-10-16 |  | Hearings planned - next hearing |  |  | Public notice
| Hearings planned - next hearing |  | PE,PA,RDT | 1 | -3601 | 0 | -5040 | 2012-10-16 | 2012-10-16 | [879 empty] | 2012-10-16 | 2012-10-16 |  | Hearings planned - next hearing |  |  | Info meeting
| Hearings planned - next hearing |  | PE,PA,RDT | 1 | -3601 | 0 | -5040 | 2012-10-16 | 2012-10-16 | [879 empty] | 2012-10-16 | 2012-10-16 |  | Hearings planned - next hearing
| Hearings planned - next hearing |  | PE,PA,RDT | 1 | -3601 | 0 | -5040 | 2012-10-16 | 2012-10-16 | [879 empty] | 2012-10-16 | 2012-10-16 |  | Hearings planned - next hearing
| Hearings planned - LAST hearing |  | PE,PA,RDT | 1 | -3601 | 0 | -5040 | 2012-10-16 | 2012-10-16 | [879 empty] | 2012-10-16 | 2012-10-16 |  | Hearings planned - LAST hearing
OPTION
| Draft program webpage |  | PE, RDT | 139 | -3623 | 200 | -5072 | 2012-02-27 | 2012-09-14 | [879 empty] | 2012-02-27 | 2012-09-14 |  | 2012-09-14
| Contribute and review |  | SE, RDT | 139 | -3623 | 200 | -5072 | 2012-02-27 | 2012-09-14 | [879 empty] | 2012-02-27 | 2012-09-14
| Messaging, plain English review |  | OCO | 139 | -3623 | 200 | -5072 | 2012-02-27 | 2012-09-14 | [879 empty] | 2012-02-27 | 2012-09-14
Loop as needed
| Approve webpage |  | PM | 139 | -3623 | 200 | -5072 | 2012-02-27 | 2012-09-14 | [879 empty] | 2012-02-27 | 2012-09-14
END OPTION
| Lead drafting effort for Notice Packet: |  | PE | 139 | -3623 | 200 | -5072 | 2012-02-27 | 2012-09-14 | [879 empty] | 2012-02-27 | 2012-09-14
| Announcement |  | RDT | 139 | -3623 | 200 | -5072 | 2012-02-27 | 2012-09-14 | [879 empty] | 2012-02-27 | 2012-09-14
| Rules - verify team is using current compilation |  | PE | 139 | -3623 | 200 | -5072 | 2012-02-27 | 2012-09-14 | [879 empty] | 2012-02-27 | 2012-09-14
| Overview | > | RDT | 139 | -3623 | 200 | -5072 | 2012-02-27 | 2012-09-14 | [879 empty] | 2012-02-27 | 2012-09-14
| Statement of need | > | RDT | 139 | -3623 | 200 | -5072 | 2012-02-27 | 2012-09-14 | [879 empty] | 2012-02-27 | 2012-09-14
| Freeform section | > | RDT | 139 | -3623 | 200 | -5072 | 2012-02-27 | 2012-09-14 | [879 empty] | 2012-02-27 | 2012-09-14
| Federal relationships | > | RDT | 139 | -3623 | 200 | -5072 | 2012-02-27 | 2012-09-14 | [879 empty] | 2012-02-27 | 2012-09-14
| Chapter 340 rules affected | > | RDT | 139 | -3623 | 200 | -5072 | 2012-02-27 | 2012-09-14 | [879 empty] | 2012-02-27 | 2012-09-14
| Fiscal impact statement | > | RDT | 139 | -3623 | 200 | -5072 | 2012-02-27 | 2012-09-14 | [879 empty] | 2012-02-27 | 2012-09-14
| Fees not involved | > | RDT | 139 | -3623 | 200 | -5072 | 2012-02-27 | 2012-09-14 | [879 empty] | 2012-02-27 | 2012-09-14 |  | Fees not involved
| Land Use | > | RDT | 139 | -3623 | 200 | -5072 | 2012-02-27 | 2012-09-14 | [879 empty] | 2012-02-27 | 2012-09-14
| SIP not involved |  | SIPCo | 139 | -3623 | 200 | -5072 | 2012-02-27 | 2012-09-14 | [879 empty] | 2012-02-27 | 2012-09-14 |  | SIP not involved
| Supporting documents |  | RDT | 139 | -3623 | 200 | -5072 | 2012-02-27 | 2012-09-14 | [879 empty] | 2012-02-27 | 2012-09-14
| Display advertisements |  | PE | 139 | -3623 | 200 | -5072 | 2012-02-27 | 2012-09-14 | [879 empty] | 2012-02-27 | 2012-09-14 |  | Display advertisements
| Obtain input from resources, specifically | > | PE | 12 | -3645 | 15 | -5102 | 2012-07-31 | 2012-08-15 | [879 empty] | 2012-07-31 | 2012-08-15
| Advisory committee not involved | > | Committee | 12 | -3645 | 15 | -5102 | 2012-07-31 | 2012-08-15 | [879 empty] | 2012-07-31 | 2012-08-15 |  | Advisory committee not involved
| Fiscal impact statement | > | Budget | 12 | -3645 | 15 | -5102 | 2012-07-31 | 2012-08-15 | [879 empty] | 2012-07-31 | 2012-08-15 |  | Fiscal impact statement
| Proposal, announcement, notice, display ads |  | OCO | 12 | -3645 | 15 | -5102 | 2012-07-31 | 2012-08-15 | [879 empty] | 2012-07-31 | 2012-08-15 |  | Proposal, announcement, notice, display ads
| Proposal and rule review if needed |  | DOJ | 12 | -3645 | 15 | -5102 | 2012-07-31 | 2012-08-15 | [879 empty] | 2012-07-31 | 2012-08-15 |  | Proposal and rule review if needed
| Blueprint |  | ARC | 12 | -3645 | 15 | -5102 | 2012-07-31 | 2012-08-15 | [879 empty] | 2012-07-31 | 2012-08-15
Loop as needed
| Schedule LDA briefing meeting |  | PE | 12 | -3645 | 15 | -5102 | 2012-07-31 | 2012-07-31 | [879 empty] | 2012-07-31 | 2012-07-31
| Meet for Notice Packet - final review |  | RDT | 1 | -3639 | 0 | -5094 | 2012-08-15 | 2012-08-15 | [879 empty] | 2012-08-15 | 2012-08-15
| Approve Notice Packet release to LDA |  | LM | 3 | -3642 | 5 | -5097 | 2012-08-15 | 2012-08-20 | [879 empty] | 2012-08-15 | 2012-08-20
Archive blueprint
| Brief lead division administrator |  | RDT | 1 | -3639 | 0 | -5094 | 2012-08-23 | 2012-08-23 | [879 empty] | 2012-08-23 | 2012-08-23
| Lead division administrator review |  | LDA | 12 | -3645 | 15 | -5102 | 2012-07-31 | 2012-08-15 | [879 empty] | 2012-07-31 | 2012-08-15
| Address LDA comments |  | RDT | 12 | -3645 | 15 | -5102 | 2012-07-31 | 2012-08-15 | [879 empty] | 2012-07-31 | 2012-08-15
| Loop as needed | [887 empty] | 2012-07-31 | 2012-07-31
| Approve Notice Packet |  | LDA | 12 | -3645 | 15 | -5102 | 2012-07-31 | 2012-08-15 | [879 empty] | 2012-07-31 | 2012-07-31
Archive Notice Packet
| OPEN PREVIEW PERIOD | [887 empty] | 2012-08-15 | 2012-08-24
| Notify EMT |  | LDA | 9 | -3644 | 10 | -5101 | 2012-08-06 | 2012-08-16 | [879 empty] | 2012-08-06 | 2012-08-16
| DEQ Staff, specifically contributing resources |  | PE | 9 | -3644 | 10 | -5101 | 2012-08-06 | 2012-08-16 | [879 empty] | 2012-08-06 | 2012-08-16
CLOSE PREVIEW PERIOD
| Decide how to address any preview feedback |  | RDT | 3 | -3640 | 2 | -5095 | 2012-08-20 | 2012-08-22 | [879 empty] | 2012-08-20 | 2012-08-22
| Modify notice documents as needed |  | PE | 5 | -3636 | 6 | -5089 | 2012-08-22 | 2012-08-28 | [879 empty] | 2012-08-22 | 2012-08-28
| Verify rules use latest rule compilation |  | PE | 1 | -3636 | 0 | -5089 | 2012-08-28 | 2012-08-28 | [879 empty] | 2012-08-28 | 2012-08-28
| Approve Notice Packet release |  | LM | 4 | -3631 | 6 | -5082 | 2012-08-29 | 2012-09-04 | [879 empty] | 2012-08-29 | 2012-09-04
| Archive Notice Packet if changed | >
| Submit SIP & DOJ approval to EPA |  |  | 1 | -3631 | 0 | -5082 | 2012-09-04 | 2012-09-04 | [879 empty] | 2012-09-04 | 2012-09-04 |  | SIP not involved, no EPA submittal required
| Notify ARC that Notice Packet is complete |  | PE | 1 | -3631 | 0 | -5082 | 2012-09-04 | 2012-09-04 | [879 empty] | 2012-09-04 | 2012-09-04
| Activate public comment box | > | PA | 1 | -3631 | 0 | -5082 | 2012-09-04 | 2012-09-04 | [879 empty] | 2012-09-04 | 2012-09-04
| Notify EQC Asssistant of potential EQC date |  | PA | 1 | -3631 | 0 | -5082 | 2012-09-04 | 2012-09-04 | [879 empty] | 2012-09-04 | 2012-09-04
| Obtain electronic signoff from budget |  | PE | 5 | -3627 | 6 | -5076 | 2012-09-04 | 2012-09-10 | [879 empty] | 2012-09-04 | 2012-09-10
| Perform final plain English review |  | ARC,OCO | 5 | -3627 | 6 | -5076 | 2012-09-04 | 2012-09-10 | [879 empty] | 2012-09-04 | 2012-09-10
` | Noticing sequence
| Post Notice to SOS |  | ARC | 1 | -3623 | 0 | -5072 | 2012-09-14 | 2012-09-14 | [879 empty] | 2012-09-14 | 2012-09-14
| Save evidence to Archive | >
| Send packet to rules webrep |  | PA | 1 | -3623 | 0 | -5072 | 2012-09-14 | 2012-09-14 | [879 empty] | 2012-09-14 | 2012-09-14
| Post packet to rules webpage |  | Webrep | 1 | -3623 | 0 | -5072 | 2012-09-14 | 2012-09-14 | [879 empty] | 2012-09-14 | 2012-09-14
| Notify agency rulemaking list |  | PA | 1 | -3623 | 0 | -5072 | 2012-09-14 | 2012-09-14 | [879 empty] | 2012-09-14 | 2012-09-14
| GovDelivery |  | PA | 1 | -3623 | 0 | -5072 | 2012-09-14 | 2012-09-14 | [879 empty] | 2012-09-14 | 2012-09-14
| Program list not on GovDelivery |  | PA | 1 | -3623 | 0 | -5072 | 2012-09-14 | 2012-09-14 | [879 empty] | 2012-09-14 | 2012-09-14
| Committee members not on GovDelivery |  | PA | 1 | -3623 | 0 | -5072 | 2012-09-14 | 2012-09-14 | [879 empty] | 2012-09-14 | 2012-09-14
| Save evidence to Archive | >
| Notify key legislators by email | > | PE | 1 | -3623 | 0 | -5072 | 2012-09-14 | 2012-09-14 | [879 empty] | 2012-09-14 | 2012-09-14
| Save evidence to Archive | >
| Post notice on Oregon Transparency |  | RG | 1 | -3623 | 0 | -5072 | 2012-09-14 | 2012-09-14 | [879 empty] | 2012-09-14 | 2012-09-14 |  | Post on Oregon Transparency
| Save evidence to Archive | >
| Publish in local newspapers if required |  | PE,PA | 1 | -3623 | 0 | -5072 | 2012-09-14 | 2012-09-14 | [879 empty] | 2012-09-14 | 2012-09-14
| Save evidence to Archive | >
| Verify notice published accurately in Bulletin |  | PE | 1 | -3610 | 0 | -5053 | 2012-10-03 | 2012-10-03 | [879 empty] | 2012-10-03 | 2012-10-03
| Save Bulletin excerpt to Archive |  | PA | 1 | -3610 | 0 | -5053 | 2012-10-03 | 2012-10-03 | [879 empty] | 2012-10-03 | 2012-10-03
| CLOSE PUBLIC COMMENT |  |  | 1 | -3597 | 0 | -5034 | 2012-10-22 | 2012-10-22 | [879 empty] | 2012-10-22 | 2012-10-22
| Public hearings, comment, response | [8 empty] | B | t
y
| Identify source of information |  |  | 0 | #REF! | -0.33333 |  | 2012-08-18 08:00 | 2012-08-18
| Identify research method (primary or secondary) |  |  | #VALUE! | #REF! | #VALUE! |  | 2012-08-19 08:00
|  |  |  | #REF! | #REF! | #REF!
| Close of public comment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | #REF! | #REF! | #REF!
|  |  |  | #REF! | #REF! | #REF!
|  |  |  | #REF! | #REF! | #REF!
|  |  |  | #REF! | #REF! | #REF!
| EQC preparation | [8 empty] | B | t
y
| Verify rules use lateset compilation |  | PE, ARC | #VALUE! | #REF! | #VALUE! |  | 2012-08-25 08:00
| Develop research information gathering tool |  |  | 0 | #REF! | -0.33333 |  | 2012-08-26 08:00 | 2012-08-26
| Post EQC | [8 empty] | B | t
y
| Verify and prepare filing |  |  | #VALUE! | #REF! | #VALUE! |  | 2012-09-13 08:00
| Cover letter |  |  | #REF! | #REF! | #REF!
| Certificate of order and filing |  |  | #REF! | #REF! | #REF!
| Rules as adopted or amended |  |  | #REF! | #REF! | #REF!
| Rules in redline/strickout |  |  | #REF! | #REF! | #REF!
| Tables |  |  | #REF! | #REF! | #REF!
|  |  |  | #REF! | #REF! | #REF!
| For exempt fees, DAS notification |  |  | #REF! | #REF! | #REF!
| For non-exempt fees: |  |  | #REF! | #REF! | #REF!
| Develop Part 2 cover letter |  |  | #REF! | #REF! | #REF!
| Complete retained Fee Approval Form |  |  | #REF! | #REF! | #REF!
| Distribute Part 2 documents |  |  | #REF! | #REF! | #REF!
| Notify stakeholders and feepayers |  |  | #REF! | #REF! | #REF!
| Lead administrator to notify legislators |  |  | #REF! | #REF! | #REF!
| Thank you letters and survey to Advisory Committee |  |  | #REF! | #REF! | #REF!
|  |  |  | #REF! | #REF! | #REF!
|  |  |  | #REF! | #REF! | #REF!
|  |  |  | #REF! | #REF! | #REF! |  | 2012-09-20 08:00 | 2012-12-18
[889 empty] | DDL_EQCMeeting | EQCStaffRptDue | EQCStaffRptDate | EQCDirDialogDue | EQCMaterialsDue | VL_EQCActivities
[9 empty] | 35 | [879 empty] | 2012-02-16 | 2012-01-12 | 2012-01-23 | 2012-02-03 | 2012-02-08
[9 empty] | 41 | [879 empty] | 2012-04-26 | 2012-03-16 | 2012-03-26 | 2012-04-06 | 2012-04-11
[9 empty] | 41 | [879 empty] | 2012-06-21 | 2012-05-11 | 2012-05-28 | 2012-06-08 | 2012-06-08
[9 empty] | 41 | [879 empty] | 2012-08-23 | 2012-07-13 | 2012-07-30 | 2012-08-10 | 2012-08-15
[9 empty] | 41 | [879 empty] | 2012-10-25 | 2012-09-14 | 2012-10-01 | 2012-10-12 | 2012-10-17
[9 empty] | 41 | [879 empty] | 2012-12-13 | 2012-11-02 | 2012-11-19 | 2012-11-30 | 2012-12-05
[9 empty] | 40 | [879 empty] | 2013-02-21 | 2013-01-14
[889 empty] | 2013-04-18 | 2013-03-11 |  |  |  | Estimate
[889 empty] | 2013-06-20 | 2013-05-13 |  |  |  | Estimate
[889 empty] | 2013-08-22 | 2013-07-15 |  |  |  | Estimate
[889 empty] | 2013-10-24 | 2013-09-16 |  |  |  | Estimate
[889 empty] | 2013-12-12 | 2013-11-04 |  |  |  | Estimate
[889 empty] | 2014-02-20 | 2014-01-13 |  |  |  | Estimate
Holidays
[889 empty] | 2011-11-11 | Veterans
[889 empty] | 2011-11-24 | Thanksgiving
[889 empty] | 2011-11-25 | furlough
[889 empty] | 2011-12-25 | Christmas
[889 empty] | 2011-12-26 | State Observed Christmas
[889 empty] | 2012-01-01 | New Year
[889 empty] | 2012-01-02 | State Observed New Year 2012
[889 empty] | 2012-01-16 | MLK Jr.
[889 empty] | 2012-02-20 | Presidents
[889 empty] | 2012-03-23 | furlough
[889 empty] | 2012-05-25 | furlough
[889 empty] | 2012-05-28 | Memorial
[889 empty] | 2012-07-04 | Independence
[889 empty] | 2012-08-17 | furlough
[889 empty] | 2012-09-03 | Labor
[889 empty] | 2012-10-19 | furlough
[889 empty] | 2012-11-11 | Veterans
[889 empty] | 2012-11-12 | State Observed Veterans
[889 empty] | 2012-11-22 | Thanksgiving
[889 empty] | 2012-11-23 | furlough
[889 empty] | 2012-12-25 | Christmas
[889 empty] | 2013-01-01 | New Year
[889 empty] | 2013-01-18 | furlough
[889 empty] | 2013-01-21 | MLK Jr.
[889 empty] | 2013-02-18 | Presidents
[889 empty] | 2013-04-19 | furlough
[889 empty] | 2013-05-24 | furlough
[889 empty] | 2013-05-27 | Memorial
[889 empty] | 2013-07-04 | Independence
[889 empty] | 2013-09-02 | Labor
[889 empty] | 2013-11-11 | Veterans
[889 empty] | 2013-11-28 | Thanksgiving
[889 empty] | 2013-12-25 | Christmas
[889 empty] | 2014-01-01 | New Year
[889 empty] | DDL_Bulletin | VL_Bulletin
[889 empty] | 2011-12-01 | 2011-11-15 | 2011-11-15 | 0
[889 empty] | 2012-01-01 | 2011-12-15 | 2011-12-15 | 0
[889 empty] | 2012-02-01 | 2012-01-13 | 2012-01-13 | 0
[889 empty] | 2012-03-01 | 2012-02-15 | 2012-02-15 | 0
[889 empty] | 2012-04-01 | 2012-03-15 | 2012-03-15 | 0
[889 empty] | 2012-05-01 | 2012-04-13 | 2012-04-13 | 0
[889 empty] | 2012-06-01 | 2012-05-15 | 2012-05-15 | 0
[889 empty] | 2012-07-01 | 2012-06-15 | 2012-06-15 | 0
[889 empty] | 2012-08-01 | 2012-07-13 | 2012-07-13 | 0
[889 empty] | 2012-09-01 | 2012-08-15 | 2012-08-15 | 0
[889 empty] | 2012-10-01 | 2012-09-14 | 2012-09-14 | 0
[889 empty] | 2012-11-01 | 2012-10-15 | 2012-10-15 | 0
[889 empty] | 2012-12-01 | 2012-11-15 | 2012-11-15 | 0
[889 empty] | 2013-01-01 | 2012-12-14 | 2012-12-14 | 0
[889 empty] | 2013-02-01 | 2013-01-15 | 2013-01-15 | 0
[889 empty] | 2013-03-01 | 2013-02-15 | 2013-02-15 | 0
[889 empty] | 2013-04-01 | 2013-03-15 | 2013-03-15 | 0
[889 empty] | 2013-05-01 | 2013-04-15 | 2013-04-15 | 0
[889 empty] | 2013-06-01 | 2013-05-15 | 2013-05-15 | 0
[889 empty] | 2013-07-01 | 2013-06-14 | 2013-06-14 | 0
[889 empty] | 2013-08-01 | 2013-07-15 | 2013-07-15 | 0
[889 empty] | 2013-09-01 | 2013-08-15 | 2013-08-15 | 0
[889 empty] | 2013-10-01 | 2013-09-13 | 2013-09-13 | 0
[889 empty] | 2013-11-01 | 2013-10-15 | 2013-10-15 | 0
[889 empty] | 2013-12-01 | 2013-11-15 | 2013-11-15 | 0
[889 empty] | 2014-01-01 | 2013-12-13 | 2013-12-13 | 0
[889 empty] | 2014-02-01 | 2014-01-15 | 2014-01-15 | 0
[889 empty] | 2014-03-01 | 2014-02-14 | 2014-02-14 | 0
[889 empty] | 2014-04-01 | 2014-03-14 | 2014-03-14 | 0
[889 empty] | 2014-05-01 | 2014-04-15 | 2014-04-15 | 0
[889 empty] | 2014-06-01 | 2014-05-15 | 2014-05-15 | 0
[889 empty] | 2014-07-01 | 2014-06-13 | 2014-06-13 | 0
[889 empty] | 2014-08-01 | 2014-07-15 | 2014-07-15 | 0
[889 empty] | 2014-09-01 | 2014-08-15 | 2014-08-15 | 0
[889 empty] | 2014-10-01 | 2014-09-15 | 2014-09-15 | 0
[889 empty] | 2014-11-01 | 2014-10-15 | 2014-10-15 | 0
[889 empty] | 2014-12-01 | 2014-11-14 | 2014-11-14 | 0
[889 empty] | 2015-01-01 | 2014-12-15 | 2014-12-15 | 0
[889 empty] | 2015-02-01 | 2015-01-15 | 2015-01-15 | 0
[889 empty] | 2015-03-01 | 2015-02-13 | 2015-02-13 | 0
[889 empty] | 2015-04-01 | 2015-03-13 | 2015-03-13 | 0
[889 empty] | 2015-05-01 | 2015-04-15 | 2015-04-15 | 0
[889 empty] | 2015-06-01 | 2015-05-15 | 2015-05-15 | 0
[889 empty] | 2015-07-01 | 2015-06-15 | 2015-06-15 | 0
[889 empty] | 2015-08-01 | 2015-07-15 | 2015-07-15 | 0
[889 empty] | 2015-09-01 | 2015-08-15 | 2015-08-15 | 0
[889 empty] | 2015-10-01 | 2015-09-15 | 2015-09-15 | 0
[889 empty] | 2015-11-01 | 2015-10-15 | 2015-10-15 | 0
[889 empty] | 2015-12-01 | 2015-11-13 | 2015-11-13 | 0
[889 empty] | 2016-01-01 | 2015-12-15 | 2015-12-15 | 0
[889 empty] | 2016-02-01 | 2016-01-15 | 2016-01-15 | 0
[889 empty] | 2016-03-01 | 2016-02-15 | 2016-02-15 | 0
[889 empty] | 2016-04-01 | 2016-03-15 | 2016-03-15 | 0
[889 empty] | 2016-05-01 | 2016-04-15 | 2016-04-15 | 0
[889 empty] | 2016-06-01 | 2016-05-13 | 2016-05-13 | 0
[889 empty] | 2016-07-01 | 2016-06-15 | 2016-06-15 | 0
[889 empty] | 2016-08-01 | 2016-07-15 | 2016-07-15 | 0
[889 empty] | 2016-09-01 | 2016-08-15 | 2016-08-15 | 0
[889 empty] | 2016-10-01 | 2016-09-15 | 2016-09-15 | 0
[889 empty] | 2016-11-01 | 2016-10-14 | 2016-10-14 | 0
[889 empty] | 2016-12-01 | 2016-11-15 | 2016-11-15 | 0
[889 empty] | 2017-01-01 | 2016-12-15 | 2016-12-15 | 0
[889 empty] | 2017-02-01 | 2017-01-13 | 2017-01-13 | 0
[889 empty] | 2017-03-01 | 2017-02-15 | 2017-02-15 | 0
[889 empty] | 2017-04-01 | 2017-03-15 | 2017-03-15 | 0
[889 empty] | 2017-05-01 | 2017-04-14 | 2017-04-14 | 0
[889 empty] | 2017-06-01 | 2017-05-15 | 2017-05-15 | 0
[889 empty] | 2017-07-01 | 2017-06-15 | 2017-06-15 | 0
[889 empty] | 2017-08-01 | 2017-07-14 | 2017-07-14 | 0
[889 empty] | 2017-09-01 | 2017-08-15 | 2017-08-15 | 0
[889 empty] | 2017-10-01 | 2017-09-15 | 2017-09-15 | 0
[889 empty] | 2017-11-01 | 2017-10-13 | 2017-10-13 | 0
[889 empty] | 2017-12-01 | 2017-11-15 | 2017-11-15 | 0
[889 empty] | 2018-01-01 | 2017-12-15 | 2017-12-15 | 0
[889 empty] | 2018-02-01 | 2018-01-15 | 2018-01-15 | 0
[889 empty] | 2018-03-01 | 2018-02-15 | 2018-02-15 | 0
[889 empty] | 2018-04-01 | 2018-03-14 | 2018-03-14 | 0
[889 empty] | 2018-05-01 | 2018-04-13 | 2018-04-13 | 0
[889 empty] | 2018-06-01 | 2018-05-15 | 2018-05-15 | 0
[889 empty] | 2018-07-01 | 2018-06-15 | 2018-06-15 | 0
[889 empty] | 2018-08-01 | 2018-07-13 | 2018-07-13 | 0
[889 empty] | 2018-09-01 | 2018-08-15 | 2018-08-15 | 0
[889 empty] | 2018-10-01 | 2018-09-14 | 2018-09-14 | 0
[889 empty] | 2018-11-01 | 2018-10-15 | 2018-10-15 | 0
[889 empty] | 2018-12-01 | 2018-11-15 | 2018-11-15 | 0
[889 empty] | 2019-01-01 | 2018-12-14 | 2018-12-14 | 0
[889 empty] | 2019-02-01 | 2019-01-15 | 2019-01-15 | 0
[889 empty] | 2019-03-01 | 2019-02-15 | 2019-02-15 | 0
[889 empty] | 2019-04-01 | 2019-03-15 | 2019-03-15 | 0
[889 empty] | 2019-05-01 | 2019-04-15 | 2019-04-15 | 0
[889 empty] | 2019-06-01 | 2019-05-15 | 2019-05-15 | 0
[889 empty] | 2019-07-01 | 2019-06-14 | 2019-06-14 | 0
[889 empty] | 2019-08-01 | 2019-07-15 | 2019-07-15 | 0
[889 empty] | 2019-09-01 | 2019-08-15 | 2019-08-15 | 0
[889 empty] | 2019-10-01 | 2019-09-13 | 2019-09-13 | 0
[889 empty] | 2019-11-01 | 2019-10-15 | 2019-10-15 | 0
[889 empty] | 2019-12-01 | 2019-11-15 | 2019-11-15 | 0
[889 empty] | 2020-01-01 | 2019-12-13 | 2019-12-13 | 0
[889 empty] | 2020-02-01 | 2020-01-15 | 2020-01-15 | 0
[889 empty] | 2020-03-01 | 2020-02-14 | 2020-02-14 | 0
[889 empty] | 2020-04-01 | 2020-03-13 | 2020-03-13 | 0
[889 empty] | 2020-05-01 | 2020-04-15 | 2020-04-15 | 0
[889 empty] | 2020-06-01 | 2020-05-15 | 2020-05-15 | 0
[889 empty] | 2020-07-01 | 2020-06-15 | 2020-06-15 | 0
[889 empty] | 2020-08-01 | 2020-07-15 | 2020-07-15 | 0
[889 empty] | 2020-09-01 | 2020-08-14 | 2020-08-14 | 0
[889 empty] | 2020-10-01 | 2020-09-15 | 2020-09-15 | 0
[889 empty] | 2020-11-01 | 2020-10-15 | 2020-10-15 | 0
[889 empty] | 2020-12-01 | 2020-11-13 | 2020-11-13 | 0
[889 empty] | 2021-01-01 | 2020-12-15 | 2020-12-15 | 0
[889 empty] | 2021-02-01 | 2021-01-15 | 2021-01-15 | 0
[889 empty] | 2021-03-01 | 2021-02-15 | 2021-02-15 | 0
[889 empty] | 2021-04-01 | 2021-03-15 | 2021-03-15 | 0
[889 empty] | 2021-05-01 | 2021-04-15 | 2021-04-15 | 0
[889 empty] | 2021-06-01 | 2021-05-14 | 2021-05-14 | 0
[889 empty] | 2021-07-01 | 2021-06-15 | 2021-06-15 | 0
[889 empty] | 2021-08-01 | 2021-07-15 | 2021-07-15 | 0
[889 empty] | 2021-09-01 | 2021-08-13 | 2021-08-13 | 0
[889 empty] | 2021-10-01 | 2021-09-15 | 2021-09-15 | 0
[889 empty] | 2021-11-01 | 2021-10-15 | 2021-10-15 | 0
[889 empty] | 2021-12-01 | 2021-11-15 | 2021-11-15 | 0
Formulas:
locked = [DEQ closed]
EQCStaffRptDue = WORKDAY([DDL_EQCMeeting]-40,1,Holidays)
EQCStaffRptDate = WORKDAY([EQCStaffRptDue],0,Holidays)
Note on A7: ABOUT KEY DATES This section includes key dates. These dates meet Oregon's rulemaking requirements, avoid weekends, Oregon holidays and fulough days. They do not consider personal holidays, furlough days or the Governor's leave. The sections below the Key dates section provide the tasks to meet these dates.
Note on A12: SECRETARY OF STATE BULLETIN Requirement Before adopting amending or repealing any permanent rule, DEQ must give notice of our intended action in the Secretary of State Bulletin at least 14 days before the first hearing and 21 days before the effective date. ORS 183.335 (1) Administrative Procedures Act notice requirement ORS 183.341 (4) APA requirement to adopt agency noticing rules OAR 340-011-0002 (a) DEQ noticing rule ORS 468A.327 Facilities required to pay fees under ORS 468A.315 (emission fees for major sources) ORS 183.360 About Secretary of State's Bulletin Default The Bulletin publishes on the first of every month regardless of weekends or holidays. The blueprint calculates the date for publishing in the earliest Secretary of State Bulletin that allows 49 full days before the effective date for legislator notification under ORS 183.335 (15) and a minimum of 14 full days before the first hearing date under OAR 340-011-0002 (a). Where used The blueprint will use to default date and the adjustment days to: • Calculate other dates on the Schedule task tab, and • Report on the Proposal tab.
Note on A246: OREGON TRANSPARENCY POSTING Requirement In addition to the information described in subsection (3) of this section, each state agency shall post on the Oregon transparency website notices of public meetings required to be provided by the state agency under ORS 192.640. ORS 184.483 (4) Background The passage of HB 2788 in 2011 adds an additional step to noticing public hearings for rulemaking. This includes all rulemaking hearings. The bill amends ORS 184.480, which defines “state agency” and 184.483(4), which directs all agencies to post notices of: • public meeting required under ORS 192.640, • on the Oregon transparency website, and • starting January 1, 2012.
Note on A247: NOTIFY AGENCY MAILING LIST Requirement Before adopting amending or repealing any permanent rule, DEQ must give notice of our intended action to the agency mailing list least 14 days before the first hearing but no later than 21 days before the effective date. This discussion does not address requests to hold an oral hearing by 10 or more persons under ORS 183.335(3) to before the Commission under OAR 340-011-0029(3). ORS 183.335 (8) Administrative Procedures Act mailing list requirement ORS 183.330(2) APA requirement for agency rules coordinator to maintain and make available the mailing list. OAR 340-011-0002 (b) DEQ rule requiring notifying persons on the department’s mailing list Default The blueprint calculates the date for notifying the agency mailing list as the same day that we send notification to legislators and at least 14 full days before the first hearing date under. Where used The blueprint will use to default date and the adjustment days to: • Calculate some dates on the Schedule tasks tab, and • Report on the Proposal tab.
Note on A248: NOTIFY KEY LEGISLATORS DEQ best practice Though the law requires agencies notify key legislators based on the effective date of the proposed rule, DEQ best practice is to notify them when we post the notice on our rulemaking website. This allows legislators the opportunity to comment during public notice. The legislative team will help identify the key legislators described below. Depending on the subject matter, the lead division administrator or legislative team member may want to call the legislators. This Schedule tab provides reminders. Requirments Legislation passed in 2011 legislation, requires us to provide the notice electronically. Forty nine (49) days before the effective dated of the adopted, amended or repealed rule, DEQ must notify the key legislators of our intended action. ORS 183.335(1)(d) If the proposed adoption, amendment or repeal: • Results from legislation that was passed within two years beforegiving notice under ORS 183.335(1), DEQ must notify the: -- Legislator who introduced the bill -- Chair or co-chairs of all committees that reported the bill out except for those committees whose sole action on the bill was referral to another committee. • Does not result from legislation that was passed within two years before giving notice under ORS 183.335(1), DEQ must notify the chair or co-chairs of any interim or session committee with authority over the subject matter of the rule. If DEQ is unable to notify the legislators above, we must notify the Speaker of the House of Representatives and the President of the Senate who are in office on the notice date. ORS 183.335(15) Where used Calculate some dates on the Schedule tasks tab, Legislators’ listed on the Proposal tab Legislators’ email tab
Note on D6: DC DAS contact for fees LDA Lead divisiion administrator LM Lead manager PE Project assistant PL Process lead RDT Rule design team RG Rules Group TL Technical lead
mm/dd/yy
Subject
Your name
Your message

## InterestedParties (hidden)
Interested parties | [5 empty] | Learn more about the participant |  |  | Phones |  | Mailing information | [8 empty] | Help establishing the committee |  |  |  |  | Do not delete
Affiliation | Name | Participation | Email | 1.27.12 meeting | 2nd meeting | Category | Expertise | Weblink | Preferred | Alternate | Salutation | Last name | First name | Title | Address 1 | Address 2 | City | State | Zip | Staff to Contact | InvitationNotes | Appointment
Zero Waste Alliance | Carson Maxted | advisory committee | cmaxted@zerowaste.org | in person |  | environmental |  | http://www.zerowaste.org/ | 503-501-8471 |  | Mr. | Maxted | Carson | [6 empty] | Peter | ACCEPTED 12/22 - invited Wayne Rifer, who suggested Carson Maxted instead. Based on our conference call discussion (no conflict with his doing our state contractor program), I invited Carson, and he accepted on 12/27/2011. | 12/30/2011 Email FROM: B Fuller | Carson Maxted | Zero Waste Alliance
EC Oregon | Dean Foor | advisory committee | dean@ecoregon.com | in person |  | industry | Anaerobic digestion facility expertise. | www.ECOregon.com | (541) 485-9095 |  | Mr. | Foor | Dean | Project Engineer | 1328 W. 2nd Ave. |  | Eugene | OR | 97402 | Bob | ACCEPTED Dean Foor has accepted the invitation. Either date (26th or 27th) works for him. | 12/30/2011 Email FROM: B Fuller | Dean Foor | EC Oregon
Agri-Plas | Mary Sue Gilliland | advisory committee | duckyrecycler@verizon.net | in person |  | producer | Plastic recycling and former plastic pyrolysis facility | http://agriplasinc.com/ | 503-390-2381 |  |  | Gilliland | Mary Sue | Vice President Operations & Development | 5016 Waconda RD NE |  | Brooks | OR | 97305-9770 | Brian | ACCEPTED 12/20 1120 left phone msg for Mary Sue. Mary Sue Gilliland will represent Agri-Plas on the committee. Both dates work. | 12/30/2011 Email FROM: B Fuller | Mary Sue Gilliland | Agri-Plas
Oregon Physicians for Social Responsibility | Joe Miller | advisory committee | jmiller@saintmarys.edu | in person |  | environmental | environmental health advocacy | http://www.psr.org/chapters/oregon/ | 503-295-7747 |  | Mr. | Miller | Joe |  | 1030 SW Jefferson Apt 534 |  | Portland | OR | 97201 | Peter | ACCEPTED 12/21 Joe accepted the invitation with a couple of reservations. Either day works for him. We're talking about if he represents PSR since he is no longer on the board. | 1/3/12 Email from Bfuller | Joe Miller | Oregon Physicians for Social Responsibility
Good Company | Josh Proudfoot | advisory committee | joshua.proudfoot@goodcompany.com | absent |  | industry | Consulting firm | http://www.goodcompany.com/ | (541)341-4663 x 213 |  |  | Proudfoot | Josh | Principle | 65 Centennial Loop, Suite B |  | Eugene | OR | 97401 |  |  |  | Josh Proudfoot | Good Company
Resource Recycling | Jerry Powell | advisory committee | jpowell@resource-recycling.com | in person |  | producer | Recycling publication | http://www.resource-recycling.com/ | (503) 233-1305 |  |  | Powell | Jerry | Executive Editor | P.O. Box 42270 |  | Portland | OR | 97242-0270 | Peter | Accepted 12/27. Both meeting dates work for him. | 12/30/2011 Email FROM: B Fuller | Jerry Powell | Resource Recycling
Tillamook County Oregon | Jennifer Purcell | advisory committee | jpurcell@co.tillamook.or.us | in person |  | government |  | http://www.co.tillamook.or.us/ |  |  |  | Purcell | Jennifer | [9 empty] | Jennifer Purcell | Tillamook County Oregon
S4Energy Solutions | Jeff Surma | advisory committee | jsurma@s4energysolutions.com | in person |  | industry | Plasma arc gasification | http://www.s4energysolutions.com/ | (509) 727-2269 (cell) |  | Mr. | Surma | Jeff | CEO | 384 SW Upper Terrace Dr. |  | Richland | WA |  | Bruce | 1/4/2012 - 2:40 pm - E-mail exchange w/Jeff Surma, CEO. Confirmed he will participate on the Adv. Comm. |  | Jeff Surma | S4Energy Solutions
ORRA | Kristan Mitchell | advisory committee | kristanm@orra.net | absent |  | industry | ORRA provides legislative advocacy, education, group insurance, meeting facilities and advice on regulatory matters to its members | http://www.orra.net/ | (800) 527-7624 |  |  | Mitchell | Kristan | Governmental Affairs Director | PO Box 2186 | 680 State Street, Suite 100 | Salem | OR | 97308-2186 | Brian | PENDING 12/20 1116 left phone msg and followed up with e-mail to Kristan. 12/23 Kristan can't make the January dates, she is going to suggest another ORRA member for consideration. ACCEPTED 1/6 Laura Leebrick (Western Oregon Waste) will be the ORRA alternate when Kristan can't make it. | 12/30/2011 Email FROM: B Fuller | Kristan Mitchell | ORRA
ORRA | Laura Leebrick | advisory committee | lleebrick@westernoregonwaste.com | in person |  | industry | ORRA provides legislative advocacy, education, group insurance, meeting facilities and advice on regulatory matters to its members | http://www.orra.net/ |  |  |  | Leebrick | Laura | [6 empty] | Brian | Accepted 1/6. Alternate to Kristan Mitchell | See ORRA appointment above. | Laura Leebrick | ORRA
Agilyx | Chris Ulum | advisory committee | mailto:culum@agilyx.com | in person |  | industry | Plastic pyrolysis technolgy/equipment maker and provider. | http://www.agilyx.com/ | (503) 217-3163 |  | Mr. | Ulum | Chris | Chief Executive Officer | 7904 SW Hunziker Street |  | Tigard | OR | 97223 | Brian | ACCEPTED 12/20 1115 left phone msg and followed up with e-mail to Chris. Agilyx will participate, both dates work. | 12/30/2011 Email FROM: B Fuller | Chris Ulum | Agilyx
Port of Tillamook Bay | Michele Bradley | advisory committee | mbradley@potb.org | absent |  | producer | Local government that operates a DEQ permitted digester | http://www.potb.org/ | (503)842-2413 ext. 111 |  | Ms. | Bradley | Michele | General Manager | 4000 Blimp Blvd |  | Tillamook | OR | 97141 | Stephanie | ACCEPTED 12/27 12:15 p.m. - Michele accepted and either date should work for her12/20 11:54 a.m.- left invitation phone message and sent follow-up email. | 12/30/2011 Email FROM: B Fuller | Michele Bradley | Port of Tillamook Bay
Waste Management | Matt Stern | advisory committee | mstern@wm.com | in person |  | industry | Integrated waste management company, planning to purchase Agilyx equipment. | http://www.wm.com/index.jsp | (503) 493-7863 |  | Mr. | Stern | Matt | Area Director of Recycling Operations | 7227 NE 55th Avenue |  | Portland | OR | 97218 | Bob | ACCEPTED 12/20, 10 AM - left invitation phone message for Matt Stern. 5:20 PM - Matt accepted the invitation; Friday 27th works for him. | 12/30/2011 Email FROM: B Fuller | Matt Stern | Waste Management
AOR | Rick Winterhalter | advisory committee | rickw@co.clackamas.or.us | in person |  | environmental | AOR is a nonprofit coalition of individuals, governments, nonprofit organizations, and businesses committed to encouraging waste prevention and recycling in Oregon. | http://www.aorr.org/index.html | 503-742-4466 |  | Mr. | Winterhalter | Rick | AOR Board Chair | 150 Beavercreek Rd. |  | Oregon City | OR | 97405-4302 | Brian | ACCEPTED 12/20 1110 left phone msg and followed up with e-mail to Rick. Rick will represent AOR on the committee. Both dates work. | 12/30/2011 Email FROM: B Fuller | Rick Winterhalter | AOR
METRO | Roy Brower | advisory committee | roy.brower@oregonmetro.gov | in person |  | government | Metro regulates SW in the Portland Metro area. Roy is responsible for plastic pyrolysis oversight. | www.oregonmetro.gov | (503) 797-1657 |  | Mr. | Brower | Roy | Manager, SW Compliance and Cleanup | 600 NE Grand Avenue |  | Portland | OR | 97232 | Stephanie | ACCEPTED 12/27 4:15 p.m. - called Roy to confirm Metro participant;Roy is out until Jan 3; 12/20 11:45 a.m.; Roy Brower accepted; Friday works best. Roy needs to confer internally to determine if he or Matt Korot is best fit for Metro. | 12/30/2011 Email FROM: B Fuller TO: Roy | Roy Brower | METRO
Energy Trust | Thad Roth | advisory committee | thad.roth@energytrust.org | in person |  |  | CT expertise and funding mechanisms. | http://energytrust.org/ | 503.445.7632 |  |  | Roth | Thad | Biomass Program Manager | [5 empty] | Bob | Accepted 1/3. | 1/4/2012 Email FROM: B Barrows | Thad Roth | Energy Trust
ReKlaim | Tom Redd | advisory committee | tomr@reklaim.com | in person |  | industry | Tire pyrolysis facility | http://www.reklaim.com/ | 206-372-1752 | (206) 351-5717 | Mr. | Redd | Tom | President | 3401 Fremont Avenue N., Suite 242 |  | Seattle | WA | 98103 | Bruce | ACCEPTED 12/22/11 - 2:50 pm - I talked with Tom Redd, the new President of Reklaim, Inc. (Note: Kevin Raymond is no longer with the company.) Mr. Redd agreed to be on the Advisory Committee. Both meeting dates in Jan. currently work for him. | 12/30/2011 Email FROM: B Fuller | Tom Redd | ReKlaim
ODEQ - AQ NWR | Gregg Grunow | committee adjunct | grunow.greg@deq.state.or.us |  |  | government | [5 empty] | Grunow | Gregg | [9 empty] | Gregg Grunow | ODEQ - AQ NWR
ODEQ - SW ER | Bruce Lumper | committee adjunct | lumper.bruce@deq.state.or.us | in person |  | government | [5 empty] | Lumper | Bruce | [9 empty] | Bruce Lumper | ODEQ - SW ER
Oregon Dept. of Energy | Matt Krumenauer | committee adjunct | Matt Krumenauer | in person |  | government | Biomass alternative energy projects | http://www.oregon.gov/ENERGY/ | 5033786043 |  | Mr. | Krumenauer | Matt | Technology Advisor | [8 empty] | Matt Krumenauer | Oregon Dept. of Energy
ODEQ - SW HQ | Loretta Pickerell | committee adjunct | pickerell.loretta@deq.state.or.us | in person |  | government | [5 empty] | Pickerell | Loretta | [9 empty] | Loretta Pickerell | ODEQ - SW HQ
ODEQ - SW HQ | Peter Spendelow | committee adjunct | spendelow.peter@deq.state.or.us | in person |  | government | [5 empty] | Spendelow | Peter | [9 empty] | Peter Spendelow | ODEQ - SW HQ
ODEQ - AQ WR | Karen White-Fallon | committee adjunct | white-fallon.karen@deq.state.or.us |  |  | government | [5 empty] | White-Fallon | Karen | [9 empty] | Karen White-Fallon | ODEQ - AQ WR
Oregon Dept of Agriculture | Wym Matthews | committee adjunct | wmatthews@oda.state.or.us |  |  | government | CAFO Program Manager | www.oregon.gov/ODA/ | 503-986-4792 |  | Mr. | Matthews | Wym |  |  |  | Salem | OR |  |  |  |  | Wym Matthews | Oregon Dept of Agriculture
ODEQ - Rule Lead | Bob Barrows | DEQ staff | barrows.bob@deq.state.or.us | in person |  | government | Familiar with Metro’s license requirement for WMI’s proposed plastic pyrolysis operation. |  |  |  |  | Barrows | Bob | [9 empty] | Bob Barrows | ODEQ - Rule Lead
ODEQ - SW ER | Brian Fuller | DEQ staff | fuller.brian@deq.state.or.us | in person |  | government | [5 empty] | Fuller | Brian | [9 empty] | Brian Fuller | ODEQ - SW ER
ODEQ - SW HQ | Christie Nuttall | DEQ staff | nuttall.christie@deq.state.or.us | in person | [7 empty] | Nuttall | Christie | [9 empty] | Christie Nuttall | ODEQ - SW HQ
ODEQ - SW NWR | Stephanie Rawson | DEQ staff | rawson.stephanie@deq.state.or.us | in person |  | government | [5 empty] | Rawson | Stephanie | [9 empty] | Stephanie Rawson | ODEQ - SW NWR
ODEQ - MSD | Maggie Vandehey | DEQ staff | vandehey.maggie@deq.state.or.us | [8 empty] | Vandehey | Maggie | [9 empty] | Maggie Vandehey | ODEQ - MSD
Pacific Environmental Advocacy Center | Aubrey Baldwin | stakeholder | abaldwin@lclark.edu |  |  | environmental | nationally recognized expertise in air quality law | http://law.lclark.edu/centers/pacific_environmental_advocacy/ | (503)768-6600 |  | Ms. | Baldwin | Aubrey | Staff Attorney | Lewis & Clark Law School | 10015 SW Terwilliger Blvd | Portland | OR | 97219
Audubon Society of Portland | Bob Sallinger | stakeholder | bsallinger@audubonportland.org |  |  | environmental |  | http://audubonportland.org/ | 503-292-6855 |  |  | Sallinger | Bob | Conservation Director | [8 empty] | Bob Sallinger | Audubon Society of Portland
Farm Power | Daryl Maas | stakeholder | daryl@farmpower.com |  |  | industry | Operates on-farm anaerobic digesters in Tillamook | www.farmpower.com | 210-527-7631 |  | Mr. | Maas | Daryl
Waste Management | Dean Kampfer | stakeholder | Dkampfer@wm.com | in person |  | industry | [5 empty] | Kampfer | Dean
Recycle Greenway | Eric Wentland | stakeholder | Eric@recyclegreenway.com | in person |  | industry |  | http://recyclegreenway.com |  |  |  | Wentland | Eric
City of Eugene | Ethan Nelson | stakeholder | Ethan Nelson |  |  | government | General waste reduction and biodiesel facility design experience | City of Eugene | 5416825224 |  |  | Nelson | Ethan | City of Eugene Manager,
Columbia Biogas | John McKinney | stakeholder | John@ColumbiaBioGas.com |  |  | industry | DEQ permitted anaerobic digester | www.columbiabiogas.com/ | 503-914-4630 |  | Mr. | McKinney | John |  | 721 NW 9th Avenue., Suite 195 |  | Portland | OR | 97209
4R Sustainability | Kim Holmes | stakeholder | kholmes@4RSustainability.com |  |  | industry | Consulting firm | www.4RSustainability.com | (503) 319-7009 |  |  | Holmes | Kim |  |  |  | Portland | OR
Waste Management | Kimberly Shanley | stakeholder | kshanle1@wm.com | by phone |  | industry |  | http://www.wm.com/index.jsp |  |  |  | Shanley | Kimberly
Rogue Disposal, Inc./ Dry Creek Landfill | Lee Fortier | stakeholder | lfortier@roguedisposal.com |  |  | industry | Rural Oregon representative |  | (541) 494-5411 |  |  | Fortier | Lee |  |  |  | Medford
North Lincoln Sanitary Svc, Lincoln City | French Lon | stakeholder | lfrench@northlincolnsanitary.com | by phone |  | government |  | http://www.northlincolnsanitary.com |  |  |  | Lon | French
Oregon Metro | Matt Korot | stakeholder | matt.korot@oregonmetro.gov | by phone |  | government | Regional Government | http://www.oregonmetro.gov/ |  |  |  | Korot | Matt
NW Environmental Defense Center | Mark Riskedahl | stakeholder | msr@nedc.org |  |  | environmental |  | http://law.lclark.edu/centers/northwest_environmental_defense_center/ | (503)768-6673 |  | Mr. | Riskedahl | Mark | Executive Director | Lewis & Clark Law School | 10015 SW Terwilliger Blvd | Portland | OR | 97219
Univ. California at Davis | Rob Williams | stakeholder | rbwilliam@ucdavis.edu | by phone | [7 empty] | Williams | Rob
| Rob Guttridge | stakeholder | RobRecycler@gmail.com | in person |  | industry | [5 empty] | Guttridge | Rob
New Earth Farm | Scott Olsen | stakeholder | scott@newearthfarm.net | by phone |  |  |  | Jttp://newearthfarm.net |  |  |  | Olsen | Scott
Stoel Rives, LLP | Tom Wood | stakeholder | trwood@stoel.com |  |  | environmental | Counsel for industries on air quality, hazardous waste management and permitting. | http://www.stoel.com | (503) 294-9396 |  | Mr. | Wood | Tom |  | 900 SW Fifth Ave., Suite 2600 |  | Portland | OR | 97204
Village Recyle | Kirk Hamrick | stakeholder | villagerecycle01@yahoo.com | in person |  | industry | [5 empty] | Hamrick | Kirk
Center for Earth Leadership | Jeanne Roy | stakeholder |  |  |  | environmental | [5 empty] | Roy | Jeanne
Knott Pit Landfill | Tim Schimke | stakeholder |  |  |  | government |  | http://www.deschutes.org/Solid-Waste/Rates-and-Fees-TOC/Hours-and-Fees.aspx |  |  |  | Schimke | Tim
SP Newsprint | David Walsh |  | david.walsh@spnewsprint.com | in person | [7 empty] | Walsh | David
Orange County Ca: Waste Management | Donald Ries |  | donald.riex@ocwr.ocgov.com | by phone |  | government |  | http://ocgov.com/ocgov/Info%20OC/Departments%20&%20Agencies/OC%20Waste%20&%20Recycling/Waste%20Management%20Commission |  |  |  | Ries | Donald
California : Dpt. Toxic Substance Control | John Hart |  | jhart1@dtsc.ca.gov | by phone |  | government |  | http://www.dtsc.ca.gov/ |  |  |  | Hart | John
Gov of California | Kerry Wicker |  | kerry.wicker@calrecycle.ca.gov | by phone |  | government |  | http://www.calrecycle.ca.gov/ |  |  |  | Wicker | Kerry
Municipal Biogas, Inc. | Alexander Kates DiGiorgio |  | municipal.biogas@gmail.com | by phone | [7 empty] | DiGiorgio | Alexander Kates
California: Wtr Resources Control Board | Nadine Langley |  | Nlangley@waterboards.ca.gov | by phone |  | government |  | http://www.waterboards.ca.gov/ |  |  |  | Langley | Nadine
| Michael Schuppenhauer |  | schuppenhauer@farmat ic.com | by phone | [7 empty] | Schuppenhauer | Michael
Oregon Metro | Scott Klag |  | scott.klag@oregonmetro.gov | by phone |  | government |  | http://www.oregonmetro.gov/ |  |  |  | Klag | Scott
US Environmental Protection Agency | Heather Valdez |  | valdez.heather@epa.gov | by phone |  | government |  | http://www.wm.com/index.jsp |  |  |  | Valdez | Heather
Note on B1: This is a concatenation of the first and last name of the participant entered under Mailing Information to the right.
Note on C1: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Note on D1: EMAIL ADDRESS To enter an email address: • Right mouse click • Select Hyperlink • Select E-mail Address • Enter Person’s name in Text to display: • Enter Person’s email address in E-mail address:
mm/dd/yy
Subject
Your name
Your message

## FeeApprovalForm (hidden)
Fee Approval Form |  |  | Request for fee The proposed rules do not affect fees. |  |  | Original Fee Approval Form 107BF21 (aka 333)
Part 1
The proposed rules do not affect fees. The Environmental Quality Commission's authority to adopt these fees is under ORS 459A.315 (2). | [5 empty] | Original Fee Change Detail Form 107BF22
Update Oregon rules to address federal air quality regulations
Agency |  |  |  | Date DAS Received:
Department of Environmental Quality
Agency number |  | Chapter
34000 |  | 340
Program
Air Quality
Brief description of fee change
text
| Anticipated rule adoption date |  | Anticipated SOS rule filing |  | Fee effective date
| 2012-12-13 |  | 2012-12-18 |  | 2012-12-18
| Proposed E-Board action |  | Contact |  | Phone number
| does not apply |  | Jerry Ebersole |  | (503) 229-6974
DAS Signature Box
| Approve |  |  | Deny
| Reviewer |  |  |  | Date
| Director, Department of Administrative Services |  |  |  | Date
Note: | Approval good only through July 1 of the next odd-numbered year or sine die, whichever is later, unless approved in legislation by the Regular Session of the Legislative Assembly.
Part 2
Administrative Rule Reference
| Actual fee amount(s) adopted |  | Date fee adopted or effective
| Agency Rule Coordinator |  |  |  | Date
Data Classification: Level 1 – Published |  |  |  | FeeApprovalForm
Fee Change Detail |  |  |  | Form Purpose
Administrative Rule
|  |  |  | Concept # | Policy Package #
|  |  |  | -0.1 | -0.1
Rule Caption
Update Oregon rules to address federal air quality regulations
Rule Title
0
Brief description of rule
#NAME? | [5 empty] | You have identified the purpose of this form as Administrative Rule. The orange instructions below are unique to the form selected.
Submit form (107BF22) to DAS with Fee Approval Form(107BF21) when changing fees administratively.
Reason for Fee Change
change in fee payer mix |  |  | #NAME?
new fee created by statute |  |  | #NAME?
increase in program costs |  |  | #NAME?
#NAME?
Program Funding Summary
|  | Date of last change | Current program costs covered by fee revenues.
Current |  | 2007-08-01 | 0 |  | 100%
Fees | How long will fee sustain program? |  | Current program costs covered by General Fund
|  |  | 0 |  | 0%
New Fees | How long will fee sustain program? |  | Minimum GF portion required by statute/rule to fund program.
|  |  | 0 |  | 0%
Proposed fee allows General Fund replacement.
|  |  | 0 |  | 0%
Biennium |  | Number of transactions | Impact on revenue (+/-). |  | Total revenue (+/-).
Current
Next |  |  | 0 |  | 0
Alternatives Considered | [5 empty] | ...proposes changes to more than one program, make another copy of the Fee Change Detail worksheet.
Affected Parties
Who pays the fees | [5 empty] | ...is based on a sliding scale provide a spreadsheet showing calculations.
Program stakeholders
Line 36 is only available if the Form Purpose is Administrative Rule.
Fee payer and stakeholder involvement in fee setting process
The ##-member Conversion Technology Workgroup met ## times in 2012 for the purpose of developing Oregon's Conversion Technology program. The workgroup provided input on the draft fee rule and the budget and fee structure. DEQ plans involve stakeholders during the public comment period.
Summarize stakeholder opposition comments
Summary of impacts
Data Classification: Level 1 – Published |  |  |  | FeeChangeDetail
Note on A3: PART 1 Part 1 of this form originates on the Proposal. The shaded area is reserved for DAS date-stamp.
Note on A22: DAS SIGNATURE BOX The shaded area to the right is reserved for DAS signatures. DAS will return the signed form. The signed form will be kept behind the FeeCoversheet in the rulemaking record until after EQC adopts fee. See FeeCoversheet tab.
Note on A30: DAS SIGNATURE BOX After the fees are adopted, complete Part 2 on the hard copy of the approved version with DAS original signature retained bewhind the Fee Approval and Notification cover sheet with other fee approval documents

## FEELetterPart1 (hidden)
Michael Jordan, Director |  |  | Please print on agency letterhead
Budget and Management Division
Department of Administrative Services
155 Cottage St NE, U10
Salem, OR 97301-3965
2026-08-04
RE: | Request for Fee Approval
Update Oregon rules to address federal air quality regulations
Dear Mr. Jordan:
The Department of Environmental Quality is planning a rulemaking that would adopt fees requiring Department of Administrative Service approval described on the enclosured Fee Approval Form and DEQ's equivelent to the fee detail form.
Please contact the following person if you have questions or need additional information.
| Jerry Ebersole | barrows.bob@deq.state.or.us
| Department of Environmental Quality | (503) 229-6974
811 SW Sixth Avenue
Portland, OR 97204
After signing the form, please return it to the contact above. Thank you for helping meet the deadlines on the fee approval form.
Sincerely,
Joni Hammond
Deputy Director
Enclosures
Cc: | Ken Rocco, Legislative Fiscal Office
Palmer Mason, Interim Government Relations Manager, DEQ
Jim Roys, MSD-Financial Srvices, DEQ
Wendy Wiles, Land Quality Division Administrator, DEQ
Loretta Pikerell, Land Quality, DEQ
Retain 10 years after repeal of entire rule |  | P1CoverLetter

## SIPLetter (hidden)
2012-01-24
Dennis McLarran, Regional Administrator | [5 empty] | Please print on agency letterhead
U.S. Environmental Protection Agency, Region 10
Department of Administrative Services
1200 Sixth Avenue
Seattle, WA 98101
RE: | Revision to the Oregon State Implementation Plan
Update Oregon rules to address federal air quality regulations
Dear Mr. McLerran:
The Oregon Department of Environmental Quality requests approval of revisions to the Oregon State Implementation Plan from the Office of Air, Waste, and Toxics, State and Tribal Air Programs Unit of the U.S. EPA, Region 10. DEQ transmits this letter and its attachments as provided in 40 CFR 51.104.
I certify that the:
1. | Oregon Environmental Quality Commission:
| a. Amended "&"Name of Rules on " | 2012-12-13
b. As a modification to the Oregon State Implementation Plan under OAR 340-200-0040.
2. | DEQ notified the public about the proposed rule amendments through the following publications. The following notices included a statement that the rule amendments would revise the State Implementation Plan:
| a. The Oregonian, a newspaper of general circulation, on |  | =KDSIPNotice
| b. The Secretary of State’s Bulletin |  | 2012-10-01
3. | DEQ held the following public hearings.
| =H1City&" hearing" |  | 2012-10-16
| =H2City&" hearing" |  | =KDHearing2
| =H3City&" hearing" |  | =KDHearing3
| =H4City&" hearing" |  | =KDHearing4
Thank you for EPA’s coordination with our agency during the rule development process and for your consideration of these revision to Oregon’s SIP. Please contact the following people for questions about:
| The enclosed rules | =Contact name | =Contact phone
| This SIP submission | Nicole Vick | (503) 229-5946
Sincerely,
Joni Hammond
Deputy Director
cc: | Donna Deneen, EPA, Region 10 | (3) complete sets | (2) redline rules | (1) Attachment 3
Paul Koprowski, EPA OR Operations office
Andrew Ginsburg, DEQ AQ Administrator
Nicole Vick, DEQ AQ SIP Coordinator
Data Classification: Level 1 – Published |  |  |  |  | SIPCoverLetter
affidavit

## SIP_Submittal (hidden)
ATTACHMENTS
Attachment
1 | Evidence the state has adopted the revision
| 1.1 | Staff Report, Agenda Item |  | A for the | 2012-12-13 |  | EQC meeting
See also, Certificate and Order for Filing Permanent Administrative Rules in Attachment 4.2.
2 | Evidence that the state has the necessary legal authority
| See "Commission Authority" on page number |  |  |  | # | of the Staff Report in Attachment 1.1.
|  | Staff Report, Agenda Item |  | A for the | 2012-12-13 |  | EQC meeting
3 | Provisions submitted for approval | [6 empty] | Attachment 1.1
| 3.1 | Adopted and amended rules submitted to Secretary of State
|  | 3.1a | General Air Pollution Procedures and Definitions 340-200-0040
|  | 3.1b | Rule title, 340-&Div1&Rule1, &Rule2, &Rule3, &Rule4
|  | 3.1c | Rule title, 340-&Div2&Rule1, &Rule2, &Rule3, &Rule4
|  | 3.1d | Rule title, 340-&Div3&Rule1, &Rule2, &Rule3, &Rule4
|  | 3.1e | Rule title, 340-&Div4&Rule1, &Rule2, &Rule3, &Rule4
| 3.2 | Redline/strikeout version of adopted and amended rules submitted to Secretary of State
4 | Evidence that the state followed the Administrative Procedures Act
| 4.1 | Public notice in the Secretary of State's Oregon Bulletin: | [5 empty] | 2012-10-01
| 4.2 | Certificate and Order for Filing Permanent Administrative Rules: | [5 empty] | 2012-12-18
filed and effective
5 | Evidence of adequate public notice
| 5.1 | Affidavit of Publication:
|  |  |  | publication |  |  |  | notice date
| 5.2 | Affidavit of Publication:
|  |  |  | publication |  |  |  | notice date
6 | Certification of public hearing
See paragraph #3 of cover letter and Attachment 7.1
7 | Compilation of public comments and department's response
| 7.1 | Presiding Officer's Report |  |  |  | for hearing held on
|  |  |  | report date |  |  |  | rulemaking hearing date
| 7.2 | Summary of public comment and agency response
response date
Data Classification: Level 1 - Published | [8 empty] | CoverAttachments
1/24/12
Maggie asks
Why not list it here rather the cover letter?
1/24/12
Maggie asks
Why not take this out of the cover letter and leave it here?
1/24/12
Maggie asks
Why duplicate the staff report information? Just reference 1.1 and page number.

## CertOfFilingPerm (hidden)
Secretary of State
Certificate and Order for Filing
PERMANENT ADMINISTRATIVE RULES
A Statement of Need and Justification accompanies this form. | [6 empty] | F
I certify the attached copies* are true, full and correct copies of the PERMANENT Rule(s) adopted on
2012-12-13
Oregon Department of Environmental Quality, Land Quality |  |  |  |  | 340
Agency and Division |  |  |  | Administrative Rules Chapter Number
Maggie Vandehey |  | 811 SW Sixth Avenue. Portland OR 97204-1390 |  |  |  | (503) 229-6878
Rules Coordinator |  | Address |  |  |  | Telephone
| 2012-12-18 |  |  | 2011-12-01
| to become effective |  |  | Rulemaking Notice published in the Oregon Bulletin
RULE CAPTION
Update Oregon rules to address federal air quality regulations
Not more than 15 words that reasonably identifies the subject matter of the agency’s intended action.
RULEMAKING ACTION
List each rule number separately, 000-000-0000.
Secure approval of new rule numbers (Adopted rules) with the Administrative Rules Unit prior to filing
ADOPT: | OAR 340-230-0565 340-230-0570 340-230-0575 340-230-0580 340-244-0239
AMEND: | OAR 340-200-0020
REPEAL: | OAR 340-244-0230
RENUMBER:
Stat. Auth.: | ORS 468.020, 468A.025, 468A.035, 468A.040 and 468A.310
Other Auth.:
Stats. Implemented: ORS | ORS 468.020, 468A.025, 468A.035, 468A.040 and 468A.310
RULE SUMMARY | #NAME?
|  |  | Maggie Vandehey |  | 2012-12-18
Authorized Signer
*With this original, file one photocopy of certificate, one paper copy of rules listed in Rulemaking Actions, and electronic copy of rules. **The Oregon Bulletin is published the 1st of each month and updates rules found in the OAR Compilation.

## DASEMAIL (hidden)
EMAIL
RECIPIENTS
TO… JORDAN Michael J * DO EXEC
Cc… PEARSON Lisa * BAM Analysts; PERRY Marylou; MASON Palmer; ROYS Jim; WILES Wendy; PICKERELL Loretta; VANDEHEY Maggie
TRACKING OPTIONS
Under tracking options, please check Request a Delivery Receipt and Request a Read Receipt. Forward receipts to Mary Lou Perry.
START EMAIL
Dear Mr. Jordan:
The Department of Environmental Quality is planning a rulemaking that would increase E-Cycles registration fees that require Department of Administrative Service approval. DEQ plans to submit the Notice of Proposed Rulemaking to Secretary of State on March 15, 2012. Our best practice is to have DAS approval before we go out for public notice.
The fee approval documents in the attachment include:
· DEQ’s system-generated Fee Approval Form that simulates DAS form 107BF22.
· DEQ's system-generated Fee Detail form that captures information requested on form 107BF22, it’s instructions and the instructions for the cover letter.
· Sample fee calculations using DEQ proposed registration fee model
· Fee Structures Used For Calculations
Please contact the following person if you have questions or need additional information about the fees.
| Marylou Perry | perry.marylou@deq.state.or.us
| Department of Environmental Quality | (503) 229-5731
811 SW Sixth Avenue
Portland, OR 97204-1390
If you have any questions about DEQ’s new rulemaking system or the format, please contact Maggie Vandehey at (503) 228-6878 or Maggie.vandehey@deq.state.or.us.
Joni Hammond
Deputy Director
END EMAIL
Thank you.
Maggie Vandehey
ext. 6878

## Sheet1 (hidden)
PEARSON Lisa * BAM Analysts; ROCCO Ken G
MASON Palmer; WESTBROOK Esther; ROICK Tom; GINSBURG Andy; OLIPHANT Margaret; ROYS Jim; LAWRENCE Richard; SHIN Sohng; STEVENS-SCHWENGER Joanie