2013 Water Quality Permit Fees rulemaking

Implementation Plan

(Fees are effective November 1, 2013.  See notes at end.)

| Updating Task | Notes | Dates |  |
| --- | --- | --- | --- |
|  |  | Prepare Documents | Task Completed |
| Fee Tables - Forward updated fee tables to web representative - Update NPDES & WPCF Domestic Permits web pages (Individual and General permits) http://www.deq.state.or.us/wq/wqpermit/dominfo.htm - Update NPDES & WPCF Industrial Permits web pages (Individual and General permits) http://www.deq.state.or.us/wq/wqpermit/indinfo.htm - Update NPDES Stormwater Permits web pages (Individual and General permits) http://www.deq.state.or.us/wq/wqpermit/stminfo.htm http://www.deq.state.or.us/wq/wqpermit/genpermits.htm - Update fee tables Division 45 and 71 tables on DEQ’s OAR website: http://www.deq.state.or.us/regulations/rules.htm. Direct links to tables as follows: http://www.deq.state.or.us/wq/rules/div045/tables.pdf BROKEN LINK – needs to be deleted http://www.deq.state.or.us/wq/rules/div071/tables1-9.pdf BROKEN LINK – needs to be deleted http://www.deq.state.or.us/wq/onsite/rules.htm | Chris to make corrections/instructions on paper and provide electronic files; Michele to make changes online (Task #2-21). A GovDelivery is included in task #28. | 10/1/13 10/1/13 10/1/13 10/1/13 10/1/13 | 11/1/13 11/1/13 11/1/13 11/1/13 11/1/13 |
| WQ Fee Q & A - Update fee tables on web page - Update all applicable responses to questions http://www.deq.state.or.us/wq/wqpermit/permitfeesfaqs.htm General Q & A - Update all applicable responses to questions http://www.deq.state.or.us/wq/wqpermit/permitfaqs.htm |  | 10/1/13 10/1/13 10/1/13 | 11/1/13 11/1/13 11/1/13 |
| Forms and Fact Sheets - *IGNORE – Erich Brandstetter currently revising document.* 07-WQ-007 Construction Stormwater Permit Guidance 1200-C NPDES General Permit http://www.deq.state.or.us/wq/stormwater/docs/forms/1200CGuidancef.pdf - 08-WQ-004 NPDES 1200-C Permit Application http://www.deq.state.or.us/wq/stormwater/constappl.htm - 08-WQ-013 Name Change and/or Permit Transfer for NPDES or WPCF Permit http://www.deq.state.or.us/wq/wqpermit/permits.htm http://www.deq.state.or.us/wq/stormwater/constappl.htm#trans http://www.deq.state.or.us/wq/wqpermit/permitfaqs.htm http://www.deq.state.or.us/pubs/forms.htm - *IGNORE – Jim Billings currently revising document.* 08-WQ-019 Application for New Water Pollution Control Facilities WPCF General Permit 600 http://www.deq.state.or.us/wq/wqpermit/indinfo.htm - 08-WQ-005 National Pollutant Discharge Elimination System Permit Application for Small MS4s http://www.deq.state.or.us/wq/wqpermit/stminfo.htm - 08-WQ-007 Fact Sheet: Applying for the 1200-C Construction Stormwater Permit http://www.deq.state.or.us/wq/stormwater/construction.htm - 08-WQ-006 Application NPDES Industrial Stormwater General Permit Nos. 1200-A, 1200-Z and 1200-COLS http://www.deq.state.or.us/wq/wqpermit/genpermits.htm - *Need to determine how to get revised form into document.* 07-WQ-017 Industrial Stormwater Guidance NPDES 1200-Z and 1200-COLS General Permits http://www.deq.state.or.us/wq/stormwater/industrial.htm - *IGNORE – No changes needed for document.* 11-WQ-021 Renewal Application Water Pollution Control Facilities General Permit #1000 http://www.deq.state.or.us/wq/wqpermit/genpermits.htm - 11-WQ-022 Renewal Application NPDES Stormwater Discharge General Permit 1200-COLS http://www.deq.state.or.us/wq/wqpermit/genpermits.htm - 11-WQ-026 Small Lot Application NPDES General Permit #1200-C http://www.deq.state.or.us/wq/wqpermit/stminfo.htm#1200c - Q-Net – Permit Coordinator’s Corner – Contains links to other websites and forms updated in previous tasks. Verify links are functioning. http://deq05/wq/wqpermits/PermitCoordCorner.htm |  | 10/2/13 10/2/13 10/2/13 10/2/13 10/2/13 10/2/13 10/2/13 10/2/13 10/2/13 10/2/13 10/2/13 10/2/13 10/2/13 | 11/1/13 11/1/13 11/1/13 11/1/13 11/1/13 11/1/13 11/1/13 11/1/13 11/1/13 11/1/13 11/1/13 11/1/13 11/1/13 |
| Rule Announcement Permit Program Website - Include a summary of the adopted rulemaking in the “Current News” section. http://www.deq.state.or.us/wq/wqpermit/permits.htm Invoicing / SIS/ Permit Holders Notification - Forward updated fee table to Melissa Kays to update invoicing database. - Develop language for annual fee invoices informing permit holders of fee increases. - Include notice of fee increases with invoices. (Note: Notices of fee increases with invoices to start 11/1/13.) | Melissa Kays is working with BSD on the database updates. BSD Analyst to add language to invoices. | 10/2/13 7/29/13 10/2/13 | 11/1/13 11/1/13 |
| DEQ Staff – WQ, Business Office, Budget, OCO - If needed, give overview of fee increases at a permit coordinator meeting. - Notification to WQ Managers, WQ Staff, BSD Analyst (Bill Brown), Budget Analyst (Yongkie Hurd), Communications Representative (Brian White), Accounting (Richard Lawrence, Laurie Hunter) | (not necessary) Provide fee update in early Oct. | (fee table already prepared) | 10/10/13 |
| MOA Agents - Forward stormwater permit MOA agents a copy of updated fee table, along with any pertinent information, and any potential changes to MOA fee-sharing arrangements. | Provide fee update in early Oct. Notify of EQC approval and provide new fee table. | (fee table already prepared) | 10/10/13 10/30/13 |
| Stakeholders - Send GovDelivery notice to the same list as the public notice period. (Use the language from #21.) - Send postcards to AMLS list plus City of Pendleton employees only. (Use the language from #21.) (Permit holders will receive notice of the rulemaking with their annual fee invoice (#24 above)). - Send notification to Blue Ribbon Committee. Miscellaneous Review Communication Plan and Rulemaking Plan for any loose ends. | Notify of EQC approval and provide new fee table. |  | 10/30/13 10/30/13 10/30/13 |

Notes:

- Use the publication numbers on documents to get the most recent electronic file from OCO.  Check to make sure the OCO file is the same version of the form as what is posted on the website.  They May Not Match!!!

- To get a new publication number for forms etc. use the Publications Tracking Form http://deq05/intranet/communication/publications.htm

- Provide Stephanie with 1-2 weeks lead time for website updates prior to the effective date of fee increase.

- DEQ has two computer servers so revisions to websites can be completed in advance and then posted on the effective date of fee increases.  The update to websites occurs manually (i.e. a button needs to be pushed).  This can have implications if the effective date of the rulemaking falls on a weekend.

- Complete as many items as possible before the EQC meeting.