## DDLs (hidden)
DDLs called from ScheduleTasks
1 | 2 | 3 | 4 | 5 | 6
DDL_EQCMeeting | EQCStaffRptDue | EQCMaterialsDue | Days to next | Next | Last
2013-03-20 | 2013-02-11 | 2013-03-13 | 91 | 2013-06-19 | 2012-12-16
2013-06-19 | 2013-05-10 | 2013-06-12 | 63 | 2013-08-21 | 2013-03-20
2013-08-21 | 2013-07-16 | 2013-08-14 | 56 | 2013-10-16 | 2013-06-19
2013-10-16 | 2013-09-10 | 2013-10-09 | 56 | 2013-12-11 | 2013-08-21
2013-12-11 | 2013-11-01 | 2013-12-04 | 98 | 2014-03-19 | 2013-10-16
2014-03-19 | 2014-02-06 | 2014-03-07 | 91 | 2014-06-18 | 2013-12-11
2014-06-18 | 2014-05-08 | 2014-06-06 | 63 | 2014-08-20 | 2014-03-19
2014-08-20 | 2014-07-10 | 2014-08-08 | 56 | 2014-10-15 | 2014-06-18
2014-10-15 | 2014-09-04 | 2014-10-03 | 56 | 2014-12-10 | 2014-08-20
2014-12-10 | 2014-10-30 | 2014-11-28 | 98 | 2015-03-18 | 2014-10-15
2015-03-18 | 2015-02-05 | 2015-03-06 | 92 | 2015-06-18 | 2014-12-10
2015-06-18 | 2015-05-08 | 2015-06-08 | 63 | 2015-08-20 | 2015-03-18
2015-08-20 | 2015-07-10 | 2015-08-10 | 63 | 2015-10-22 | 2015-06-18
2015-10-22 | 2015-09-11 | 2015-10-12 | 56 | 2015-12-17 | 2015-08-20
2015-12-17 | 2015-11-06 | 2015-12-07 | 90 | 2016-03-16 | 2015-10-22
2016-03-16 | 2016-02-04 | 2016-03-04 | 91 | 2016-06-15 | 2015-12-17
2016-06-15 | 2016-05-05 | 2016-06-03 | 91
http://www.leg.state.or.us/ors/187.html
DEQClosed | [5 empty] | LEGAL HOLIDAYS 187.010 Legal holidays; acts deferred to next business day; effect on labor agreements. (1) The following days are legal holidays in this state: (a) Each Sunday. (b) New Year’s Day on January 1. (c) Martin Luther King, Jr.’s Birthday on the third Monday in January. (d) Presidents Day, for the purpose of commemorating Presidents Washington and Lincoln, on the third Monday in February. (e) Memorial Day on the last Monday in May. (f) Independence Day on July 4. (g) Labor Day on the first Monday in September. (h) Veterans Day on November 11. (i) Thanksgiving Day on the fourth Thursday in November. (j) Christmas Day on December 25. (2) Each time a holiday, other than Sunday, listed in subsection (1) of this section falls on Sunday, the succeeding Monday shall be a legal holiday. Each time a holiday listed in subsection (1) of this section falls on Saturday, the preceding Friday shall be a legal holiday. (3) Any act authorized, required or permitted to be performed on a holiday as designated in this section may be performed on the next succeeding business day; and no liability or loss of rights of any kind shall result from such delay. (4) In enumerating legal holidays in subsection (1) of this section, the Legislative Assembly does not intend to limit or otherwise affect public or private collective bargaining or collective bargaining agreements. [Amended by 1955 c.4 §1; 1969 c.455 §1; 1973 c.51 §1; 1975 c.633 §1; 1977 c.135 §1; 1977 c.321 §1; 1985 c.518 §1] 187.020 Additional legal holidays. In addition to those specified in ORS 187.010, the following days are legal holidays in this state: (1) Every day appointed by the Governor as a holiday. (2) Every day appointed by the President of the United States as a day of mourning, rejoicing or other special observance only when the Governor also appoints that day as a holiday. [Amended by 1969 c.455 §2; 1975 c.633 §2; 1977 c.135 §2; 1977 c.321 §2; 1985 c.518 §2]
2013-01-01 | New Year | 2013-01-01
2013-01-18 | furlough | 2013-01-18
2013-01-21 | MLK Jr. | 2013-01-21
2013-02-18 | Presidents | 2013-02-18
2013-04-19 | furlough | 2013-04-19
2013-05-24 | furlough | 2013-05-24
2013-05-27 | Memorial | 2013-05-27
2013-07-04 | Independence | 2013-07-04
2013-09-02 | Labor | 2013-09-02
2013-11-11 | Veterans | 2013-11-11
2013-11-28 | Thanksgiving | 2013-11-28
2013-12-25 | Christmas | 2013-12-25
2014-01-01 | New Year | 2014-01-01
2014-01-20 | MLK Jr. | 2014-01-20
2014-02-17 | Presidents | 2014-02-17
2014-05-26 | Memorial | 2014-05-26
2014-07-04 | Independence | 2014-07-04
2014-09-02 | Labor | 2014-09-02
2014-11-11 | Veterans | 2014-11-11
2014-11-27 | Thanksgiving | 2014-11-27
2014-12-25 | Christmas | 2014-12-25
2015-01-01 | New Year | 2015-01-01
2015-01-19 | MLK Jr. | 2015-01-19
2015-02-16 | Presidents | 2015-02-16
2015-05-25 | Memorial | 2015-05-25
2015-07-03 | Independence | 2015-07-03
2015-09-07 | Labor | 2015-09-07
2015-11-11 | Veterans | 2015-11-11
2015-11-26 | Thanksgiving | 2015-11-26
2015-12-25 | Christmas | 2015-12-25
2016-01-01 | New Year | 2016-01-01
2016-01-18 | MLK Jr. | 2016-01-18
2016-02-15 | Presidents | 2016-02-15
2016-05-30 | Memorial | 2016-05-30
2016-07-04 | Independence | 2016-07-04
2016-09-05 | Labor | 2016-09-05
2016-11-11 | Veterans | 2016-11-11
2016-11-24 | Thanksgiving | 2016-11-24
2016-12-26 | Christmas | 2016-12-26
2017-01-02 | New Year | 2017-01-02
2017-01-16 | MLK Jr. | 2017-01-16
2017-02-20 | Presidents | 2017-02-20
2017-05-29 | Memorial | 2017-05-29
2017-07-04 | Independence | 2017-07-04
2017-09-04 | Labor | 2017-09-04
2017-11-10 | Veterans | 2017-11-10
2017-11-23 | Thanksgiving | 2017-11-23
2017-12-25 | Christmas | 2017-12-25
2018-01-01 | New Year | 2018-01-01
Called from ScheduleTasks
DDL_Bulletin | VL_Bulletin
2013-01-01 | 2012-12-14 | 2012-12-14
2013-02-01 | 2013-01-15 | 2013-01-15
2013-03-01 | 2013-02-15 | 2013-02-15
2013-04-01 | 2013-03-15 | 2013-03-15
2013-05-01 | 2013-04-15 | 2013-04-15
2013-06-01 | 2013-05-15 | 2013-05-15
2013-07-01 | 2013-06-14 | 2013-06-14
2013-08-01 | 2013-07-15 | 2013-07-15
2013-09-01 | 2013-08-15 | 2013-08-15
2013-10-01 | 2013-09-13 | 2013-09-13
2013-11-01 | 2013-10-15 | 2013-10-15
2013-12-01 | 2013-11-15 | 2013-11-15
2014-01-01 | 2013-12-13 | 2013-12-13
2014-02-01 | 2014-01-15 | 2014-01-15
2014-03-01 | 2014-02-14 | 2014-02-14
2014-04-01 | 2014-03-14 | 2014-03-14
2014-05-01 | 2014-04-15 | 2014-04-15
2014-06-01 | 2014-05-15 | 2014-05-15
2014-07-01 | 2014-06-13 | 2014-06-13
2014-08-01 | 2014-07-15 | 2014-07-15
2014-09-01 | 2014-08-15 | 2014-08-15
2014-10-01 | 2014-09-15 | 2014-09-15
2014-11-01 | 2014-10-15 | 2014-10-15
2014-12-01 | 2014-11-14 | 2014-11-14
2015-01-01 | 2014-12-15 | 2014-12-15
2015-02-01 | 2015-01-15 | 2015-01-15
2015-03-01 | 2015-02-13 | 2015-02-13
2015-04-01 | 2015-03-13 | 2015-03-13
2015-05-01 | 2015-04-15 | 2015-04-15
2015-06-01 | 2015-05-15 | 2015-05-15
2015-07-01 | 2015-06-15 | 2015-06-15
2015-08-01 | 2015-07-15 | 2015-07-15
2015-09-01 | 2015-08-15 | 2015-08-15
2015-10-01 | 2015-09-15 | 2015-09-15
2015-11-01 | 2015-10-15 | 2015-10-15
2015-12-01 | 2015-11-13 | 2015-11-13
2016-01-01 | 2015-12-15 | 2015-12-15
2016-02-01 | 2016-01-15 | 2016-01-15
2016-03-01 | 2016-02-15 | 2016-02-15
2016-04-01 | 2016-03-15 | 2016-03-15
2016-05-01 | 2016-04-15 | 2016-04-15
2016-06-01 | 2016-05-13 | 2016-05-13
2016-07-01 | 2016-06-15 | 2016-06-15
2016-08-01 | 2016-07-15 | 2016-07-15
2016-09-01 | 2016-08-15 | 2016-08-15
2016-10-01 | 2016-09-15 | 2016-09-15
2016-11-01 | 2016-10-14 | 2016-10-14
2016-12-01 | 2016-11-15 | 2016-11-15
2017-01-01 | 2016-12-15 | 2016-12-15
2017-02-01 | 2017-01-13 | 2017-01-13
2017-03-01 | 2017-02-15 | 2017-02-15
2017-04-01 | 2017-03-15 | 2017-03-15
2017-05-01 | 2017-04-14 | 2017-04-14
2017-06-01 | 2017-05-15 | 2017-05-15
2017-07-01 | 2017-06-15 | 2017-06-15
2017-08-01 | 2017-07-14 | 2017-07-14
2017-09-01 | 2017-08-15 | 2017-08-15
2017-10-01 | 2017-09-15 | 2017-09-15
2017-11-01 | 2017-10-13 | 2017-10-13
2017-12-01 | 2017-11-15 | 2017-11-15
2018-01-01 | 2017-12-15 | 2017-12-15
2018-02-01 | 2018-01-15 | 2018-01-15
2018-03-01 | 2018-02-15 | 2018-02-15
2018-04-01 | 2018-03-14 | 2018-03-14
2018-05-01 | 2018-04-13 | 2018-04-13
2018-06-01 | 2018-05-15 | 2018-05-15
2018-07-01 | 2018-06-15 | 2018-06-15
2018-08-01 | 2018-07-13 | 2018-07-13
2018-09-01 | 2018-08-15 | 2018-08-15
2018-10-01 | 2018-09-14 | 2018-09-14
2018-11-01 | 2018-10-15 | 2018-10-15
2018-12-01 | 2018-11-15 | 2018-11-15
2019-01-01 | 2018-12-14 | 2018-12-14
2019-02-01 | 2019-01-15 | 2019-01-15
2019-03-01 | 2019-02-15 | 2019-02-15
2019-04-01 | 2019-03-15 | 2019-03-15
2019-05-01 | 2019-04-15 | 2019-04-15
2019-06-01 | 2019-05-15 | 2019-05-15
2019-07-01 | 2019-06-14 | 2019-06-14
2019-08-01 | 2019-07-15 | 2019-07-15
2019-09-01 | 2019-08-15 | 2019-08-15
2019-10-01 | 2019-09-13 | 2019-09-13
2019-11-01 | 2019-10-15 | 2019-10-15
2019-12-01 | 2019-11-15 | 2019-11-15
2020-01-01 | 2019-12-13 | 2019-12-13
2020-02-01 | 2020-01-15 | 2020-01-15
2020-03-01 | 2020-02-14 | 2020-02-14
2020-04-01 | 2020-03-13 | 2020-03-13
2020-05-01 | 2020-04-15 | 2020-04-15
2020-06-01 | 2020-05-15 | 2020-05-15
2020-07-01 | 2020-06-15 | 2020-06-15
2020-08-01 | 2020-07-15 | 2020-07-15
2020-09-01 | 2020-08-14 | 2020-08-14
2020-10-01 | 2020-09-15 | 2020-09-15
2020-11-01 | 2020-10-15 | 2020-10-15
2020-12-01 | 2020-11-13 | 2020-11-13
2021-01-01 | 2020-12-15 | 2020-12-15
2021-02-01 | 2021-01-15 | 2021-01-15
2021-03-01 | 2021-02-15 | 2021-02-15
2021-04-01 | 2021-03-15 | 2021-03-15
2021-05-01 | 2021-04-15 | 2021-04-15
2021-06-01 | 2021-05-14 | 2021-05-14
2021-07-01 | 2021-06-15 | 2021-06-15
2021-08-01 | 2021-07-15 | 2021-07-15
2021-09-01 | 2021-08-13 | 2021-08-13
2021-10-01 | 2021-09-15 | 2021-09-15
2021-11-01 | 2021-10-15 | 2021-10-15
2021-12-01 | 2021-11-15 | 2021-11-15
Called from ScheduleTasks
Formulas:
Next = [DDL_EQCMeeting]+[Days to next]
Last = [DDL_EQCMeeting]-[Days to next, row above]
EQCStaffRptDue = WORKDAY([DDL_EQCMeeting]-40,-1,S.DDL_DEQClosed)
EQCMaterialsDue = WORKDAY([DDL_EQCMeeting]-9,-1,S.DDL_DEQClosed)
EQCMaterialsDue = [DDL_EQCMeeting]

## ScheduleTasks
CALCULATIONS - DO NOT DELETE
| Schedule of Tasks | Diesel Grants | [5 empty] | ↓ Adjust start date | [699 empty] | 470 | testing area
[8 empty] | 0 |  |  |  |  | Workday |  |  | Weekend |  |  | Closed | [17 empty] | Workday |  |  | Weekend |  |  | Closed | [21 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [21 empty] | Workday |  |  | Weekend |  |  | Closed | [21 empty] | Workday |  |  | Weekend |  |  | Closed | [21 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [21 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [21 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [21 empty] | Workday |  |  | Weekend |  |  | Closed | [21 empty] | Workday |  |  | Weekend |  |  | Closed | [22 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [21 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [26 empty] | Gantt
| Overview of Key Dates |  |  | Workdays |  | Today 07/23/13 |  | 2013-07-23 | [5 empty] | 2013-07-29 | [6 empty] | 2013-08-05 | [6 empty] | 2013-08-12 | [6 empty] | 2013-08-19 | [6 empty] | 2013-08-26 | [6 empty] | 2013-09-02 | [6 empty] | 2013-09-09 | [6 empty] | 2013-09-16 | [6 empty] | 2013-09-23 | [6 empty] | 2013-09-30 | [6 empty] | 2013-10-07 | [6 empty] | 2013-10-14 | [6 empty] | 2013-10-21 | [6 empty] | 2013-10-28 | [6 empty] | 2013-11-04 | [6 empty] | 2013-11-11 | [6 empty] | 2013-11-18 | [6 empty] | 2013-11-25 | [6 empty] | 2013-12-02 | [6 empty] | 2013-12-09 | [6 empty] | 2013-12-16 | [6 empty] | 2013-12-23 | [6 empty] | 2013-12-30 | [6 empty] | 2014-01-06 | [6 empty] | 2014-01-13 | [6 empty] | 2014-01-20 | [6 empty] | 2014-01-27 | [6 empty] | 2014-02-03 | [6 empty] | 2014-02-10 | [6 empty] | 2014-02-17 | [6 empty] | 2014-02-24 | [6 empty] | 2014-03-03 | [6 empty] | 2014-03-10 | [6 empty] | 2014-03-17 | [6 empty] | 2014-03-24 | [6 empty] | 2014-03-31 | [6 empty] | 2014-04-07 | [6 empty] | 2014-04-14 | [6 empty] | 2014-04-21 | [6 empty] | 2014-04-28 | [6 empty] | 2014-05-05 | [6 empty] | 2014-05-12 | [6 empty] | 2014-05-19 | [6 empty] | 2014-05-26 | [6 empty] | 2014-06-02 | [6 empty] | 2014-06-09 | [6 empty] | 2014-06-16 | [6 empty] | 2014-06-23 | [6 empty] | 2014-06-30 | [6 empty] | 2014-07-07 | [6 empty] | 2014-07-14 | [6 empty] | 2014-07-21 | [6 empty] | 2014-07-28 | [6 empty] | 2014-08-04 | [6 empty] | 2014-08-11 | [6 empty] | 2014-08-18 | [6 empty] | 2014-08-25 | [6 empty] | 2014-09-01 | [6 empty] | 2014-09-08 | [6 empty] | 2014-09-15 | [6 empty] | 2014-09-22 | [6 empty] | 2014-09-29 | [6 empty] | 2014-10-06 | [6 empty] | 2014-10-13 | [6 empty] | 2014-10-20 | [6 empty] | 2014-10-27 | [6 empty] | 2014-11-03 | [6 empty] | 2014-11-10 | [6 empty] | 2014-11-17 | [6 empty] | 2014-11-24 | [6 empty] | 2014-12-01 | [6 empty] | 2014-12-08 | [6 empty] | 2014-12-15 | [6 empty] | 2014-12-22 | [6 empty] | 2014-12-29 | [6 empty] | 2015-01-05 | [6 empty] | 2015-01-12 | [6 empty] | 2015-01-19 | [6 empty] | 2015-01-26 | [6 empty] | 2015-02-02 | [6 empty] | 2015-02-09 | [6 empty] | 2015-02-16 | [6 empty] | 2015-02-23 | [6 empty] | 2015-03-02 | [6 empty] | 2015-03-09 | [6 empty] | 2015-03-16 | [6 empty] | 2015-03-23 | [6 empty] | 2015-03-30 | [6 empty] | 2015-04-06 | [6 empty] | 2015-04-13 | [6 empty] | 2015-04-20 | [6 empty] | 2015-04-27 | [6 empty] | 2015-05-04 | [6 empty] | 2015-05-11 | [6 empty] | 2015-05-18 | [6 empty] | 2015-05-25 | [6 empty] | 2015-06-01 | [6 empty] | 2015-06-08 | [6 empty] | 2015-06-15 | T | X |  | 2013-12-02 |  | Form Control DO NOT LOCK
|  |  |  | This Task | From Today | Start Task | End Task | 2013-07-23 | [5 empty] | 2013-07-29 | [6 empty] | 2013-08-05 | [6 empty] | 2013-08-12 | [6 empty] | 2013-08-19 | [6 empty] | 2013-08-26 | [6 empty] | 2013-09-02 | [6 empty] | 2013-09-09 | [6 empty] | 2013-09-16 | [6 empty] | 2013-09-23 | [6 empty] | 2013-09-30 | [6 empty] | 2013-10-07 | [6 empty] | 2013-10-14 | [6 empty] | 2013-10-21 | [6 empty] | 2013-10-28 | [6 empty] | 2013-11-04 | [6 empty] | 2013-11-11 | [6 empty] | 2013-11-18 | [6 empty] | 2013-11-25 | [6 empty] | 2013-12-02 | [6 empty] | 2013-12-09 | [6 empty] | 2013-12-16 | [6 empty] | 2013-12-23 | [6 empty] | 2013-12-30 | [6 empty] | 2014-01-06 | [6 empty] | 2014-01-13 | [6 empty] | 2014-01-20 | [6 empty] | 2014-01-27 | [6 empty] | 2014-02-03 | [6 empty] | 2014-02-10 | [6 empty] | 2014-02-17 | [6 empty] | 2014-02-24 | [6 empty] | 2014-03-03 | [6 empty] | 2014-03-10 | [6 empty] | 2014-03-17 | [6 empty] | 2014-03-24 | [6 empty] | 2014-03-31 | [6 empty] | 2014-04-07 | [6 empty] | 2014-04-14 | [6 empty] | 2014-04-21 | [6 empty] | 2014-04-28 | [6 empty] | 2014-05-05 | [6 empty] | 2014-05-12 | [6 empty] | 2014-05-19 | [6 empty] | 2014-05-26 | [6 empty] | 2014-06-02 | [6 empty] | 2014-06-09 | [6 empty] | 2014-06-16 | [6 empty] | 2014-06-23 | [6 empty] | 2014-06-30 | [6 empty] | 2014-07-07 | [6 empty] | 2014-07-14 | [6 empty] | 2014-07-21 | [6 empty] | 2014-07-28 | [6 empty] | 2014-08-04 | [6 empty] | 2014-08-11 | [6 empty] | 2014-08-18 | [6 empty] | 2014-08-25 | [6 empty] | 2014-09-01 | [6 empty] | 2014-09-08 | [6 empty] | 2014-09-15 | [6 empty] | 2014-09-22 | [6 empty] | 2014-09-29 | [6 empty] | 2014-10-06 | [6 empty] | 2014-10-13 | [6 empty] | 2014-10-20 | [6 empty] | 2014-10-27 | [6 empty] | 2014-11-03 | [6 empty] | 2014-11-10 | [6 empty] | 2014-11-17 | [6 empty] | 2014-11-24 | [6 empty] | 2014-12-01 | [6 empty] | 2014-12-08 | [6 empty] | 2014-12-15 | [6 empty] | 2014-12-22 | [6 empty] | 2014-12-29 | [6 empty] | 2015-01-05 | [6 empty] | 2015-01-12 | [6 empty] | 2015-01-19 | [6 empty] | 2015-01-26 | [6 empty] | 2015-02-02 | [6 empty] | 2015-02-09 | [6 empty] | 2015-02-16 | [6 empty] | 2015-02-23 | [6 empty] | 2015-03-02 | [6 empty] | 2015-03-09 | [6 empty] | 2015-03-16 | [6 empty] | 2015-03-23 | [6 empty] | 2015-03-30 | [6 empty] | 2015-04-06 | [6 empty] | 2015-04-13 | [6 empty] | 2015-04-20 | [6 empty] | 2015-04-27 | [6 empty] | 2015-05-04 | [6 empty] | 2015-05-11 | [6 empty] | 2015-05-18 | [6 empty] | 2015-05-25 | [6 empty] | 2015-06-01 | [6 empty] | 2015-06-08 | [6 empty] | 2015-06-15 | T | X | [5 empty] | Next EQC Meeting 03/03/00 | [12 empty] | 2013-06-20
[5 empty] | 105 | 2013-04-05 | 2013-12-16 | [693 empty] | B | X | 2013-07-23 | 2013-12-16 |  | 2 | 14 | time axis 2013-07-23 to 2015-06-15
[701 empty] | Y | X
[701 empty] | 0 | X | [5 empty] | Future S.CodeName
| Rule Permanent Temporary | [699 empty] | 1 | X | 1900-03-03 | [5 empty] | 2013-04-05
[701 empty] | 0 | X
| EQC Rulemaking Action Item |  |  |  | 61 | 2013-10-16 | 2013-10-16 | [693 empty] | 1 |  |  | 2013-08-21 |  |  |  |  | Start | 2.2 | 1.9667 | 1.7333 | 1.5 |  |  |  | good | good | good | good
| INVOLVED before Rulemaking Action Item |  |  |  |  | Option 1 ↓ | Option 2 ↓ | [693 empty] | 1 | X |  |  |  | TRUE |  | INVOLVED before Rulemaking Action Item |  | Crawl | Walk | Run | Bolt | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
| Director's Dialog |  |  |  | 22 | 2013-08-21 | 2013-08-21 | [693 empty] | 1 |  | 2013-08-21 | 2013-08-21 |  | TRUE |  |  | Rule Type | 21 | 14 | 7 | 0 | DDL_Pace | Notice to EPA |  | Fees | Notice to SOS | Bulletin | Hearing | EQC | EQC early involvement | Day between EQC
| Information Item |  |  |  | 22 | 2013-08-21 | 2013-08-21 | [693 empty] | 0 |  | 2013-08-21 | 2013-08-21 |  | FALSE |  |  | SIP | 0 | 0 | 0 | 0 | bar: 1 to good 10
| Facilitated Hearing |  |  |  | 22 | 2013-08-21 | 2013-08-21 | [693 empty] | 0 |  | 2013-08-21 | 2013-08-21 |  | FALSE |  | Facilitated Hearing | AC | 0 | 0 | 0 | 0 | Crawl | 2013-04-05 | 2013-04-05 | 2013-04-05 | 2013-04-05 | 2014-02-01 | 2013-04-05 | 2014-06-18 | 2014-03-19 | 63
[701 empty] | 0 | X
| 1-State Implementation Plan (AQ rules) NOT involved |  |  | 138 | 71 | 2013-04-15 | 2013-10-30 | [693 empty] | 0 |  | 2013-04-15 | 2013-10-30 |  | FALSE |  | 1-State Implementation Plan (AQ rules) NOT involved | Fee | 0 | 0 | 0 | 0 | Walk | 2013-04-05 | 2013-04-05 | 2013-04-05 | 2013-04-05 | 2013-12-01 | 2013-04-05 | 2014-03-19 | 2013-12-11 | 91
[701 empty] | 0 | X | [6 empty] | Notice | 0 | 0 | 0 | 0 | Run | 2013-04-05 | 2013-04-05 | 2013-04-05 | 2013-04-05 | 2013-10-01 | 2013-04-05 | 2013-12-11 | 2013-08-21 | 98
| 2-Advisory Committee NOT involved |  |  | 1 | -74 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  | FALSE |  | 2-Advisory Committee NOT involved | EQC Prep | 45 | 45 | 45 | 45 | Bolt | 2013-04-05 | 2013-04-05 | 2013-04-05 | 2013-04-05 | 2013-08-01 | 2013-04-05 | 2013-10-16 | 2013-08-21 | 56
[701 empty] | 0 | X | [7 empty] | 66 | 59 | 52 | 45
| 3-Fees Not Involved |  |  | 71 | -4 | 2013-04-05 | 2013-07-18 | [693 empty] | 0 |  | 2013-04-05 | 2013-07-18 | FALSE | FALSE |  | 3-Fees Not Involved
| DAS - Fee approval not involved | [699 empty] | 0 | X |  |  |  | 1 |  | DAS - Fee approval not involved
| DAS - Email notice not involved | [699 empty] | 0 | X | [5 empty] | DAS - Email notice not involved
[701 empty] | 0 | X
| 4-PublicNotice - not required for TEMPORARY rules (APA) | [699 empty] | 0 | X | [5 empty] | 4-PublicNotice - not required for TEMPORARY rules (APA)
| EPA - SIP not involved |  |  |  | -16 | 2013-07-01 | 2013-07-01 | [693 empty] | 0 |  |  | 2013-07-01 |  |  |  | EPA - SIP not involved
| DAS - fees not involved |  |  |  | -74 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  |  | 2013-04-05 |  |  | 0 | DAS - fees not involved
| SOS - not involved |  |  |  | -7 | 2013-07-15 | 2013-07-15 | [693 empty] | 0 |  |  | 2013-07-15 |  |  |  | SOS - not involved
| SOS - not involved |  |  |  | 8 |  | 2013-08-01 | [693 empty] | 0 |  |  | 2013-08-01 |  | FALSE | 0 | SOS - not involved
| 5-Public Comment and Testimony | [699 empty] | 0 | X | [5 empty] | IF(S.InvolveHearing=TRUE," with hearings"," no hearings"))
| No public notice with hearing |  |  |  | 18 | 2013-08-15 | 2013-08-15 | [693 empty] | 0 |  |  | 2013-08-15 |  | FALSE | 0 | No public notice with hearing
| No public comment period |  |  |  | -74 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  |  | 2013-04-05 |  |  |  | No public comment period
| 6-EQC Preparation | [699 empty] | 1 | X
| Submit staff report | Q |  |  | 35 | 2013-09-10 | 2013-09-10 | [693 empty] | 1 |  |  | 2013-09-10 |  |  | 41 | WORKDAY(S.SubmitStaffRpt-42,1,S.DDL_EQCMeeting)
| Present EQC Action Item | Q |  |  | 61 | 2013-10-16 | 2013-10-16 | [693 empty] | 1 |  |  | 2013-10-16
| 7-Post EQC | [699 empty] | 1 | X |  |  |  |  | 55
| SOS - file rules |  |  |  | 63 | 2013-10-18 | 2013-10-18 | [693 empty] | 1 |  |  | 2013-10-18
| EPA - SIP not involved |  |  |  | 71 | 2013-10-30 | 2013-10-30 | [693 empty] | 0 |  |  | 2013-10-30 |  |  |  | EPA - SIP not involved
| DAS - fees not involved |  |  |  | 64 | 2013-10-21 | 2013-10-21 | [693 empty] | 0 |  |  | 2013-10-21 |  |  |  | DAS - fees not involved
| Rules become effective |  |  |  | 63 | 2013-10-18 | 2013-10-18 | [693 empty] | 1 |  |  | 2013-10-18 | 2013-10-26
[701 empty] | 0 | X
| 1-Planning | [699 empty] | T | X
| Task |  | Owner | This Task | Workdays | Start Task | End Task | [693 empty] | B | X
[5 empty] | 83 | 2013-04-05 | 2013-08-05 | [693 empty] | B | X | 2013-04-05 | 2013-08-05
[701 empty] | Y | X
| After approved on DEQ's Annual Rulemaking Plan: | DEQ | [698 empty] | 1 | X
| Expand Core Team |  | LM,SE,DE | 1 | -6 | 2013-07-16 | 2013-07-16 | [693 empty] | 1 |  | 2013-04-05 | 2013-07-16
| Notify new members |  | LM, Mgrs | 1 | -6 | 2013-07-16 | 2013-07-16 | [693 empty] | 1 |  | 2013-07-16 | 2013-07-16
| Add rulemaking to work plans as needed |  | LM, Mgrs | 1 | -6 | 2013-07-16 | 2013-07-16 | [693 empty] | 1 |  | 2013-07-16 | 2013-07-16
| Team kickoff meeting/training/work session |  | Team,LA | 1 | -6 | 2013-07-16 | 2013-07-16 | [693 empty] | 1 |  | 2013-07-16 | 2013-07-16
| Maintaining rulemaking record | [699 empty] | 1 | X
| File naming conventions | [699 empty] | 1 | X
| Rulemaking SharePoint | SP | [698 empty] | 1 | X
| Shared drive: Rules _Development | [699 empty] | 1 | X
| Discuss Overview of Key Dates above | [699 empty] | 1 | X
| Overview of main external work products | [699 empty] | 1 | X
| Rules Registry | DEQ | [698 empty] | 1 | X
| INVITATION.TO.COMMENT (blank in folder 4) | [699 empty] | 1 | X
| RULES.REDLINE | [699 empty] | 1 | X
| NOTICE (blank in folder 4) | [699 empty] | 0 | X
| FEE.ANALYSIS (blank in folder 3) | [699 empty] | 0 | X
| STAFF.RPT.Temporary (blank in folder 6) | [699 empty] | 0 | X
| STAFF.RPT.Permanent (blank in folder 6) | [699 empty] | 1 | X
| Review/refine RESOURCES | [699 empty] | 1 | X | [5 empty] | Review/refine RESOURCES
| Review/refine CONSIDERATIONS | [699 empty] | 1 | X | [5 empty] | Review/refine CONSIDERATIONS
| Schedule recurring team meetings | [699 empty] | 1 | X
| Obtain rules and new numbers if needed |  | DE, SE. MV | 1 | -6 | 2013-07-16 | 2013-07-16 | [693 empty] | 1 |  | 2013-07-16 | 2013-07-16
| Save rules as PROPOSED.RULES |  | DE | 1 | -6 | 2013-07-16 | 2013-07-16 | [693 empty] | 1 |  | 2013-07-16 | 2013-07-16
| Work with SOS on any new division/rule numbers |  | DE,MV | 1 | -6 | 2013-07-16 | 2013-07-16 | [693 empty] | 1 |  | 2013-07-16 | 2013-07-16
| Identify land use rules | Q | SE,DE | 1 | -6 | 2013-07-16 | 2013-07-16 | [693 empty] | 1 |  | 2013-07-16 | 2013-07-16
| State Implementation Plan |  | SE,SIPCo | 53 | -17 | 2013-04-15 | 2013-07-01 | [693 empty] | 0 |  | 2013-04-15 | 2013-07-01
| Identify SIP rules |  | SE,SIPCo | 1 | -72 | 2013-04-15 | 2013-04-15 | [693 empty] | 0 |  | 2013-04-15 | 2013-04-15
| Subtask |  | SE,SIPCo | 1 | -72 | 2013-04-15 | 2013-04-15 | [693 empty] | 0 |  | 2013-04-15 | 2013-04-15
| Subtask |  | SE,SIPCo | 1 | -72 | 2013-04-15 | 2013-04-15 | [693 empty] | 0 |  | 2013-04-15 | 2013-04-15
| Subtask |  | SE,SIPCo | 1 | -72 | 2013-04-15 | 2013-04-15 | [693 empty] | 0 |  | 2013-04-15 | 2013-04-15
| Subtask |  | SE,SIPCo | 1 | -72 | 2013-04-15 | 2013-04-15 | [693 empty] | 0 |  | 2013-04-15 | 2013-04-15
| Task |  | SE,SIPCo | 1 | -72 | 2013-04-15 | 2013-04-15 | [693 empty] | 0 |  | 2013-04-15 | 2013-04-15
| Submit Notice to EPA - 45 day before 1st hearing |  | SE,SIPCo | 1 | -17 | 2013-07-01 | 2013-07-01 | [693 empty] | 0 |  | 2013-07-01 | 2013-07-01
[701 empty] | W | X
| 2-Advisory Committee NOT involved | [699 empty] | T | X
| Task |  | Owner | Task | Workdays | Start Task | End Task | [693 empty] | B | X
[5 empty] | 1 | 2013-04-05 | 2013-04-05 | [693 empty] | B | X | 2013-04-05 | 2013-04-05
[701 empty] | Y | X
| Review 0-Advisory Committee Learning Tools | Q | [698 empty] | 0 | X
| Review Public Involvement Resources | Q | Team | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Discuss meeting notice requirements | [699 empty] | 1
| Public Meeting Laws | i | Team |  | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| EQC quorum notification requirements | i | Team | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Oregon Transparency requirements | i | Team | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Develop ROSTER (blank in folder 4) |  | Team | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Identify potential meeting dates and venues |  | DS | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Draft optional AC.CHARTER |  | Team | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Develop committee communications | [699 empty] | 0 | X
| Draft optional AC.MESSAGE.MAP | Q | DE | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Draft AC.MEMBER.INVITE |  | DE, SC | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Draft optional AC.WEB.PAGE |  | DE | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Review drafts above |  | Team | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Generally, the core team does not need to save developmental drafts unless the document represents a significant shift in rulemaking direction. This applies to reviews or requests for input beyond the core team. For each document that had significant changes in any loop, save the document to Rules_Development using the same name followed by folder number and next higher version number. EXAMPLE: MESSAGE.MAP-2.01, MESSAGE.MAP-2.02... | [699 empty] | 0 | X
| Loop as needed | [699 empty] | 0 | X
| Approve charter and communications |  | LM or LA | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Initial voice contact |  | @ LA direction | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Add committee/EQC to GovDelivery | Q | DS |  | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Send invitation to potential committee members |  | @ LA direction | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Add meeting dates to DEQ public meetings | DEQ | Team | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Maintain optional committee web page |  | DE, DS | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Release unneeded venues |  | DS | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Meeting 1 |  |  |  |  | 2013-07-23 | 6:00 p.m. | [693 empty] | 0 | X
| Identify meeting roles |  | Team | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Meeting preparation | [699 empty] | 0 | X
| Draft AGENDA.07.23.13 | Q | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft AGENDA.mm.dd.yyyy.2.00
| Enter custom task here |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| START OPTION - Presentation | [699 empty] | 0 | X
| Draft optional PRESENTATION.07.23.13 | Q | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Involve stakeholder presenters, if any |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Approve optional presentation materials |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Post optional presentation materials on committee webpage |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| END OPTION | [699 empty] | 0 | X
| Draft COMMITTEE.NOTICE.07.23.13 |  | DE | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft COMMITTEE.NOTICE.mm.dd.yyyy.2.00
| Loop as needed | [699 empty] | 0 | X
| Send meeting notice (link to optional webpage) |  | DS | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Hold meeting |  | Team | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Draft MINUTES.07.23.13 | Q | DE | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft MINUTES.mm.dd.yyy.2.00
| Debrief conference |  | Team | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Meeting 2 |  |  |  |  | 2013-07-23 | 6:00 p.m. | [693 empty] | 0 | X
| Identify meeting roles |  | Team | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Meeting preparation | [699 empty] | 0 | X
| Draft AGENDA.07.23.13 | Q | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft AGENDA.mm.dd.yyyy.2.00
| Enter custom task here |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| START OPTION - Presentation | [699 empty] | 0 | X
| Draft optional PRESENTATION.07.23.13 | Q | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Involve stakeholder presenters, if any |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Approve optional presentation materials |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Post optional presentation materials on committee webpage |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| END OPTION | [699 empty] | 0 | X
| Draft COMMITTEE.NOTICE.07.23.13 |  | DE | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft COMMITTEE.NOTICE.mm.dd.yyyy.2.00
| Loop as needed | [699 empty] | 0 | X
| Send meeting notice (link to optional webpage) |  | DS | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Hold meeting |  | Team | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Draft MINUTES.07.23.13 | Q | DE | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft MINUTES.mm.dd.yyy.2.00
| Debrief conference |  | Team | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Meeting 3 |  |  |  |  | 2013-07-23 | 6:00 p.m. | [693 empty] | 0 | X
| Identify meeting roles |  | Team | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Meeting preparation | [699 empty] | 0 | X
| Draft AGENDA.07.23.13 | Q | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft AGENDA.mm.dd.yyyy.2.00
| Enter custom task here |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| START OPTION - Presentation | [699 empty] | 0 | X
| Draft optional PRESENTATION.07.23.13 | Q | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Involve stakeholder presenters, if any |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Approve optional presentation materials |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Post optional presentation materials on committee webpage |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| END OPTION | [699 empty] | 0 | X
| Draft COMMITTEE.NOTICE.07.23.13 |  | DE | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft COMMITTEE.NOTICE.mm.dd.yyyy.2.00
| Loop as needed | [699 empty] | 0 | X
| Send meeting notice (link to optional webpage) |  | DS | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Hold meeting |  | Team | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Draft MINUTES.07.23.13 | Q | DE | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft MINUTES.mm.dd.yyy.2.00
| Debrief conference |  | Team | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Meeting 4 |  |  |  |  | 2013-07-23 | 6:00 p.m. | [693 empty] | 0 | X
| Identify meeting roles |  | Team | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Meeting preparation | [699 empty] | 0 | X
| Draft AGENDA.07.23.13 | Q | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft AGENDA.mm.dd.yyyy.2.00
| Enter custom task here |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| START OPTION - Presentation | [699 empty] | 0 | X
| Draft optional PRESENTATION.07.23.13 | Q | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Involve stakeholder presenters, if any |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Approve optional presentation materials |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Post optional presentation materials on committee webpage |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| END OPTION | [699 empty] | 0 | X
| Draft COMMITTEE.NOTICE.07.23.13 |  | DE | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft COMMITTEE.NOTICE.mm.dd.yyyy.2.00
| Loop as needed | [699 empty] | 0 | X
| Send meeting notice (link to optional webpage) |  | DS | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Hold meeting |  | Team | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Draft MINUTES.07.23.13 | Q | DE | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft MINUTES.mm.dd.yyy.2.00
| Debrief conference |  | Team | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Meeting 5 |  |  |  |  | 2013-07-23 | 6:00 p.m. | [693 empty] | 0 | X
| Identify meeting roles |  | Team | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Meeting preparation | [699 empty] | 0 | X
| Draft AGENDA.07.23.13 | Q | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft AGENDA.mm.dd.yyyy.2.00
| Enter custom task here |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| START OPTION - Presentation | [699 empty] | 0 | X
| Draft optional PRESENTATION.07.23.13 | Q | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Involve stakeholder presenters, if any |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Approve optional presentation materials |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Post optional presentation materials on committee webpage |  | Assign | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| END OPTION | [699 empty] | 0 | X
| Draft COMMITTEE.NOTICE.07.23.13 |  | DE | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft COMMITTEE.NOTICE.mm.dd.yyyy.2.00
| Loop as needed | [699 empty] | 0 | X
| Send meeting notice (link to optional webpage) |  | DS | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Hold meeting |  | Team | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Draft MINUTES.07.23.13 | Q | DE | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft MINUTES.mm.dd.yyy.2.00
| Debrief conference |  | Team | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
X
[701 empty] | W | X
| 3-Fees Not Involved | [699 empty] | T | X | [5 empty] | 3-Fees Not Involved
| Task |  | Owner | Task | Workdays | Start Task | End Task | [693 empty] | B | X
[5 empty] | 71 | 2013-04-05 | 2013-07-18 | [693 empty] | B | X | 2013-04-05 | 2013-07-18
[701 empty] | Y | X
| Finalize CONSIDERATIONS¦7Financial |  | Team | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| No DAS involvement |  | Team | 68 | -7 | 2013-04-05 | 2013-07-15 | [693 empty] | 0 | X | 2013-04-05 | 2013-07-15 |  |  |  | No DAS involvement
| Draft Fee Notification Packet | [699 empty] | 0 | X | [5 empty] | a. FEE.ANALYSIS (blank in folder 3)
| a. FEE.ANALYSIS (blank in folder 3) | [699 empty] | 0 | X | [5 empty] | b. FEE.SUPPORT.DOCS
| b. FEE.SUPPORT.DOCS | [699 empty] | 0 | X
| Go to next step in 4-Public Notice | [699 empty] | 0 | X
| No DAS involvement |  | Team | 48 | -28 | 2013-04-05 | 2013-06-14 | [693 empty] | 0 |  | 2013-04-05 | 2013-06-14 |  |  |  | No DAS involvement
| Draft Fee Approval Packet | [699 empty] | 0 | X | [5 empty] | a. FEE.ANALYSIS (blank in folder 3)
| a. FEE.ANALYSIS (blank in folder 3) | [699 empty] | 0 | X | [5 empty] | b. FEE.SUPPORT.DOCS
| b. FEE.SUPPORT.DOCS | [699 empty] | 0 | X | [5 empty] | a. FEE.APPROVAL (link through FEE.ANALYSIS)
| a. FEE.APPROVAL (link through FEE.ANALYSIS) | [699 empty] | 0 | X | [5 empty] | b. FEE.DETAIL (link through FEE.ANALYSIS)
| b. FEE.DETAIL (link through FEE.ANALYSIS) | [699 empty] | 0 | X
| Finalize Fee Approval Packet |  | Team | 1 | -28 | 2013-06-14 | 2013-06-14 | [693 empty] | 0 |  | 2013-06-14 | 2013-06-14
| 1st approval loop |  | DE, Fiscal, LM | 1 | -28 | 2013-06-14 | 2013-06-14 | [693 empty] | 0 |  | 2013-06-14 | 2013-06-14
| 2nd approval loop |  | DE, Fiscal, LM | 1 | -28 | 2013-06-14 | 2013-06-14 | [693 empty] | 0 |  | 2013-06-14 | 2013-06-14
| 3rd approval loop |  | DE, Fiscal, LM | 1 | -28 | 2013-06-14 | 2013-06-14 | [693 empty] | 0 |  | 2013-06-14 | 2013-06-14
| Final approval loop |  | DE, Fiscal, LM | 1 | -28 | 2013-06-14 | 2013-06-14 | [693 empty] | 0 |  | 2013-06-14 | 2013-06-14
| Generally, the core team does not need to save developmental drafts unless the document represents a significant shift in rulemaking direction. This applies to reviews or requests for input beyond the core team. For each document that had significant changes in any loop, save the document to Rules_Development using the same name followed by folder number and next higher version number. EXAMPLE: FEE.ANALYSIS-3.01, FEE.ANALYSIS-3.02... | [699 empty] | 0 | X
| Loop as needed | [699 empty] | 0 | X
| START option - informal DAS review | [699 empty] | 0 | X
| Email draft packet for informal review |  | DE, Fiscal | 1 | -28 | 2013-06-14 | 2013-06-14 | [693 empty] | 0 |  | 2013-06-14 | 2013-06-14
| Address DAS concerns |  | Team, Fiscal | 1 | -28 | 2013-06-14 | 2013-06-14 | [693 empty] | 0 |  | 2013-06-14 | 2013-06-14
| END option | [699 empty] | 0 | X
| SUBMIT Fee Approval Packet | [699 empty] | 0 | X
| Send DAS.EMAILS.pdf |  | MV, Fiscal | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Send DAS.EMAILS.pdf
| Follow up for status |  | Fiscal staff | 1 | -72 | 2013-04-15 | 2013-04-15 | [693 empty] | 0 |  | 2013-04-15 | 2013-04-15
| Received DAS Fee Response |  | MV, Fiscal | 1 | -72 | 2013-04-15 | 2013-04-15 | [693 empty] | 0 |  | 2013-04-15 | 2013-04-15
| If denied, make changes needed for approval | [699 empty] | 0 | X
| 1st DAS loop |  | LM,DE,Fiscal | 1 | -72 | 2013-04-15 | 2013-04-15 | [693 empty] | 0 |  | 2013-04-15 | 2013-04-15
| 2nd DAS loop |  | LM,DE,Fiscal | 1 | -72 | 2013-04-15 | 2013-04-15 | [693 empty] | 0 |  | 2013-04-15 | 2013-04-15
| 3rd DAS loop |  | LM,DE,Fiscal | 1 | -72 | 2013-04-15 | 2013-04-15 | [693 empty] | 0 |  | 2013-04-15 | 2013-04-15
| Final DAS loop |  | LM,DE,Fiscal | 1 | -72 | 2013-04-15 | 2013-04-15 | [693 empty] | 0 |  | 2013-04-15 | 2013-04-15
| Generally, the core team does not need to save developmental drafts unless the document represents a significant shift in rulemaking direction. This applies to reviews or requests for input beyond the core team. For each document that had significant changes in any loop, save the document to Rules_Development using the same name followed by folder number and next higher version number. EXAMPLE: FEE.ANALYSIS-3.01, FEE.ANALYSIS-3.02... | [699 empty] | 0 | X
| Loop as needed | [699 empty] | 0 | X
| If approved, scan/file DAS.PART1.pdf |  | DS | 1 | -72 | 2013-04-15 | 2013-04-15 | [693 empty] | 0 |  | 2013-04-15 | 2013-04-15
[701 empty] | W | X
| 4-PublicNotice - not required for TEMPORARY rules (APA) | [699 empty] | T | X
| Task |  | Owner | Task | Workdays | Start Task | End Task | [693 empty] | B | X
[5 empty] | 1 | 2013-04-05 | 2013-04-05 | [693 empty] | B | X | 2013-04-05 | 2013-04-05
1900-04-20 | [700 empty] | Y | X
| No hearings planned | [699 empty] | 0 | X | [5 empty] | No hearings planned
| FIRST hearing |  | Enter city name |  |  | 2013-08-15 | 5 p.m. | [693 empty] | 0 | X | 2013-08-15
| 2nd hearing |  | Enter city name |  |  | 2013-08-15 | 5 p.m. | [693 empty] | 0 | X | 2013-08-15 | 5 p.m.
| 3rd hearing |  | Enter city name |  |  | 2013-08-15 | 5 p.m. | [693 empty] | 0 | X | 2013-08-15 | 5 p.m.
| 4th hearing |  | Enter city name |  |  | 2013-08-15 | 5 p.m. | [693 empty] | 0 | X | 2013-08-15 | 5 p.m.
| 5th hearing |  | Enter city name |  |  | 2013-08-15 | 5 p.m. | [693 empty] | 0 | X | 2013-08-15 | 5 p.m.
| 6th hearing |  | Enter city name |  |  | 2013-08-15 | 5 p.m. | [693 empty] | 0 | X | 2013-08-15 | 5 p.m.
| 7th hearing |  | Enter city name |  |  | 2013-08-15 | 5 p.m. | [693 empty] | 0 | X | 2013-08-15 | 5 p.m.
| LAST hearing |  | Enter city name |  |  | 2013-08-15 | 5 p.m. | [693 empty] | 0 | X | 2013-08-15 | 5 p.m.
| Reserve venues/equipment hearings |  | DS | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| START OPTION - program webpage | [699 empty] | 0 | X
| Draft program WEBPAGE |  | DE, Team | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Content contributions |  | SE, Team, SC | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| 1st loop for LM approval of webpage |  | LM | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| 2nd loop for LM approval of webpage |  | LM | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| 3rd loop for LM approval of webpage |  | LM | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Final loop for LM approval of webpage |  | LM | 1 | -78 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| END OPTION | [699 empty] | 0 | X
| Develop Notice Packet |  | DE | 48 | -28 | 2013-04-05 | 2013-06-14 | [693 empty] | 0 |  | 2013-04-05 | 2013-06-14
| Generally, the core team does not need to save developmental drafts unless the document represents a significant shift in rulemaking direction. This applies to reviews or requests for input beyond the core team. For each document that had significant changes in any loop, save the document to Rules_Development using the same name followed by folder number and next higher version number. EXAMPLE: WEBPAGE-4.01, WEBPAGE-4.02... | [699 empty] | 0 | X
| a. INVITATION.TO.COMMENT (blank in folder 4) |  | Team | 48 | -28 | 2013-04-05 | 2013-06-14 | [693 empty] | 0 |  | 2013-04-05 | 2013-06-14 |  |  |  | a. INVITATION.TO.COMMENT (blank in folder 4)
| b. PROPOSED.RULES | Q | DE | 48 | -28 | 2013-04-05 | 2013-06-14 | [693 empty] | 0 |  | 2013-04-05 | 2013-06-14 |  |  |  | b. PROPOSED.RULES
| Verify using latest rules |  | DE | 48 | -28 | 2013-04-05 | 2013-06-14 | [693 empty] | 0 |  | 2013-04-05 | 2013-06-14
| c. NOTICE (blank in folder 4) |  | Team | 48 | -28 | 2013-04-05 | 2013-06-14 | [693 empty] | 0 |  | 2013-04-05 | 2013-06-14
| Overview | [699 empty] | 0 | X
| Statement of need | [699 empty] | 0 | X
| Federal relationships | [699 empty] | 0 | X
| Rules affected, authorities, supporting docs | [699 empty] | 0 | X
| Statement of fiscal impact | [699 empty] | 0 | X
| Integrate FEE.ANALYSIS | [699 empty] | 0 | X | [5 empty] | Delete Fee section
| Land use | [699 empty] | 0 | X
| d. SUPPORTING.DOCS |  | Team | 48 | -28 | 2013-04-05 | 2013-06-14 | [693 empty] | 0 |  | 2013-04-05 | 2013-06-14 |  |  |  | d. SUPPORTING.DOCS
| SIP not involved |  | SIPCo | 48 | -28 | 2013-04-05 | 2013-06-14 | [693 empty] | 0 |  | 2013-04-05 | 2013-06-14 |  |  |  | SIP not involved
| Draft ##AD if needed | Q | Team | 48 | -28 | 2013-04-05 | 2013-06-14 | [693 empty] | 0 |  | 2013-04-05 | 2013-06-14 |  |  |  | Draft ##AD if needed
| Identify hearings officers |  | DE | 48 | -28 | 2013-04-05 | 2013-06-14 | [693 empty] | 0 |  | 2013-04-05 | 2013-06-14 |  |  |  | Display advertisements not involved
| Get Notice Packet recommendations from RESOURCES |  | DE | 48 | -28 | 2013-04-05 | 2013-06-14 | [693 empty] | 0 |  | 2013-04-05 | 2013-06-14
| Advisory Committee-Statement of fiscal impact | [699 empty] | 0 | X | [5 empty] | Proposal, invitation to comment, notice
| Budget-Statement of fiscal impact | [699 empty] | 0 | X | [5 empty] | Fiscal impact statement
| SIP Coordinator-as needed for b. & e. above | [699 empty] | 0 | X | [5 empty] | Proposal, invitation to comment, notice
| DOJ-as needed for b. and c. above | [699 empty] | 0 | X | [5 empty] | Proposal, invitation to comment, notice
| ARC and OCO-for entire Notice Packet | [699 empty] | 0 | X
| 1st loop for LM approval of packet |  | LM | 1 | -28 | 2013-06-14 | 2013-06-14 | [693 empty] | 0 |  | 2013-06-14 | 2013-06-14
| 2nd loop for LM approval of packet |  | LM | 1 | -28 | 2013-06-14 | 2013-06-14 | [693 empty] | 0 |  | 2013-06-14 | 2013-06-14
| 3rd loop for LM approval of packet |  | LM | 1 | -28 | 2013-06-14 | 2013-06-14 | [693 empty] | 0 |  | 2013-06-14 | 2013-06-14
| Final loop for LM approval of packet |  | LM | 1 | -28 | 2013-06-14 | 2013-06-14 | [693 empty] | 0 |  | 2013-06-14 | 2013-06-14
| Generally, the core team does not need to save developmental drafts unless the document represents a significant shift in rulemaking direction. This applies to reviews or requests for input beyond the core team. For each document that had significant changes in any loop, save the document to Rules_Development using the same name followed by folder number and next higher version number. EXAMPLE: NOTICE-4.01, NOTICE-4.0,... | [699 empty] | 0 | X
| Loop as needed | [699 empty] | 0 | X
| LA briefing meeting |  | Team, LA | 1 | -28 | 2013-06-14 | 2013-06-14 | [693 empty] | 0 |  | 2013-06-14 | 2013-06-14
| OPEN preview period for Notice Packet |  | LA, DE | 1 | -28 | 2013-06-14 | 2013-06-14 | [693 empty] | 0 |  | 2013-06-14 | 2013-06-14
| Notify EMT | [699 empty] | 0 | X
| Notify DEQ contributing RESOURCES | [699 empty] | 0 | X
| CLOSE Notice Packet preview period |  | DE | 1 | -23 | 2013-06-21 | 2013-06-21 | [693 empty] | 0 |  | 2013-06-21 | 2013-06-21
| Decide how to address any feedback |  | Team | 12 | -11 | 2013-06-21 | 2013-07-09 | [693 empty] | 0 |  | 2013-06-21 | 2013-07-09
| Modify notice documents as needed |  | DE | 12 | -11 | 2013-06-21 | 2013-07-09 | [693 empty] | 0 |  | 2013-06-21 | 2013-07-09
| Obtain BUDGET.REVIEW.FISCAL |  | DE | 3 | -9 | 2013-07-09 | 2013-07-11 | [693 empty] | 0 |  | 2013-07-09 | 2013-07-11 |  |  |  | Obtain BUDGET-REVIEW.FISCAL.4.00
| Verify compilation of PROPOSED.RULES |  | DE | 1 | -11 | 2013-07-09 | 2013-07-09 | [693 empty] | 0 |  | 2013-07-09 | 2013-07-09 |  |  |  | Verify compilation of PROPOSED.RULES
| Obtain managers approval of Notice Packet |  | DE,LM,LA | 3 | -9 | 2013-07-09 | 2013-07-11 | [693 empty] | 0 |  | 2013-07-09 | 2013-07-11
| Notify ARC Notice Packet approved |  | DE | 1 | -9 | 2013-07-11 | 2013-07-11 | [693 empty] | 0 |  | 2013-07-11 | 2013-07-11
| Submit SIP & DOJ approval to EPA |  | SIPCo | 1 | -9 | 2013-07-11 | 2013-07-11 | [693 empty] | 0 |  | 2013-07-11 | 2013-07-11
| Perform final plain English review if changes |  | ARC/SC | 3 | -7 | 2013-07-11 | 2013-07-15 | [693 empty] | 0 |  | 2013-07-11 | 2013-07-15
| Noticing sequence | [699 empty] | 0 | X
| ARC Actions - Submit/save official notifications: | Q | MV | 14 | 8 | 2013-07-15 | 2013-08-01 | [693 empty] | 0 |  | 2013-07-15 | 2013-08-01 |  |  |  | Notice not involved
| SOS.EMAIL.PROOF | [699 empty] | 0 | X | [5 empty] | SOS.EMAIL.PROOF
| SOS.NOTICE.PROOF | [699 empty] | 0 | X | [5 empty] | SOS.NOTICE.PROOF
| SOS.FISCAL.PROOF | [699 empty] | 0 | X | [5 empty] | SOS.FISCAL.PROOF
| SOS.HOUSING.COSTS | [699 empty] | 0 | X | [5 empty] | SOS.HOUSING.COSTS
| LC.NOTICE | [699 empty] | 0 | X | [5 empty] | LC.NOTICE
| No DAS involvement | [699 empty] | 0 | X | [5 empty] | LC.NOTICE.PROOF
| DAS.EXEMPT.EMAIL | [699 empty] | 0 | X | [5 empty] | DAS.EXEMPT.EMAIL
| DAS.EXEMPT.EMAIL.PROOF | [699 empty] | 0 | X | [5 empty] | DAS.EXEMPT.EMAIL.PROOF
| Design Support Responsibility |  | DS, webrep | 1 | -7 | 2013-07-15 | 2013-07-15 | [693 empty] | 0 |  | 2013-07-15 | 2013-07-15 |  |  |  | No DAS involvement
| Post Notice Packet to Rules Registry | DEQ | [698 empty] | 0 | X
| Test public comment box | [699 empty] | 0 | X
| Add hearing dates to DEQ meeting calendar | DEQ | [698 empty] | 0 | X
| Notify EQC Assistant of target EQC date | [699 empty] | 0 | X
| GovDelivery, including advisory committee | [699 empty] | 0 | X
| GOV.DELIVERY.CONTENT" | [699 empty] | 0 | X | [5 empty] | GOV.DELIVERY.CONTENT"
| Save AGENCY.MAILING.LIST | [699 empty] | 0 | X | [5 empty] | Save AGENCY.MAILING.LIST
| Save PROOF.OF.DELIVERY | [699 empty] | 0 | X | [5 empty] | Save PROOF.OF.DELIVERY
| Design Expert Responsibility |  | DE, Fiscal | 1 | -7 | 2013-07-15 | 2013-07-15 | [693 empty] | 0 |  | 2013-07-15 | 2013-07-15
| Send KEY.LEG.NOTICE | [699 empty] | 0 | X | [5 empty] | Send KEY.LEG.NOTICE
| Save KEY.LEG.PROOF | [699 empty] | 0 | X | [5 empty] | Save KEY.LEG.PROOF
| Publish in local newspaper if required | [699 empty] | 0 | X
| Save ##PRINT.PROOF | [699 empty] | 0 | X | [5 empty] | Save ##PRINT.PROOF
| Verify notice published accurately in Bulletin | [699 empty] | 0 | X
| Save BULLETIN.PROOF | [699 empty] | 0 | X | [5 empty] | Save BULLETIN.PROOF
[701 empty] | W | X
| 5-Public comment is not involved. | [699 empty] | T | X | [5 empty] | 5-Public comment is not involved.
| Task |  |  | Task | Workdays | Start Task | End Task | [693 empty] | B | X
[5 empty] | 54 | 2013-06-25 | 2013-09-10 | [693 empty] | B | X | 2013-06-25 | 2013-09-10
[701 empty] | Y | X
| Design Support Responsibilities |  | DS | 37 | 18 | 2013-06-25 | 2013-08-15 | [693 empty] | 0 |  | 2013-06-25 | 2013-08-15
| Verify venues and equipment reservations | [699 empty] | 0 | X
| Gather supplies | Q | [698 empty] | 0 | X
| Design Team Responsibilities |  | Team | 37 | 18 | 2013-06-25 | 2013-08-15 | [693 empty] | 0 |  | 2013-06-25 | 2013-08-15
| START OPTION - information meeting | [699 empty] | 0 | X | [5 empty] | Develop HEARING.TEXT
| Develop HEARING.TEXT | [699 empty] | 0 | X | [5 empty] | Develop HEARING.MESSAGE.MAP
| Develop HEARING.MESSAGE.MAP | Q | [698 empty] | 0 | X | [5 empty] | Develop HEARING.PRESENTATION
| Develop HEARING.PRESENTATION | [699 empty] | 0 | X
| Practice presentation | [699 empty] | 0 | X
| Make presentation adjustments |  | Team | 1 | -21 | 2013-06-25 | 2013-06-25 | [693 empty] | 0 |  | 2013-06-25 | 2013-06-25
| 1st loop |  | Team | 1 | -21 | 2013-06-25 | 2013-06-25 | [693 empty] | 0 |  | 2013-06-25 | 2013-06-25
| 2nd loop |  | Team | 1 | -21 | 2013-06-25 | 2013-06-25 | [693 empty] | 0 |  | 2013-06-25 | 2013-06-25
| 3rd loop |  | Team | 1 | -21 | 2013-06-25 | 2013-06-25 | [693 empty] | 0 |  | 2013-06-25 | 2013-06-25
| Final loop |  | Team | 1 | -21 | 2013-06-25 | 2013-06-25 | [693 empty] | 0 |  | 2013-06-25 | 2013-06-25
| Generally, the core team does not need to save developmental drafts unless the document represents a significant shift in rulemaking direction. This applies to reviews or requests for input beyond the core team. For each document that had significant changes in any loop, save the document to Rules_Development using the same name followed by folder number and next higher version number. EXAMPLE: HEARING.TEXT-5.01, HEARING.TEXT-5.02... | [699 empty] | 0 | X
| Loop as needed | [699 empty] | 0 | X
| Approve presentation |  | LM | 1 | -21 | 2013-06-25 | 2013-06-25 | [693 empty] | 0 |  | 2013-06-25 | 2013-06-25
| END OPTION | [699 empty] | 0 | X
| No hearings planned | [699 empty] | 0 | X | [5 empty] | No hearings planned
| Enter city name hearing |  | Team, PO | 1 | 18 | 2013-08-15 | 2013-08-15 | [693 empty] | 0
| Enter city name hearing |  | Team, PO | 1 | 18 | 2013-08-15 | 2013-08-15 | [693 empty] | 0
| Enter city name hearing |  | Team, PO | 1 | 18 | 2013-08-15 | 2013-08-15 | [693 empty] | 0
| Enter city name hearing |  | Team, PO | 1 | 18 | 2013-08-15 | 2013-08-15 | [693 empty] | 0
| Enter city name hearing |  | Team, PO | 1 | 18 | 2013-08-15 | 2013-08-15 | [693 empty] | 0
| Enter city name hearing |  | Team, PO | 1 | 18 | 2013-08-15 | 2013-08-15 | [693 empty] | 0
| Enter city name hearing |  | Team, PO | 1 | 18 | 2013-08-15 | 2013-08-15 | [693 empty] | 0
| Enter city name hearing |  | Team, PO | 1 | 18 | 2013-08-15 | 2013-08-15 | [693 empty] | 0
| Add info to COMMENTS |  | PO | -91 | -78 | 2013-08-15 | 2013-04-05 | [693 empty] | 0 |  | 2013-08-15 | 2013-04-05 |  |  |  | Add info to COMMENTS
` | Add PO report to STAFF.RPT |  | PO | -91 | -78 | 2013-08-15 | 2013-04-05 | [693 empty] | 0 |  | 2013-08-15 | 2013-04-05 |  |  |  | Add PO report to STAFF.RPT
| CLOSE PUBLIC COMMENT | [5 empty] | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05
| Design Support (DS) Responsibility | [699 empty] | 0 | X
| Enter data into COMMENTS | [699 empty] | 0 | X | [5 empty] | Enter data into COMMENTS
| Steps 1, Step 2 worksheets |  | DS | 41 | 36 | 2013-07-15 | 2013-09-10 | [693 empty] | 0 |  | 2013-07-15 | 2013-09-10
| Scan/Link COMMENTS.ID###.pdf |  | DS | 26 | 36 | 2013-08-05 | 2013-09-10 | [693 empty] | 0 |  | 2013-08-05 | 2013-09-10 |  |  |  | Scan/Link COMMENTS.ID###.pdf
| Design Team Responsibility | [699 empty] | 0 | X
| Develop COMMENTS | [699 empty] | 0 | X | [5 empty] | Develop COMMENTS
| Enter comments |  | Team | 26 | 36 | 2013-08-05 | 2013-09-10 | [693 empty] | 0 |  | 2013-08-05 | 2013-09-10
| Develop categories of responses |  | Team | 26 | 36 | 2013-08-05 | 2013-09-10 | [693 empty] | 0 |  | 2013-08-05 | 2013-09-10
| Finalize DEQ response to comments |  | Team | 26 | 36 | 2013-08-05 | 2013-09-10 | [693 empty] | 0 |  | 2013-08-05 | 2013-09-10
| 1st loop for LM approval of packet |  | LM | 26 | 36 | 2013-08-05 | 2013-09-10 | [693 empty] | 0 |  | 2013-08-05 | 2013-09-10
| 2nd loop for LM approval of packet |  | LM | 26 | 36 | 2013-08-05 | 2013-09-10 | [693 empty] | 0 |  | 2013-08-05 | 2013-09-10
| 3rd loop for LM approval of packet |  | LM | 26 | 36 | 2013-08-05 | 2013-09-10 | [693 empty] | 0 |  | 2013-08-05 | 2013-09-10
| Final loop for LM approval of packet |  | LM | 26 | 36 | 2013-08-05 | 2013-09-10 | [693 empty] | 0 |  | 2013-08-05 | 2013-09-10
| Generally, the core team does not need to save developmental drafts unless the document represents a significant shift in rulemaking direction. This applies to reviews or requests for input beyond the core team. For each document that had significant changes in any loop, save the document to Rules_Development using the same name followed by folder number and next higher version number. EXAMPLE: COMMENTS-5.01, COMMENTs-5.02... | [699 empty] | 0 | X
| Loop as needed | [699 empty] | 0 | X
| Close comment box in Outlook |  | DS | 1 | 36 | 2013-09-10 | 2013-09-10 | [693 empty] | 0 |  | 2013-09-10 | 2013-09-10
[701 empty] | W | X
| 6-EQC Preparation | [699 empty] | T | X
| Task |  | Owner | Task | Workdays | Start Task | End Task | [693 empty] | B | X
[5 empty] | 67 | 2013-07-15 | 2013-10-16 | [693 empty] | B | X | 2013-07-15 | 2013-10-16
[701 empty] | Y | X
| Design Expert (DE) Responsibility |  | DE | 41 | 36 | 2013-07-15 | 2013-09-10 | [693 empty] | 1 |  | 2013-07-15 | 2013-09-10
` | STAFF.RPT.Temporary (blank in folder 6) | [699 empty] | 1 |  |  |  |  | STAFF.RPT.Temporary (blank in folder 6)
| Select EQC recommendation in staff report | [699 empty] | 1 | X
| Integrate NOTICE into staff report | [699 empty] | 0 | X |  |  |  | Integrate NOTICE into STAFF.RPT.Temporary
| Verify PROPOSED.RULES current compilation | DEQ | [698 empty] | 1 | X |  |  |  | Verify PROPOSED.RULES.6.01
| DO NOT MODIFY reviewed/executed sections: | [699 empty] | 0 | X
| Statement of need | [699 empty] | 0 | X
| Federal relationships | [699 empty] | 0 | X
| Fiscal impact statement | [699 empty] | 0 | X
| Fees | [699 empty] | 0 | X
| Land use | [699 empty] | 0 | X
| Design Team (DT) Responsibility |  | Team | 41 | 36 | 2013-07-15 | 2013-09-10 | [693 empty] | 1 |  | 2013-07-15 | 2013-09-10
| Finalize following sections in STAFF.RPT.Temporary | [699 empty] | 1 | X |  |  |  | Finalize following sections in STAFF.RPT.Temporary
| Overview | [699 empty] | 1 | X
| Rules affected, authorities, supporting docs | [699 empty] | 1 | X
| Implementation | [699 empty] | 1 | X
| Public involvement | [699 empty] | 1 | X
| Summary of comments and DEQ responses | [699 empty] | 0 | X
| Commenters | [699 empty] | 0 | X
| Approve as finalized | [699 empty] | 1 | X
| Finalize EQC Packet: |  | DE | 41 | 36 | 2013-07-15 | 2013-09-10 | [693 empty] | 1 |  | 2013-07-15 | 2013-09-10 |  | STAFF.RPT.Temporary
| STAFF.RPT.Temporary | [699 empty] | 1 | X |  |  |  | INVITATION.TO.COMMENT
| PROPOSED RULES | [699 empty] | 1 | X |  |  |  | PROPOSED RULES
| STATE IMPLEMENTATION PLAN | [699 empty] | 0 | X |  |  |  | STATE IMPLEMENTATION PLAN
| Optional SUPPORTING.DOCS | [699 empty] | 1 | X |  |  |  | Optional SUPPORTING.DOCS
| Review/approve EQC Packet | [699 empty] | 1 | X
| 1st loop for packet approval |  | Team, LM, LA | 6 | 6 | 2013-07-23 | 2013-07-30 | [693 empty] | 1 |  | 2013-07-15 | 2013-09-10
| 2nd loop for packet approval |  | Team, LM, LA | 6 | 13 | 2013-08-01 | 2013-08-08 | [693 empty] | 1 |  | 2013-07-30 | 2013-09-10
| 3rd loop for packet approval |  | Team, LM, LA | 6 | 13 | 2013-08-01 | 2013-08-08 | [693 empty] | 1 |  | 2013-08-08 | 2013-09-10
| Final loop for packet approval |  | Team, LM, LA | 6 | 13 | 2013-08-01 | 2013-08-08 | [693 empty] | 1 |  | 2013-08-08 | 2013-09-10
| Generally, the core team does not need to save developmental drafts unless the document represents a significant shift in rulemaking direction. This applies to reviews or requests for input beyond the core team. For each document that had significant changes in any loop, save the document to Rules_Development using the same name followed by folder number and next higher version number. EXAMPLE: STAFF.RPT.Permanent-6.01,STAFF.RPT.Permanent-6.02... | [699 empty] | 1 | X
| Loop as needed | [699 empty] | 1 | X
| Approve EQC PACKET |  | LM | 23 | 36 | 2013-08-08 | 2013-09-10 | [693 empty] | 1 |  | 2013-08-08 | 2013-09-10
| SUBMIT EQC PACKET |  | DE | 1 | 36 | 2013-09-10 | 2013-09-10 | [693 empty] | 1 |  | 2013-09-10 | 2013-09-10
| Final OCO plain English review |  | SC | 5 | 40 | 2013-09-10 | 2013-09-16 | [693 empty] | 1 |  | 2013-09-10 | 2013-09-16
| Develop EQC presentation |  | DE, Team | 66 | 61 | 2013-07-15 | 2013-10-15 | [693 empty] | 1 |  | 2013-07-15 | 2013-10-15
| START OPTION | [699 empty] | 1 | X
| Practice presentation |  | Team | 1 | 61 | 2013-10-15 | 2013-10-15 | [693 empty] | 1 |  | 2013-10-15 | 2013-10-15
| Make presentation adjustments |  | DE | 1 | 61 | 2013-10-15 | 2013-10-15 | [693 empty] | 1 |  | 2013-10-15 | 2013-10-15
| Loop as needed | [699 empty] | 1 | X
| END OPTION | [699 empty] | 1 | X
| ATTEND EQC MEETING | [5 empty] | 2013-10-16 | [693 empty] | 1 |  | 2013-10-16 | 2013-10-16
[701 empty] | W | X
| 7-Post EQC | [699 empty] | T | X
| Task |  | Owner | Task | Workdays | Start Task | End Task | [693 empty] | B | X
[5 empty] | 1 | 2013-09-10 | 2013-12-16 | [693 empty] | B | X | 2013-09-10 | 2013-12-16
[701 empty] | Y | X
| Design Expert Responsibility | [699 empty] | 0 | X
| Prepare documents and notify ARC when done |  | DE,SE | 1 | 62 | 2013-10-16 | 2013-10-16 | [693 empty] | 1 |  | 2013-10-16 | 2013-10-16
| EQC.RULES.10.16.2013 | [699 empty] | 1 | X | [5 empty] | EQC.RULES.10.16.2013
| EQC.REDLINE.10.16.2013 | [699 empty] | 1 | X | [5 empty] | EQC.REDLINE.10.16.2013
| 340-###-###.TABLE##-## | [699 empty] | 1 | X | [5 empty] | 340-###-###.TABLE##-##
| EQC.ACTION | [699 empty] | 1 | X | [5 empty] | EQC.ACTION
| Fees not involved |  | DE, Fiscal staff | 48 | -27 | 2013-04-05 | 2013-06-15 | [693 empty] | 0 |  | 2013-04-05 | 2013-06-15 |  |  |  | Fees not involved
| a. SIGNED.PART.1 | [699 empty] | 0 | X | [5 empty] | a. SIGNED.PART.1
| b. FEE.EXCERPT.FROM.RULE | [699 empty] | 0 | X | [5 empty] | b. FEE.EXCERPT.FROM.RULE
| PROOF.OF.DAS.SUBMITTAL | [699 empty] | 0 | X | [5 empty] | PROOF.OF.DAS.SUBMITTAL
| Optional STAKEHOLDER.NOTIFICATION |  | Team | 1 | 105 | 2013-12-16 | 2013-12-16 | [693 empty] | 1 |  | 2013-12-16 | 2013-12-16 |  |  |  | Optional STAKEHOLDER.NOTIFICATION
| Optional LEGISLATOR.NOTICE |  | LA | 1 | 105 | 2013-12-16 | 2013-12-16 | [693 empty] | 1 |  | 2013-12-16 | 2013-12-16 |  |  |  | Optional LEGISLATOR.NOTICE
| EPA.SIP |  | LA | 1 | 105 | 2013-12-16 | 2013-12-16 | [693 empty] | 0 |  | 2013-12-16 | 2013-12-16 |  |  |  | Optional LEGISLATOR.NOTICE
| AC.THANK.YOU | Q | Team | 1 | 105 | 2013-12-16 | 2013-12-16 | [693 empty] | 0 |  | 2013-12-16 | 2013-12-16 |  |  |  | COMMITTEE.THANK.YOU
| AC.SURVEY |  | Team | 1 | 105 | 2013-12-16 | 2013-12-16 | [693 empty] | 0 |  | 2013-12-16 | 2013-12-16 |  |  |  | COMMITTEE.SURVEY
| YourName.EMAILS |  | Team | 1 | 105 | 2013-12-16 | 2013-12-16 | [693 empty] | 1 |  | 2013-12-16 | 2013-12-16 |  |  |  | YourName.EMAILS
| EVALUATION |  | Team | 1 | 105 | 2013-12-16 | 2013-12-16 | [693 empty] | 1 |  | 2013-12-16 | 2013-12-16 |  |  |  | EVALUATION
| Agency Rules Coordinator Responsibility | [699 empty] | 1 | X
| Submit filing |  | MV | 1 | 64 | 2013-10-18 | 2013-10-18 | [693 empty] | 1 |  | 2013-10-18 | 2013-10-18
| EFFECTIVE DATE |  |  | 1 | 64 | 2013-10-18 | 2013-10-18 | [693 empty] | 1 |  | 2013-10-18 | 2013-10-18
| Save as PROOF.OF.SOS.FILING | [699 empty] | 1 | X | [5 empty] | Save as PROOF.OF.SOS.FILING
| Save as PROOF.OF.LC.SUBMITTAL | [699 empty] | 1 | X | [5 empty] | Save as LC.SHUTTLE.PROOF
| No DAS involvement |  | MV | 108 | 36 | 2013-04-05 | 2013-09-10 | [693 empty] | 0 |  | 2013-04-05 | 2013-09-10 |  |  |  | No DAS involvement
| a. FEE.EXCERPT.FROM.RULE | [699 empty] | 0 | X | [5 empty] | a. FEE.EXCERPT.FROM.RULE
| b. FEE.EXEMPT.EMAIL | [699 empty] | 0 | X | [5 empty] | b. FEE.EXEMPT.EMAIL
| c. DAS.SHUTTLE.PROOF | [699 empty] | 0 | X | [5 empty] | c. DAS.SHUTTLE.PROOF
| Design Support Responsibility | [699 empty] | 1 | X
| Lead archival process |  |  | 1 | 105 | 2013-12-16 | 2013-12-16 | [693 empty] | 1 |  | 2013-12-16 | 2013-12-16
[7 empty] | $B$429 | [694 empty] | X
B
Formulas:
Closed = IF(WEEKDAY(CV6)=2,[Closed, row below],"")
Closed = IF(WEEKDAY(OK6)=2,[Closed, row below],"")
Workday = IF(WEEKDAY(DQ6)=2,[Workday, row below],"")
Workday = IF(WEEKDAY(QH6)=2,[Workday, row below],"")
Weekend = IF(WEEKDAY(GW6)=2,[Weekend, row below],"")
Weekend = IF(WEEKDAY(YX6)=2,[Weekend, row below],"")
Workdays = NETWORKDAYS(TODAY(),[End Task])
Workdays = NETWORKDAYS([Start Task],S.BANNER.AdvisoryCommitteeEnd,S.DDL_DEQClosed)
This Task = NETWORKDAYS([Start Task],[End Task],S.DDL_DEQClosed)
mm/dd/yy
Subject
Your name
Your message
DEQ Closed
To restore any cell under columns G or H to default, place cursor in cell then enter "=AA" followed by the cell address. EXAMPLE: =AAH13 would restore the default EQC meeting.

## ConditionalFormat (hidden)
|  | Example | Calculation | Applies to | Last row
Column I: Section Separator codes
T | Section title | White on Teal | =IF($AAE4="T",TRUE) | =$B$4:$ZZ$474
Y | Highlight for section title | Teal on Yellow | =IF($AAE4="Y",TRUE) | "
W |  | White on white | =IF($AAE4="W",TRUE) | "
0 OR 1 | Indicates task involved/not involved | White on white | =IF($AAE4=0,TRUE) | "
Office Closure |  | See DDL worksheet | S.DDL_DEQClosed is the "holiday" table in WORKDAY function
|  | Office Closure date | =IF(WORKDAY($G20-1,1,S.DDL_DEQClosed)<>$G20,TRUE) | $G$20:$G$480 (or last row)
|  | Office Closure date | =IF(WORKDAY($H20-1,1,S.DDL_DEQClosed)<>$H20,TRUE) | $H$20:$H$480 (or last row)
|  | Date has past | =IF(WORKDAY($G10-1,1,S.DDL_DEQClosed)<>$G10,TRUE) | $G$10:$G$480 (or last row)
|  | " | =IF(WORKDAY($H10-1,1,S.DDL_DEQClosed)<>$H10,TRUE) | $H$10:$H$480 (or last row)
Gantt
| An 'X' in $J10 identifies the row as for Gantt to format | Workday | =AND($J10<>"X",$G10<=L$7,$H10>=K$7) | $K10:$AHC$450
|  | Weekend | =IF(OR(WEEKDAY(K$7)=1,WEEKDAY(K$7)=7),TRUE) | $K10:$AHC$450
|  | Closed | =IF(ISERROR(VLOOKUP(K$7,S.DDL_DEQClosed,1,FALSE)),0,1) | $K10:$AHC$450
S.LastCellGantt
s.LastCellschedule