## DDLs (hidden)
DDLs called from ScheduleTasks
1 | 2 | 3 | 4 | 5 | 6
DDL_EQCMeeting | EQCStaffRptDue | EQCMaterialsDue | Days to next | Next | Last
2013-03-20 | 2013-02-11 | 2013-03-13 | 91 | 2013-06-19 | 2012-12-16
2013-06-19 | 2013-05-10 | 2013-06-12 | 63 | 2013-08-21 | 2013-03-20
2013-08-21 | 2013-07-16 | 2013-08-14 | 56 | 2013-10-16 | 2013-06-19
2013-10-16 | 2013-09-10 | 2013-10-09 | 56 | 2013-12-11 | 2013-08-21
2013-12-11 | 2013-11-01 | 2013-12-04 | 98 | 2014-03-19 | 2013-10-16
2014-03-19 | 2014-02-06 | 2014-03-07 | 91 | 2014-06-18 | 2013-12-11
2014-06-18 | 2014-05-08 | 2014-06-06 | 63 | 2014-08-20 | 2014-03-19
2014-08-20 | 2014-07-10 | 2014-08-08 | 56 | 2014-10-15 | 2014-06-18
2014-10-15 | 2014-09-04 | 2014-10-03 | 56 | 2014-12-10 | 2014-08-20
2014-12-10 | 2014-10-30 | 2014-11-28 | 98 | 2015-03-18 | 2014-10-15
2015-03-18 | 2015-02-05 | 2015-03-06 | 92 | 2015-06-18 | 2014-12-10
2015-06-18 | 2015-05-08 | 2015-06-08 | 63 | 2015-08-20 | 2015-03-18
2015-08-20 | 2015-07-10 | 2015-08-10 | 63 | 2015-10-22 | 2015-06-18
2015-10-22 | 2015-09-11 | 2015-10-12 | 56 | 2015-12-17 | 2015-08-20
2015-12-17 | 2015-11-06 | 2015-12-07 | 90 | 2016-03-16 | 2015-10-22
2016-03-16 | 2016-02-04 | 2016-03-04 | 91 | 2016-06-15 | 2015-12-17
2016-06-15 | 2016-05-05 | 2016-06-03 | 91
http://www.leg.state.or.us/ors/187.html
DEQClosed | [5 empty] | LEGAL HOLIDAYS 187.010 Legal holidays; acts deferred to next business day; effect on labor agreements. (1) The following days are legal holidays in this state: (a) Each Sunday. (b) New Year’s Day on January 1. (c) Martin Luther King, Jr.’s Birthday on the third Monday in January. (d) Presidents Day, for the purpose of commemorating Presidents Washington and Lincoln, on the third Monday in February. (e) Memorial Day on the last Monday in May. (f) Independence Day on July 4. (g) Labor Day on the first Monday in September. (h) Veterans Day on November 11. (i) Thanksgiving Day on the fourth Thursday in November. (j) Christmas Day on December 25. (2) Each time a holiday, other than Sunday, listed in subsection (1) of this section falls on Sunday, the succeeding Monday shall be a legal holiday. Each time a holiday listed in subsection (1) of this section falls on Saturday, the preceding Friday shall be a legal holiday. (3) Any act authorized, required or permitted to be performed on a holiday as designated in this section may be performed on the next succeeding business day; and no liability or loss of rights of any kind shall result from such delay. (4) In enumerating legal holidays in subsection (1) of this section, the Legislative Assembly does not intend to limit or otherwise affect public or private collective bargaining or collective bargaining agreements. [Amended by 1955 c.4 §1; 1969 c.455 §1; 1973 c.51 §1; 1975 c.633 §1; 1977 c.135 §1; 1977 c.321 §1; 1985 c.518 §1] 187.020 Additional legal holidays. In addition to those specified in ORS 187.010, the following days are legal holidays in this state: (1) Every day appointed by the Governor as a holiday. (2) Every day appointed by the President of the United States as a day of mourning, rejoicing or other special observance only when the Governor also appoints that day as a holiday. [Amended by 1969 c.455 §2; 1975 c.633 §2; 1977 c.135 §2; 1977 c.321 §2; 1985 c.518 §2]
2013-01-01 | New Year | 2013-01-01
2013-01-18 | furlough | 2013-01-18
2013-01-21 | MLK Jr. | 2013-01-21
2013-02-18 | Presidents | 2013-02-18
2013-04-19 | furlough | 2013-04-19
2013-05-24 | furlough | 2013-05-24
2013-05-27 | Memorial | 2013-05-27
2013-07-04 | Independence | 2013-07-04
2013-09-02 | Labor | 2013-09-02
2013-11-11 | Veterans | 2013-11-11
2013-11-28 | Thanksgiving | 2013-11-28
2013-12-25 | Christmas | 2013-12-25
2014-01-01 | New Year | 2014-01-01
2014-01-20 | MLK Jr. | 2014-01-20
2014-02-17 | Presidents | 2014-02-17
2014-05-26 | Memorial | 2014-05-26
2014-07-04 | Independence | 2014-07-04
2014-09-02 | Labor | 2014-09-02
2014-11-11 | Veterans | 2014-11-11
2014-11-27 | Thanksgiving | 2014-11-27
2014-12-25 | Christmas | 2014-12-25
2015-01-01 | New Year | 2015-01-01
2015-01-19 | MLK Jr. | 2015-01-19
2015-02-16 | Presidents | 2015-02-16
2015-05-25 | Memorial | 2015-05-25
2015-07-03 | Independence | 2015-07-03
2015-09-07 | Labor | 2015-09-07
2015-11-11 | Veterans | 2015-11-11
2015-11-26 | Thanksgiving | 2015-11-26
2015-12-25 | Christmas | 2015-12-25
2016-01-01 | New Year | 2016-01-01
2016-01-18 | MLK Jr. | 2016-01-18
2016-02-15 | Presidents | 2016-02-15
2016-05-30 | Memorial | 2016-05-30
2016-07-04 | Independence | 2016-07-04
2016-09-05 | Labor | 2016-09-05
2016-11-11 | Veterans | 2016-11-11
2016-11-24 | Thanksgiving | 2016-11-24
2016-12-26 | Christmas | 2016-12-26
2017-01-02 | New Year | 2017-01-02
2017-01-16 | MLK Jr. | 2017-01-16
2017-02-20 | Presidents | 2017-02-20
2017-05-29 | Memorial | 2017-05-29
2017-07-04 | Independence | 2017-07-04
2017-09-04 | Labor | 2017-09-04
2017-11-10 | Veterans | 2017-11-10
2017-11-23 | Thanksgiving | 2017-11-23
2017-12-25 | Christmas | 2017-12-25
2018-01-01 | New Year | 2018-01-01
Called from ScheduleTasks
DDL_Bulletin | VL_Bulletin
2013-01-01 | 2012-12-14 | 2012-12-14
2013-02-01 | 2013-01-15 | 2013-01-15
2013-03-01 | 2013-02-15 | 2013-02-15
2013-04-01 | 2013-03-15 | 2013-03-15
2013-05-01 | 2013-04-15 | 2013-04-15
2013-06-01 | 2013-05-15 | 2013-05-15
2013-07-01 | 2013-06-14 | 2013-06-14
2013-08-01 | 2013-07-15 | 2013-07-15
2013-09-01 | 2013-08-15 | 2013-08-15
2013-10-01 | 2013-09-13 | 2013-09-13
2013-11-01 | 2013-10-15 | 2013-10-15
2013-12-01 | 2013-11-15 | 2013-11-15
2014-01-01 | 2013-12-13 | 2013-12-13
2014-02-01 | 2014-01-15 | 2014-01-15
2014-03-01 | 2014-02-14 | 2014-02-14
2014-04-01 | 2014-03-14 | 2014-03-14
2014-05-01 | 2014-04-15 | 2014-04-15
2014-06-01 | 2014-05-15 | 2014-05-15
2014-07-01 | 2014-06-13 | 2014-06-13
2014-08-01 | 2014-07-15 | 2014-07-15
2014-09-01 | 2014-08-15 | 2014-08-15
2014-10-01 | 2014-09-15 | 2014-09-15
2014-11-01 | 2014-10-15 | 2014-10-15
2014-12-01 | 2014-11-14 | 2014-11-14
2015-01-01 | 2014-12-15 | 2014-12-15
2015-02-01 | 2015-01-15 | 2015-01-15
2015-03-01 | 2015-02-13 | 2015-02-13
2015-04-01 | 2015-03-13 | 2015-03-13
2015-05-01 | 2015-04-15 | 2015-04-15
2015-06-01 | 2015-05-15 | 2015-05-15
2015-07-01 | 2015-06-15 | 2015-06-15
2015-08-01 | 2015-07-15 | 2015-07-15
2015-09-01 | 2015-08-15 | 2015-08-15
2015-10-01 | 2015-09-15 | 2015-09-15
2015-11-01 | 2015-10-15 | 2015-10-15
2015-12-01 | 2015-11-13 | 2015-11-13
2016-01-01 | 2015-12-15 | 2015-12-15
2016-02-01 | 2016-01-15 | 2016-01-15
2016-03-01 | 2016-02-15 | 2016-02-15
2016-04-01 | 2016-03-15 | 2016-03-15
2016-05-01 | 2016-04-15 | 2016-04-15
2016-06-01 | 2016-05-13 | 2016-05-13
2016-07-01 | 2016-06-15 | 2016-06-15
2016-08-01 | 2016-07-15 | 2016-07-15
2016-09-01 | 2016-08-15 | 2016-08-15
2016-10-01 | 2016-09-15 | 2016-09-15
2016-11-01 | 2016-10-14 | 2016-10-14
2016-12-01 | 2016-11-15 | 2016-11-15
2017-01-01 | 2016-12-15 | 2016-12-15
2017-02-01 | 2017-01-13 | 2017-01-13
2017-03-01 | 2017-02-15 | 2017-02-15
2017-04-01 | 2017-03-15 | 2017-03-15
2017-05-01 | 2017-04-14 | 2017-04-14
2017-06-01 | 2017-05-15 | 2017-05-15
2017-07-01 | 2017-06-15 | 2017-06-15
2017-08-01 | 2017-07-14 | 2017-07-14
2017-09-01 | 2017-08-15 | 2017-08-15
2017-10-01 | 2017-09-15 | 2017-09-15
2017-11-01 | 2017-10-13 | 2017-10-13
2017-12-01 | 2017-11-15 | 2017-11-15
2018-01-01 | 2017-12-15 | 2017-12-15
2018-02-01 | 2018-01-15 | 2018-01-15
2018-03-01 | 2018-02-15 | 2018-02-15
2018-04-01 | 2018-03-14 | 2018-03-14
2018-05-01 | 2018-04-13 | 2018-04-13
2018-06-01 | 2018-05-15 | 2018-05-15
2018-07-01 | 2018-06-15 | 2018-06-15
2018-08-01 | 2018-07-13 | 2018-07-13
2018-09-01 | 2018-08-15 | 2018-08-15
2018-10-01 | 2018-09-14 | 2018-09-14
2018-11-01 | 2018-10-15 | 2018-10-15
2018-12-01 | 2018-11-15 | 2018-11-15
2019-01-01 | 2018-12-14 | 2018-12-14
2019-02-01 | 2019-01-15 | 2019-01-15
2019-03-01 | 2019-02-15 | 2019-02-15
2019-04-01 | 2019-03-15 | 2019-03-15
2019-05-01 | 2019-04-15 | 2019-04-15
2019-06-01 | 2019-05-15 | 2019-05-15
2019-07-01 | 2019-06-14 | 2019-06-14
2019-08-01 | 2019-07-15 | 2019-07-15
2019-09-01 | 2019-08-15 | 2019-08-15
2019-10-01 | 2019-09-13 | 2019-09-13
2019-11-01 | 2019-10-15 | 2019-10-15
2019-12-01 | 2019-11-15 | 2019-11-15
2020-01-01 | 2019-12-13 | 2019-12-13
2020-02-01 | 2020-01-15 | 2020-01-15
2020-03-01 | 2020-02-14 | 2020-02-14
2020-04-01 | 2020-03-13 | 2020-03-13
2020-05-01 | 2020-04-15 | 2020-04-15
2020-06-01 | 2020-05-15 | 2020-05-15
2020-07-01 | 2020-06-15 | 2020-06-15
2020-08-01 | 2020-07-15 | 2020-07-15
2020-09-01 | 2020-08-14 | 2020-08-14
2020-10-01 | 2020-09-15 | 2020-09-15
2020-11-01 | 2020-10-15 | 2020-10-15
2020-12-01 | 2020-11-13 | 2020-11-13
2021-01-01 | 2020-12-15 | 2020-12-15
2021-02-01 | 2021-01-15 | 2021-01-15
2021-03-01 | 2021-02-15 | 2021-02-15
2021-04-01 | 2021-03-15 | 2021-03-15
2021-05-01 | 2021-04-15 | 2021-04-15
2021-06-01 | 2021-05-14 | 2021-05-14
2021-07-01 | 2021-06-15 | 2021-06-15
2021-08-01 | 2021-07-15 | 2021-07-15
2021-09-01 | 2021-08-13 | 2021-08-13
2021-10-01 | 2021-09-15 | 2021-09-15
2021-11-01 | 2021-10-15 | 2021-10-15
2021-12-01 | 2021-11-15 | 2021-11-15
Called from ScheduleTasks
Formulas:
Next = [DDL_EQCMeeting]+[Days to next]
Last = [DDL_EQCMeeting]-[Days to next, row above]
EQCStaffRptDue = WORKDAY([DDL_EQCMeeting]-40,-1,S.DDL_DEQClosed)
EQCMaterialsDue = WORKDAY([DDL_EQCMeeting]-9,-1,S.DDL_DEQClosed)
EQCMaterialsDue = [DDL_EQCMeeting]

## ScheduleTasks
CALCULATIONS - DO NOT DELETE
| Schedule of Tasks | Infrastructure SIP | [5 empty] | ↓ Adjust start date | [699 empty] | 470 | testing area
[8 empty] | 0 |  |  |  |  | Workday |  |  | Weekend |  |  | Closed | [17 empty] | Workday |  |  | Weekend |  |  | Closed | [21 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [21 empty] | Workday |  |  | Weekend |  |  | Closed | [21 empty] | Workday |  |  | Weekend |  |  | Closed | [21 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [21 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [21 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [21 empty] | Workday |  |  | Weekend |  |  | Closed | [21 empty] | Workday |  |  | Weekend |  |  | Closed | [22 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [21 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [26 empty] | Gantt
| Overview of Key Dates |  |  | Workdays |  | Today 05/29/13 |  | 2013-05-29 |  |  |  |  | 2013-06-03 | [6 empty] | 2013-06-10 | [6 empty] | 2013-06-17 | [6 empty] | 2013-06-24 | [6 empty] | 2013-07-01 | [6 empty] | 2013-07-08 | [6 empty] | 2013-07-15 | [6 empty] | 2013-07-22 | [6 empty] | 2013-07-29 | [6 empty] | 2013-08-05 | [6 empty] | 2013-08-12 | [6 empty] | 2013-08-19 | [6 empty] | 2013-08-26 | [6 empty] | 2013-09-02 | [6 empty] | 2013-09-09 | [6 empty] | 2013-09-16 | [6 empty] | 2013-09-23 | [6 empty] | 2013-09-30 | [6 empty] | 2013-10-07 | [6 empty] | 2013-10-14 | [6 empty] | 2013-10-21 | [6 empty] | 2013-10-28 | [6 empty] | 2013-11-04 | [6 empty] | 2013-11-11 | [6 empty] | 2013-11-18 | [6 empty] | 2013-11-25 | [6 empty] | 2013-12-02 | [6 empty] | 2013-12-09 | [6 empty] | 2013-12-16 | [6 empty] | 2013-12-23 | [6 empty] | 2013-12-30 | [6 empty] | 2014-01-06 | [6 empty] | 2014-01-13 | [6 empty] | 2014-01-20 | [6 empty] | 2014-01-27 | [6 empty] | 2014-02-03 | [6 empty] | 2014-02-10 | [6 empty] | 2014-02-17 | [6 empty] | 2014-02-24 | [6 empty] | 2014-03-03 | [6 empty] | 2014-03-10 | [6 empty] | 2014-03-17 | [6 empty] | 2014-03-24 | [6 empty] | 2014-03-31 | [6 empty] | 2014-04-07 | [6 empty] | 2014-04-14 | [6 empty] | 2014-04-21 | [6 empty] | 2014-04-28 | [6 empty] | 2014-05-05 | [6 empty] | 2014-05-12 | [6 empty] | 2014-05-19 | [6 empty] | 2014-05-26 | [6 empty] | 2014-06-02 | [6 empty] | 2014-06-09 | [6 empty] | 2014-06-16 | [6 empty] | 2014-06-23 | [6 empty] | 2014-06-30 | [6 empty] | 2014-07-07 | [6 empty] | 2014-07-14 | [6 empty] | 2014-07-21 | [6 empty] | 2014-07-28 | [6 empty] | 2014-08-04 | [6 empty] | 2014-08-11 | [6 empty] | 2014-08-18 | [6 empty] | 2014-08-25 | [6 empty] | 2014-09-01 | [6 empty] | 2014-09-08 | [6 empty] | 2014-09-15 | [6 empty] | 2014-09-22 | [6 empty] | 2014-09-29 | [6 empty] | 2014-10-06 | [6 empty] | 2014-10-13 | [6 empty] | 2014-10-20 | [6 empty] | 2014-10-27 | [6 empty] | 2014-11-03 | [6 empty] | 2014-11-10 | [6 empty] | 2014-11-17 | [6 empty] | 2014-11-24 | [6 empty] | 2014-12-01 | [6 empty] | 2014-12-08 | [6 empty] | 2014-12-15 | [6 empty] | 2014-12-22 | [6 empty] | 2014-12-29 | [6 empty] | 2015-01-05 | [6 empty] | 2015-01-12 | [6 empty] | 2015-01-19 | [6 empty] | 2015-01-26 | [6 empty] | 2015-02-02 | [6 empty] | 2015-02-09 | [6 empty] | 2015-02-16 | [6 empty] | 2015-02-23 | [6 empty] | 2015-03-02 | [6 empty] | 2015-03-09 | [6 empty] | 2015-03-16 | [6 empty] | 2015-03-23 | [6 empty] | 2015-03-30 | [6 empty] | 2015-04-06 | [6 empty] | 2015-04-13 | [6 empty] | 2015-04-20 |  | T | X |  | 2013-12-02 |  | Form Control DO NOT LOCK
|  |  |  | This Task | From Today | Start Task | End Task | 2013-05-29 |  |  |  |  | 2013-06-03 | [6 empty] | 2013-06-10 | [6 empty] | 2013-06-17 | [6 empty] | 2013-06-24 | [6 empty] | 2013-07-01 | [6 empty] | 2013-07-08 | [6 empty] | 2013-07-15 | [6 empty] | 2013-07-22 | [6 empty] | 2013-07-29 | [6 empty] | 2013-08-05 | [6 empty] | 2013-08-12 | [6 empty] | 2013-08-19 | [6 empty] | 2013-08-26 | [6 empty] | 2013-09-02 | [6 empty] | 2013-09-09 | [6 empty] | 2013-09-16 | [6 empty] | 2013-09-23 | [6 empty] | 2013-09-30 | [6 empty] | 2013-10-07 | [6 empty] | 2013-10-14 | [6 empty] | 2013-10-21 | [6 empty] | 2013-10-28 | [6 empty] | 2013-11-04 | [6 empty] | 2013-11-11 | [6 empty] | 2013-11-18 | [6 empty] | 2013-11-25 | [6 empty] | 2013-12-02 | [6 empty] | 2013-12-09 | [6 empty] | 2013-12-16 | [6 empty] | 2013-12-23 | [6 empty] | 2013-12-30 | [6 empty] | 2014-01-06 | [6 empty] | 2014-01-13 | [6 empty] | 2014-01-20 | [6 empty] | 2014-01-27 | [6 empty] | 2014-02-03 | [6 empty] | 2014-02-10 | [6 empty] | 2014-02-17 | [6 empty] | 2014-02-24 | [6 empty] | 2014-03-03 | [6 empty] | 2014-03-10 | [6 empty] | 2014-03-17 | [6 empty] | 2014-03-24 | [6 empty] | 2014-03-31 | [6 empty] | 2014-04-07 | [6 empty] | 2014-04-14 | [6 empty] | 2014-04-21 | [6 empty] | 2014-04-28 | [6 empty] | 2014-05-05 | [6 empty] | 2014-05-12 | [6 empty] | 2014-05-19 | [6 empty] | 2014-05-26 | [6 empty] | 2014-06-02 | [6 empty] | 2014-06-09 | [6 empty] | 2014-06-16 | [6 empty] | 2014-06-23 | [6 empty] | 2014-06-30 | [6 empty] | 2014-07-07 | [6 empty] | 2014-07-14 | [6 empty] | 2014-07-21 | [6 empty] | 2014-07-28 | [6 empty] | 2014-08-04 | [6 empty] | 2014-08-11 | [6 empty] | 2014-08-18 | [6 empty] | 2014-08-25 | [6 empty] | 2014-09-01 | [6 empty] | 2014-09-08 | [6 empty] | 2014-09-15 | [6 empty] | 2014-09-22 | [6 empty] | 2014-09-29 | [6 empty] | 2014-10-06 | [6 empty] | 2014-10-13 | [6 empty] | 2014-10-20 | [6 empty] | 2014-10-27 | [6 empty] | 2014-11-03 | [6 empty] | 2014-11-10 | [6 empty] | 2014-11-17 | [6 empty] | 2014-11-24 | [6 empty] | 2014-12-01 | [6 empty] | 2014-12-08 | [6 empty] | 2014-12-15 | [6 empty] | 2014-12-22 | [6 empty] | 2014-12-29 | [6 empty] | 2015-01-05 | [6 empty] | 2015-01-12 | [6 empty] | 2015-01-19 | [6 empty] | 2015-01-26 | [6 empty] | 2015-02-02 | [6 empty] | 2015-02-09 | [6 empty] | 2015-02-16 | [6 empty] | 2015-02-23 | [6 empty] | 2015-03-02 | [6 empty] | 2015-03-09 | [6 empty] | 2015-03-16 | [6 empty] | 2015-03-23 | [6 empty] | 2015-03-30 | [6 empty] | 2015-04-06 | [6 empty] | 2015-04-13 | [6 empty] | 2015-04-20 |  | T | X | [5 empty] | Next EQC Meeting 03/31/00 | [12 empty] | 2013-06-20
[5 empty] | 144 | 2013-04-05 | 2013-12-16 | [693 empty] | B | X | 2013-05-29 | 2013-12-16 |  | 1 | 28 | time axis 2013-05-29 to 2015-04-21
[701 empty] | Y | X
[701 empty] | 0 | X | [5 empty] | Future S.CodeName
| Rule Permanent Temporary | [699 empty] | 1 | X | 1900-03-31 | [5 empty] | 2013-04-05
[701 empty] | 0 | X
x | EQC Rulemaking Action Item |  |  |  | 99 | 2013-10-16 | 2013-10-16 | [693 empty] | 1 |  |  | 2013-10-16 |  |  |  |  | Start | 5.4667 | 4.9 | 4.3333 | 3.7667 |  |  |  | good | good | good | good
| INVOLVED before Rulemaking Action Item |  |  |  |  | Option 1 ↓ | Option 2 ↓ | [693 empty] | 1 | X |  |  |  | TRUE |  | INVOLVED before Rulemaking Action Item |  | Crawl | Walk | Run | Bolt | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
x | Director's Dialog |  |  |  | 16 | 2013-06-19 | 2013-06-19 | [693 empty] | 1 |  | 2013-08-21 | 2013-06-19 |  | TRUE |  |  | Rule Type | 28 | 21 | 14 | 7 | DDL_Pace | Notice to EPA |  | Fees | Notice to SOS | Bulletin | Hearing | EQC | EQC early involvement | Day between EQC
| Information Item |  |  |  | 60 | 2013-08-21 | 2013-08-21 | [693 empty] | 0 |  | 2013-08-21 | 2013-08-21 |  | FALSE |  |  | SIP | 25 | 20 | 15 | 10 | bar: 1 to good 10
| Facilitated Hearing |  |  |  | 60 | 2013-08-21 | 2013-08-21 | [693 empty] | 0 |  | 2013-08-21 | 2013-08-21 |  | FALSE |  | Facilitated Hearing | AC | 0 | 0 | 0 | 0 | Crawl | 2014-01-06 | 2013-04-05 | 2013-04-05 | 2014-01-15 | 2014-02-01 | 2014-02-18 | 2014-06-18 | 2014-03-19 | 63
[701 empty] | 0 | X
x | 1-State Implementation Plan (AQ rules) |  |  | 138 | 109 | 2013-04-15 | 2013-10-30 | [693 empty] | 1 |  | 2013-04-15 | 2013-10-30 |  | TRUE |  | 1-State Implementation Plan (AQ rules) | Fee | 0 | 0 | 0 | 0 | Walk | 2013-11-01 | 2013-04-05 | 2013-04-05 | 2013-11-15 | 2013-12-01 | 2013-12-16 | 2014-03-19 | 2013-12-11 | 91
[701 empty] | 0 | X | [6 empty] | Notice | 66 | 61 | 56 | 51 | Run | 2013-09-03 | 2013-04-05 | 2013-04-05 | 2013-09-13 | 2013-10-01 | 2013-10-15 | 2013-12-11 | 2013-08-21 | 98
| 2-Advisory Committee NOT involved |  |  | 1 | -36 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  | FALSE |  | 2-Advisory Committee NOT involved | EQC Prep | 45 | 45 | 45 | 45 | Bolt | 2013-07-01 | 2013-04-05 | 2013-04-05 | 2013-07-15 | 2013-08-01 | 2013-08-15 | 2013-10-16 | 2013-08-21 | 56
[701 empty] | 0 | X | [7 empty] | 164 | 147 | 130 | 113
| 3-Fees Not Involved |  |  | 71 | 36 | 2013-04-05 | 2013-07-18 | [693 empty] | 0 |  | 2013-04-05 | 2013-07-18 | FALSE | FALSE |  | 3-Fees Not Involved
| DAS - Fee approval not involved | [699 empty] | 0 | X |  |  |  | 2 |  | DAS - Fee approval not involved
| DAS - Email notice not involved | [699 empty] | 0 | X | [5 empty] | DAS - Email notice not involved
[701 empty] | 0 | X
x | 4-Public Notice WITH hearing | [699 empty] | 1 | X | [5 empty] | 4-Public Notice WITH hearing
| EPA - submit 45 days BEFORE 1st hearing (H31) |  |  |  | 24 | 2013-07-01 | 2013-07-01 | [693 empty] | 1 |  |  | 2013-07-01 |  |  |  | EPA - submit 45 days BEFORE 1st hearing (H31)
| DAS - fees not involved |  |  |  | -36 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  |  | 2013-04-05 |  |  | 14 | DAS - fees not involved
x | SOS - submit on workday <=15th of month BEFORE Bulletin (H29) |  |  |  | 33 | 2013-07-15 | 2013-07-15 | [693 empty] | 1 |  |  | 2013-07-15 |  |  |  | SOS - submit on workday <=15th of month BEFORE Bulletin (H29)
x | SOS - Bulletin always publishes 1st of month |  |  |  | 46 |  | 2013-08-01 | [693 empty] | 1 |  |  | 2013-08-01 |  | TRUE | 30 | SOS - Bulletin always publishes 1st of month
| 5-Public Comment and Testimony | [699 empty] | 1 | X | [5 empty] | IF(S.InvolveHearing=TRUE," with hearings"," no hearings"))
x | First Hearing => 15th workday AFTER Bulletin (H29) |  |  |  | 56 | 2013-08-15 | 2013-08-15 | [693 empty] | 1 |  |  | 2013-08-15 |  | TRUE | 14 | First Hearing => 15th workday AFTER Bulletin (H29)
x | Close PUBLIC COMMENT |  |  |  | 58 | 2013-08-19 | 2013-08-19 | [693 empty] | 1 |  |  | 2013-08-19 |  |  |  | Close PUBLIC COMMENT
| 6-EQC Preparation | [699 empty] | 1 | X
x | Submit staff report | Q |  |  | 73 | 2013-09-10 | 2013-09-10 | [693 empty] | 1 |  |  | 2013-09-10 |  |  | 41 | WORKDAY(S.SubmitStaffRpt-42,1,S.DDL_EQCMeeting)
x | Present EQC Action Item | Q |  |  | 99 | 2013-10-16 | 2013-10-16 | [693 empty] | 1 |  |  | 2013-10-16
| 7-Post EQC | [699 empty] | 1 | X |  |  |  |  | 127
x | SOS - file rules |  |  |  | 101 | 2013-10-18 | 2013-10-18 | [693 empty] | 1 |  |  | 2013-10-18
x | EPA - submit SIP |  |  |  | 109 | 2013-10-30 | 2013-10-30 | [693 empty] | 1 |  |  | 2013-10-30 |  |  |  | EPA - submit SIP
| DAS - fees not involved |  |  |  | 102 | 2013-10-21 | 2013-10-21 | [693 empty] | 0 |  |  | 2013-10-21 |  |  |  | DAS - fees not involved
x | Rules become effective |  |  |  | 101 | 2013-10-18 | 2013-10-18 | [693 empty] | 1 |  |  | 2013-10-18 | 2013-10-26
[701 empty] | 0 | X
| 1-Planning | [699 empty] | T | X
| Task |  | Owner | This Task | Workdays | Start Task | End Task | [693 empty] | B | X
[5 empty] | 83 | 2013-04-05 | 2013-08-05 | [693 empty] | B | X | 2013-04-05 | 2013-08-05
[701 empty] | Y | X
| After approved on DEQ's Annual Rulemaking Plan: | DEQ | [698 empty] | 1 | X
x | Expand Core Team |  | LM,SE,DE | 7 | -33 | 2013-04-05 | 2013-04-15 | [693 empty] | 1 |  | 2013-04-05 | 2013-04-05
x | Notify new members |  | LM, Mgrs | 31 | -8 | 2013-04-05 | 2013-05-20 | [693 empty] | 1 |  | 2013-04-15 | 2013-04-05
x | Add rulemaking to work plans as needed |  | LM, Mgrs | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 1 |  | 2013-05-20 | 2013-04-05
x | Team kickoff meeting/training/work session |  | Team,LA | 1 | -8 | 2013-05-20 | 2013-05-20 | [693 empty] | 1 |  | 2013-04-05 | 2013-05-20
y | Maintaining rulemaking record | [699 empty] | 1 | X
y | File naming conventions | [699 empty] | 1 | X
y | Rulemaking SharePoint | SP | [698 empty] | 1 | X
y | Shared drive: Rules _Development | [699 empty] | 1 | X
y | Discuss Overview of Key Dates above | [699 empty] | 1 | X
y | Overview of main external work products | [699 empty] | 1 | X
| Rules Registry | DEQ | [698 empty] | 1 | X
| INVITATION.TO.COMMENT (blank in folder 4) | [699 empty] | 1 | X
| RULES.REDLINE | [699 empty] | 1 | X
| NOTICE (blank in folder 4) | [699 empty] | 1 | X
| FEE.ANALYSIS (blank in folder 3) | [699 empty] | 0 | X
| STAFF.RPT.Temporary (blank in folder 6) | [699 empty] | 1 | X
| STAFF.RPT.Permanent (blank in folder 6) | [699 empty] | 1 | X
x | Review/refine RESOURCES | [699 empty] | 1 | X | [5 empty] | Review/refine RESOURCES
x | Review/refine CONSIDERATIONS | [699 empty] | 1 | X | [5 empty] | Review/refine CONSIDERATIONS
x | Schedule recurring team meetings | [699 empty] | 1 | X
x | Obtain rules and new numbers if needed |  | DE, SE. MV | 8 | 3 | 2013-05-20 | 2013-05-31 | [693 empty] | 1 |  | 2013-05-20 | 2013-05-20
x | Save rules as PROPOSED.RULES |  | DE | 1 | 3 | 2013-05-31 | 2013-05-31 | [693 empty] | 1 |  | 2013-05-31 | 2013-05-31
y | Work with SOS on any new division/rule numbers |  | DE,MV | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 1 |  | 2013-05-31 | 2013-04-05
x | Identify land use rules | Q | SE,DE | 38 | 3 | 2013-04-05 | 2013-05-31 | [693 empty] | 1 |  | 2013-04-05 | 2013-04-05
x | State Implementation Plan |  | SE,SIPCo | 53 | 24 | 2013-04-15 | 2013-07-01 | [693 empty] | 1 |  | 2013-04-15 | 2013-07-01
| Identify SIP rules |  | SE,SIPCo | 1 | -33 | 2013-04-15 | 2013-04-15 | [693 empty] | 1 |  | 2013-04-15 | 2013-04-15
| Subtask |  | SE,SIPCo | 1 | -33 | 2013-04-15 | 2013-04-15 | [693 empty] | 1 |  | 2013-04-15 | 2013-04-15
| Subtask |  | SE,SIPCo | 1 | -33 | 2013-04-15 | 2013-04-15 | [693 empty] | 1 |  | 2013-04-15 | 2013-04-15
| Subtask |  | SE,SIPCo | 1 | -33 | 2013-04-15 | 2013-04-15 | [693 empty] | 1 |  | 2013-04-15 | 2013-04-15
| Subtask |  | SE,SIPCo | 1 | -33 | 2013-04-15 | 2013-04-15 | [693 empty] | 1 |  | 2013-04-15 | 2013-04-15
| Task |  | SE,SIPCo | 1 | -33 | 2013-04-15 | 2013-04-15 | [693 empty] | 1 |  | 2013-04-15 | 2013-04-15
x | Submit Notice to EPA - 45 day before 1st hearing |  | SE,SIPCo | 1 | 24 | 2013-07-01 | 2013-07-01 | [693 empty] | 1 |  | 2013-07-01 | 2013-07-01
[701 empty] | W | X
| 2-Advisory Committee NOT involved | [699 empty] | T | X
| Task |  | Owner | Task | Workdays | Start Task | End Task | [693 empty] | B | X
[5 empty] | 1 | 2013-04-05 | 2013-04-05 | [693 empty] | B | X | 2013-04-05 | 2013-04-05
[701 empty] | Y | X
| Review 0-Advisory Committee Learning Tools | Q | [698 empty] | 0 | X
| Review Public Involvement Resources | Q | Team | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Discuss meeting notice requirements | [699 empty] | 1
| Public Meeting Laws | i | Team |  | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| EQC quorum notification requirements | i | Team | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Oregon Transparency requirements | i | Team | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Develop ROSTER (blank in folder 4) |  | Team | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Identify potential meeting dates and venues |  | DS | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Draft optional AC.CHARTER |  | Team | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Develop committee communications | [699 empty] | 0 | X
| Draft optional AC.MESSAGE.MAP | Q | DE | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Draft AC.MEMBER.INVITE |  | DE, SC | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Draft optional AC.WEB.PAGE |  | DE | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Review drafts above |  | Team | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Generally, the core team does not need to save developmental drafts unless the document represents a significant shift in rulemaking direction. This applies to reviews or requests for input beyond the core team. For each document that had significant changes in any loop, save the document to Rules_Development using the same name followed by folder number and next higher version number. EXAMPLE: MESSAGE.MAP-2.01, MESSAGE.MAP-2.02... | [699 empty] | 0 | X
| Loop as needed | [699 empty] | 0 | X
| Approve charter and communications |  | LM or LA | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Initial voice contact |  | @ LA direction | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Add committee/EQC to GovDelivery | Q | DS |  | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Send invitation to potential committee members |  | @ LA direction | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Add meeting dates to DEQ public meetings | DEQ | Team | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Maintain optional committee web page |  | DE, DS | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Release unneeded venues |  | DS | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Meeting 1 |  |  |  |  | 2013-05-29 | 6:00 p.m. | [693 empty] | 0 | X
| Identify meeting roles |  | Team | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Meeting preparation | [699 empty] | 0 | X
| Draft AGENDA.05.29.13 | Q | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft AGENDA.mm.dd.yyyy.2.00
| Enter custom task here |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| START OPTION - Presentation | [699 empty] | 0 | X
| Draft optional PRESENTATION.05.29.13 | Q | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Involve stakeholder presenters, if any |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Approve optional presentation materials |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Post optional presentation materials on committee webpage |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| END OPTION | [699 empty] | 0 | X
| Draft COMMITTEE.NOTICE.05.29.13 |  | DE | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft COMMITTEE.NOTICE.mm.dd.yyyy.2.00
| Loop as needed | [699 empty] | 0 | X
| Send meeting notice (link to optional webpage) |  | DS | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Hold meeting |  | Team | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Draft MINUTES.05.29.13 | Q | DE | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft MINUTES.mm.dd.yyy.2.00
| Debrief conference |  | Team | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Meeting 2 |  |  |  |  | 2013-05-29 | 6:00 p.m. | [693 empty] | 0 | X
| Identify meeting roles |  | Team | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Meeting preparation | [699 empty] | 0 | X
| Draft AGENDA.05.29.13 | Q | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft AGENDA.mm.dd.yyyy.2.00
| Enter custom task here |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| START OPTION - Presentation | [699 empty] | 0 | X
| Draft optional PRESENTATION.05.29.13 | Q | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Involve stakeholder presenters, if any |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Approve optional presentation materials |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Post optional presentation materials on committee webpage |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| END OPTION | [699 empty] | 0 | X
| Draft COMMITTEE.NOTICE.05.29.13 |  | DE | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft COMMITTEE.NOTICE.mm.dd.yyyy.2.00
| Loop as needed | [699 empty] | 0 | X
| Send meeting notice (link to optional webpage) |  | DS | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Hold meeting |  | Team | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Draft MINUTES.05.29.13 | Q | DE | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft MINUTES.mm.dd.yyy.2.00
| Debrief conference |  | Team | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Meeting 3 |  |  |  |  | 2013-05-29 | 6:00 p.m. | [693 empty] | 0 | X
| Identify meeting roles |  | Team | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Meeting preparation | [699 empty] | 0 | X
| Draft AGENDA.05.29.13 | Q | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft AGENDA.mm.dd.yyyy.2.00
| Enter custom task here |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| START OPTION - Presentation | [699 empty] | 0 | X
| Draft optional PRESENTATION.05.29.13 | Q | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Involve stakeholder presenters, if any |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Approve optional presentation materials |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Post optional presentation materials on committee webpage |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| END OPTION | [699 empty] | 0 | X
| Draft COMMITTEE.NOTICE.05.29.13 |  | DE | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft COMMITTEE.NOTICE.mm.dd.yyyy.2.00
| Loop as needed | [699 empty] | 0 | X
| Send meeting notice (link to optional webpage) |  | DS | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Hold meeting |  | Team | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Draft MINUTES.05.29.13 | Q | DE | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft MINUTES.mm.dd.yyy.2.00
| Debrief conference |  | Team | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Meeting 4 |  |  |  |  | 2013-05-29 | 6:00 p.m. | [693 empty] | 0 | X
| Identify meeting roles |  | Team | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Meeting preparation | [699 empty] | 0 | X
| Draft AGENDA.05.29.13 | Q | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft AGENDA.mm.dd.yyyy.2.00
| Enter custom task here |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| START OPTION - Presentation | [699 empty] | 0 | X
| Draft optional PRESENTATION.05.29.13 | Q | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Involve stakeholder presenters, if any |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Approve optional presentation materials |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Post optional presentation materials on committee webpage |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| END OPTION | [699 empty] | 0 | X
| Draft COMMITTEE.NOTICE.05.29.13 |  | DE | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft COMMITTEE.NOTICE.mm.dd.yyyy.2.00
| Loop as needed | [699 empty] | 0 | X
| Send meeting notice (link to optional webpage) |  | DS | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Hold meeting |  | Team | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Draft MINUTES.05.29.13 | Q | DE | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft MINUTES.mm.dd.yyy.2.00
| Debrief conference |  | Team | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Meeting 5 |  |  |  |  | 2013-05-29 | 6:00 p.m. | [693 empty] | 0 | X
| Identify meeting roles |  | Team | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Meeting preparation | [699 empty] | 0 | X
| Draft AGENDA.05.29.13 | Q | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft AGENDA.mm.dd.yyyy.2.00
| Enter custom task here |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Enter custom task here |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| START OPTION - Presentation | [699 empty] | 0 | X
| Draft optional PRESENTATION.05.29.13 | Q | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Involve stakeholder presenters, if any |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Approve optional presentation materials |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Post optional presentation materials on committee webpage |  | Assign | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| END OPTION | [699 empty] | 0 | X
| Draft COMMITTEE.NOTICE.05.29.13 |  | DE | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft COMMITTEE.NOTICE.mm.dd.yyyy.2.00
| Loop as needed | [699 empty] | 0 | X
| Send meeting notice (link to optional webpage) |  | DS | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Hold meeting |  | Team | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| Draft MINUTES.05.29.13 | Q | DE | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Draft MINUTES.mm.dd.yyy.2.00
| Debrief conference |  | Team | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
X
[701 empty] | W | X
| 3-Fees Not Involved | [699 empty] | T | X | [5 empty] | 3-Fees Not Involved
| Task |  | Owner | Task | Workdays | Start Task | End Task | [693 empty] | B | X
[5 empty] | 71 | 2013-04-05 | 2013-07-18 | [693 empty] | B | X | 2013-04-05 | 2013-07-18
[701 empty] | Y | X
| Finalize CONSIDERATIONS¦7Financial |  | Team | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05
| No DAS involvement |  | Team | 68 | 34 | 2013-04-05 | 2013-07-15 | [693 empty] | 0 | X | 2013-04-05 | 2013-07-15 |  |  |  | No DAS involvement
| Draft Fee Notification Packet | [699 empty] | 0 | X | [5 empty] | a. FEE.ANALYSIS (blank in folder 3)
| a. FEE.ANALYSIS (blank in folder 3) | [699 empty] | 0 | X | [5 empty] | b. FEE.SUPPORT.DOCS
| b. FEE.SUPPORT.DOCS | [699 empty] | 0 | X
| Go to next step in 4-Public Notice | [699 empty] | 0 | X
| No DAS involvement |  | Team | 48 | 13 | 2013-04-05 | 2013-06-14 | [693 empty] | 0 |  | 2013-04-05 | 2013-06-14 |  |  |  | No DAS involvement
| Draft Fee Approval Packet | [699 empty] | 0 | X | [5 empty] | a. FEE.ANALYSIS (blank in folder 3)
| a. FEE.ANALYSIS (blank in folder 3) | [699 empty] | 0 | X | [5 empty] | b. FEE.SUPPORT.DOCS
| b. FEE.SUPPORT.DOCS | [699 empty] | 0 | X | [5 empty] | a. FEE.APPROVAL (link through FEE.ANALYSIS)
| a. FEE.APPROVAL (link through FEE.ANALYSIS) | [699 empty] | 0 | X | [5 empty] | b. FEE.DETAIL (link through FEE.ANALYSIS)
| b. FEE.DETAIL (link through FEE.ANALYSIS) | [699 empty] | 0 | X
| Finalize Fee Approval Packet |  | Team | 1 | 13 | 2013-06-14 | 2013-06-14 | [693 empty] | 0 |  | 2013-06-14 | 2013-06-14
| 1st approval loop |  | DE, Fiscal, LM | 1 | 13 | 2013-06-14 | 2013-06-14 | [693 empty] | 0 |  | 2013-06-14 | 2013-06-14
| 2nd approval loop |  | DE, Fiscal, LM | 1 | 13 | 2013-06-14 | 2013-06-14 | [693 empty] | 0 |  | 2013-06-14 | 2013-06-14
| 3rd approval loop |  | DE, Fiscal, LM | 1 | 13 | 2013-06-14 | 2013-06-14 | [693 empty] | 0 |  | 2013-06-14 | 2013-06-14
| Final approval loop |  | DE, Fiscal, LM | 1 | 13 | 2013-06-14 | 2013-06-14 | [693 empty] | 0 |  | 2013-06-14 | 2013-06-14
| Generally, the core team does not need to save developmental drafts unless the document represents a significant shift in rulemaking direction. This applies to reviews or requests for input beyond the core team. For each document that had significant changes in any loop, save the document to Rules_Development using the same name followed by folder number and next higher version number. EXAMPLE: FEE.ANALYSIS-3.01, FEE.ANALYSIS-3.02... | [699 empty] | 0 | X
| Loop as needed | [699 empty] | 0 | X
| START option - informal DAS review | [699 empty] | 0 | X
| Email draft packet for informal review |  | DE, Fiscal | 1 | 13 | 2013-06-14 | 2013-06-14 | [693 empty] | 0 |  | 2013-06-14 | 2013-06-14
| Address DAS concerns |  | Team, Fiscal | 1 | 13 | 2013-06-14 | 2013-06-14 | [693 empty] | 0 |  | 2013-06-14 | 2013-06-14
| END option | [699 empty] | 0 | X
| SUBMIT Fee Approval Packet | [699 empty] | 0 | X
| Send DAS.EMAILS.pdf |  | MV, Fiscal | 1 | -39 | 2013-04-05 | 2013-04-05 | [693 empty] | 0 |  | 2013-04-05 | 2013-04-05 |  |  |  | Send DAS.EMAILS.pdf
| Follow up for status |  | Fiscal staff | 1 | -33 | 2013-04-15 | 2013-04-15 | [693 empty] | 0 |  | 2013-04-15 | 2013-04-15
| Received DAS Fee Response |  | MV, Fiscal | 1 | -33 | 2013-04-15 | 2013-04-15 | [693 empty] | 0 |  | 2013-04-15 | 2013-04-15
| If denied, make changes needed for approval | [699 empty] | 0 | X
| 1st DAS loop |  | LM,DE,Fiscal | 1 | -33 | 2013-04-15 | 2013-04-15 | [693 empty] | 0 |  | 2013-04-15 | 2013-04-15
| 2nd DAS loop |  | LM,DE,Fiscal | 1 | -33 | 2013-04-15 | 2013-04-15 | [693 empty] | 0 |  | 2013-04-15 | 2013-04-15
| 3rd DAS loop |  | LM,DE,Fiscal | 1 | -33 | 2013-04-15 | 2013-04-15 | [693 empty] | 0 |  | 2013-04-15 | 2013-04-15
| Final DAS loop |  | LM,DE,Fiscal | 1 | -33 | 2013-04-15 | 2013-04-15 | [693 empty] | 0 |  | 2013-04-15 | 2013-04-15
| Generally, the core team does not need to save developmental drafts unless the document represents a significant shift in rulemaking direction. This applies to reviews or requests for input beyond the core team. For each document that had significant changes in any loop, save the document to Rules_Development using the same name followed by folder number and next higher version number. EXAMPLE: FEE.ANALYSIS-3.01, FEE.ANALYSIS-3.02... | [699 empty] | 0 | X
| Loop as needed | [699 empty] | 0 | X
| If approved, scan/file DAS.PART1.pdf |  | DS | 1 | -33 | 2013-04-15 | 2013-04-15 | [693 empty] | 0 |  | 2013-04-15 | 2013-04-15
[701 empty] | W | X
| 4-Public Notice WITH hearing | [699 empty] | T | X
| Task |  | Owner | Task | Workdays | Start Task | End Task | [693 empty] | B | X
[5 empty] | 93 | 2013-04-05 | 2013-08-19 | [693 empty] | B | X | 2013-04-05 | 2013-08-19
1900-04-20 | [700 empty] | Y | X
| Enter hearing dates | [699 empty] | 1 | X | [5 empty] | Enter hearing dates
x | FIRST hearing |  | Portland |  |  | 2013-08-15 | 6 p.m. | [693 empty] | 1 | X | 2013-08-15
| 2nd hearing |  | Enter city name |  |  | 2013-08-15 | 6 p.m. | [693 empty] | 1 | X | 2013-08-15 | 6 p.m.
| 3rd hearing |  | Enter city name |  |  | 2013-08-15 | 6 p.m. | [693 empty] | 1 | X | 2013-08-15 | 6 p.m.
| 4th hearing |  | Enter city name |  |  | 2013-08-15 | 6 p.m. | [693 empty] | 1 | X | 2013-08-15 | 6 p.m.
| 5th hearing |  | Enter city name |  |  | 2013-08-15 | 6 p.m. | [693 empty] | 1 | X | 2013-08-15 | 6 p.m.
| 6th hearing |  | Enter city name |  |  | 2013-08-15 | 6 p.m. | [693 empty] | 1 | X | 2013-08-15 | 6 p.m.
| 7th hearing |  | Enter city name |  |  | 2013-08-15 | 6 p.m. | [693 empty] | 1 | X | 2013-08-15 | 6 p.m.
| LAST hearing |  | Enter city name |  |  | 2013-08-15 | 6 p.m. | [693 empty] | 1 | X | 2013-08-15 | 6 p.m.
x | Reserve venues/equipment hearings |  | DS | 12 | 4 | 2013-05-15 | 2013-06-03 | [693 empty] | 1 |  | 2013-04-05 | 2013-05-15
| START OPTION - program webpage | [699 empty] | 1 | X
x | Draft program WEBPAGE |  | DE, Team | 4 | 6 | 2013-05-31 | 2013-06-05 | [693 empty] | 1 |  | 2013-06-03 | 2013-05-31
x | Content contributions |  | SE, Team, SC | 4 | 9 | 2013-06-05 | 2013-06-10 | [693 empty] | 1 |  | 2013-06-05 | 2013-06-05
x | 1st loop for LM approval of webpage |  | LM | 5 | 13 | 2013-06-10 | 2013-06-14 | [693 empty] | 1 |  | 2013-06-10 | 2013-06-10
| 2nd loop for LM approval of webpage |  | LM | 1 | 13 | 2013-06-14 | 2013-06-14 | [693 empty] | 1 |  | 2013-06-14 | 2013-06-14
| 3rd loop for LM approval of webpage |  | LM | 1 | 13 | 2013-06-14 | 2013-06-14 | [693 empty] | 1 |  | 2013-06-14 | 2013-06-14
x | Final loop for LM approval of webpage |  | LM | 5 | 17 | 2013-06-14 | 2013-06-20 | [693 empty] | 1 |  | 2013-06-14 | 2013-06-14
| END OPTION | [699 empty] | 1 | X
x | Develop Notice Packet |  | DE | 48 | 13 | 2013-04-05 | 2013-06-14 | [693 empty] | 1 |  | 2013-04-05 | 2013-06-14
| Generally, the core team does not need to save developmental drafts unless the document represents a significant shift in rulemaking direction. This applies to reviews or requests for input beyond the core team. For each document that had significant changes in any loop, save the document to Rules_Development using the same name followed by folder number and next higher version number. EXAMPLE: WEBPAGE-4.01, WEBPAGE-4.02... | [699 empty] | 1 | X
x | a. INVITATION.TO.COMMENT (blank in folder 4) |  | Team | 48 | 13 | 2013-04-05 | 2013-06-14 | [693 empty] | 1 |  | 2013-04-05 | 2013-06-14 |  |  |  | a. INVITATION.TO.COMMENT (blank in folder 4)
x | b. PROPOSED.RULES | Q | DE | 48 | 13 | 2013-04-05 | 2013-06-14 | [693 empty] | 1 |  | 2013-04-05 | 2013-06-14 |  |  |  | b. PROPOSED.RULES
x | Verify using latest rules |  | DE | 48 | 13 | 2013-04-05 | 2013-06-14 | [693 empty] | 1 |  | 2013-04-05 | 2013-06-14
x | c. NOTICE (blank in folder 4) |  | Team | 48 | 13 | 2013-04-05 | 2013-06-14 | [693 empty] | 1 |  | 2013-04-05 | 2013-06-14
x | Overview | [699 empty] | 1 | X
x | Statement of need | [699 empty] | 1 | X
x | Federal relationships | [699 empty] | 1 | X
x | Rules affected, authorities, supporting docs | [699 empty] | 1 | X
x | Statement of fiscal impact | [699 empty] | 1 | X
| Integrate FEE.ANALYSIS | [699 empty] | 0 | X | [5 empty] | Delete Fee section
x | Land use | [699 empty] | 1 | X
x | d. SUPPORTING.DOCS |  | Team | 48 | 13 | 2013-04-05 | 2013-06-14 | [693 empty] | 1 |  | 2013-04-05 | 2013-06-14 |  |  |  | d. SUPPORTING.DOCS
x | e. SIP |  | SIPCo | 48 | 13 | 2013-04-05 | 2013-06-14 | [693 empty] | 1 |  | 2013-04-05 | 2013-06-14 |  |  |  | e. SIP
x | Draft ##AD if needed | Q | Team | 11 | 13 | 2013-05-31 | 2013-06-14 | [693 empty] | 1 |  | 2013-04-05 | 2013-06-14 |  |  |  | Draft ##AD if needed
x | Identify hearings officers |  | DE | 18 | 13 | 2013-05-20 | 2013-06-14 | [693 empty] | 1 |  | 2013-04-05 | 2013-06-14 |  |  |  | Display advertisements, if needed
x | Get Notice Packet recommendations from RESOURCES |  | DE | 48 | 13 | 2013-04-05 | 2013-06-14 | [693 empty] | 1 |  | 2013-04-05 | 2013-06-14
| Advisory Committee-Statement of fiscal impact | [699 empty] | 0 | X | [5 empty] | Proposal, invitation to comment, notice, display ads
x | Budget-Statement of fiscal impact | [699 empty] | 1 | X | [5 empty] | Fiscal impact statement
x | SIP Coordinator-as needed for b. & e. above | [699 empty] | 1 | X | [5 empty] | Proposal, invitation to comment, notice, display ads
x | DOJ-as needed for b. and c. above | [699 empty] | 1 | X | [5 empty] | Proposal, invitation to comment, notice, display ads
x | ARC and OCO-for entire Notice Packet | [699 empty] | 1 | X
x | 1st loop for LM approval of packet |  | LM | 3 | 5 | 2013-05-31 | 2013-06-04 | [693 empty] | 1 |  | 2013-06-14 | 2013-05-31
| 2nd loop for LM approval of packet |  | LM | 3 | 10 | 2013-06-07 | 2013-06-11 | [693 empty] | 1 |  | 2013-06-04 | 2013-06-07
| 3rd loop for LM approval of packet |  | LM | 1 | 12 | 2013-06-13 | 2013-06-13 | [693 empty] | 1 |  | 2013-06-11 | 2013-06-13
x | Final loop for LM approval of packet |  | LM | 1 | 12 | 2013-06-13 | 2013-06-13 | [693 empty] | 1 |  | 2013-06-13 | 2013-06-13
| Generally, the core team does not need to save developmental drafts unless the document represents a significant shift in rulemaking direction. This applies to reviews or requests for input beyond the core team. For each document that had significant changes in any loop, save the document to Rules_Development using the same name followed by folder number and next higher version number. EXAMPLE: NOTICE-4.01, NOTICE-4.0,... | [699 empty] | 1 | X
| Loop as needed | [699 empty] | 1 | X
x | LA briefing meeting |  | Team, LA | 1 | 13 | 2013-06-14 | 2013-06-14 | [693 empty] | 1 |  | 2013-06-14 | 2013-06-14
x | OPEN preview period for Notice Packet |  | LA, DE | 1 | 13 | 2013-06-14 | 2013-06-14 | [693 empty] | 1 |  | 2013-06-14 | 2013-06-14
x | Notify EMT | [699 empty] | 1 | X
x | Notify DEQ contributing RESOURCES | [699 empty] | 1 | X
x | CLOSE Notice Packet preview period |  | DE | 1 | 18 | 2013-06-21 | 2013-06-21 | [693 empty] | 1 |  | 2013-06-21 | 2013-06-21
x | Decide how to address any feedback |  | Team | 7 | 24 | 2013-06-21 | 2013-07-01 | [693 empty] | 1 |  | 2013-06-21 | 2013-07-09
x | Modify notice documents as needed |  | DE | 9 | 26 | 2013-06-21 | 2013-07-03 | [693 empty] | 1 |  | 2013-06-21 | 2013-07-03
x | Obtain BUDGET.REVIEW.FISCAL |  | DE | 3 | 32 | 2013-07-09 | 2013-07-11 | [693 empty] | 1 |  | 2013-07-09 | 2013-07-11 |  |  |  | Obtain BUDGET-REVIEW.FISCAL.4.00
x | Verify compilation of PROPOSED.RULES |  | DE | 1 | 30 | 2013-07-09 | 2013-07-09 | [693 empty] | 1 |  | 2013-07-09 | 2013-07-09 |  |  |  | Verify compilation of PROPOSED.RULES
x | Obtain managers approval of Notice Packet |  | DE,LM,LA | 6 | 32 | 2013-07-03 | 2013-07-11 | [693 empty] | 1 |  | 2013-07-09 | 2013-07-11
x | Notify ARC Notice Packet approved |  | DE | 1 | 32 | 2013-07-11 | 2013-07-11 | [693 empty] | 1 |  | 2013-07-11 | 2013-07-11
x | Submit SIP & DOJ approval to EPA |  | SIPCo | 1 | 32 | 2013-07-11 | 2013-07-11 | [693 empty] | 1 |  | 2013-07-11 | 2013-07-11
x | Perform final plain English review if changes |  | ARC/SC | 3 | 34 | 2013-07-11 | 2013-07-15 | [693 empty] | 1 |  | 2013-07-11 | 2013-07-15
| Noticing sequence | [699 empty] | 1 | X
x | ARC Actions - Submit/save official notifications: | Q | MV | 14 | 46 | 2013-07-15 | 2013-08-01 | [693 empty] | 1 |  | 2013-07-15 | 2013-08-01 |  |  |  | Submit/publish notice in SOS Bulletin
x | SOS.EMAIL.PROOF | [699 empty] | 1 | X | [5 empty] | SOS.EMAIL.PROOF
x | SOS.NOTICE.PROOF | [699 empty] | 1 | X | [5 empty] | SOS.NOTICE.PROOF
x | SOS.FISCAL.PROOF | [699 empty] | 1 | X | [5 empty] | SOS.FISCAL.PROOF
x | SOS.HOUSING.COSTS | [699 empty] | 1 | X | [5 empty] | SOS.HOUSING.COSTS
x | LC.NOTICE | [699 empty] | 1 | X | [5 empty] | LC.NOTICE
| No DAS involvement | [699 empty] | 0 | X | [5 empty] | LC.NOTICE.PROOF
| DAS.EXEMPT.EMAIL | [699 empty] | 0 | X | [5 empty] | DAS.EXEMPT.EMAIL
| DAS.EXEMPT.EMAIL.PROOF | [699 empty] | 0 | X | [5 empty] | DAS.EXEMPT.EMAIL.PROOF
x | Design Support Responsibility |  | DS, webrep | 1 | 34 | 2013-07-15 | 2013-07-15 | [693 empty] | 1 |  | 2013-07-15 | 2013-07-15 |  |  |  | No DAS involvement
x | Post Notice Packet to Rules Registry | DEQ | [698 empty] | 1 | X
x | Test public comment box | [699 empty] | 1 | X
x | Add hearing dates to DEQ meeting calendar | DEQ | [698 empty] | 1 | X
x | Notify EQC Assistant of target EQC date | [699 empty] | 1 | X
x | GovDelivery, including advisory committee | [699 empty] | 1 | X
x | GOV.DELIVERY.CONTENT" | [699 empty] | 1 | X | [5 empty] | GOV.DELIVERY.CONTENT"
x | Save AGENCY.MAILING.LIST | [699 empty] | 1 | X | [5 empty] | Save AGENCY.MAILING.LIST
x | Save PROOF.OF.DELIVERY | [699 empty] | 1 | X | [5 empty] | Save PROOF.OF.DELIVERY
x | Design Expert Responsibility |  | DE, Fiscal | 1 | 34 | 2013-07-15 | 2013-07-15 | [693 empty] | 1 |  | 2013-07-15 | 2013-07-15
x | Send KEY.LEG.NOTICE | [699 empty] | 1 | X | [5 empty] | Send KEY.LEG.NOTICE
x | Save KEY.LEG.PROOF | [699 empty] | 1 | X | [5 empty] | Save KEY.LEG.PROOF
x | Publish in local newspaper if required | [699 empty] | 1 | X
x | Save ##PRINT.PROOF | [699 empty] | 1 | X | [5 empty] | Save ##PRINT.PROOF
x | Verify notice published accurately in Bulletin | [699 empty] | 1 | X
x | Save BULLETIN.PROOF | [699 empty] | 1 | X | [5 empty] | Save BULLETIN.PROOF
[701 empty] | W | X
| 5-Public Comment and Testimony | [699 empty] | T | X | [5 empty] | 5-Public Comment and Testimony
| Task |  |  | Task | Workdays | Start Task | End Task | [693 empty] | B | X
[5 empty] | 54 | 2013-06-25 | 2013-09-10 | [693 empty] | B | X | 2013-06-25 | 2013-09-10
[701 empty] | Y | X
x | Design Support Responsibilities |  | DS | 11 | 31 | 2013-06-25 | 2013-07-10 | [693 empty] | 1 |  | 2013-06-25 | 2013-08-15
x | Verify venues and equipment reservations | [699 empty] | 1 | X
x | Gather supplies | Q | [698 empty] | 1 | X
x | Design Team Responsibilities |  | Team | 27 | 47 | 2013-06-25 | 2013-08-01 | [693 empty] | 1 |  | 2013-06-25 | 2013-08-15
x | START OPTION - information meeting | [699 empty] | 1 | X | [5 empty] | Develop HEARING.TEXT
x | Develop HEARING.TEXT | [699 empty] | 1 | X | [5 empty] | Develop HEARING.MESSAGE.MAP
x | Develop HEARING.MESSAGE.MAP | Q | [698 empty] | 1 | X | [5 empty] | Develop HEARING.PRESENTATION
x | Develop HEARING.PRESENTATION | [699 empty] | 1 | X
x | Practice presentation | [699 empty] | 1 | X
x | Make presentation adjustments |  | Team | 7 | 26 | 2013-06-25 | 2013-07-03 | [693 empty] | 1 |  | 2013-06-25 | 2013-06-25
x | 1st loop |  | Team | 5 | 31 | 2013-07-03 | 2013-07-10 | [693 empty] | 1 |  | 2013-07-03 | 2013-07-03
| 2nd loop |  | Team | 1 | 31 | 2013-07-10 | 2013-07-10 | [693 empty] | 1 |  | 2013-07-10 | 2013-07-10
| 3rd loop |  | Team | 1 | 31 | 2013-07-10 | 2013-07-10 | [693 empty] | 1 |  | 2013-07-10 | 2013-07-10
x | Final loop |  | Team | 6 | 36 | 2013-07-10 | 2013-07-17 | [693 empty] | 1 |  | 2013-07-10 | 2013-07-10
| Generally, the core team does not need to save developmental drafts unless the document represents a significant shift in rulemaking direction. This applies to reviews or requests for input beyond the core team. For each document that had significant changes in any loop, save the document to Rules_Development using the same name followed by folder number and next higher version number. EXAMPLE: HEARING.TEXT-5.01, HEARING.TEXT-5.02... | [699 empty] | 1 | X
| Loop as needed | [699 empty] | 1 | X
x | Approve presentation |  | LM | 1 | 36 | 2013-07-17 | 2013-07-17 | [693 empty] | 1 |  | 2013-07-17 | 2013-07-17
| END OPTION | [699 empty] | 1 | X
x | Hold hearings (change dates under Overview of Key Dates) | [699 empty] | 1 | X | [5 empty] | Hold hearings (change dates under Overview of Key Dates)
x | Portland |  | Team, PO | 1 | 57 | 2013-08-15 | 2013-08-15 | [693 empty] | 1
| Enter city name hearing |  | Team, PO | 1 | 57 | 2013-08-15 | 2013-08-15 | [693 empty] | 1
| Enter city name hearing |  | Team, PO | 1 | 57 | 2013-08-15 | 2013-08-15 | [693 empty] | 1
| Enter city name hearing |  | Team, PO | 1 | 57 | 2013-08-15 | 2013-08-15 | [693 empty] | 1
| Enter city name hearing |  | Team, PO | 1 | 57 | 2013-08-15 | 2013-08-15 | [693 empty] | 1
| Enter city name hearing |  | Team, PO | 1 | 57 | 2013-08-15 | 2013-08-15 | [693 empty] | 1
| Enter city name hearing |  | Team, PO | 1 | 57 | 2013-08-15 | 2013-08-15 | [693 empty] | 1
| Enter city name hearing |  | Team, PO | 1 | 57 | 2013-08-15 | 2013-08-15 | [693 empty] | 1
x | Add info to COMMENTS |  | PO | 3 | 59 | 2013-08-15 | 2013-08-19 | [693 empty] | 1 |  | 2013-08-15 | 2013-08-19 |  |  |  | Add info to COMMENTS
x | Add PO report to STAFF.RPT |  | PO | 3 | 59 | 2013-08-15 | 2013-08-19 | [693 empty] | 1 |  | 2013-08-15 | 2013-08-19 |  |  |  | Add PO report to STAFF.RPT
x | CLOSE PUBLIC COMMENT | [5 empty] | 2013-08-19 | [693 empty] | 1 |  | 2013-08-19
x | Design Support (DS) Responsibility | [699 empty] | 1 | X
x | Enter data into COMMENTS | [699 empty] | 1 | X | [5 empty] | Enter data into COMMENTS
x | Steps 1, Step 2 worksheets |  | DS | 28 | 61 | 2013-07-15 | 2013-08-21 | [693 empty] | 1 |  | 2013-07-15 | 2013-09-10
x | Scan/Link COMMENTS.ID###.pdf |  | DS | 13 | 61 | 2013-08-05 | 2013-08-21 | [693 empty] | 1 |  | 2013-08-05 | 2013-09-10 |  |  |  | Scan/Link COMMENTS.ID###.pdf
x | Design Team Responsibility | [699 empty] | 1 | X
x | Develop COMMENTS | [699 empty] | 1 | X | [5 empty] | Develop COMMENTS
x | Enter comments |  | Team | 13 | 61 | 2013-08-05 | 2013-08-21 | [693 empty] | 1 |  | 2013-08-05 | 2013-09-10
x | Develop categories of responses |  | Team | 13 | 61 | 2013-08-05 | 2013-08-21 | [693 empty] | 1 |  | 2013-08-05 | 2013-09-10
x | Finalize DEQ response to comments |  | Team | 17 | 65 | 2013-08-05 | 2013-08-27 | [693 empty] | 1 |  | 2013-08-05 | 2013-09-10
x | 1st loop for LM approval of packet |  | LM | 4 | 68 | 2013-08-27 | 2013-08-30 | [693 empty] | 1 |  | 2013-08-05 | 2013-09-10
| 2nd loop for LM approval of packet |  | LM | 26 | 75 | 2013-08-05 | 2013-09-10 | [693 empty] | 1 |  | 2013-08-05 | 2013-09-10
| 3rd loop for LM approval of packet |  | LM | 26 | 75 | 2013-08-05 | 2013-09-10 | [693 empty] | 1 |  | 2013-08-05 | 2013-09-10
x | Final loop for LM approval of packet |  | LM | 3 | 72 | 2013-09-03 | 2013-09-05 | [693 empty] | 1 |  | 2013-08-05 | 2013-09-10
| Generally, the core team does not need to save developmental drafts unless the document represents a significant shift in rulemaking direction. This applies to reviews or requests for input beyond the core team. For each document that had significant changes in any loop, save the document to Rules_Development using the same name followed by folder number and next higher version number. EXAMPLE: COMMENTS-5.01, COMMENTs-5.02... | [699 empty] | 1 | X
| Loop as needed | [699 empty] | 1 | X
x | Close comment box in Outlook |  | DS | 1 | 72 | 2013-09-05 | 2013-09-05 | [693 empty] | 1 |  | 2013-09-05 | 2013-09-05
[701 empty] | W | X
| 6-EQC Preparation | [699 empty] | T | X
| Task |  | Owner | Task | Workdays | Start Task | End Task | [693 empty] | B | X
[5 empty] | 67 | 2013-07-15 | 2013-10-16 | [693 empty] | B | X | 2013-07-15 | 2013-10-16
[701 empty] | Y | X
x | Design Expert (DE) Responsibility |  | DE | 14 | 47 | 2013-07-15 | 2013-08-01 | [693 empty] | 1 |  | 2013-07-15 | 2013-09-10
x | STAFF.RPT.Permanent (blank in folder 6) | [699 empty] | 1 |  |  |  |  | STAFF.RPT.Permanent (blank in folder 6)
x | Select EQC recommendation in staff report | [699 empty] | 1 | X
x | Integrate NOTICE into staff report | [699 empty] | 1 | X |  |  |  | Integrate NOTICE into staff report
x | Verify PROPOSED.RULES current compilation | DEQ | [698 empty] | 1 | X |  |  |  | Verify PROPOSED.RULES.6.01
x | DO NOT MODIFY reviewed/executed sections: | [699 empty] | 1 | X
x | Statement of need | [699 empty] | 1 | X
x | Federal relationships | [699 empty] | 1 | X
x | Fiscal impact statement | [699 empty] | 1 | X
x | Fees | [699 empty] | 1 | X
x | Land use | [699 empty] | 1 | X
x | Design Team (DT) Responsibility |  | Team | 39 | 73 | 2013-07-15 | 2013-09-06 | [693 empty] | 1 |  | 2013-07-15 | 2013-09-10
x | Finalize following sections in STAFF.RPT.Permanent | [699 empty] | 1 | X |  |  |  | Finalize following sections in STAFF.RPT.Permanent
x | Overview | [699 empty] | 1 | X
x | Rules affected, authorities, supporting docs | [699 empty] | 1 | X
x | Implementation | [699 empty] | 1 | X
x | Public involvement | [699 empty] | 1 | X
x | Summary of comments and DEQ responses | [699 empty] | 1 | X
x | Commenters | [699 empty] | 1 | X
x | Approve as finalized | [699 empty] | 1 | X
x | Finalize EQC Packet: |  | DE | 40 | 74 | 2013-07-15 | 2013-09-09 | [693 empty] | 1 |  | 2013-07-15 | 2013-09-10 |  | STAFF.RPT.Permanent
x | STAFF.RPT.Permanent | [699 empty] | 1 | X |  |  |  | INVITATION.TO.COMMENT
x | PROPOSED RULES | [699 empty] | 1 | X |  |  |  | PROPOSED RULES
x | STATE IMPLEMENTATION PLAN | [699 empty] | 1 | X |  |  |  | STATE IMPLEMENTATION PLAN
x | Optional SUPPORTING.DOCS | [699 empty] | 1 | X |  |  |  | Optional SUPPORTING.DOCS
x | Review/approve EQC Packet | [699 empty] | 1 | X
x | 1st loop for packet approval |  | Team, LM, LA | 6 | 52 | 2013-08-01 | 2013-08-08 | [693 empty] | 1 |  | 2013-07-15 | 2013-09-10
x | 2nd loop for packet approval |  | Team, LM, LA | 5 | 58 | 2013-08-12 | 2013-08-16 | [693 empty] | 1 |  | 2013-08-08 | 2013-09-10
| 3rd loop for packet approval |  | Team, LM, LA | 17 | 75 | 2013-08-16 | 2013-09-10 | [693 empty] | 1 |  | 2013-08-16 | 2013-09-10
x | Final loop for packet approval |  | Team, LM, LA | 8 | 72 | 2013-08-26 | 2013-09-05 | [693 empty] | 1 |  | 2013-09-10 | 2013-09-10
| Generally, the core team does not need to save developmental drafts unless the document represents a significant shift in rulemaking direction. This applies to reviews or requests for input beyond the core team. For each document that had significant changes in any loop, save the document to Rules_Development using the same name followed by folder number and next higher version number. EXAMPLE: STAFF.RPT.Permanent-6.01,STAFF.RPT.Permanent-6.02... | [699 empty] | 1 | X
| Loop as needed | [699 empty] | 1 | X
x | Approve EQC PACKET |  | LM | 3 | 75 | 2013-09-06 | 2013-09-10 | [693 empty] | 1 |  | 2013-09-05 | 2013-09-10
x | SUBMIT EQC PACKET |  | DE | 1 | 75 | 2013-09-10 | 2013-09-10 | [693 empty] | 1 |  | 2013-09-10 | 2013-09-10
| Final OCO plain English review |  | SC | 5 | 79 | 2013-09-10 | 2013-09-16 | [693 empty] | 1 |  | 2013-09-10 | 2013-09-16
x | Develop EQC presentation |  | DE, Team | 66 | 100 | 2013-07-15 | 2013-10-15 | [693 empty] | 1 |  | 2013-07-15 | 2013-10-15
| START OPTION | [699 empty] | 1 | X
x | Practice presentation |  | Team | 5 | 94 | 2013-10-01 | 2013-10-07 | [693 empty] | 1 |  | 2013-10-15 | 2013-10-01
x | Make presentation adjustments |  | DE | 3 | 96 | 2013-10-07 | 2013-10-09 | [693 empty] | 1 |  | 2013-10-07 | 2013-10-07
| Loop as needed | [699 empty] | 1 | X
| END OPTION | [699 empty] | 1 | X
| ATTEND EQC MEETING | [5 empty] | 2013-10-16 | [693 empty] | 1 |  | 2013-10-16 | 2013-10-16
[701 empty] | W | X
| 7-Post EQC | [699 empty] | T | X
| Task |  | Owner | Task | Workdays | Start Task | End Task | [693 empty] | B | X
[5 empty] | 1 | 2013-09-10 | 2013-12-16 | [693 empty] | B | X | 2013-09-10 | 2013-12-16
[701 empty] | Y | X
| Design Expert Responsibility | [699 empty] | 0 | X
x | Prepare documents and notify ARC when done |  | DE,SE | 1 | 101 | 2013-10-16 | 2013-10-16 | [693 empty] | 1 |  | 2013-10-16 | 2013-10-16
x | EQC.RULES.10.16.2013 | [699 empty] | 1 | X | [5 empty] | EQC.RULES.10.16.2013
x | EQC.REDLINE.10.16.2013 | [699 empty] | 1 | X | [5 empty] | EQC.REDLINE.10.16.2013
x | 340-###-###.TABLE##-## | [699 empty] | 1 | X | [5 empty] | 340-###-###.TABLE##-##
x | EQC.ACTION | [699 empty] | 1 | X | [5 empty] | EQC.ACTION
| Fees not involved |  | DE, Fiscal staff | 48 | 13 | 2013-04-05 | 2013-06-15 | [693 empty] | 0 |  | 2013-04-05 | 2013-06-15 |  |  |  | Fees not involved
| a. SIGNED.PART.1 | [699 empty] | 0 | X | [5 empty] | a. SIGNED.PART.1
| b. FEE.EXCERPT.FROM.RULE | [699 empty] | 0 | X | [5 empty] | b. FEE.EXCERPT.FROM.RULE
| PROOF.OF.DAS.SUBMITTAL | [699 empty] | 0 | X | [5 empty] | PROOF.OF.DAS.SUBMITTAL
x | Optional STAKEHOLDER.NOTIFICATION |  | Team | 1 | 144 | 2013-12-16 | 2013-12-16 | [693 empty] | 1 |  | 2013-12-16 | 2013-12-16 |  |  |  | Optional STAKEHOLDER.NOTIFICATION
x | Optional LEGISLATOR.NOTICE |  | LA | 1 | 144 | 2013-12-16 | 2013-12-16 | [693 empty] | 1 |  | 2013-12-16 | 2013-12-16 |  |  |  | Optional LEGISLATOR.NOTICE
x | EPA.SIP |  | LA | 1 | 144 | 2013-12-16 | 2013-12-16 | [693 empty] | 1 |  | 2013-12-16 | 2013-12-16 |  |  |  | Optional LEGISLATOR.NOTICE
| AC.THANK.YOU | Q | Team | 1 | 144 | 2013-12-16 | 2013-12-16 | [693 empty] | 0 |  | 2013-12-16 | 2013-12-16 |  |  |  | COMMITTEE.THANK.YOU
| AC.SURVEY |  | Team | 1 | 144 | 2013-12-16 | 2013-12-16 | [693 empty] | 0 |  | 2013-12-16 | 2013-12-16 |  |  |  | COMMITTEE.SURVEY
x | YourName.EMAILS |  | Team | 1 | 144 | 2013-12-16 | 2013-12-16 | [693 empty] | 1 |  | 2013-12-16 | 2013-12-16 |  |  |  | YourName.EMAILS
x | EVALUATION |  | Team | 1 | 144 | 2013-12-16 | 2013-12-16 | [693 empty] | 1 |  | 2013-12-16 | 2013-12-16 |  |  |  | EVALUATION
x | Agency Rules Coordinator Responsibility | [699 empty] | 1 | X
x | Submit filing |  | MV | 1 | 103 | 2013-10-18 | 2013-10-18 | [693 empty] | 1 |  | 2013-10-18 | 2013-10-18
x | EFFECTIVE DATE |  |  | 1 | 103 | 2013-10-18 | 2013-10-18 | [693 empty] | 1 |  | 2013-10-18 | 2013-10-18
x | Save as PROOF.OF.SOS.FILING | [699 empty] | 1 | X | [5 empty] | Save as PROOF.OF.SOS.FILING
x | Save as PROOF.OF.LC.SUBMITTAL | [699 empty] | 1 | X | [5 empty] | Save as LC.SHUTTLE.PROOF
| No DAS involvement |  | MV | 108 | 75 | 2013-04-05 | 2013-09-10 | [693 empty] | 0 |  | 2013-04-05 | 2013-09-10 |  |  |  | No DAS involvement
| a. FEE.EXCERPT.FROM.RULE | [699 empty] | 0 | X | [5 empty] | a. FEE.EXCERPT.FROM.RULE
| b. FEE.EXEMPT.EMAIL | [699 empty] | 0 | X | [5 empty] | b. FEE.EXEMPT.EMAIL
| c. DAS.SHUTTLE.PROOF | [699 empty] | 0 | X | [5 empty] | c. DAS.SHUTTLE.PROOF
| Design Support Responsibility | [699 empty] | 1 | X
x | Lead archival process |  |  | 1 | 144 | 2013-12-16 | 2013-12-16 | [693 empty] | 1 |  | 2013-12-16 | 2013-12-16
[7 empty] | $T$9 | [694 empty] | X
B
Formulas:
Closed = IF(WEEKDAY(DW6)=2,[Closed, row below],"")
Closed = IF(WEEKDAY(QN6)=2,[Closed, row below],"")
Workday = IF(WEEKDAY(ER6)=2,[Workday, row below],"")
Workday = IF(WEEKDAY(RI6)=2,[Workday, row below],"")
Weekend = IF(WEEKDAY(HX6)=2,[Weekend, row below],"")
Weekend = IF(WEEKDAY(IZ6)=2,[Weekend, row below],"")
Workdays = NETWORKDAYS(TODAY(),[End Task])
Workdays = NETWORKDAYS([Start Task],S.BANNER.AdvisoryCommitteeEnd,S.DDL_DEQClosed)
This Task = NETWORKDAYS([Start Task],[End Task],S.DDL_DEQClosed)
mm/dd/yy
Subject
Your name
Your message
DEQ Closed
To restore any cell under columns G or H to default, place cursor in cell then enter "=AA" followed by the cell address. EXAMPLE: =AAH13 would restore the default EQC meeting.

## ConditionalFormat (hidden)
|  | Example | Calculation | Applies to | Last row
Column I: Section Separator codes
T | Section title | White on Teal | =IF($AAE4="T",TRUE) | =$B$4:$ZZ$474
Y | Highlight for section title | Teal on Yellow | =IF($AAE4="Y",TRUE) | "
W |  | White on white | =IF($AAE4="W",TRUE) | "
0 OR 1 | Indicates task involved/not involved | White on white | =IF($AAE4=0,TRUE) | "
Office Closure |  | See DDL worksheet | S.DDL_DEQClosed is the "holiday" table in WORKDAY function
|  | Office Closure date | =IF(WORKDAY($G20-1,1,S.DDL_DEQClosed)<>$G20,TRUE) | $G$20:$G$480 (or last row)
|  | Office Closure date | =IF(WORKDAY($H20-1,1,S.DDL_DEQClosed)<>$H20,TRUE) | $H$20:$H$480 (or last row)
|  | Date has past | =IF(WORKDAY($G10-1,1,S.DDL_DEQClosed)<>$G10,TRUE) | $G$10:$G$480 (or last row)
|  | " | =IF(WORKDAY($H10-1,1,S.DDL_DEQClosed)<>$H10,TRUE) | $H$10:$H$480 (or last row)
Gantt
| An 'X' in $J10 identifies the row as for Gantt to format | Workday | =AND($J10<>"X",$G10<=L$7,$H10>=K$7) | $K10:$AHC$450
|  | Weekend | =IF(OR(WEEKDAY(K$7)=1,WEEKDAY(K$7)=7),TRUE) | $K10:$AHC$450
|  | Closed | =IF(ISERROR(VLOOKUP(K$7,S.DDL_DEQClosed,1,FALSE)),0,1) | $K10:$AHC$450
S.LastCellGantt
s.LastCellschedule

## Sheet1
Key dates in the rulemaking schedule for October EQC adoption
SortA | SortB | Preparing the people involved | Who | Start | Deadline | Description
47 |  | Expand Core Team | LM,SE,DE | 2013-04-05 | 2013-04-15
48 |  | Notify new members | LM, Mgrs | 2013-04-05 | 2013-05-20
49 |  | Add rulemaking to work plans as needed | LM, Mgrs | 2013-04-05 | 2013-04-05
50 |  | Team kickoff meeting/training/work session | Team,LA | 2013-05-20 | 2013-05-20
51 |  | Maintaining rulemaking record
52 |  | File naming conventions
53 |  | Rulemaking SharePoint
54 |  | Shared drive: Rules _Development
55 |  | Discuss Overview of Key Dates above
56 |  | Overview of main external work products
64 |  | Review/refine RESOURCES
65 |  | Review/refine CONSIDERATIONS
66 |  | Schedule recurring team meetings
67 |  | Obtain rules and new numbers if needed | DE, SE. MV | 2013-05-20 | 2013-05-31 | Rule Coordinators and Rule Writer obtain rules and new numbers if needed
68 |  | Save rules as PROPOSED.RULES | DE | 2013-05-31 | 2013-05-31 | Rule Coordinator saves rules as PROPOSED.RULES
69 |  | Work with SOS on any new division/rule numbers | DE,MV | 2013-04-05 | 2013-04-05 | Rule Coordinators work with SOS to establish any new division or rule numbers
70 |  | Identify land use rules | SE,DE | 2013-04-05 | 2013-05-31 | Rule Writer identifies land use rules
Public Notice
71 |  | State Implementation Plan | SE,SIPCo | 2013-04-15 | 2013-07-01
78 |  | Submit Notice to EPA - 45 day before 1st hearing | SE,SIPCo |  | 2013-07-01 | Rule Writer and Rule Coordinator obtain EPA’s unofficial approval of SIP rulemaking materials. Rule Writer, Rule Coordinator, Margaret Oliphant, and Rule Writer's manager involve EPA early on in rule development. Rule Writer works directly with the EPA project manager (e.g. Kristin Hall, Claudia Vaupel) to ensure the technical content of the rulemaking satisfies EPA's SIP requirements. Rule Coordinator works directly with the EPA project manager and the Rule Writer to ensure DEQ has met the procedural requirements for a SIP (e.g. holding a hearing)
28 |  | SOS - submit on workday <=15th of month BEFORE Bulletin (H29) |  |  | 2013-07-15 | Rule Coordinator faxes and emails rule documents to SOS
29 |  | SOS - Bulletin always publishes 1st of month |  |  | 2013-08-01 | SOS publishes the proposed rulemaking in its Bulletin. Rule Writer verifies SOS published the bulletin accurately.
254 |  | FIRST hearing | Portland | 6 p.m. | 2013-08-15 | Rule Writer and Presiding Officer hold hearing
262 |  | Reserve venues/equipment hearings | DS | 2013-05-15 | 2013-06-03 | Rule Coordinator reserves any necessary venues or equipment (digital recorder) for the hearing
264 |  | Draft program WEBPAGE | DE, Team | 2013-05-31 | 2013-06-05 | Rule Writer identifies whether an existing DEQ webpage is relevent to the rulemaking. Rule Writer, William Knight, and Rule Writer's Manager decide whether rulemaking mertis its own webpage, or whether we should add information about the rulemaking to the existing webpage.
265 |  | Content contributions | SE, Team, SC | 2013-06-05 | 2013-06-10 | Content contributions
266 |  | 1st loop for LM approval of webpage | LM | 2013-06-10 | 2013-06-14 | 1st loop for LM approval of webpage
269 |  | Final loop for LM approval of webpage | LM | 2013-06-14 | 2013-06-20 | Final loop for LM approval of webpage
Draft Public Notice Packet
271 |  | Develop Notice Packet | DE | 2013-04-05 | 2013-06-14 | Rule Writer and Manager take the lead on developing the Notice Packet. Rule Coordinator assists with process.
273 |  | a. INVITATION.TO.COMMENT (blank in folder 4) | Team | 2013-04-05 | 2013-06-14
274 |  | b. PROPOSED.RULES | DE | 2013-04-05 | 2013-06-14 | Rule Coordinator provides Rule Writer the latest version of the rules
275 |  | Verify using latest rules | DE | 2013-04-05 | 2013-06-14 | Rule Coordinator verifies with SOS that DEQ has the latest version of the rules
276 |  | c. NOTICE (blank in folder 4) | Team | 2013-04-05 | 2013-06-14
277 |  | Overview
278 |  | Statement of need
279 |  | Federal relationships
280 |  | Rules affected, authorities, supporting docs
281 |  | Statement of fiscal impact
283 |  | Land use
284 |  | d. SUPPORTING.DOCS | Team | 2013-04-05 | 2013-06-14
285 |  | e. SIP | SIPCo | 2013-04-05 | 2013-06-14
286 |  | Draft ##AD if needed | Team | 2013-05-31 | 2013-06-14 | Rule Writer drafts adverstisement. Rule Coordinator submits adverstisement to News Media
287 |  | Identify hearings officers | DE | 2013-05-20 | 2013-06-14 | Need process for this.
288 |  | Get Notice Packet recommendations from RESOURCES | DE | 2013-04-05 | 2013-06-14 | Rule Writer obtain review of rulemaking material from Robin Williams, William Knight
290 |  | Budget-Statement of fiscal impact
291 |  | SIP Coordinator-as needed for b. & e. above
292 |  | DOJ-as needed for b. and c. above
293 |  | ARC and OCO-for entire Notice Packet
Manager approval for entire Notice Packet
294 |  | 1st loop for LM approval of packet | LM | 2013-05-31 | 2013-06-04 | 1st loop for LM approval of packet
297 |  | Final loop for LM approval of packet | LM | 2013-06-13 | 2013-06-13 | Final loop for LM approval of packet
300 |  | LA briefing meeting | Team, LA | 2013-06-14 | 2013-06-14 | LA briefing meeting
301 |  | OPEN preview period for Notice Packet | LA, DE |  | 2013-06-14 | OPEN preview period for Notice Packet
302 |  | Notify EMT |  |  |  | Notify EMT
303 |  | Notify DEQ contributing RESOURCES |  |  |  | Notify DEQ contributing RESOURCES
304 |  | CLOSE Notice Packet preview period | DE |  | 2013-06-21 | CLOSE Notice Packet preview period
305 |  | Decide how to address any feedback | Team | 2013-06-21 | 2013-07-01 | Decide how to address any feedback
306 |  | Modify notice documents as needed | DE | 2013-06-21 | 2013-07-03 | Modify notice documents as needed
307 |  | Obtain BUDGET.REVIEW.FISCAL | DE | 2013-07-09 | 2013-07-11 | Obtain BUDGET.REVIEW.FISCAL
308 |  | Verify compilation of PROPOSED.RULES | DE | 2013-07-09 | 2013-07-09 | Verify compilation of PROPOSED.RULES
309 |  | Obtain managers approval of Notice Packet | DE,LM,LA | 2013-07-03 | 2013-07-11 | Obtain managers approval of Notice Packet
310 |  | Notify ARC Notice Packet approved | DE | 2013-07-11 | 2013-07-11 | Notify ARC Notice Packet approved
311 |  | Submit SIP & DOJ approval to EPA | SIPCo | 2013-07-11 | 2013-07-11 | Submit SIP & DOJ approval to EPA
312 |  | Perform final plain English review if changes | ARC/SC | 2013-07-11 | 2013-07-15 | Perform final plain English review if changes
314 |  | ARC Actions - Submit/save official notifications: | MV | 2013-07-15 | 2013-08-01 | ARC Actions - Submit/save official notifications:
315 |  | SOS.EMAIL.PROOF |  |  |  | SOS.EMAIL.PROOF
316 |  | SOS.NOTICE.PROOF |  |  |  | SOS.NOTICE.PROOF
317 |  | SOS.FISCAL.PROOF |  |  |  | SOS.FISCAL.PROOF
318 |  | SOS.HOUSING.COSTS |  |  |  | SOS.HOUSING.COSTS
319 |  | LC.NOTICE |  |  |  | LC.NOTICE
323 |  | Design Support Responsibility | DS, webrep | 2013-07-15 | 2013-07-15 | Design Support Responsibility
324 |  | Post Notice Packet to Rules Registry |  |  |  | Post Notice Packet to Rules Registry
325 |  | Test public comment box |  |  |  | Test public comment box
326 |  | Add hearing dates to DEQ meeting calendar |  |  |  | Add hearing dates to DEQ meeting calendar
327 |  | Notify EQC Assistant of target EQC date |  |  |  | Notify EQC Assistant of target EQC date
328 |  | GovDelivery, including advisory committee |  |  |  | GovDelivery, including advisory committee
329 |  | GOV.DELIVERY.CONTENT" |  |  |  | GOV.DELIVERY.CONTENT"
330 |  | Save AGENCY.MAILING.LIST |  |  |  | Save AGENCY.MAILING.LIST
331 |  | Save PROOF.OF.DELIVERY |  |  |  | Save PROOF.OF.DELIVERY
332 |  | Design Expert Responsibility | DE, Fiscal | 2013-07-15 | 2013-07-15 | Design Expert Responsibility
333 |  | Send KEY.LEG.NOTICE |  |  |  | Send KEY.LEG.NOTICE
334 |  | Save KEY.LEG.PROOF |  |  |  | Save KEY.LEG.PROOF
335 |  | Publish in local newspaper if required |  |  |  | Publish in local newspaper if required
336 |  | Save ##PRINT.PROOF |  |  |  | Save ##PRINT.PROOF
337 |  | Verify notice published accurately in Bulletin |  |  |  | Verify notice published accurately in Bulletin
338 |  | Save BULLETIN.PROOF |  |  |  | Save BULLETIN.PROOF
Prepare for hearing
344 |  | Design Support Responsibilities | DS | 2013-06-25 | 2013-07-10 | Design Support Responsibilities
345 |  | Verify venues and equipment reservations |  |  |  | Design Support (Mark Nelson?? Carol Thornberg??) to verify venues and equipment reservations
346 |  | Gather supplies |  |  |  | Gather supplies
347 |  | Design Team Responsibilities | Team | 2013-06-25 | 2013-08-01 | Design Team Responsibilities
348 |  | START OPTION - information meeting |  |  |  | Rule Coordinator provides Rule Writer and Presiding Officer the template for hearings text. Rule Writer and Rule Writer's Manager develop and approve hearing presentation.
349 |  | Develop HEARING.TEXT
350 |  | Develop HEARING.MESSAGE.MAP
351 |  | Develop HEARING.PRESENTATION
352 |  | Practice presentation
353 |  | Make presentation adjustments | Team | 2013-06-25 | 2013-07-03
354 |  | 1st loop | Team | 2013-07-03 | 2013-07-10
357 |  | Final loop | Team | 2013-07-10 | 2013-07-17
360 |  | Approve presentation | LM | 2013-07-17 | 2013-07-17
13 |  | Director's Dialog |  |  | 2013-06-19 | Rule Writer's Manager provides Division Adminsitrator and Stephanie Caldera material for Director's Dialogue.
362 |  | Hold hearings (change dates under Overview of Key Dates) |  |  |  | Hold hearings (change dates under Overview of Key Dates)
363 |  | Portland | Team, PO | 2013-08-15 | 2013-08-15 | Portland
32 |  | Close PUBLIC COMMENT |  |  | 2013-08-19
373 |  | CLOSE PUBLIC COMMENT |  |  | 2013-08-19 | CLOSE PUBLIC COMMENT
371 |  | Add info to COMMENTS | PO | 2013-08-15 | 2013-08-19
372 |  | Add PO report to STAFF.RPT | PO | 2013-08-15 | 2013-08-19 | Add PO report to STAFF.RPT
374 |  | Design Support (DS) Responsibility |  |  |  | Design Support (DS) Responsibility
375 |  | Enter data into COMMENTS |  |  |  | Enter data into COMMENTS
376 |  | Steps 1, Step 2 worksheets | DS | 2013-07-15 | 2013-08-21 | Steps 1, Step 2 worksheets
377 |  | Scan/Link COMMENTS.ID###.pdf | DS | 2013-08-05 | 2013-08-21 | Scan/Link COMMENTS.ID###.pdf
378 |  | Design Team Responsibility |  |  |  | Design Team Responsibility
379 |  | Develop COMMENTS |  |  |  | Develop COMMENTS
380 |  | Enter comments | Team | 2013-08-05 | 2013-08-21 | Enter comments
381 |  | Develop categories of responses | Team | 2013-08-05 | 2013-08-21 | Develop categories of responses
382 |  | Finalize DEQ response to comments | Team | 2013-08-05 | 2013-08-27 | Finalize DEQ response to comments
383 |  | 1st loop for LM approval of packet | LM | 2013-08-27 | 2013-08-30 | 1st loop for LM approval of packet
386 |  | Final loop for LM approval of packet | LM | 2013-09-03 | 2013-09-05 | Final loop for LM approval of packet
389 |  | Close comment box in Outlook | DS | 2013-09-05 | 2013-09-05 | Rule Coordinator send request to HQ Help desk to close the comment inbox.
EQC Staff Report
395 |  | Design Expert (DE) Responsibility | DE | 2013-07-15 | 2013-08-01 | Design Expert (DE) Responsibility
396 |  | STAFF.RPT.Permanent (blank in folder 6) |  |  |  | STAFF.RPT.Permanent (blank in folder 6)
397 |  | Select EQC recommendation in staff report |  |  |  | Select EQC recommendation in staff report
398 |  | Integrate NOTICE into staff report |  |  |  | Integrate NOTICE into staff report
399 |  | Verify PROPOSED.RULES current compilation |  |  |  | Verify PROPOSED.RULES current compilation
400 |  | DO NOT MODIFY reviewed/executed sections:
401 |  | Statement of need
402 |  | Federal relationships
403 |  | Fiscal impact statement
404 |  | Fees
405 |  | Land use
406 |  | Design Team (DT) Responsibility | Team | 2013-07-15 | 2013-09-06 | Design Team (DT) Responsibility
407 |  | Finalize following sections in STAFF.RPT.Permanent |  |  |  | Finalize following sections in STAFF.RPT.Permanent
408 |  | Overview |  |  |  | Overview
409 |  | Rules affected, authorities, supporting docs |  |  |  | Rules affected, authorities, supporting docs
410 |  | Implementation |  |  |  | Implementation
411 |  | Public involvement |  |  |  | Public involvement
412 |  | Summary of comments and DEQ responses |  |  |  | Summary of comments and DEQ responses
413 |  | Commenters |  |  |  | Commenters
414 |  | Approve as finalized |  |  |  | Approve as finalized
415 |  | Finalize EQC Packet: | DE | 2013-07-15 | 2013-09-09 | Finalize EQC Packet:
416 |  | STAFF.RPT.Permanent
417 |  | PROPOSED RULES
418 |  | STATE IMPLEMENTATION PLAN
419 |  | Optional SUPPORTING.DOCS
420 |  | Review/approve EQC Packet |  |  |  | Review/approve EQC Packet
421 |  | 1st loop for packet approval | Team, LM, LA | 2013-08-01 | 2013-08-08 | Rule Writer submits EQC packet to Rule Writer's Manager, Andy Ginsburg, Rule Coordinator, and William Knight for review. Reviewers return comments by deadline. Rule Writer addresses comments.
422 |  | 2nd loop for packet approval | Team, LM, LA | 2013-08-12 | 2013-08-16 | Rule Writer submits revised EQC packet to Rule Writer's Manager, Andy Ginsburg, Rule Coordinator, and William Knight for review. Reviewers return comments by deadline. Rule Writer addresses comments.
424 |  | Final loop for packet approval | Team, LM, LA | 2013-08-26 | 2013-09-05 | Rule Writer submits revised EQC packet to Rule Writer's Manager, Andy Ginsburg, Rule Coordinator, and William Knight for review. Reviewers return comments by deadline. Rule Writer addresses comments.
427 |  | Approve EQC PACKET | LM | 2013-09-06 | 2013-09-10 | Rule Writer's Manager approves the EQC staff report and materials for submittal to the Director's Office.
428 |  | SUBMIT EQC PACKET | DE | 2013-09-10 | 2013-09-10 | Rule Coordinator submits EQC packet to Stephanie Caldera
430 |  | Develop EQC presentation | DE, Team | 2013-07-15 | 2013-10-15 | Rule Coordinator provides template for EQC presentations to Rule Writer. Rule Writer adds rulemaking presentation to template.
432 |  | Practice presentation | Team | 2013-10-01 | 2013-10-07 | Rule Writer practices presentation with Rule Writer's manager and likely PMT
433 |  | Make presentation adjustments | DE | 2013-10-07 | 2013-10-09 | Rule Writer addresses feedback, revises presentation as needed
35 |  | Present EQC Action Item |  |  | 2013-10-16 | Rule Writer presents rulemaking proposal to EQC
37 |  | SOS - file rules |  |  | 2013-10-18 | SOS - file rules
443 |  | Prepare documents and notify ARC when done | DE,SE | 2013-10-16 | 2013-10-16 | Prepare documents and notify ARC when done
444 |  | EQC.RULES.10.16.2013 |  |  |  | EQC.RULES.10.16.2013
445 |  | EQC.REDLINE.10.16.2013 |  |  |  | EQC.REDLINE.10.16.2013
446 |  | 340-###-###.TABLE##-## |  |  |  | 340-###-###.TABLE##-##
447 |  | EQC.ACTION |  |  |  | EQC.ACTION
452 |  | Optional STAKEHOLDER.NOTIFICATION | Team | 2013-12-16 | 2013-12-16 | Optional STAKEHOLDER.NOTIFICATION
453 |  | Optional LEGISLATOR.NOTICE | LA | 2013-12-16 | 2013-12-16 | Optional LEGISLATOR.NOTICE
454 |  | EPA.SIP | LA | 2013-12-16 | 2013-12-16 | EPA.SIP
457 |  | YourName.EMAILS | Team | 2013-12-16 | 2013-12-16 | YourName.EMAILS
458 |  | EVALUATION | Team | 2013-12-16 | 2013-12-16 | EVALUATION
459 |  | Agency Rules Coordinator Responsibility |  |  |  | Agency Rule Coordinator Responsibility
460 |  | Submit filing | MV | 2013-10-18 | 2013-10-18 | Submit filing
461 |  | EFFECTIVE DATE |  | 2013-10-18 | 2013-10-18 | EFFECTIVE DATE
38 |  | EPA - submit SIP |  |  | 2013-10-30 | EPA - submit SIP
40 |  | Rules become effective |  |  | 2013-10-18 | Rules become effective
462 |  | Save as PROOF.OF.SOS.FILING |  |  |  | Save as PROOF.OF.SOS.FILING
463 |  | Save as PROOF.OF.LC.SUBMITTAL |  |  |  | Save as PROOF.OF.LC.SUBMITTAL
469 |  | Lead archival process |  | 2013-12-16 | 2013-12-16 | Lead archival process