## Modified Schedule
January Special EQC Conference Call - Longer-term Financing Rulemaking
Activity | Date | Notes
Advisory Committee meetings | 8/7 and 9/5/2013
Post-Advisory Committee internal meetings | 8/14 and 9/10/2013
Prepare rulemaking packet | 9/5-9/25/2013
EPA review proposed rules | 9/15-9/25/2013 | EPA Region 10 reviews proposed rules for "fatal flaws"
Rulemaking packet internal review | 9/26-10/8/2013 | Usually want 30 days of review, will do a quick 2 week review
Rulemaking packet approved | 2013-10-11
Submit SOS Notice | 2013-10-15
Director's dialog | 2013-10-16
SOS Notice published | 2013-11-01 | Public comment period starts
EPA review and approval | 10/15/2013-1/15/2014 | Contingency plan will be in place for a late EPA Regional and HQ approval
Public hearings (3) | 11/18-11/26/2013
Close public comment period | 2013-12-02
Prepare staff report | 12/3-12/17/2013
Submit staff report | 12/18/2013-1/6/2014 | Due 6 weeks prior to EQC meeting, flexibility allowed for 2-3 weeks
Present EQC action item | Late Jan. 2014
SOS - file rules | Late Jan. 2014
Rules become effective | Late Jan. 2014