**New Timeline for Longer-term Financing Rulemaking**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Activity** | **Date** | **Notes** |   |   |   |   |   |
| Advisory Committee meetings  | 8/7 and 9/5/2013 |   |  |  |  |  |   |
| Post-Advisory Committee internal meetings | 8/14 and 9/10/2013 |   |  |  |  |  |   |
| Prepare rulemaking packet | 9/5-9/25/2013 |   |  |  |  |  |   |
| EPA review proposed rules | 9/15-9/25/2013 | EPA Region 10 reviews proposed rules for "fatal flaws" |
| Rulemaking packet internal review | 9/26-10/8/2013 | Usually want 30 days of review, will do a quick 2 week review |
| Rulemaking packet approved | 10/11/2013 |   |  |  |  |  |   |
| Submit SOS Notice  | 10/15/2013 |   |  |  |  |  |   |
| Director's dialog | 10/16/2013 |   |  |  |  |  |   |
| SOS Notice published | 11/1/2013 | Public comment period starts |  |  |   |
| EPA review and approval | 10/15/2013-1/15/2014 | Contingency plan will be in place for a late EPA Regional and HQ approval |
| Public hearings (3) | 11/18-11/26/2013 |   |  |  |  |  |   |
| Close public comment period | 12/2/2013 |   |  |  |  |  |   |
| Prepare staff report | 12/3-12/17/2013 |   |  |  |  |  |   |
| Submit staff report  | 12/18/2013-1/6/2014 | Due 6 weeks prior to EQC meeting, flexibility allowed for 2-3 weeks |
| Present EQC action item  | Late Jan. 2014 |   |  |  |  |  |   |
| SOS - file rules | Late Jan. 2014 |   |  |  |  |  |   |
| Rules become effective | Late Jan. 2014 |   |   |   |   |   |   |