## Modified Schedule
January Special EQC Conference Call
Activity | Date | Notes
Director's dialog | 2013-08-21
End Advisory Committee meetings | Week of 8/26-29th or as scheduled for 9/5
Notice packet ready for internal review | 2013-09-11 | Usually want 30 days of review, could do a quick 2 week review
Notice packet approved | 2013-10-11
Submit SOS notice | 2013-10-15
SOS notice published | 2013-11-01
EPA review and approval | 10/15/2013-1/15/2014 | EPA Region 10 and HQ approval could take 3-4+ months
Public hearings (3) | 11/18-11/26/2013
Close public comment period | 2013-12-02
Submit staff report | 2013-11-29 | Due 6 weeks prior to EQC, flexibility might be possible
Present EQC action item | 2014-01-10
SOS - file rules | 2014-01-14
Rules become effective | 2014-01-14
Highlighted activity notes challenging timeframe