## Modified Schedule
Scenario 1: December EQC Meeting
Activity | Date | Notes
Director's dialog | 2013-08-21
End Advisory Committee meetings | Week of 8/26-8/29 | Recommendations report would need to be done quickly for notice
Notice packet ready for internal review | End of August
Notice packet approved | 2013-09-09 | Usually want 30 days of review, could do a quick 2 week review
Submit SOS notice | 2013-09-13
SOS notice published | 2013-10-01
EPA review and approval | 9/13-12/13/2013 | EPA Region 10 and HQ approval could take 3-4+ months
Public hearings (3) | 10/16-10/22/2013
Close public comment period | 2013-10-31
Submit staff report | 2013-11-01 | Due 6 weeks prior to EQC, flexibility might be possible
Present EQC action item | 2013-12-11
SOS - file rules | 2013-12-13
Rules become effective | 2013-12-13
Scenario 2: January Special EQC Conference Call
Activity | Date | Notes
Director's dialog | 2013-08-21
End Advisory Committee meetings | Week of 8/26-29th or as scheduled for 9/5
Notice packet ready for internal review | 2013-09-11 | Usually want 30 days of review, could do a quick 2 week review
Notice packet approved | 2013-10-11
Submit SOS notice | 2013-10-15
SOS notice published | 2013-11-01
EPA review and approval | 10/15/2013-1/15/2014 | EPA Region 10 and HQ approval could take 3-4+ months
Public hearings (3) | 11/18-11/26/2013
Close public comment period | 2013-12-02
Submit staff report | 2013-11-29 | Due 6 weeks prior to EQC, flexibility might be possible
Present EQC action item | 2014-01-10
SOS - file rules | 2014-01-14
Rules become effective | 2014-01-14
Highlighted activity notes challenging timeframe