|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Scenario 1: December EQC Meeting |  |  |  |  |  |  |  |
| **Activity** | **Date** | **Notes** |  |  |  |  |  |
| Director's dialog | 8/21/2013 |  |  |  |  |  |  |
| End Advisory Committee meetings | Week of 8/26-8/29 | Recommendations report would need to be done quickly for notice | | | | | |
| Notice packet ready for internal review | End of August |  |  |  |  |  |  |
| Notice packet approved | 9/9/2013 | Usually want 30 days of review, could do a quick 2 week review | | | | | |
| Submit SOS notice | 9/13/2013 |  |  |  |  |  |  |
| SOS notice published | 10/1/2013 |  |  |  |  |  |  |
| EPA review and approval | 9/13-12/13/2013 | Expect to have to go through EPA Region 10 and HQ | | | | | |
| Public hearings (3) | 10/16-10/22/2013 |  |  |  |  |  |  |
| Close public comment period | 10/31/2013 |  |  |  |  |  |  |
| Submit staff report | 11/1/2013 | Due 6 weeks prior to EQC, flexibility might be possible | | | | | |
| Present EQC action item | 12/11/2013 |  |  |  |  |  |  |
| SOS - file rules | 12/13/2013 |  |  |  |  |  |  |
| Rules become effective | 12/13/2013 |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |
| Scenario 2: January Special EQC Conference Call | |  |  |  |  |  |  |
| **Activity** | **Date** | **Notes** |  |  |  |  |  |
| Director's dialog | 8/21/2013 |  |  |  |  |  |  |
| End Advisory Committee meetings | Week of 8/26-29th or as scheduled for 9/5 |  |  |  |  |  |  |
| Notice packet ready for internal review | 9/11/2013 | Usually want 30 days of review, could do a quick 2 week review | | | | | |
| Notice packet approved | 10/11/2013 |  |  |  |  |  |  |
| Submit SOS notice | 10/15/2013 |  |  |  |  |  |  |
| SOS notice published | 11/1/2013 |  |  |  |  |  |  |
| EPA review and approval | 10/15/2013-1/15/2014 | Expect to have to go through EPA Region 10 and HQ | | | | | |
| Public hearings (3) | 11/18-11/26/2013 |  |  |  |  |  |  |
| Close public comment period | 12/2/2013 |  |  |  |  |  |  |
| Submit staff report | 11/29/2013 | Due 6 weeks prior to EQC, flexibility might be possible | | | | | |
| Present EQC action item | 1/10/2014 |  |  |  |  |  |  |
| SOS - file rules | 1/14/2014 |  |  |  |  |  |  |
| Rules become effective | 1/14/2014 |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |
| Highlighted activity notes challenging timeframe |  |  |  |  |  |  |  |