## Modified Schedule
Activity | Date | Notes
EQC rulemaking action item | 2013-12-11
Director's dialog | 2013-08-21
End Advisory Committee meetings | August 7th, day long meeting? | Recommendations report would need to be done quickly so can be included in notice
Notice packet ready for internal review | End of August
Notice packet go through reviews | 2013-09-09 | Usually want 30 days of review, could do a quick 2 week review
Submit SOS notice | 2013-09-13
EPA review | 9/13-11/29? | Expect to have to go through EPA HQ
SOS notice published | 2013-10-01
Hearings | 10/16-10/22/2013 | Option is a I-link for these hearings, 1 hearing date and have videoing other places
Close public comment period | 2013-10-25 | Do we anticipate lots of comments? Need time to incorporate into staff report - could be days to weeks
Submit staff report (6 weeks prior to EQC) | 2013-11-01
Present EQC action item | 2013-12-11
SOS - file rules | 2013-12-13
Rules become effective | 2013-12-13