## DDLs (hidden)
DDLs called from ScheduleTasks
1 | 2 | 3 | 4 | 5 | 6
DDL_EQCMeeting | EQCStaffRptDue | EQCMaterialsDue | Days to next | Next | Last
2013-03-20 | 2013-02-11 | 2013-03-13 | 91 | 2013-06-19 | 2012-12-16
2013-06-19 | 2013-05-10 | 2013-06-12 | 63 | 2013-08-21 | 2013-03-20
2013-08-21 | 2013-07-16 | 2013-08-14 | 56 | 2013-10-16 | 2013-06-19
2013-10-16 | 2013-09-10 | 2013-10-09 | 56 | 2013-12-11 | 2013-08-21
2013-12-11 | 2013-11-01 | 2013-12-04 | 98 | 2014-03-19 | 2013-10-16
2014-03-19 | 2014-02-06 | 2014-03-07 | 91 | 2014-06-18 | 2013-12-11
2014-06-18 | 2014-05-08 | 2014-06-06 | 63 | 2014-08-20 | 2014-03-19
2014-08-20 | 2014-07-10 | 2014-08-08 | 56 | 2014-10-15 | 2014-06-18
2014-10-15 | 2014-09-04 | 2014-10-03 | 56 | 2014-12-10 | 2014-08-20
2014-12-10 | 2014-10-30 | 2014-11-28 | 98 | 2015-03-18 | 2014-10-15
2015-03-18 | 2015-02-05 | 2015-03-06 | 92 | 2015-06-18 | 2014-12-10
2015-06-18 | 2015-05-08 | 2015-06-08 | 63 | 2015-08-20 | 2015-03-18
2015-08-20 | 2015-07-10 | 2015-08-10 | 63 | 2015-10-22 | 2015-06-18
2015-10-22 | 2015-09-11 | 2015-10-12 | 56 | 2015-12-17 | 2015-08-20
2015-12-17 | 2015-11-06 | 2015-12-07 | 90 | 2016-03-16 | 2015-10-22
2016-03-16 | 2016-02-04 | 2016-03-04 | 91 | 2016-06-15 | 2015-12-17
2016-06-15 | 2016-05-05 | 2016-06-03 | 91
http://www.leg.state.or.us/ors/187.html
DEQClosed | [5 empty] | LEGAL HOLIDAYS 187.010 Legal holidays; acts deferred to next business day; effect on labor agreements. (1) The following days are legal holidays in this state: (a) Each Sunday. (b) New Year’s Day on January 1. (c) Martin Luther King, Jr.’s Birthday on the third Monday in January. (d) Presidents Day, for the purpose of commemorating Presidents Washington and Lincoln, on the third Monday in February. (e) Memorial Day on the last Monday in May. (f) Independence Day on July 4. (g) Labor Day on the first Monday in September. (h) Veterans Day on November 11. (i) Thanksgiving Day on the fourth Thursday in November. (j) Christmas Day on December 25. (2) Each time a holiday, other than Sunday, listed in subsection (1) of this section falls on Sunday, the succeeding Monday shall be a legal holiday. Each time a holiday listed in subsection (1) of this section falls on Saturday, the preceding Friday shall be a legal holiday. (3) Any act authorized, required or permitted to be performed on a holiday as designated in this section may be performed on the next succeeding business day; and no liability or loss of rights of any kind shall result from such delay. (4) In enumerating legal holidays in subsection (1) of this section, the Legislative Assembly does not intend to limit or otherwise affect public or private collective bargaining or collective bargaining agreements. [Amended by 1955 c.4 §1; 1969 c.455 §1; 1973 c.51 §1; 1975 c.633 §1; 1977 c.135 §1; 1977 c.321 §1; 1985 c.518 §1] 187.020 Additional legal holidays. In addition to those specified in ORS 187.010, the following days are legal holidays in this state: (1) Every day appointed by the Governor as a holiday. (2) Every day appointed by the President of the United States as a day of mourning, rejoicing or other special observance only when the Governor also appoints that day as a holiday. [Amended by 1969 c.455 §2; 1975 c.633 §2; 1977 c.135 §2; 1977 c.321 §2; 1985 c.518 §2]
2013-01-01 | New Year | 2013-01-01
2013-01-18 | furlough | 2013-01-18
2013-01-21 | MLK Jr. | 2013-01-21
2013-02-18 | Presidents | 2013-02-18
2013-04-19 | furlough | 2013-04-19
2013-05-24 | furlough | 2013-05-24
2013-05-27 | Memorial | 2013-05-27
2013-07-04 | Independence | 2013-07-04
2013-09-02 | Labor | 2013-09-02
2013-11-11 | Veterans | 2013-11-11
2013-11-28 | Thanksgiving | 2013-11-28
2013-12-25 | Christmas | 2013-12-25
2014-01-01 | New Year | 2014-01-01
2014-01-20 | MLK Jr. | 2014-01-20
2014-02-17 | Presidents | 2014-02-17
2014-05-26 | Memorial | 2014-05-26
2014-07-04 | Independence | 2014-07-04
2014-09-02 | Labor | 2014-09-02
2014-11-11 | Veterans | 2014-11-11
2014-11-27 | Thanksgiving | 2014-11-27
2014-12-25 | Christmas | 2014-12-25
2015-01-01 | New Year | 2015-01-01
2015-01-19 | MLK Jr. | 2015-01-19
2015-02-16 | Presidents | 2015-02-16
2015-05-25 | Memorial | 2015-05-25
2015-07-03 | Independence | 2015-07-03
2015-09-07 | Labor | 2015-09-07
2015-11-11 | Veterans | 2015-11-11
2015-11-26 | Thanksgiving | 2015-11-26
2015-12-25 | Christmas | 2015-12-25
2016-01-01 | New Year | 2016-01-01
2016-01-18 | MLK Jr. | 2016-01-18
2016-02-15 | Presidents | 2016-02-15
2016-05-30 | Memorial | 2016-05-30
2016-07-04 | Independence | 2016-07-04
2016-09-05 | Labor | 2016-09-05
2016-11-11 | Veterans | 2016-11-11
2016-11-24 | Thanksgiving | 2016-11-24
2016-12-26 | Christmas | 2016-12-26
2017-01-02 | New Year | 2017-01-02
2017-01-16 | MLK Jr. | 2017-01-16
2017-02-20 | Presidents | 2017-02-20
2017-05-29 | Memorial | 2017-05-29
2017-07-04 | Independence | 2017-07-04
2017-09-04 | Labor | 2017-09-04
2017-11-10 | Veterans | 2017-11-10
2017-11-23 | Thanksgiving | 2017-11-23
2017-12-25 | Christmas | 2017-12-25
2018-01-01 | New Year | 2018-01-01
Called from ScheduleTasks
DDL_Bulletin | VL_Bulletin
2013-01-01 | 2012-12-14 | 2012-12-14
2013-02-01 | 2013-01-15 | 2013-01-15
2013-03-01 | 2013-02-15 | 2013-02-15
2013-04-01 | 2013-03-15 | 2013-03-15
2013-05-01 | 2013-04-15 | 2013-04-15
2013-06-01 | 2013-05-15 | 2013-05-15
2013-07-01 | 2013-06-14 | 2013-06-14
2013-08-01 | 2013-07-15 | 2013-07-15
2013-09-01 | 2013-08-15 | 2013-08-15
2013-10-01 | 2013-09-13 | 2013-09-13
2013-11-01 | 2013-10-15 | 2013-10-15
2013-12-01 | 2013-11-15 | 2013-11-15
2014-01-01 | 2013-12-13 | 2013-12-13
2014-02-01 | 2014-01-15 | 2014-01-15
2014-03-01 | 2014-02-14 | 2014-02-14
2014-04-01 | 2014-03-14 | 2014-03-14
2014-05-01 | 2014-04-15 | 2014-04-15
2014-06-01 | 2014-05-15 | 2014-05-15
2014-07-01 | 2014-06-13 | 2014-06-13
2014-08-01 | 2014-07-15 | 2014-07-15
2014-09-01 | 2014-08-15 | 2014-08-15
2014-10-01 | 2014-09-15 | 2014-09-15
2014-11-01 | 2014-10-15 | 2014-10-15
2014-12-01 | 2014-11-14 | 2014-11-14
2015-01-01 | 2014-12-15 | 2014-12-15
2015-02-01 | 2015-01-15 | 2015-01-15
2015-03-01 | 2015-02-13 | 2015-02-13
2015-04-01 | 2015-03-13 | 2015-03-13
2015-05-01 | 2015-04-15 | 2015-04-15
2015-06-01 | 2015-05-15 | 2015-05-15
2015-07-01 | 2015-06-15 | 2015-06-15
2015-08-01 | 2015-07-15 | 2015-07-15
2015-09-01 | 2015-08-15 | 2015-08-15
2015-10-01 | 2015-09-15 | 2015-09-15
2015-11-01 | 2015-10-15 | 2015-10-15
2015-12-01 | 2015-11-13 | 2015-11-13
2016-01-01 | 2015-12-15 | 2015-12-15
2016-02-01 | 2016-01-15 | 2016-01-15
2016-03-01 | 2016-02-15 | 2016-02-15
2016-04-01 | 2016-03-15 | 2016-03-15
2016-05-01 | 2016-04-15 | 2016-04-15
2016-06-01 | 2016-05-13 | 2016-05-13
2016-07-01 | 2016-06-15 | 2016-06-15
2016-08-01 | 2016-07-15 | 2016-07-15
2016-09-01 | 2016-08-15 | 2016-08-15
2016-10-01 | 2016-09-15 | 2016-09-15
2016-11-01 | 2016-10-14 | 2016-10-14
2016-12-01 | 2016-11-15 | 2016-11-15
2017-01-01 | 2016-12-15 | 2016-12-15
2017-02-01 | 2017-01-13 | 2017-01-13
2017-03-01 | 2017-02-15 | 2017-02-15
2017-04-01 | 2017-03-15 | 2017-03-15
2017-05-01 | 2017-04-14 | 2017-04-14
2017-06-01 | 2017-05-15 | 2017-05-15
2017-07-01 | 2017-06-15 | 2017-06-15
2017-08-01 | 2017-07-14 | 2017-07-14
2017-09-01 | 2017-08-15 | 2017-08-15
2017-10-01 | 2017-09-15 | 2017-09-15
2017-11-01 | 2017-10-13 | 2017-10-13
2017-12-01 | 2017-11-15 | 2017-11-15
2018-01-01 | 2017-12-15 | 2017-12-15
2018-02-01 | 2018-01-15 | 2018-01-15
2018-03-01 | 2018-02-15 | 2018-02-15
2018-04-01 | 2018-03-14 | 2018-03-14
2018-05-01 | 2018-04-13 | 2018-04-13
2018-06-01 | 2018-05-15 | 2018-05-15
2018-07-01 | 2018-06-15 | 2018-06-15
2018-08-01 | 2018-07-13 | 2018-07-13
2018-09-01 | 2018-08-15 | 2018-08-15
2018-10-01 | 2018-09-14 | 2018-09-14
2018-11-01 | 2018-10-15 | 2018-10-15
2018-12-01 | 2018-11-15 | 2018-11-15
2019-01-01 | 2018-12-14 | 2018-12-14
2019-02-01 | 2019-01-15 | 2019-01-15
2019-03-01 | 2019-02-15 | 2019-02-15
2019-04-01 | 2019-03-15 | 2019-03-15
2019-05-01 | 2019-04-15 | 2019-04-15
2019-06-01 | 2019-05-15 | 2019-05-15
2019-07-01 | 2019-06-14 | 2019-06-14
2019-08-01 | 2019-07-15 | 2019-07-15
2019-09-01 | 2019-08-15 | 2019-08-15
2019-10-01 | 2019-09-13 | 2019-09-13
2019-11-01 | 2019-10-15 | 2019-10-15
2019-12-01 | 2019-11-15 | 2019-11-15
2020-01-01 | 2019-12-13 | 2019-12-13
2020-02-01 | 2020-01-15 | 2020-01-15
2020-03-01 | 2020-02-14 | 2020-02-14
2020-04-01 | 2020-03-13 | 2020-03-13
2020-05-01 | 2020-04-15 | 2020-04-15
2020-06-01 | 2020-05-15 | 2020-05-15
2020-07-01 | 2020-06-15 | 2020-06-15
2020-08-01 | 2020-07-15 | 2020-07-15
2020-09-01 | 2020-08-14 | 2020-08-14
2020-10-01 | 2020-09-15 | 2020-09-15
2020-11-01 | 2020-10-15 | 2020-10-15
2020-12-01 | 2020-11-13 | 2020-11-13
2021-01-01 | 2020-12-15 | 2020-12-15
2021-02-01 | 2021-01-15 | 2021-01-15
2021-03-01 | 2021-02-15 | 2021-02-15
2021-04-01 | 2021-03-15 | 2021-03-15
2021-05-01 | 2021-04-15 | 2021-04-15
2021-06-01 | 2021-05-14 | 2021-05-14
2021-07-01 | 2021-06-15 | 2021-06-15
2021-08-01 | 2021-07-15 | 2021-07-15
2021-09-01 | 2021-08-13 | 2021-08-13
2021-10-01 | 2021-09-15 | 2021-09-15
2021-11-01 | 2021-10-15 | 2021-10-15
2021-12-01 | 2021-11-15 | 2021-11-15
Called from ScheduleTasks
Formulas:
Next = [DDL_EQCMeeting]+[Days to next]
Last = [DDL_EQCMeeting]-[Days to next, row above]
EQCStaffRptDue = WORKDAY([DDL_EQCMeeting]-40,-1,S.DDL_DEQClosed)
EQCMaterialsDue = WORKDAY([DDL_EQCMeeting]-9,-1,S.DDL_DEQClosed)
EQCMaterialsDue = [DDL_EQCMeeting]

## ScheduleOfTasks
CALCULATIONS - DO NOT DELETE
| Schedule of Tasks | Incorporate Lane Regional Air Protection Agency Rules into State Implementation Plan | [6 empty] | ↓ Adjust start date
[9 empty] | 0 |  |  |  |  | Workday |  |  | Weekend |  |  | Closed | [17 empty] | Workday |  |  | Weekend |  |  | Closed | [21 empty] | Workday |  |  | Weekend |  |  | Closed | [20 empty] | Workday |  |  | Weekend |  |  | Closed | [21 empty] | Fill | Gantt |  |  |  |  | Last row = 763
| Overview of Key Dates | [7 empty] | #REF! |  |  |  | 2013-10-28 | [6 empty] | 2013-11-04 | [6 empty] | 2013-11-11 | [6 empty] | 2013-11-18 | [6 empty] | 2013-11-25 | [6 empty] | 2013-12-02 | [6 empty] | 2013-12-09 | [6 empty] | 2013-12-16 | [6 empty] | 2013-12-23 | [6 empty] | 2013-12-30 | [6 empty] | 2014-01-06 | [6 empty] | 2014-01-13 | [6 empty] | 2014-01-20 | [6 empty] | 2014-01-27 | [6 empty] | 2014-02-03 | [6 empty] | 2014-02-10 |  |  | T | X |  | 2
| Today 10/24/13 |  |  | Networkdays |  | Task | [114 empty] | B | X
[5 empty] | From today | Start ↓ | End | [113 empty] | B | X
| Task |  |  |  | 96 | 2013-10-02 | 2014-03-06 | [113 empty] | B | X |  | 2014-03-06 | time axis 2013-10-24 to 2014-02-11
[121 empty] | Y | X
[121 empty] | 0 | X |  | 1899-12-31
|  |  | Days added | [117 empty] | 0 | X
[121 empty] | 0 | X | [6 empty] | `
| PERMANENT Rulemaking | P |  | 84 | [116 empty] | 1 | X |  |  |  | 84 | PERMANENT Rulemaking
[121 empty] | 0 | X
| Rule proposal complexity (1=Minimal, 2= Moderate, 3=Complex) | 1 |  | 0 | [116 empty] | 1 | X |  |  |  | 0
[121 empty] | 0 | X
| Advisory Committee - not involved | N |  | 0 | 0 | 0 | 0 | [113 empty] | 1 |  | 0 | 0 |  | 0 | Advisory Committee - not involved
[121 empty] | 0 | X
| Fees - not involved | N |  | 0 | 0 | 0 | 0 | [113 empty] | 1 |  | 0 | 0 |  | 0 | Fees - not involved
| -blank- | N | i | 0 | [116 empty] | 0 | X |  |  |  | 0 | -blank-
[121 empty] | 0 | X
| State Implementation Plan (AQ rules) | Y |  | 14 | [116 empty] | 1 | X |  |  |  | 14 | State Implementation Plan (AQ rules)
| EPA - submit SIP Development Plan 6 months before comment period opens |  |  |  | 0 |  | 0 | [113 empty] | 0 |  |  | 0 |  |  | EPA - submit SIP Development Plan 6 months before comment period opens
| EPA- submit Notice Packet 45 days before comment period opens |  |  |  | 4 |  | 2013-10-29 | [113 empty] | 1 |  |  | 2013-10-29 |  |  | EPA- submit Notice Packet 45 days before comment period opens
[121 empty] | 0 | X
| Public Notice | Y |  | 7 | [116 empty] | 1 | X |  |  |  | 7 | Public Notice
| EMT - preview period open a minimum of 7 workdays |  |  |  | 24 | 2013-11-18 | 2013-11-27 | [113 empty] | 1 |  | 2013-11-18 | 2013-11-27 |  |  | EMT - preview period open a minimum of 7 workdays
| this is Andy's and JoanieS's review period | [119 empty] | 1 | X |  |  |  |  | this is Andy's and JoanieS's review period
| Rule publication - submit at least 5 workdays BEFORE Open comment |  |  |  | 35 | 2013-12-06 | 2013-12-13 | [113 empty] | 1 |  | 2013-12-06 | 2013-12-13 |  |  | Rule publication - submit at least 5 workdays BEFORE Open comment
| SOS - submit on workday no later than 15th of month BEFORE Bulletin |  |  |  | 35 |  | 2013-12-13 | [113 empty] | 1 |  |  | 2013-12-13 |  |  | SOS - submit on workday no later than 15th of month BEFORE Bulletin
| SOS - Oregon Bulletin always publishes on the 1st of month |  |  |  | 46 | ` | 2014-01-01 | [113 empty] | 1 |  |  | 2014-01-01 |  |  | SOS - Oregon Bulletin always publishes on the 1st of month
| -blank- |  |  |  | 0 |  | 0 | [113 empty] | 0 |  |  | 0 |  |  | -blank-
| Public Comment and Testimony | [119 empty] | 1 | X |  |  |  |  | Public Comment and Testimony
| Open public comment |  |  |  | 35 |  | 2013-12-13 | [113 empty] | 1 |  |  | 2013-12-13 |  |  | Open public comment
| Hold 1st hearing at least 30 days AFTER open comment | Y | 0 |  | 54 |  | 2014-01-13 | [113 empty] | 1 |  |  | 2014-01-13 |  | 0 | Hold 1st hearing at least 30 days AFTER open comment
| Close public comment - best practice, 3 days after last hearing |  |  |  | 57 |  | 2014-01-16 | [113 empty] | 1 |  |  | 2014-01-16 |  |  | Close public comment - best practice, 3 days after last hearing
| EQC Preparation | [119 empty] | 1 | X
| Involvement before Rulemaking Action Item |  |  |  |  | Option 1 ↓ | Option 2 ↓ | [113 empty] | 1 | X |  |  |  |  | Involvement before Rulemaking Action Item
| Director's Report - some material comes from monthly status report | Y | i |  | 33 | 2013-12-11 | 2013-12-11 | [113 empty] | 1 |  | 2013-12-11 | 2013-12-11 |  |  | Director's Report - some material comes from monthly status report
| -blank- | N | i | 0 | 0 | 0 | 2013-08-21 | [113 empty] | 0 |  | 0 | 0 |  | 0 | -blank-
| -blank- | N |  |  | 0 | 0 | 2013-06-19 | [113 empty] | 0 |  | 0 | 0 |  |  | -blank-
[121 empty] | 1 | X
| Rule publication - submit PERMANENT staff report |  |  |  | 71 |  | 2014-02-06 | [113 empty] | 1 |  |  | 2014-02-06 |  |  | Rule publication - submit PERMANENT staff report
| EQC meeting - PERMANENT Rulemaking Action Item |  |  |  | 99 |  | 2014-03-19 | [113 empty] | 1 |  |  | 2014-03-19 |  |  | EQC meeting - PERMANENT Rulemaking Action Item
| calendar days adjustment +/- > |  | 0 | 105 | [116 empty] | 1 | X |  |  |  | 0
| calendar days added > |  | 105 | 105 | [116 empty] | 1 | X |  |  |  | 105
| Post EQC Activities | [119 empty] | 1 | X
| SOS - file rules |  |  |  | 101 |  | 2014-03-21 | [113 empty] | 1 |  |  | 2014-03-21
| DAS - fees not involved |  |  |  | 0 |  | 2014-03-24 | [113 empty] | 0 |  |  | 2014-03-24 |  |  | DAS - fees not involved
| Rules become effective select 'Y' if effective upon filing > | Y |  |  | 101 |  | 2014-03-21 | [113 empty] | 1 |  |  | 2014-03-21 | 2014-03-29
| EPA - goal to submit SIP within 60 days of adoption |  |  |  | 142 |  | 2014-05-19 | [113 empty] | 1 |  |  | 2014-05-19 |  |  | EPA - goal to submit SIP within 60 days of adoption
[121 empty] | 0 | X
| Planning | [119 empty] | T | X
|  |  |  | Networkdays |  | Task | [114 empty] | B | X
| Incorporate Lane Regional Air Protection Agency Rules into State Implementation Plan |  |  | For Task | From today | Start | End | [113 empty] | B | X
| Task |  |  |  | 1 | 2013-10-02 | 2013-10-02 | [113 empty] | B | X | 2013-10-02 | 2013-10-02 | 2013-10-07
[121 empty] | Y | X
| Review version history and maintaining the rulemaking record > | i | [118 empty] | W | X
| CONCEPT DEVELOPMENT | [119 empty] | 1 | X
| After Andy & managers approve concept development work... | i |  |  |  |  | 2013-10-02 | [113 empty] | 1 |  |  | 2013-10-02 |  |  | After Andy & managers approve concept development work...
| MargaretMGR | [119 empty] | 1 | X |  |  |  |  | MargaretMGR
| * assigns staff to work with AndreaDRC & Maggie |  |  | 1 | -17 | 2013-10-02 | 2013-10-02 | [113 empty] | 1 |  | 2013-10-02 | 2013-10-02 |  |  | * assigns staff to work with AndreaDRC & Maggie
| * adds work to staff workplan as needed |  |  | 1 | -17 | 2013-10-02 | 2013-10-02 | [113 empty] | 1 |  | 2013-10-02 | 2013-10-02 |  |  | * adds work to staff workplan as needed
| * chats with AndreaDRC & Maggie |  |  | 1 | -17 | 2013-10-02 | 2013-10-02 | [113 empty] | 1 |  | 2013-10-02 | 2013-10-02 |  |  | * chats with AndreaDRC & Maggie
| * identifies existing Q-Time for intitial concept development work |  |  | 1 | -17 | 2013-10-02 | 2013-10-02 | [113 empty] | 1 |  | 2013-10-02 | 2013-10-02 |  |  | * identifies existing Q-Time for intitial concept development work
| AndreaDRC adds staff to Names tab of this workbook |  |  | 1 | -17 | 2013-10-02 | 2013-10-02 | [113 empty] | 1 |  | 2013-10-02 | 2013-10-02 |  |  | AndreaDRC adds staff to Names tab of this workbook
| Maggie | [119 empty] | 1 | X |  |  |  |  | Maggie
| * establishes SharePoint & Rule_Development sites | [5 empty] | 2013-10-02 | [113 empty] | 1 |  |  | 2013-10-02
| * schedules team kickoff training/work session | [5 empty] | 2013-10-02 | [113 empty] | 1 |  |  | 2013-10-02 |  |  | * schedules team kickoff training/work session
| Team = AndreaRW, MargaretMGR, AndreaDRC & Maggie | [119 empty] | 1 | X |  |  |  |  | Team = AndreaRW, MargaretMGR, AndreaDRC & Maggie
| Team participates in kickoff training/work session (future iLearn) about: |  |  |  | -17 |  | 2013-10-02 | [113 empty] | 1 |  |  | 2013-10-02
| * maintaining rulemaking record | [119 empty] | 1 | X
| * file naming conventions for common rulemaking documents and emails | [119 empty] | 1 | X
| * rulemaking SharePoint | i | [118 empty] | 1 | X
| * shared Rule _Development drive | [119 empty] | 1 | X
| * work products for this phase (templates preloaded to SharePoint folder 1): | [119 empty] | 1 | X
| - Overview of Key Dates at top of this SCHEDULE | [119 empty] | 1 | X
| - initial draft RESOURCES workbook | [119 empty] | 1 | X
| - initial draft CONSIDERATIONS workbook | [119 empty] | 1 | X
| * broad overview of work products for future phases | [119 empty] | 1 | X
| - Rulemaking Activities Web page | i | [118 empty] | 1 | X
| - INVITATION.TO.COMMENT (blank in folder 4) | [119 empty] | 1 | X
| - RULES.REDLINE | [119 empty] | 1 | X
| - NOTICE (blank in folder 4) | [119 empty] | 1 | X
| - FEE.ANALYSIS (blank in folder 3) | [119 empty] | 0 | X
| - STAFF.RPT.Permanent (blank in folder 6) | [119 empty] | 1 | X |  |  |  |  | - STAFF.RPT.Permanent (blank in folder 6)
| AndreaRW coordinates team work & agreement with initial drafts of: | [119 empty] | 1 | X |  |  |  |  | AndreaRW coordinates team work & agreement with initial drafts of:
| * RESOUCES workbook |  |  | 1 | -17 | 2013-10-02 | 2013-10-02 | [113 empty] | 1 |  | 2013-10-02 | 2013-10-02
| * CONSIDERATIONS workbook |  |  | 1 | -17 | 2013-10-02 | 2013-10-02 | [113 empty] | 1 |  | 2013-10-02 | 2013-10-02
| * Overview of Key Dates at top of this SCHEDULE |  |  | 1 | -17 | 2013-10-02 | 2013-10-02 | [113 empty] | 1 |  | 2013-10-02 | 2013-10-02
| AndreaDRC & Maggie develop DEQ Rulemaking Plan materials when team agrees |  |  | 1 | -17 | 2013-10-02 | 2013-10-02 | [113 empty] | 1 |  | 2013-10-02 | 2013-10-02 |  |  | AndreaDRC & Maggie develop DEQ Rulemaking Plan materials when team agrees
| MargaretMGR briefs managers |  |  | 1 | -17 | 2013-10-02 | 2013-10-02 | [113 empty] | 1 |  | 2013-10-02 | 2013-10-02 |  |  | MargaretMGR briefs managers
| Managers = Andy and program managers | [119 empty] | 1 | X |  |  |  |  | Managers = Andy and program managers
| Managers discuss adding concept to DEQ Rulemaking Plan |  |  | 1 | -17 | 2013-10-02 | 2013-10-02 | [113 empty] | 1 |  | 2013-10-02 | 2013-10-02
| Andy: | [119 empty] | 1 | X |  |  |  |  | Andy:
| * reviews workbook summaries and key dates on SharePoint |  |  | 4 | -14 | 2013-10-02 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-02 | 2013-10-07 |  |  | * reviews materials on SharePoint"
| * decides whether to add concept to DEQ Rulemaking Plan |  |  |  | -14 |  | 2013-10-07 | [113 empty] | 1 |  |  | 2013-10-07
| * emails approval to AndreaRW, MargaretMGR, AndreaDRC & Maggie |  |  |  | -14 |  | 2013-10-07 | [113 empty] | 1 |  |  | 2013-10-07 |  |  | * emails approval to AndreaRW, MargaretMGR, AndreaDRC & Maggie
| AndreaRW: | [119 empty] | 1 | X |  |  |  |  | AndreaRW:
| * saves email as Rule_Development ¦ 1-Planning ¦ DA.APPROVAL.pdf | i |  |  | -14 |  | 2013-10-07 | [113 empty] | 1 |  |  | 2013-10-07 |  |  | * saves email as Rule_Development ¦ 1-Planning ¦ DA.APPROVAL.pdf
| * selects 'A' if apprroved, 'P' if postponed, 'R' if rejected | A | [118 empty] | 1 | X |  |  |  |  | * selects 'A' if apprroved, 'P' if postponed, 'R' if rejected
| START RULEMAKING | [119 empty] | 1 | X
| AndreaRW drafts EMAIL.AddToPlan | I |  | 1 | -14 | 2013-10-07 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-07 | 2013-10-07 |  |  | AndreaRW drafts EMAIL.AddToPlan
| for Andy to send: | [119 empty] | 1 | X |  |  |  |  | for Andy to send:
| To: EMTdescribing addition to DEQ Rulemaking Plan | [119 empty] | 1 | X |  |  |  |  | To: EMTdescribing addition to DEQ Rulemaking Plan
| To: Stephanie to include in monthly Director's Report | [119 empty] | 1 | X |  |  |  |  | To: Stephanie to include in monthly Director's Report
| Dick asks EQC how they want to be involved with rulemaking | [119 empty] | 1 | ` |  |  |  |  | Dick asks EQC how they want to be involved with rulemaking
| Stephanie informs team about EQC involvement by email | [119 empty] | 1 | X |  |  |  |  | Stephanie informs team about EQC involvement by email
| Cc… MargaretMGR, AndreaRW, AndreaDRC, Maggie & program managers | [119 empty] | 1 | X |  |  |  |  | Cc… MargaretMGR, AndreaRW, AndreaDRC, Maggie & program managers
| (The rolling plan/process takes the place of the old annual plan/process.) | [119 empty] | 1 | X
| ONBOARD TEAM RESOURCES | [119 empty] | 1 | X
| MargaretMGR & AndreaRW determine whether to expand team 'Y' to expand > | Y |  | 1 | -14 | 2013-10-07 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-07 | 2013-10-07 |  |  | MargaretMGR & AndreaRW determine whether to expand team 'Y' to expand >
| MargaretMGR: | [119 empty] | 1 | X |  |  |  |  | MargaretMGR:
| * obtains Q-Time number unique to this rulemaking |  |  | 1 | -14 | 2013-10-07 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-07 | 2013-10-07 |  |  | * obtains unique Q-Time number for this rulemaking from RobertB
| * provides managers with scope of work to potentially add to work plans |  |  | 1 | -14 | 2013-10-07 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-07 | 2013-10-07
| * ensures core team members have approval from their managers |  |  | 1 | -14 | 2013-10-07 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-07 | 2013-10-07
| * obtains additional Q-Time number(s) from RobertB if needed |  |  | 1 | -14 | 2013-10-07 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-07 | 2013-10-07 |  |  | * obtains additional Q-Time number(s) from RobertB if needed
| AndreaRW oraganizes team meetings to discuss and refine: | [119 empty] | 1 | X |  |  |  |  | AndreaRW oraganizes team meetings to discuss and refine:
| * RESOURCES workbook to identify rulemaking and implementation needs |  |  | 1 | -14 | 2013-10-07 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-07 | 2013-10-07
| * CONSIDERATIONS workbook to expand understanding of scope of work |  |  | 1 | -14 | 2013-10-07 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-07 | 2013-10-07
| * CONSIDERATIONS workbook to expand understanding of potential risks |  |  | 1 | -14 | 2013-10-07 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-07 | 2013-10-07
` | * SCHEDULE workbook to reach consensus on timeline |  |  | 1 | -14 | 2013-10-07 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-07 | 2013-10-07
| COMMUNICATIONS PLANNING | [119 empty] | 1 | X
| AndreaRW schedules/holds meeting with team, especially MargaretMGR and |  |  | 1 | -14 | 2013-10-07 | 2013-10-07 | < | [112 empty] | 1 |  | 2013-10-07 | 2013-10-07 |  |  | AndreaRW schedules/holds meeting with team, especially MargaretMGR and
` | JoanieS, WilliamK to discuss/determine need for: | [119 empty] | 1 | X |  |  |  |  | JoanieS, WilliamK to discuss/determine need for:
| - Communications Plan 'Y' to develop | Y | [118 empty] | 1 | X
| - Message Map 'Y' to develop | Y | [118 empty] | 1 | X
| - Program Web page 'Y' to develop | Y | [118 empty] | 1 | X
| - Information Meetings before hearing 'Y' to develop | Y | [118 empty] | 1 | X
| START COMMUNICATIONS OPTION | [119 empty] | 1 | X
| AndreaRW leads: | [119 empty] | 1 | X |  |  |  |  | AndreaRW leads:
| * soliciting communications content |  |  | 1 | -14 | 2013-10-07 | 2013-10-07 | < | [112 empty] | 1 |  | 2013-10-07 | 2013-10-07
| * drafting COMMUNICATION.PLAN with WilliamK | i |  | 1 | -14 | 2013-10-07 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-07 | 2013-10-07 |  |  | * drafting COMMUNICATION.PLAN with WilliamK
| * drafting MESSAGE.MAP with WilliamK | i |  | 1 | -14 | 2013-10-07 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-07 | 2013-10-07 |  |  | * drafting MESSAGE.MAP with WilliamK
| * drafting PROGRAM.WEB.PAGE content with team and Michele |  |  | 1 | -14 | 2013-10-07 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-07 | 2013-10-07 |  |  | * drafting PROGRAM.WEB.PAGE content with team and Michele
| * leads communication option review/approval loops |  |  | 1 | -14 | 2013-10-07 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-07 | 2013-10-07
| MargaretMGR:: | [119 empty] | 1 | X |  |  |  |  | MargaretMGR::
| * shares content with Andy and approves content: |  |  | 1 | -14 | 2013-10-07 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-07 | 2013-10-07 |  |  | * shares content with Andy and approves content:
| 1st loop - team modifies content to get to approval |  |  | 1 | -14 | 2013-10-07 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-07 | 2013-10-07
| 2nd loop - team modifies content to get to approval | N |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| 3rd loop - team modifies content to get to approval | N |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| Final loop - team modifies content to get to approval | N |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| AndreaRW: | [119 empty] | 1 | X |  |  |  |  | AndreaRW:
| * submits Web Request to post program Web page |  |  | 0 | 0 | 0 | 0 | [113 empty] | 1 |  | 0 | 0
` | * verifies Web content meets team expectations |  |  | 0 | 0 | 0 | 0 | [113 empty] | 1 |  | 0 | 0
| * works with Michele to make adjustments |  |  | 0 | 0 | 0 | 0 | [113 empty] | 1 |  | 0 | 0 |  |  | * works with Michele to make adjustments
| TEAM REFINEMENT CONSENSUS | [119 empty] | 1 | X
| AndreaRW coordinates with Team to: | [119 empty] | 1 | X |  |  |  |  | AndreaRW coordinates with Team to:
| * refine communications plan with WilliamK |  |  | 1 | -14 | 2013-10-07 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-07 | 2013-10-07 |  |  | * refine communications plan with WilliamK
| * reach consensus with communication plan |  |  | 1 | -14 | 2013-10-07 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-07 | 2013-10-07 |  |  | * reach consensus with communication plan
| * reach consensus with Message Map |  |  | 1 | -14 | 2013-10-07 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-07 | 2013-10-07 |  |  | * reach consensus with Message Map
| * identify land use rules | i |  | 1 | -14 | 2013-10-07 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-07 | 2013-10-07
| PREPARE TO DRAFT RULES (future iLearn) | [119 empty] | 1 | X
| AndreaRW: | [119 empty] | 1 | X |  |  |  |  | AndreaRW:
| * obtains starting rules from Oregon State Archives | i |  |  | -14 |  | 2013-10-07 | [113 empty] | 1 |  |  | 2013-10-07
| * saves rules as Rule_Development¦1-Planning¦STARTING.RULES | [119 empty] | 1
| ONLY the rule writer works on rules at this location to ensure the | [119 empty] | 1 | X
| redline/strikethrough remains consitent and that no reviewer copied test from | [119 empty] | 1 | X
| from other locations or turned off track changes | [119 empty] | 1 | X
| * uploads STARTING.RULES to SharePoint¦1-Planning |  |  | 1 | -14 | 2013-10-07 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-07 | 2013-10-07
| All contributors/reviewers work on draft rules on SharePoint | [119 empty] | 1 | X
| * requests Maggie provide numbers for new rules/divisions |  |  | 1 | -14 | 2013-10-07 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-07 | 2013-10-07 |  |  | * requests Maggie provide numbers for new rules/divisions
| Maggie obtains, verifies, provides previously unused numbers |  |  | 1 | -14 | 2013-10-07 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-07 | 2013-10-07 |  |  | Maggie obtains, verifies, provides previously unused numbers
| AndreaDRC identifies rules that may be involved in other rulemakings |  |  | 1 | -14 | 2013-10-07 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-07 | 2013-10-07 |  |  | AndreaDRC identifies rules that may be involved in other rulemakings
| AndreaRW: | [119 empty] | 1 | X |  |  |  |  | AndreaRW:
| * coordinates with AndreaSIP to identify SIP rules |  |  | 1 | -14 | 2013-10-07 | 2013-10-07 | [113 empty] | 1 |  | 2013-10-07 | 2013-10-07 |  |  | * coordinates with AndreaSIP to identify SIP rules
| * gathers all planning emails for the Rule Record and saves as: | i |  | 1 | -17 | 2013-10-02 | 2013-10-02 | [113 empty] | 1 |  | 2013-10-02 | 2013-10-02 |  |  | * gathers all planning emails for the Rule Record and saves as:
| Rule_Development¦1-Planning¦EMAILS.Planning.pdf | [119 empty] | 1 | X
[121 empty] | W | X
| Advisory Committee - not involved | [119 empty] | T | X
|  |  |  | Networkdays |  | Task | [114 empty] | B | X
| Incorporate Lane Regional Air Protection Agency Rules into State Implementation Plan |  |  | For Task | From today | Start | End | [113 empty] | B | X
| Task |  |  |  | 0 | 0 | 0 | [113 empty] | B | X | 0 | 0
[121 empty] | Y | X
| Review version history and maintaining the rulemaking record > | i | [118 empty] | W | X
| During team meeting, AndreaDRC leads discussion on: (future iLearn) | [119 empty] | 0 | X |  |  |  |  | During team meeting, AndreaDRC leads discussion on: (future iLearn)
| * Review advisory committee Q-Card > | i |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| * Public Involvement Resources including when to engage WilliamK | i |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0 |  |  | * Public Involvement Resources including when to engage WilliamK
| * Meeting notice requirements |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| * Public Meeting Laws | i |  |  | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0 |  |  | May be required in future
| * EQC quorum notification requirements (ORS 192.630) | i |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0 |  |  | * Oregon Transparency law (not required for Advisory Committees) | i
| * Need for optional committee Web page |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| * Need for optional committee charter |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| * Potential committee members |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| * Potential meeting dates and venues |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| AndreaRW coordinates with team to: | [119 empty] | 0 | X |  |  |  |  | AndreaRW coordinates with team to:
| * develop AC.ROSTER (blank in folder 4) |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| * add EQC members to Cc. list for ALL committee communications |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| Bill@WRB-consulting.com | [119 empty] | 1 | X
| JoKRanch@hotmail.com | [119 empty] | 1 | X
| EdArmstrong2@gmail.com | [119 empty] | 1 | X
| MorganRider@gmail.com | [119 empty] | 1 | X
| cjohnson@eou.edu | [119 empty] | 1 | X
| * reserve potential meeting dates and venues |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| * draft committee AC.INVITATION (links to GovDelivery/Web pages) |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| * draft content for optional committee Web page | Y |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| * draft optional AC.CHARTER | Y |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| MargaretMGR shares draft roster and invitation with Andy |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0 |  |  | MargaretMGR shares draft roster and invitation with Andy
| Team addresses any concerns and validates accuracy of how addressed |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| MargaretMGR approves: | [119 empty] | 1 | X |  |  |  |  | MargaretMGR approves:
| * potential committee roster |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| Team: | [119 empty] | 1 | X
| * makes initial voice contact with potential committee members |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| * finalizes AC.ROSTER based on responses |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| AndreaRW: | [119 empty] | 0 | X |  |  |  |  | AndreaRW:
| * submits Web Request to initiate optional Committee Web page | i |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| * submits Web Request at anytime when Web page needs updating |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| * sends invitation to potential committee members who agreed to serve |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| * maintains advisory committee record |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| Meeting 1 | Y |  |  |  | 1900-01-15 | 6:00 p.m. | [113 empty] | 0 | X | 1900-01-15
| Team identifies meeting roles |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| AndreaRW coordinates or drafts: | [119 empty] | 0 | X |  |  |  |  | AndreaRW coordinates or drafts:
| * AC.AGENDA.01.16.00, gets team agreement | i |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01 |  |  | * AC.AGENDA.01.16.00, gets team agreement
| * AC.NOTIFICATION.01.16.00 |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01 |  |  | * AC.NOTIFICATION.01.16.00
| * adds meeting to DEQ Online Calendar (password = dudeman) | i |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| * releases unneeded venues |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| Team assigns custom task here |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| Team assigns custom task here |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| Team assigns custom task here |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| Team assigns custom task here |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| START OPTION - Presentation Select option > | Y | [118 empty] | 0 | X
| Enter staff name here | [119 empty] | 0 | X
| * drafts optional AC.PRESENTATION.01.16.00 | i |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01 |  |  | * drafts optional AC.PRESENTATION.01.16.00
| Enter staff name here | [119 empty] | 0 | X
| * involves stakeholder presenters, if any |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| Team approves presentation materials |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| AndreaRW submits Web Request to post materials | i |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01 |  |  | AndreaRW submits Web Request to post materials
| Team practices presentation |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| AndreaRW sends meeting notice with link to Web page |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01 |  |  | AndreaRW sends meeting notice with link to Web page
| Team facilitates/holds meeting |  | Set above at Meeting 1 title |  |  |  | 1900-01-15 | [113 empty] | 0 |  |  | 1900-01-15
| AndreaRW drafts AC.MINUTES 01.16.00 | i |  | 1 | 0 | 1900-01-15 | 1900-01-15 | [113 empty] | 0 |  | 1900-01-15 | 1900-01-15 |  |  | AndreaRW drafts AC.MINUTES 01.16.00
| Team holds debrief meeting |  |  | 1 | 0 | 1900-01-15 | 1900-01-15 | [113 empty] | 0 |  | 1900-01-15 | 1900-01-15
| Meeting 2 | Y |  |  |  | 1900-01-15 | 6:00 p.m. | [113 empty] | 0 | X | 1900-01-15
| Team identifies meeting roles |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| AndreaRW coordinates or drafts: | [119 empty] | 0 | X |  |  |  |  | AndreaRW coordinates or drafts:
| * AC.AGENDA.01.16.00, gets team agreement | i |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01 |  |  | * AC.AGENDA.01.16.00, gets team agreement
| * AC.NOTIFICATION.01.16.00 |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01 |  |  | * AC.NOTIFICATION.01.16.00
| * adds meeting to DEQ Online Calendar (password = dudeman) | i |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| * releases unneeded venues |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| Team assigns custom task here |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| Team assigns custom task here |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| Team assigns custom task here |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| Team assigns custom task here |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| START OPTION - Presentation Select option > | Y | [118 empty] | 0 | X
| Enter staff name here | [119 empty] | 0 | X
| * drafts optional AC.PRESENTATION.01.16.00 | i |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01 |  |  | * drafts optional AC.PRESENTATION.01.16.00
| Enter staff name here | [119 empty] | 0 | X
| * involves stakeholder presenters, if any |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| Team approves presentation materials |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| AndreaRW submits Web Request to post materials | i |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01 |  |  | AndreaRW submits Web Request to post materials
| Team practices presentation |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| AndreaRW sends meeting notice with link to Web page |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01 |  |  | AndreaRW sends meeting notice with link to Web page
| Team facilitates/holds meeting |  | Set above at Meeting 2 title |  |  |  | 1900-01-15 | [113 empty] | 0 |  |  | 1900-01-15
| AndreaRW drafts AC.MINUTES 01.16.00 | i |  | 1 | 0 | 1900-01-15 | 1900-01-15 | [113 empty] | 0 |  | 1900-01-15 | 1900-01-15 |  |  | AndreaRW drafts AC.MINUTES 01.16.00
| Team holds debrief meeting |  |  | 1 | 0 | 1900-01-15 | 1900-01-15 | [113 empty] | 0 |  | 1900-01-15 | 1900-01-15
| Meeting 3 | N |  |  |  | 1900-01-15 | 6:00 p.m. | [113 empty] | 0 | X | 1900-01-15
| Team identifies meeting roles |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| AndreaRW coordinates or drafts: | [119 empty] | 0 | X |  |  |  |  | AndreaRW coordinates or drafts:
| * AC.AGENDA.01.16.00, gets team agreement | i |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01 |  |  | * AC.AGENDA.01.16.00, gets team agreement
| * AC.NOTIFICATION.01.16.00 |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01 |  |  | * AC.NOTIFICATION.01.16.00
| * adds meeting to DEQ Online Calendar (password = dudeman) | i |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| * releases unneeded venues |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| Team assigns custom task here |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| Team assigns custom task here |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| Team assigns custom task here |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| Team assigns custom task here |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| START OPTION - Presentation Select option > | Y | [118 empty] | 0 | X
| Enter staff name here | [119 empty] | 0 | X
| * drafts optional AC.PRESENTATION.01.16.00 | i |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01 |  |  | * drafts optional AC.PRESENTATION.01.16.00
| Enter staff name here | [119 empty] | 0 | X
| * involves stakeholder presenters, if any |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| Team approves presentation materials |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| AndreaRW submits Web Request to post materials | i |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01 |  |  | AndreaRW submits Web Request to post materials
| Team practices presentation |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| AndreaRW sends meeting notice with link to Web page |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01 |  |  | AndreaRW sends meeting notice with link to Web page
| Team facilitates/holds meeting |  | Set above at Meeting 3 title |  |  |  | 1900-01-15 | [113 empty] | 0 |  |  | 1900-01-15
| AndreaRW drafts AC.MINUTES01.16.00 | i |  | 1 | 0 | 1900-01-15 | 1900-01-15 | [113 empty] | 0 |  | 1900-01-15 | 1900-01-15 |  |  | AndreaRW drafts AC.MINUTES01.16.00
| Team holds debrief meeting |  |  | 1 | 0 | 1900-01-15 | 1900-01-15 | [113 empty] | 0 |  | 1900-01-15 | 1900-01-15
| Meeting 4 | N |  |  |  | 1900-01-15 | 6:00 p.m. | [113 empty] | 0 | X | 1900-01-15
| Team identifies meeting roles |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| AndreaRW coordinates or drafts: | [119 empty] | 0 | X |  |  |  |  | AndreaRW coordinates or drafts:
| * AC.AGENDA.01.16.00, gets team agreement | i |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01 |  |  | * AC.AGENDA.01.16.00, gets team agreement
| * AC.NOTIFICATION.01.16.00 |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01 |  |  | * AC.NOTIFICATION.01.16.00
| * adds meeting to DEQ Online Calendar (password = dudeman) | i |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| * releases unneeded venues |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| Team assigns custom task here |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| Team assigns custom task here |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| Team assigns custom task here |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| Team assigns custom task here |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| START OPTION - Presentation Select option > | Y | [118 empty] | 0 | X
| Enter staff name here | [119 empty] | 0 | X
| * drafts optional AC.PRESENTATION.01.16.00 | i |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01 |  |  | * drafts optional AC.PRESENTATION.01.16.00
| Enter staff name here | [119 empty] | 0 | X
| * involves stakeholder presenters, if any |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| Team approves presentation materials |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| AndreaRW submits Web Request to post materials | i |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01 |  |  | AndreaRW submits Web Request to post materials
| Team practices presentation |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| AndreaRW sends meeting notice with link to Web page |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01 |  |  | AndreaRW sends meeting notice with link to Web page
| Team facilitates/holds meeting |  | Set above at Meeting 4 title |  |  |  | 1900-01-15 | [113 empty] | 0 |  |  | 1900-01-15
| AndreaRW drafts AC.MINUTES01.16.00 | i |  | 1 | 0 | 1900-01-15 | 1900-01-15 | [113 empty] | 0 |  | 1900-01-15 | 1900-01-15 |  |  | AndreaRW drafts AC.MINUTES01.16.00
| Team holds debrief meeting |  |  | 1 | 0 | 1900-01-15 | 1900-01-15 | [113 empty] | 0 |  | 1900-01-15 | 1900-01-15
| Meeting 5 | N |  |  |  | 1900-01-15 | 6:00 p.m. | [113 empty] | 0 | X | 1900-01-15
| Team identifies meeting roles |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| AndreaRW coordinates or drafts: | [119 empty] | 0 | X |  |  |  |  | AndreaRW coordinates or drafts:
| * AC.AGENDA.01.16.00, gets team agreement | i |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01 |  |  | * AC.AGENDA.01.16.00, gets team agreement
| * AC.NOTIFICATION.01.16.00 |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01 |  |  | * AC.NOTIFICATION.01.16.00
| * adds meeting to DEQ Online Calendar (password = dudeman) | i |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| * releases unneeded venues |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| Team assigns custom task here |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| Team assigns custom task here |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| Team assigns custom task here |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| Team assigns custom task here |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| START OPTION - Presentation Select option > | Y | [118 empty] | 0 | X
| Enter staff name here | [119 empty] | 0 | X
| * drafts optional AC.PRESENTATION.01.16.00 | i |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01 |  |  | * drafts optional AC.PRESENTATION.01.16.00
| Enter staff name here | [119 empty] | 0 | X
| * involves stakeholder presenters, if any |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| Team approves presentation materials |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| AndreaRW submits Web Request to post materials | i |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01 |  |  | AndreaRW submits Web Request to post materials
| Team practices presentation |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01
| AndreaRW sends meeting notice with link to Web page |  |  | 1 | 0 | 1900-01-01 | 1900-01-01 | [113 empty] | 0 |  | 1900-01-01 | 1900-01-01 |  |  | AndreaRW sends meeting notice with link to Web page
| Team facilitates/holds meeting |  | Set above at Meeting 5 title |  |  |  | 1900-01-15 | [113 empty] | 0 |  |  | 1900-01-15
| AndreaRW drafts AC.MINUTES01.16.00 | i |  | 1 | 0 | 1900-01-15 | 1900-01-15 | [113 empty] | 0 |  | 1900-01-15 | 1900-01-15 |  |  | AndreaRW drafts AC.MINUTES01.16.00
| Team holds debrief meeting |  |  | 1 | 0 | 1900-01-15 | 1900-01-15 | [113 empty] | 0 |  | 1900-01-15 | 1900-01-15
| AndreaRW gathers all advisory committee emails for the Rule Record and saves as: | i |  | 0 | 0 | 0 | 0 | [113 empty] | 0 | X | 0 | 0 |  |  | AndreaRW gathers all advisory committee emails for the Rule Record and saves as:
| Rule_Development¦3-FeesApproval¦EMAILS.Fees.pdf | [119 empty] | 0 | X
[121 empty] | W | X
| Fees - not involved | [119 empty] | T | X |  |  |  |  | Fees - not involved
|  |  |  | Networkdays |  | Task | [114 empty] | B | X
| Incorporate Lane Regional Air Protection Agency Rules into State Implementation Plan |  |  | For Task | From today | Start | End | [113 empty] | B | X
| Task |  |  |  | 0 | 0 | 0 | [113 empty] | B | X | 0 | 0
[121 empty] | Y | X
| Review version history and maintaining the rulemaking record > | i | [118 empty] | W | X
| AndreaRW: | [119 empty] | 1 | X |  |  |  |  | AndreaRW:
| * devlopes Fee Approval Packet resources: Robin and team | i |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0 |  |  | * devlopes Fee Approval Packet resources: Robin and team
| Fee Approval Packet includes: | [119 empty] | 0 | X
| blank row |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0 |  |  | blank row
| blank row |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0 |  |  | blank row
| blank line | i |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0 |  |  | blank line
| blank row | i |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0 |  |  | blank row
| * initiates MargaretMGR's Fee Approval Packet review and approval, addresses suggestions |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0 |  |  | * initiates MargaretMGR's Fee Approval Packet review and approval, addresses suggestions
| 1st loop of MargaretMGR's Fee Approval Packet review and approval |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0 |  |  | 1st loop of MargaretMGR's Fee Approval Packet review and approval
| 2nd loop of MargaretMGR's Fee Approval Packet review and approval | N |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0 |  |  | 2nd loop of MargaretMGR's Fee Approval Packet review and approval
| 3rd loop of MargaretMGR's Fee Approval Packet review and approval | N |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0 |  |  | 3rd loop of MargaretMGR's Fee Approval Packet review and approval
| 4th loop of MargaretMGR's Fee Approval Packet review and approval | N |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0 |  |  | 4th loop of MargaretMGR's Fee Approval Packet review and approval
| * emails RulePublications@deq.state.or.us for plain English, style guide | i |  | Rule publication |  |  | 2013-12-06 | [113 empty] | 1 |  |  | 2013-12-06
| and tone review since this will become part of Notice and EQC packets | [119 empty] | 1 | X
| AndreaDRC coordinates: | [119 empty] | 0 | X |  |  |  |  | AndreaDRC coordinates:
| * sending EMAIL.DAS.APPROVAL with Fee Approval Packet attached |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| - in Outlook, request delivery and read receipts | [119 empty] | 0 | X
| - save receipts to Rule_Dev.¦3-Fee.Approval¦PROOF.DAS.REQUEST.pdf | [119 empty] | 0 | X
| * following up on status about 15 days after sending |  |  | 1 | 0 | 1900-01-09 | 1900-01-09 | [113 empty] | 0 |  | 1900-01-09 | 1900-01-09
| DAS sends AndreaRW response |  |  | 1 | 0 | 1900-01-09 | 1900-01-09 | [113 empty] | 0 |  | 1900-01-09 | 1900-01-09 |  |  | DAS sends AndreaRW response
| If denied, AndreaRW coordinates addressing DAS response |  |  | 1 | 0 | 1900-01-09 | 1900-01-09 | [113 empty] | 0 |  | 1900-01-09 | 1900-01-09 |  |  | If denied, AndreaRW coordinates addressing DAS response
| 1st loop of MargaretMGR's approval of response to DAS denial |  |  | 1 | 0 | 1900-01-09 | 1900-01-09 | [113 empty] | 0 |  | 1900-01-09 | 1900-01-09 |  |  | 1st loop of MargaretMGR's approval of response to DAS denial
| 2nd loop of MargaretMGR's approval of response to DAS denial | N |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0 |  |  | 2nd loop of MargaretMGR's approval of response to DAS denial
| 3rd loop of MargaretMGR's approval of response to DAS denial | N |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0 |  |  | 3rd loop of MargaretMGR's approval of response to DAS denial
| 4th loop of MargaretMGR's approval of response to DAS denial | N |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0 |  |  | 4th loop of MargaretMGR's approval of response to DAS denial
| If approved, AndreaRW scans and files DAS.PART1.pdf |  |  | 1 | 0 | 1900-01-09 | 1900-01-09 | [113 empty] | 0 |  | 1900-01-09 | 1900-01-09 |  |  | If approved, AndreaRW scans and files DAS.PART1.pdf
| Next step happens under 4-Public Notice section | [119 empty] | 0 | X
| AndreaRW gathers all fee emails for the Rule Record and saves as: | i | [118 empty] | 0 | X |  |  |  |  | AndreaRW gathers all fee emails for the Rule Record and saves as:
| Rule_Development¦3-FeesApproval¦EMAILS.Fees.pdf | [119 empty] | 0 | X
[121 empty] | W | X
| Public Notice | [119 empty] | T | X
|  |  |  | Networkdays |  | Task | [114 empty] | B | X
| Incorporate Lane Regional Air Protection Agency Rules into State Implementation Plan |  |  | For Task | From today | Start | End | [113 empty] | B | X
| Task |  |  |  | 73 | 2013-10-02 | 2014-01-16 | [113 empty] | B | X | 2013-10-02 | 2014-01-16 | 2013-12-13
1900-04-20 | [120 empty] | Y | X
| Review version history and maintaining the rulemaking record > | i | [118 empty] | W | X
| AndreaRW enters hearings locations, dates and times: | [119 empty] | 1 | X |  |  |  |  | AndreaRW enters hearings locations, dates and times:
| LRAPA | Y |  | FIRST hearing |  | 2014-01-13 | 6pm | [113 empty] | 1 | X | 2014-01-13 | 5 p.m.
| Enter city name | N |  | 2nd hearing |  | 0 | 6pm | [113 empty] | 0 | X | 0 | 6pm
| Enter city name | N |  | 3rd hearing |  | 0 | 6pm | [113 empty] | 0 | X | 0 | 6pm
| Enter city name | N |  | 4th hearing |  | 0 | 6pm | [113 empty] | 0 | X | 0 | 6pm
| Enter city name | N |  | 5th hearing |  | 0 | 6pm | [113 empty] | 0 | X | 0 | 6pm
| Enter city name | N |  | 6th hearing |  | 0 | 6pm | [113 empty] | 0 | X | 0 | 6pm
| Enter city name | N |  | 7th hearing |  | 0 | 6pm | [113 empty] | 0 | X | 0 | 6pm
| Enter city name | N |  | 8th hearing |  | 0 | 6pm | [113 empty] | 0 | X | 2014-01-13 | 6pm
|  |  |  | LAST |  | 2014-01-13 | [114 empty] | 1 | X | 2014-01-13 |  |  |  | AndreaRW:
| SavvySupport reserves venues/equipment for hearings |  |  | 70 | 54 | 2013-10-02 | 2014-01-13 | [113 empty] | 1 |  | 2013-10-02 | 2014-01-13 |  |  | SavvySupport reserves venues/equipment for hearings
| Identify EQC facilitated hearing, coordinate with commissioner: | [119 empty] | 0 | X
| EQC quorum notification requirements (ORS 192.630) | i | [118 empty] | 0 | X
| No EQC facilitated hearing |  |  |  | 0 |  | 0 | [113 empty] | 0 |  |  | 0 |  |  | No EQC facilitated hearing
| No EQC facilitated hearing |  |  |  | 0 |  | 0 | [113 empty] | 0 |  |  | 0 |  |  | No EQC facilitated hearing
| No EQC facilitated hearing |  |  |  | 0 |  | 0 | [113 empty] | 0 |  |  | 0 |  |  | No EQC facilitated hearing
| No EQC facilitated hearing |  |  |  | 0 |  | 0 | [113 empty] | 0 |  |  | 0 |  |  | No EQC facilitated hearing
| Bill@WRB-consulting.com | [119 empty] | 1 | X
| JoKRanch@hotmail.com | [119 empty] | 1 | X
| EdArmstrong2@gmail.com | [119 empty] | 1 | X
| MorganRider@gmail.com | [119 empty] | 1 | X
| cjohnson@eou.edu | [119 empty] | 1 | X
| AndreaRW coordinates/drafts Notice Packet that includes: |  |  | 29700 | 16 | 0 | 2013-11-15 | [113 empty] | 1 |  | 0 | 2013-11-15 |  |  | AndreaRW coordinates/drafts Notice Packet that includes:
| a. LRAPAINVITATION.TO.COMMENT preloaded in SharePoint folder 4 |  |  | 29700 | 16 | 0 | 2013-11-15 | [113 empty] | 1 |  | 0 | 2013-11-15 |  |  | a. LRAPAINVITATION.TO.COMMENT preloaded in SharePoint folder 4
| b. LRAPAPROPOSED.RULES |  |  | 29700 | 16 | 0 | 2013-11-15 | [113 empty] | 1 |  | 0 | 2013-11-15 |  |  | b. LRAPAPROPOSED.RULES
| AndreaRW verifies: | [119 empty] | 1 | X |  |  |  |  | AndreaRW verifies:
| - drafted rules are current compared to Oregon State Archives | i |  | 29700 | 16 | 0 | 2013-11-15 | [113 empty] | 1 |  | 0 | 2013-11-15
| - statutory authorities are correct for each rule |  |  | 29700 | 16 | 0 | 2013-11-15 | [113 empty] | 1 |  | 0 | 2013-11-15
| - statutes implemented are correct for each rules |  |  | 29700 | 16 | 0 | 2013-11-15 | [113 empty] | 1 |  | 0 | 2013-11-15
| - SIP note is at bottom of all SIP rules |  |  | 29700 | 16 | 0 | 2013-11-15 | [113 empty] | 1 |  | 0 | 2013-11-15 |  |  | - SIP note is at bottom of all SIP rules
| c. NOTICE preloaded in SharePoint folder 4 |  |  | 29700 | 16 | 0 | 2013-11-15 | [113 empty] | 1 |  | 0 | 2013-11-15
| - section, Overview tells rulemaking story |  |  | 29700 | 16 | 0 | 2013-11-15 | [113 empty] | 1 |  | 0 | 2013-11-15
| - optional section, Background as part of the story |  |  | 29700 | 16 | 0 | 2013-11-15 | [113 empty] | 1 |  | 0 | 2013-11-15
| - section, Statement of Need |  |  | 29700 | 16 | 0 | 2013-11-15 | [113 empty] | 1 |  | 0 | 2013-11-15
| - section, Federal Relationship |  |  | 29700 | 16 | 0 | 2013-11-15 | [113 empty] | 1 |  | 0 | 2013-11-15
| - section, Rules affected, authorities… |  |  | 29700 | 16 | 0 | 2013-11-15 | [113 empty] | 1 |  | 0 | 2013-11-15
| - section, Statement of fiscal and economic impact |  |  | 29700 | 16 | 0 | 2013-11-15 | [113 empty] | 1 |  | 0 | 2013-11-15
| - integrates FEE.ANALYSIS section |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| - section, Land use |  |  | 29700 | 16 | 0 | 2013-11-15 | [113 empty] | 1 |  | 0 | 2013-11-15
| d. SUPPORTING.DOCS - optional |  |  | 29700 | 16 | 0 | 2013-11-15 | [113 empty] | 1 |  | 0 | 2013-11-15
| AndreaRW: | [119 empty] | 1 | X |  |  |  |  | AndreaRW:
| * asks Carol to schedule future meetings: | [5 empty] | 2013-09-16 | [113 empty] | 1 |  |  | 2013-09-16 |  |  | * asks Carol to schedule future meetings:
| - DA briefing meeting with AndreaRW & MargaretMGR | [5 empty] | 2013-11-15 | [113 empty] | 1 |  |  | 2013-11-15 |  |  | - DA briefing meeting with AndreaRW & MargaretMGR
| - time on DA calendar to review Notice during Preview week |  |  | 8 | 24 | 2013-11-18 | 2013-11-27 | [113 empty] | 1 |  | 2013-11-18 | 2013-11-27
| * asks RESOURCES for input, especially: |  |  | 31 | 15 | 2013-10-02 | 2013-11-14 | [113 empty] | 1 |  | 2013-10-02 | 2013-11-14
| * Advisory Commiitee not involved |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0 |  |  | * Advisory Commiitee not involved
| - Affected staff for contributions |  |  | 31 | 15 | 2013-10-02 | 2013-11-14 | [113 empty] | 1 |  | 2013-10-02 | 2013-11-14
| - Contributing staff for validation |  |  | 31 | 15 | 2013-10-02 | 2013-11-14 | [113 empty] | 1 |  | 2013-10-02 | 2013-11-14
| - AndreaSIP, edit for sufficiency of SIP inclusion |  |  | 31 | 15 | 2013-10-02 | 2013-11-14 | [113 empty] | 1 |  | 2013-10-02 | 2013-11-14 |  |  | - AndreaSIP, edit for sufficiency of SIP inclusion
| - AndreaDRC for program sufficiency, consistency & clarity |  |  | 31 | 15 | 2013-10-02 | 2013-11-14 | [113 empty] | 1 |  | 2013-10-02 | 2013-11-14 |  |  | - AndreaDRC for program sufficiency, consistency & clarity
| - LarryK for legal sufficiency of NOTICE and PROPOSED RULES if needed |  |  | 31 | 15 | 2013-10-02 | 2013-11-14 | [113 empty] | 1 |  | 2013-10-02 | 2013-11-14 |  |  | - LarryK for legal sufficiency of NOTICE and PROPOSED RULES if needed
| - Maggie for OR rulemaking sufficiency, consistency & clarity |  |  | 31 | 15 | 2013-10-02 | 2013-11-14 | [113 empty] | 1 |  | 2013-10-02 | 2013-11-14 |  |  | - Maggie for OR rulemaking sufficiency, consistency & clarity
| - Robin for sufficiency of fiscal analysis |  |  | 31 | 15 | 2013-10-02 | 2013-11-14 | [113 empty] | 1 |  | 2013-10-02 | 2013-11-14
| - Enter custom resource here |  |  | 31 | 15 | 2013-10-02 | 2013-11-14 | [113 empty] | 1 |  | 2013-10-02 | 2013-11-14
| - Enter custom resource here |  |  | 31 | 15 | 2013-10-02 | 2013-11-14 | [113 empty] | 1 |  | 2013-10-02 | 2013-11-14
| - Enter custom resource here |  |  | 31 | 15 | 2013-10-02 | 2013-11-14 | [113 empty] | 1 |  | 2013-10-02 | 2013-11-14
| * adapts Notice packet to address input from RESOURCES |  |  | 31 | 15 | 2013-10-02 | 2013-11-14 | [113 empty] | 1 |  | 2013-10-02 | 2013-11-14
| Rule Publications inserts Web page & online public comment URLs later | [119 empty] | 1 | X
[121 empty] | 1 | X
| Name initiator and subject for custom review loop 1 | N |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| * enter custom action word and reviewer |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| * enter custom action word and reviewer |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| * enter custom action word and reviewer |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| Name initiator and subject for custom review loop 2 | N |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| * enter custom action word and reviewer |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| * enter custom action word and reviewer |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| * enter custom action word and reviewer |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| Name initiator and subject for custom review loop 3 | N |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| * enter custom action word and reviewer |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| * enter custom action word and reviewer |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
| * enter custom action word and reviewer |  |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0
[121 empty] | 1 | X
| AndreaRW: | [119 empty] | 1 | X |  |  |  |  | AndreaRW:
| * finalizes Notice packet |  |  | 31 | 15 | 2013-10-02 | 2013-11-14 | [113 empty] | 1 |  | 2013-10-02 | 2013-11-14
| * updates prevously scheduled DA briefing and review, if changed, with Carol | [5 empty] | 2013-11-14 | [113 empty] | 1 |  |  | 2013-11-14 |  |  | * updates prevously scheduled DA briefing and review, if changed, with Carol
| * initiates MargaretMGR's review/approval, addresses suggestions |  |  | 1 | 15 | 2013-11-14 | 2013-11-14 | [113 empty] | 1 |  | 2013-11-14 | 2013-11-14 |  |  | * initiates MargaretMGR's review/approval, addresses suggestions
| 1st loop of MargaretMGR's Notice Packet review and approval |  |  | 1 | 15 | 2013-11-14 | 2013-11-14 | [113 empty] | 1 |  | 2013-11-14 | 2013-11-14 |  |  | 1st loop of MargaretMGR's Notice Packet review and approval
| 2nd loop of MargaretMGR's Notice Packet review and approval | Y |  | 1 | 15 | 2013-11-14 | 2013-11-14 | [113 empty] | 1 |  | 2013-11-14 | 2013-11-14 |  |  | 2nd loop of MargaretMGR's Notice Packet review and approval
| 3rd loop of MargaretMGR's Notice Packet review and approval | N |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0 |  |  | 3rd loop of MargaretMGR's Notice Packet review and approval
| 4th loop of MargaretMGR's Notice Packet review and approval | N |  | 0 | 0 | 0 | 0 | [113 empty] | 0 |  | 0 | 0 |  |  | 4th loop of MargaretMGR's Notice Packet review and approval
| * coordinates SIP inclusion with AndreaSIP |  |  | 49 | 33 | 2013-10-02 | 2013-12-11 | [113 empty] | 1 |  | 2013-10-02 | 2013-12-11 |  |  | * coordinates SIP inclusion with AndreaSIP
| * determines if newspaper advertisements are required; resource AndreaDRC | Y |  | 49 | 33 | 2013-10-02 | 2013-12-11 | [113 empty] | 1 |  | 2013-10-02 | 2013-12-11 |  |  | * determines if newspaper advertisements are required; resource AndreaDRC
| - identifies publications and publication dates |  |  | 49 | 33 | 2013-10-02 | 2013-12-11 | [113 empty] | 1 |  | 2013-10-02 | 2013-12-11
| NOTICE.AD01.OREGONIAN |  | Enter publication date > |  |  |  | 2013-12-11 | [113 empty] | 1 |  |  | 2013-12-11
| NOTICE.AD02.REGISTERGUARD |  | Enter publication date > |  |  |  | 2013-12-11 | [113 empty] | 1 |  |  | 2013-12-11
| NOTICE.AD03.[INSERT NAME PUBLICATION] |  | Enter publication date > |  |  |  | 2013-12-11 | [113 empty] | 1 |  |  | 2013-12-11
| NOTICE.AD04.[INSERT NAME PUBLICATION] |  | Enter publication date > |  |  |  | 2013-12-11 | [113 empty] | 1 |  |  | 2013-12-11
| NOTICE.AD05.[INSERT NAME PUBLICATION] |  | Enter publication date > |  |  |  | 2013-12-11 | [113 empty] | 1 |  |  | 2013-12-11
| NOTICE.AD06.[INSERT NAME PUBLICATION] |  | Enter publication date > |  |  |  | 2013-12-11 | [113 empty] | 1 |  |  | 2013-12-11
| NOTICE.AD07.[INSERT NAME PUBLICATION] |  | Enter publication date > |  |  |  | 2013-12-11 | [113 empty] | 1 |  |  | 2013-12-11
| NOTICE.AD08.[INSERT NAME PUBLICATION] |  | Enter publication date > |  |  |  | 2013-12-11 | [113 empty] | 1 |  |  | 2013-12-11
| - develops an AD.STANDARD for each hearing if required | i |  | 49 | 33 | 2013-10-02 | 2013-12-11 | [113 empty] | 1 |  | 2013-10-02 | 2013-12-11
| - develops AD.LEGAL for each hearing if required | i |  | 49 | 33 | 2013-10-02 | 2013-12-11 | [113 empty] | 1 |  | 2013-10-02 | 2013-12-11
| - saves as NOTICE.AD.Hearing1, etc. in SharePoint folder 4 |  |  | 49 | 33 | 2013-10-02 | 2013-12-11 | [113 empty] | 1 |  | 2013-10-02 | 2013-12-11
| - determines when ADs need to be submitted to contractor |  | Submit to Ad contractor > |  |  |  | 2013-12-11 | [113 empty] | 1 |  |  | 2013-12-11
| - shares contents of HearingAndAdDates tab with MargaretMGR | i |  | 49 | 33 | 2013-10-02 | 2013-12-11 | [113 empty] | 1 |  | 2013-10-02 | 2013-12-11 |  |  | - shares contents of HearingAndAdDates tab with MargaretMGR
| - obtains MargaretMGR's email approval |  |  | 49 | 33 | 2013-10-02 | 2013-12-11 | [113 empty] | 1 |  | 2013-10-02 | 2013-12-11 |  |  | - obtains MargaretMGR's email approval
| * identifies hearings officer(s) |  |  | 49 | 33 | 2013-10-02 | 2013-12-11 | [113 empty] | 1 |  | 2013-10-02 | 2013-12-11
| * completes preview EMAIL.PREVIEW | i |  | 32 | 16 | 2013-10-02 | 2013-11-15 | [113 empty] | 1 |  | 2013-10-02 | 2013-11-15
| - follows instructions in template | [119 empty] | 1 | X
| * prepares for key legislator notification | [119 empty] | 1 | X
| - reviews ORS 183.335(5), determines key legislators to notice | i |  | 49 | 33 | 2013-10-02 | 2013-12-11 | [113 empty] | 1 |  | 2013-10-02 | 2013-12-11
| - validates recipients with MargaretMGR & MargaretLEG |  |  | 49 | 33 | 2013-10-02 | 2013-12-11 | [113 empty] | 1 |  | 2013-10-02 | 2013-12-11 |  |  | - validates recipients with MargaretMGR & MargaretLEG
| - obtains approval of legislator's emails from MargaretLEG by email |  |  | 49 | 33 | 2013-10-02 | 2013-12-11 | [113 empty] | 1 |  | 2013-10-02 | 2013-12-11 |  |  | - obtains approval of legislator's emails from MargaretLEG by email
| - adapts EMAIL.NOTICE.TO.KEY.LEGISLATORS | i |  | 49 | 33 | 2013-10-02 | 2013-12-11 | [113 empty] | 1 |  | 2013-10-02 | 2013-12-11
| AndreaRW and MargaretMGR: | [119 empty] | 1 | [5 empty] | AndreaRW and MargaretMGR:
| * brief Andy |  |  | DA briefing meeting |  |  | 2013-11-15 | [113 empty] | 1 |  |  | 2013-11-15 |  |  | * brief Andy
| * reminds Andy & JoanieS that this IS the lead DA review period | [119 empty] | 1 | [5 empty] | * reminds Andy & JoanieS that this IS the lead DA review period
| Andy personalizes EMAIL.PREVIEW and | [119 empty] | 1 | [5 empty] | Andy personalizes EMAIL.PREVIEW and
| STARTS preview period for Notice Packet by |  |  |  | 17 |  | 2013-11-18 | [113 empty] | 1 |  |  | 2013-11-18
| sending email To...EMT & EQC assistant with | [119 empty] | 1 | X
| Cc…to contributing and affected staff | [119 empty] | 1 | X
| END preview period for Notice Packet |  |  |  | 24 |  | 2013-11-27 | [113 empty] | 1 |  |  | 2013-11-27
| AndreaRW: | [119 empty] | 1 | X |  |  |  |  | AndreaRW:
| * saves EMAIL.PREVIEW.pdf to Rule_Development¦4-Notice | i |  |  | 17 |  | 2013-11-18 | [113 empty] | 1 |  |  | 2013-11-18
| * modifies documents as needed |  |  | 45 | 29 | 2013-10-02 | 2013-12-05 | [113 empty] | 1 |  | 2013-10-02 | 2013-12-05
| * talks with MargaretMGR decides how to address any feedback |  |  |  | 29 | 2013-10-02 | 2013-12-05 | [113 empty] | 1 |  | 2013-10-02 | 2013-12-05 |  |  | * talks with MargaretMGR decides how to address any feedback
| * obtains EMAIL.BUDGET.SIGNOFF | i |  | 45 | 29 | 2013-10-02 | 2013-12-05 | [113 empty] | 1 |  | 2013-10-02 | 2013-12-05
| * saves Budget response as Rule_Development¦4.Notice¦BUDGET.SIGNOFF | i |  |  |  |  | 2013-12-05 | [113 empty] | 1 |  |  | 2013-12-05
| * verifies PROPOSED.RULES based on current compilation |  |  | 45 | 29 | 2013-10-02 | 2013-12-05 | [113 empty] | 1 |  | 2013-10-02 | 2013-12-05
| * finalizes Notice Packet with MargaretMGR |  |  | 45 | 29 | 2013-10-02 | 2013-12-05 | [113 empty] | 1 |  | 2013-10-02 | 2013-12-05 |  |  | * finalizes Notice Packet with MargaretMGR
| [ENTER NAME OF PERSON SUBMITTING AD]: | [119 empty] | 1 | X
| * submits AD to contractor |  | Set above |  |  |  | 2013-12-11 | [113 empty] | 1 |  |  | 2013-12-11 |  |  | * modifies documents as needed
| MargaretMGR: | [119 empty] | 1 | X |  |  |  |  | MargaretMGR:
| * resubmits Notice Packet to Andy - OPTIONAL | Y |  | 45 | 29 | 2013-10-02 | 2013-12-05 | [113 empty] | 1 |  | 2013-10-02 | 2013-12-05 |  |  | * resubmits Notice Packet to Andy - OPTIONAL
| - manages review/approval process with Andy | [119 empty] | 1 | X |  |  |  |  | - manages review/approval process with Andy
| * emails management's approval to publish Notice Packet to AndreaRW | i |  | Management notice approval |  |  | 2013-12-05 | [113 empty] | 1 |  |  | 2013-12-05 |  |  | * emails management's approval to publish Notice Packet to AndreaRW
| - copies AndreaDRC and Maggie | [119 empty] | 1 | X |  |  |  |  | - copies AndreaDRC and Maggie
| AndreaRW: | [119 empty] | 1 | X |  |  |  |  | AndreaRW:
| * saves email as Rule_Development¦4-Notice¦MGR.APPROVAL.Notice.pdf | [5 empty] | 2013-12-05 | [113 empty] | 1 |  |  | 2013-12-05
| Noticing sequence | [119 empty] | 1 | X
| AndreaRW: | [119 empty] | 1 | X |  |  |  |  | AndreaRW:
| * emails approval to RulePublications@deq.state.or.us | i |  | Rule publication |  |  | 2013-12-06 | [113 empty] | 1 |  |  | 2013-12-06
| * relaxes while RulePublications does its work that includes: | [119 empty] | 1 | X
| - sending you a confirmation email that includes: | [119 empty] | 1 | X
| URL to online public comment form | [119 empty] | 1 | X
| URL to Rulemaking Activities Web page for this proposal | [119 empty] | 1 | X
| URL for Outlook Comment box | [119 empty] | 1 | X
| - editing for SOS submittal and authorization -- Maggie | [119 empty] | 1 | X |  |  |  |  | - editing for SOS submittal and authorization -- Maggie
| - inserting URLs into Invitation to Comment | [119 empty] | 1 | X
| - editing for plain English, style guide and tone -- WilliamK | [119 empty] | 1 | X |  |  |  |  | - editing for plain English, style guide and tone -- WilliamK
| - verifying/clarifying consolidated edits with AndreaRW | [119 empty] | 1 | X |  |  |  |  | - verifying/clarifying consolidated edits with AndreaRW
| - establishing Outlook comment box with AndreaRW as owner | [119 empty] | 1 | X |  |  |  |  | - establishing Outlook comment box with AndreaRW as owner
| - establishing Rulemaking Activities Web page for proposed rule | i | [118 empty] | 1 | X
| - establishing online public comment form | [119 empty] | 1 | X
| - adding hearings to DEQ online calendar | i | [118 empty] | 1 | X
| - validating Web page, comment form, hearing date accuracy with AndreaRW | [119 empty] | 1 | X |  |  |  |  | - validating Web page, comment form, hearing date accuracy with AndreaRW
| - submitting notice to SOS for publication in Oregon Bulletin | i | [118 empty] | 1
| - saving proof on Rule_development¦4.Notice¦NOTICE.WITH.PROOF.pdf | [119 empty] | 1 | X
| - emailing DAS notification of fees that don't require DAS approval | [119 empty] | 0
| - saving Rule_Development¦4.Notice¦PROOF.DAS.NOTIFICATION | [119 empty] | 0
| * creates an autoreply to Outlook comment box for University students | i |  |  | 32 |  | 2013-12-10 | [113 empty] | 1 |  |  | 2013-12-10
| * submits rules and notice to EPA |  |  |  | 32 |  | 2013-12-10 | [113 empty] | 1 |  |  | 2013-12-10
| [ENTER NAME OF STAFF PERSON HERE]: | [119 empty] | 1 | X |  |  |  |  | AndreaDRC:
| * opens public comment by notifying agency rulemaking list that includes: |  | Set under Overview of Key Dates |  |  |  | 2013-12-13 | [113 empty] | 1 |  |  | 2013-12-13
| - GovDelivery |  |  | 1 | 35 | 2013-12-13 | 2013-12-13 | [113 empty] | 1 |  | 2013-12-13 | 2013-12-13
| - advisory committee |  |  | 1 | 35 | 2013-12-13 | 2013-12-13 | [113 empty] | 1 |  | 2013-12-13 | 2013-12-13
| - program-specific list |  |  | 1 | 35 | 2013-12-13 | 2013-12-13 | [113 empty] | 1 |  | 2013-12-13 | 2013-12-13
| * saves proof of delivery under Rule_Development¦4-Notice |  |  | 1 | 35 | 2013-12-13 | 2013-12-13 | [113 empty] | 1 |  | 2013-12-13 | 2013-12-13
| - NONDELIVERABLE.Notice.pdf (combined into 1 .pdf, scanned envelopes) | i |  | 1 | 35 | 2013-12-13 | 2013-12-13 | [113 empty] | 1 |  | 2013-12-13 | 2013-12-13
| - CONTENT.pdf | [119 empty] | 1 | X
| - LIST.pdf | [119 empty] | 1 | X
| - PROOF.OF.NOTICE.pdf (includes delivery confirmations) | [119 empty] | 1 | X
| AndreaDRC: | [119 empty] | 1 | X |  |  |  |  | AndreaDRC:
| ` |  |  | 1 | 35 | 2013-12-13 | 2013-12-13 | [113 empty] | 1 |  | 2013-12-13 | 2013-12-13
| * copies AndreaRW | [119 empty] | 1 | [5 empty] | * copies AndreaRW
| * requests Outlook Receipt | i | [118 empty] | 1
| * saves combined emails/receipts under Rule_Development¦4-Notice as: | [119 empty] | 1 | X
| PROOF.OF.KEY.LEG.NOTICE.pdf | [119 empty] | 1 | X
| AndreaRW: | [119 empty] | 1 | X |  |  |  |  | AndreaRW:
| * verifies newspaper advertisements are correct |  |  | 1 | 35 | 2013-12-13 | 2013-12-13 | [113 empty] | 1 |  | 2013-12-13 | 2013-12-13
| * obtains copy of affidavit of publication from Accounting |  |  | 1 | 35 | 2013-12-13 | 2013-12-13 | [113 empty] | 1 |  | 2013-12-13 | 2013-12-13
| * saves affidavit under Rule_Development¦4-Notice as: |  |  | 1 | 35 | 2013-12-13 | 2013-12-13 | [113 empty] | 1 |  | 2013-12-13 | 2013-12-13
| AFFIDAVIT.AD01, AFFIDAVIT.AD02, etc. | [119 empty] | 1 | X
| AndreaDRC & Michele maintain Rukemaking Activities Web page |  |  | 23 | 57 | 2013-12-13 | 2014-01-16 | [113 empty] | 1 |  | 2013-12-13 | 2014-01-16 |  |  | AndreaDRC & Michele maintain Rukemaking Activities Web page
| AndreaRW gathers and saves all notice emails for the Rule Record as: | i |  | 73 | 57 | 2013-10-02 | 2014-01-16 | [113 empty] | 1 |  | 2013-10-02 | 2014-01-16 |  |  | AndreaRW gathers and saves all notice emails for the Rule Record as:
| Rule_Development¦4-PublicNotice¦EMAILS.Notice.pdf | [119 empty] | 1 | X
[121 empty] | W | X
| Public Comment and Testimony | [119 empty] | T | X |  |  |  |  | Public Comment and Testimony
|  |  |  | Networkdays |  | Task | [114 empty] | B | X
| Incorporate Lane Regional Air Protection Agency Rules into State Implementation Plan |  |  | For Task | From today | Start | End | [113 empty] | B | X
| Task |  |  |  | -29741 | 2014-01-16 | 0 | [112 empty] | < | B | X | 2014-01-16 | 0
[121 empty] | Y | X
| Review version history and maintaining the rulemaking record > | i | [118 empty] | W | X
| SavvySupport reserves venues and equipment, gathers supplies | i |  | -4 | 54 | 2014-01-16 | 2014-01-13 | [113 empty] | 1 |  | 2014-01-16 | 2014-01-13 |  |  | SavvySupport reserves venues and equipment, gathers supplies
| START INFORMATION MEETING OPTION | [119 empty] | 1 | X |  |  |  |  | START INFORMATION MEETING OPTION
| AndreaRW: | [119 empty] | 1 | X |  |  |  |  | AndreaRW:
| * develops INFO.MEETING.TEXT |  |  | 1 | 57 | 2014-01-16 | 2014-01-16 | [113 empty] | 1 |  | 2014-01-16 | 2014-01-16
| * modifies MESSAGE.MAP | i |  | 1 | 57 | 2014-01-16 | 2014-01-16 | [113 empty] | 1 |  | 2014-01-16 | 2014-01-16
| * develops INFO.PRESENTATION |  |  | 1 | 57 | 2014-01-16 | 2014-01-16 | [113 empty] | 1 |  | 2014-01-16 | 2014-01-16
| * practices presentation |  |  | 1 | 57 | 2014-01-16 | 2014-01-16 | [113 empty] | 1 |  | 2014-01-16 | 2014-01-16
| * makes presentation adjustments |  |  | 1 | 57 | 2014-01-16 | 2014-01-16 | [113 empty] | 1 |  | 2014-01-16 | 2014-01-16
| * initiates MargaretMGR's review/approval, addresses suggestions |  |  | 1 | 57 | 2014-01-16 | 2014-01-16 | [113 empty] | 1 |  | 2014-01-16 | 2014-01-16 |  |  | * initiates MargaretMGR's review/approval, addresses suggestions
| 1st loop MargaretMGR reviews/approves optional info meeting materials |  |  | 1 | 57 | 2014-01-16 | 2014-01-16 | [113 empty] | 1 |  | 2014-01-16 | 2014-01-16 |  |  | 1st loop MargaretMGR reviews/approves optional info meeting materials
| 2nd loop MargaretMGR reviews/approves optional info meeting materials | N |  | 1 | 57 | 2014-01-16 | 2014-01-16 | [113 empty] | 1 |  | 2014-01-16 | 2014-01-16 |  |  | 2nd loop MargaretMGR reviews/approves optional info meeting materials
| 3rd loop MargaretMGR reviews/approves optional info meeting materials | N |  | 1 | 57 | 2014-01-16 | 2014-01-16 | [113 empty] | 1 |  | 2014-01-16 | 2014-01-16 |  |  | 3rd loop MargaretMGR reviews/approves optional info meeting materials
| 4th loop MargaretMGR reviews/approves optional info meeting materials | N |  | 1 | 57 | 2014-01-16 | 2014-01-16 | [113 empty] | 1 |  | 2014-01-16 | 2014-01-16 |  |  | 4th loop MargaretMGR reviews/approves optional info meeting materials
| CarrieAnn: | [119 empty] | 1 | X |  |  |  |  | CarrieAnn:
| * reviews responsibilities of hearings officer |  |  | 24 | 71 | 2014-01-03 | 2014-02-06 | [112 empty] | < | 1 |  | 2014-01-03 | 2014-02-06
| * develops introductory and logistics script | i |  | 24 | 71 | 2014-01-03 | 2014-02-06 | [112 empty] | < | 1 |  | 2014-01-03 | 2014-02-06
| * holds the following hearings with assigned team: | [119 empty] | 1 | [5 empty] | * holds the following hearings with assigned team:
| 1. LRAPA hearing |  |  |  | 54 |  | 2014-01-13 | [113 empty] | 1 |  |  | 2014-01-13 |  |  | 1. LRAPA hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.1.mp3 | [119 empty] | 1 | X
| 2. Enter city name hearing |  |  |  | 0 |  | 0 | [113 empty] | 0 |  |  | 0 |  |  | 2. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.2.mp3 | [119 empty] | 0 | X
| 3. Enter city name hearing |  |  |  | 0 |  | 0 | [113 empty] | 0 |  |  | 0 |  |  | 3. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.3.mp3 | [119 empty] | 0 | X
| 4. Enter city name hearing |  |  |  | 0 |  | 0 | [113 empty] | 0 |  |  | 0 |  |  | 4. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.4.mp3 | [119 empty] | 0 | X
| 5. Enter city name hearing |  |  |  | 0 |  | 0 | [113 empty] | 0 |  |  | 0 |  |  | 5. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.5.mp3 | [119 empty] | 0 | X
| 6. Enter city name hearing |  |  |  | 0 |  | 0 | [113 empty] | 0 |  |  | 0 |  |  | 6. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.6.mp3 | [119 empty] | 0 | X
| 7. Enter city name hearing |  |  |  | 0 |  | 0 | [113 empty] | 0 |  |  | 0 |  |  | 7. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.7.mp3 | [119 empty] | 0 | X
| 8. Enter city name hearing |  |  |  | 0 |  | 0 | [113 empty] | 0 |  |  | 0 |  |  | 8. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.8.mp3 | [119 empty] | 0 | X
| SavvySupport, for comments not received through online form: | [119 empty] | 1 | X |  |  |  |  | SavvySupport, for comments not received through online form:
| * stamps DEQ receipt date on mailed comments |  |  | 4 | 57 | 2014-01-13 | 2014-01-16 | [113 empty] | 1 |  | 2014-01-13 | 2014-01-16
| * adds commenter and comment to COMMENTS |  |  | 4 | 57 | 2014-01-13 | 2014-01-16 | [113 empty] | 1 |  | 2014-01-13 | 2014-01-16
| * scans and links comments by ID###.pdf - optional |  |  | 24 | 71 | 2014-01-03 | 2014-02-06 | [113 empty] | 1 |  | 2014-01-03 | 2014-02-06
| CLOSE PUBLIC COMMENT | [5 empty] | 2014-01-16 | [113 empty] | 1 |  | 2014-01-16 | 2014-01-16
| AndreaRW: | [119 empty] | 1 | X |  |  |  |  | AndreaRW:
| * saves online public comment information to COMMENTS |  |  | 4 | 57 | 2014-01-13 | 2014-01-16 | [113 empty] | 1 |  | 2014-01-13 | 2014-01-16
| * coordinates with team to: | [119 empty] | 1 | X
| - develop category titles to bundle similar comments |  |  | 1 | 54 | 2014-01-13 | 2014-01-13 | [113 empty] | 1 |  | 2014-01-13 | 2014-01-13
| - organize comments into categories |  |  | 1 | 54 | 2014-01-13 | 2014-01-13 | [113 empty] | 1 |  | 2014-01-13 | 2014-01-13
| - draft DEQ responses to each categories of comments |  |  | 1 | 54 | 2014-01-13 | 2014-01-13 | [113 empty] | 1 |  | 2014-01-13 | 2014-01-13
| * leads team work finalizing DEQ responses to public comment |  |  | 1 | 57 | 2014-01-16 | 2014-01-16 | [113 empty] | 1 |  | 2014-01-16 | 2014-01-16
| * emails comment/responses link to RulePublications@deq.state.or.us | i |  |  |  |  | 0 | [113 empty] | 1 |  | 2014-01-16 | 0
| Rule Publications: |  |  | 0 | 0 | 0 | 0 | [113 empty] | 1 | X
| * edits for plain English, style guide and tone | [119 empty] | 1 | X
| since this will become part of the EQC Packet | [119 empty] | 1 | X
` | * contacts AndreaRW with questions, clarificatios and suggestions | [119 empty] | 1 | X |  |  |  |  | * contacts AndreaRW with questions, clarificatios and suggestions
| MargaretMGR: | [119 empty] | 1 | X |  |  |  |  | MargaretMGR:
| * shares comments/responses to comments with Andy and approves |  |  | 1 | 54 | 2014-01-13 | 2014-01-13 | [113 empty] | 1 |  | 2014-01-13 | 2014-01-13 |  |  | * shares comments/responses to comments with Andy and approves
| 1st loop - team modifies responses to get to approval |  |  | 1 | 57 | 2014-01-16 | 2014-01-16 | [113 empty] | 1 |  | 2014-01-16 | 2014-01-16
| 2nd loop - team modifies responses to get to approval | Y |  | 1 | 57 | 2014-01-16 | 2014-01-16 | [113 empty] | 1 |  | 2014-01-16 | 2014-01-16
| 3rd loop - team modifies responses to get to approval | Y |  | 1 | 57 | 2014-01-16 | 2014-01-16 | [113 empty] | 1 |  | 2014-01-16 | 2014-01-16
| Final loop - team modifies responses to get to approval | Y |  | 1 | 57 | 2014-01-16 | 2014-01-16 | [113 empty] | 1 |  | 2014-01-16 | 2014-01-16
| AndreaRW: | [119 empty] | 1 | X |  |  |  |  | AndreaRW:
| * gathers emails ABOUT comments, not actual comments, for Rule Record | i |  | 1 | 57 | 2014-01-16 | 2014-01-16 | [113 empty] | 1 |  | 2014-01-16 | 2014-01-16
| * saves them as Rule_Development¦5-PublicComment...¦EMAIL.Comment.pdf | [119 empty] | 1 | X
[121 empty] | W | X
| EQC Preparation | [119 empty] | T | X
|  |  |  | Networkdays |  | Task | [114 empty] | B | X
| Incorporate Lane Regional Air Protection Agency Rules into State Implementation Plan |  |  | For Task | From today | Start | End | [113 empty] | B | X
| Task |  |  |  | 115 | 2013-10-02 | 2014-03-19 | [113 empty] | B | X | 2013-10-02 | 2014-03-19
[121 empty] | Y | X
| Review version history and maintaining the rulemaking record > | i | [118 empty] | W | X
| AndreaRW: |  |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06 |  |  | AndreaRW:
| * drafts content of Director's Report to EQC |  |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06 |  |  | * drafts content of Director's Report to EQC
| * no EQC Information Item | i |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 0 |  | 2013-10-02 | 2014-02-06 |  |  | * no EQC Information Item
| * leads EQC material review |  |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06 |  |  | * leads EQC material review
| AndreaRW develops STAFF.RPT.Permanent preloaded in folder 6 by: |  |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06 |  |  | AndreaRW develops STAFF.RPT.Permanent preloaded in folder 6 by:
| * selecting EQC recommendation in staff report |  |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06
| * integrating NOTICE into STAFF REPORT.Permanent by |  |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06 |  |  | * integrating NOTICE into STAFF REPORT.Permanent by
| inserting message into header of each reviewed and noticed section: | [119 empty] | 1 | X
| - Statement of need | [119 empty] | 1 | X
| - Federal relationships | [119 empty] | 1 | X
| - Fiscal impact statement | [119 empty] | 1 | X
| - Fees | [119 empty] | 1 | X
| - Land use | [119 empty] | 1 | X
| - NAME OTHER SECTION UNCHANGED SINCE PUBLIC NOTICE REVIEW | [119 empty] | 1 | X
| - NAME OTHER SECTION UNCHANGED SINCE PUBLIC NOTICE REVIEW | [119 empty] | 1 | X
| * verifies PROPOSED.RULES use latest compilation compared | i |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06
| compared to Oregon State Archives | [119 empty] | 1 | X
| * coordinates work on STAFF.RPT.Permanent sections: | [119 empty] | 1 | X |  |  |  |  | * coordinates work on STAFF.RPT.Permanent sections:
| - updates to current story, inserts message above if unchanged since notice: | [119 empty] | 1 | X
| > Overview - update as needed to tell current story or insert message above |  |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06
| > Background (optional) - update as needed to tell current story |  |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06
| > Rules affected, authorities, supporting docs- update as needed |  |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06
| - Implementation - draft |  |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06
| - Public Involvement - update to reflect actual |  |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06
| - Summary of comments and DEQ responses |  |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06
| > inserts message above to indicate previous reviews | [119 empty] | 1 | X
| - Commenters |  |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06
| * finalizes draft of EQC Packet: | [119 empty] | 1 | X
| - STAFF.RPT.Permanent |  |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06 |  |  | - STAFF.RPT.Permanent
| - PROPOSED.RULES |  |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06
| - SUPPORTING.DOCUMENTS |  |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06
| * submits draft EQC Packet review to: | [119 empty] | 1 | X
| - MargaretMGR for lead manager perspective |  |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06 |  |  | - MargaretMGR for lead manager perspective
| - LarryK, if needed |  |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06 |  |  | - LarryK, if needed
| - AndreaSIP for SIP review |  |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06 |  |  | - AndreaSIP for SIP review
| - AndreaDRC for division continuity |  |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06 |  |  | - AndreaDRC for division continuity
| - Enter custom reviewer and action |  |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06
| - Enter custom reviewer and action |  |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06
| - Enter custom reviewer and perspective |  |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06
| Enter custom review loop 1 | Y |  | 1 | 71 | 2014-02-06 | 2014-02-06 | [113 empty] | 1 |  | 2014-02-06 | 2014-02-06
| * enter custom action word and reviewer |  |  | 1 | 71 | 2014-02-06 | 2014-02-06 | [113 empty] | 1 |  | 2014-02-06 | 2014-02-06
| * enter custom action word and reviewer |  |  | 1 | 71 | 2014-02-06 | 2014-02-06 | [113 empty] | 1 |  | 2014-02-06 | 2014-02-06
| * enter custom action word and reviewer |  |  | 1 | 71 | 2014-02-06 | 2014-02-06 | [113 empty] | 1 |  | 2014-02-06 | 2014-02-06
| Name initiator and subject for custom review loop 2 | Y |  | 1 | 71 | 2014-02-06 | 2014-02-06 | [113 empty] | 1 |  | 2014-02-06 | 2014-02-06
| * enter custom action word and reviewer |  |  | 1 | 71 | 2014-02-06 | 2014-02-06 | [113 empty] | 1 |  | 2014-02-06 | 2014-02-06
| * enter custom action word and reviewer |  |  | 1 | 71 | 2014-02-06 | 2014-02-06 | [113 empty] | 1 |  | 2014-02-06 | 2014-02-06
| * enter custom action word and reviewer |  |  | 1 | 71 | 2014-02-06 | 2014-02-06 | [113 empty] | 1 |  | 2014-02-06 | 2014-02-06
| Name initiator and subject for custom review loop 3 | Y |  | 1 | 71 | 2014-02-06 | 2014-02-06 | [113 empty] | 1 |  | 2014-02-06 | 2014-02-06
| * enter custom action word and reviewer |  |  | 1 | 71 | 2014-02-06 | 2014-02-06 | [113 empty] | 1 |  | 2014-02-06 | 2014-02-06
| * enter custom action word and reviewer |  |  | 1 | 71 | 2014-02-06 | 2014-02-06 | [113 empty] | 1 |  | 2014-02-06 | 2014-02-06
| * enter custom action word and reviewer |  |  | 1 | 71 | 2014-02-06 | 2014-02-06 | [113 empty] | 1 |  | 2014-02-06 | 2014-02-06
| AndreaRW: | [119 empty] | 1 | X |  |  |  |  | AndreaRW:
| * discusses need for 1¦1 briefings with commissioners with MargaretMGR & Andy | Y |  | 1 | 71 | 2014-02-06 | 2014-02-06 | [113 empty] | 1 |  | 2014-02-06 | 2014-02-06 |  |  | * discusses need for 1¦1 briefings with commissioners with MargaretMGR & Andy
| Enter staff who will brief each commissioner individually | [119 empty] | 1
| * obtains final EQC Packet approval from: | [119 empty] | 1 | X
| - MargaretMGR for lead manager approval |  |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06 |  |  | - MargaretMGR for lead manager approval
| - Andy for division administrator approval |  |  | 87 | 71 | 2013-10-02 | 2014-02-06 | [113 empty] | 1 |  | 2013-10-02 | 2014-02-06 |  |  | - Andy for division administrator approval
| * emails RulePublications@deq.state.or.us that EQC Packet is ready | i |  |  |  |  | 2014-02-06 | [113 empty] | 1 |  |  | 2014-02-06
| * relaxes while RulePublications does its work that includes: | [119 empty] | 1 | X
| - sending AndreaRW an email confirmation | [119 empty] | 1 | [5 empty] | - sending AndreaRW an email confirmation
| - editing with SOS and Legislative Counsel perspective - Maggie | [119 empty] | 1 | [5 empty] | - editing with SOS and Legislative Counsel perspective - Maggie
| - editing with EQC perspective, prepares packet for EQC - Stephanie | [119 empty] | 1 | [5 empty] | - editing with EQC perspective, prepares packet for EQC - Stephanie
| - contacting AndreaRW with questions or modifications | [119 empty] | 1 | [5 empty] | - contacting AndreaRW with questions or modifications
| - contacting AndreaRW when staff report ready for EQC - Stephanie | [119 empty] | 1 | [5 empty] | - contacting AndreaRW when staff report ready for EQC - Stephanie
| * notifies the following according to division's best practice | [119 empty] | 1 | X
| - key stakeholders |  |  | 114 | 98 | 2013-10-02 | 2014-03-18 | [113 empty] | 1 |  | 2013-10-02 | 2014-03-18
| - advisory committee members |  |  | 29782 | 98 | 0 | 2014-03-18 | [113 empty] | 0 |  | 0 | 2014-03-18
| - commenters |  |  | 114 | 98 | 2013-10-02 | 2014-03-18 | [113 empty] | 1 |  | 2013-10-02 | 2014-03-18
| - interested parties (optional) |  |  | 114 | 98 | 2013-10-02 | 2014-03-18 | [113 empty] | 1 |  | 2013-10-02 | 2014-03-18
| * leads team development of EQC presentation |  |  | 114 | 98 | 2013-10-02 | 2014-03-18 | [113 empty] | 1 |  | 2013-10-02 | 2014-03-18
| * coordinates presentation practices |  |  | 114 | 98 | 2013-10-02 | 2014-03-18 | [113 empty] | 1 |  | 2013-10-02 | 2014-03-18
| * makes any presentation adjustments |  |  | 114 | 98 | 2013-10-02 | 2014-03-18 | [113 empty] | 1 |  | 2013-10-02 | 2014-03-18
| Presentation team ATTENDS EQC MEETING |  |  |  |  | 2014-03-19 | 2014-03-19 | [113 empty] | 1 |  | 2014-03-19 | 2014-03-19
| AndreaRW collects emails about EQC preparations for Rule Record and saves as: | i |  | 1 | 99 | 2014-03-19 | 2014-03-19 | [113 empty] | 1 |  | 2014-03-19 | 2014-03-19 |  |  | AndreaRW collects emails about EQC preparations for Rule Record and saves as:
| Rule_Development¦6-EQCPreparation¦EMAILS.EQC.Prep.pdf | [119 empty] | 1 | X
[121 empty] | W | X
| Post EQC | [119 empty] | T | X
|  |  |  | Networkdays |  | Task | [114 empty] | B | X
| Incorporate Lane Regional Air Protection Agency Rules into State Implementation Plan |  |  | For Task | From today | Start | End | [113 empty] | B | X
[5 empty] | 64 | 2014-03-19 | 2014-06-17 | [113 empty] | B | X | 2014-03-19 | 2014-06-17
[121 empty] | Y | X
| Review version history and maintaining the rulemaking record > | i | [118 empty] | W | X
| Work shifts from SharePoint to Rule_Development | [119 empty] | 1 | X
| AndreaRW: | [119 empty] | 1 | X |  |  |  |  | AndreaRW:
| * prepares/saves documents to Rule_Development¦7-PostEQC |  |  |  | 99 |  | 2014-03-19 | [113 empty] | 1 |  |  | 2014-03-19
| - ADDENDUM.TO.STAFF.RPT (if presented to EQC) |  |  |  | 99 |  | 2014-03-19 | [113 empty] | 1 |  |  | 2014-03-19
| - ADOPTED.RULES.3.19.2014.docx |  |  |  | 99 |  | 2014-03-19 | [113 empty] | 1 |  |  | 2014-03-19 |  |  | - ADOPTED.RULES.3.19.2014.docx
| - ADOPTED.REDLINE.RULES.docx |  |  |  | 99 |  | 2014-03-19 | [113 empty] | 1 |  |  | 2014-03-19 |  |  | - ADOPTED.REDLINE.RULES.docx
| - TABLES.FOR.DIVSION.###.docx (1 .docx per division) |  |  |  | 99 |  | 2014-03-19 | [113 empty] | 1 |  |  | 2014-03-19 |  |  | - TABLES.FOR.DIVSION.###.docx (1 .docx per division)
| - TABLES.FOR.DIVISION.###.docx (1 .docx per division), etc. |  |  |  | 99 |  | 2014-03-19 | [113 empty] | 1 |  |  | 2014-03-19 |  |  | - TABLES.FOR.DIVISION.###.docx (1 .docx per division), etc.
| * emails Maggie affirming EQC action and document readiness |  |  |  | 99 |  | 2014-03-19 | [113 empty] | 1 |  |  | 2014-03-19 |  |  | * emails Maggie affirming EQC action and document readiness
| * emails optional STAKEHOLDER.NOTIFICATION of EQC action | Y |  |  | 99 |  | 2014-03-19 | [113 empty] | 1 |  |  | 2014-03-19
| * coordinates EPA.SIP.SUBMITAL with AndreaSIP |  |  |  | 99 |  | 2014-03-19 | [113 empty] | 1 |  |  | 2014-03-19 |  |  | * coordinates EPA.SIP.SUBMITAL with AndreaSIP
| * coordinates AC.THANK.YOU email or letter with MargaretMGR | i |  |  | 99 |  | 2014-03-19 | [113 empty] | 0 |  |  | 2014-03-19 |  |  | * coordinates AC.THANK.YOU email or letter with MargaretMGR
| * coordinates AC.SURVEY with MargaretMGR | i |  |  | 99 |  | 2014-03-19 | [113 empty] | 0 |  |  | 2014-03-19 |  |  | * coordinates AC.SURVEY with MargaretMGR
| * coordinates optional discussion on project evaluation, lessons learned |  |  |  | 99 |  | 2014-03-19 | [113 empty] | 1 |  |  | 2014-03-19
| AndreaDRC: | [119 empty] | 1 | X |  |  |  |  | AndreaDRC:
| * no DAS involvement |  |  |  | 0 |  | 0 | [113 empty] | 0 |  |  | 0 |  |  | * no DAS involvement
| * no DAS involvement |  |  |  | 0 |  | 0 | [113 empty] | 0 |  |  | 0 |  |  | * no DAS involvement
| * no DAS involvement |  |  |  | 0 |  | 0 | [113 empty] | 0 |  |  | 0 |  |  | * no DAS involvement
| * no DAS involvement |  |  |  | 0 |  | 0 | [113 empty] | 0 |  |  | 0 |  |  | * no DAS involvement
| Maggie: | [119 empty] | 1 | X |  |  |  |  | Maggie:
| * prepares and e-files ADOPTED RULES with Secretary of State | i |  |  | 101 |  | 2014-03-21 | [113 empty] | 1 |  |  | 2014-03-21
| - CERTIFICATE.pdf | [119 empty] | 1 | X
| - ADOPTED.RULES.pdf | [119 empty] | 1 | X
| - 340-### TABLES.pdf | [119 empty] | 1 | X
| - 340-### TABLES.pdf | [119 empty] | 1 | X
| - AUTHORIZATION.pdf | [119 empty] | 1 | X
| EFFECTIVE DATE |  |  |  | 101 |  | 2014-03-21 | [113 empty] | 1 |  |  | 2014-03-21
| * shuttles ADOPTED REDLINE.RULES to Legislative Counsel (return receipt) | i |  |  | 101 |  | 2014-03-21 | [113 empty] | 1 |  |  | 2014-03-21
| - CERTIFICATE.pdf | [119 empty] | 1 | X
| - ADOPTED.REDLINE.RULES.pdf | [119 empty] | 1 | X
| - self-addressed envelope, fold underside of flap over a 2nd certificate" | [119 empty] | 1 | X
| write "Please date stamp certificate and return." on underside of flap | [119 empty] | 1 | X
| * saves proof as Rule_Development¦7-PostEQC¦PROOF.OF.FILING.pdf | i |  |  | 101 |  | 2014-03-21 | [113 empty] | 1 |  |  | 2014-03-21
| 1 CERTIFICATE.pdf | [119 empty] | 1 | X
| 2 ADOPTED.RULES.pdf | [119 empty] | 1 | X
| 2a 340-### TABLES.pdf | [119 empty] | 1 | X
| 2b 340-### TABLES.pdf | [119 empty] | 1 | X
| 3 AUTHORIZATION.pdf | [119 empty] | 1 | X
| 4 ADOPTED.REDLINE.RULES.pdf | [119 empty] | 1 | X
| 5 LC-SHUTTLE.RECEIPT.pdf | [119 empty] | 1 | X
| * retires SharePoint to Rule_Development¦SharePointAtClose |  |  |  | 101 |  | 2014-03-21 | [113 empty] | 1 |  |  | 2014-03-21
| that includes version history and coordination with AndreaRW | [119 empty] | 1 | X |  |  |  |  | that includes version history and coordination with AndreaRW
| AndreaRW: | [119 empty] | 1 | X |  |  |  |  | AndreaRW:
| * gathers emails about post EQC activities for the Rule Record and saves as: |  |  | 1 | 101 | 2014-03-21 | 2014-03-21 | [113 empty] | 1 |  | 2014-03-21 | 2014-03-21
| Rule_Development¦7-PostEQC¦EMAILS.PostEQC.pdf | [119 empty] | 1 | X
| * verifies accuracy of rules published in Oregon Bulletin |  |  | 1 | 112 | 2014-04-07 | 2014-04-07 | [113 empty] | 1 |  | 2014-04-07 | 2014-04-07
| If errors, AndreaRW works with Maggie to correct and selects 'Y' > | Y |  | 1 | 112 | 2014-04-07 | 2014-04-07 | [113 empty] | 1 |  | 2014-04-07 | 2014-04-07 |  |  | If errors, AndreaRW works with Maggie to correct and selects 'Y' >
| AndreaSIP submits SIP to EPA within 60 days AFTER adoption |  |  | 34 | 132 | 2014-03-19 | 2014-05-05 | [113 empty] | 1 |  | 2014-03-19 | 2014-05-05 |  |  | AndreaSIP submits SIP to EPA within 60 days AFTER adoption
| Maggie moves rulemaking record to Rule_Development¦Filed Rules | i |  | 1 | 101 | 2014-03-21 | 2014-03-21 | [113 empty] | 1 |  | 2014-03-21 | 2014-03-21 |  |  | Maggie moves rulemaking record to Rule_Development¦Filed Rules
| organized by SOS certificate and order number "DEQ ##-yyyy" | [119 empty] | 1 | X
| in coordination with AndreaRW | [119 empty] | 1 | X |  |  |  |  | in coordination with AndreaRW
| AndreaRW: | [119 empty] | 1 | X |  |  |  |  | AndreaRW:
| * places all physical records in archival box - do not print electronic records |  |  | 62 | 162 | 2014-03-21 | 2014-06-17 | [113 empty] | 1 |  | 2014-03-21 | 2014-06-17
| * labels the box by SOS certificate and order number "DEQ ##-yyyy" |  |  |  | 162 |  | 2014-06-17 | [113 empty] | 1 |  | 0 | 2014-06-17
| * delivers archival box to Maggie |  |  |  | 162 |  | 2014-06-17 | [113 empty] | 1 |  | 0 | 2014-06-17 |  |  | * delivers archival box to Maggie
| AndreaDRC coordinates retiring Q-Time number(s) with RobertB |  |  | 1 | 101 | 2014-03-21 | 2014-03-21 | [113 empty] | 1 |  | 2014-03-21 | 2014-03-21 |  |  | AndreaDRC coordinates retiring Q-Time number(s) with RobertB
| At the close of the rulemaking records, Maggie archives the record | [119 empty] | 1 | [5 empty] | At the close of the rulemaking records, Maggie archives the record
| FROM: \\deqhq1\Rule_Development | i | [118 empty] | 1
| TO: \\deqhq1\Rule_Archives | [119 empty] | 1 | X
| TEAM CELEBRATES |  |  | 62 | 162 | 2014-03-21 | 2014-06-17 | [113 empty] | 1 |  | 2014-03-21 | 2014-06-17
| AndreaRW takes a vacation | [119 empty] | 1 | X |  |  |  |  | AndreaRW takes a vacation
1
[7 empty] | $H$763 | [114 empty] | X
B
Formulas:
From today = IF(YEAR([End])>2000,NETWORKDAYS(TODAY(),[End],S.DDL_DEQClosed),0)
From today = IF(S.SIP.Involved="N",0,IF(S.General.Complexity=1,0,NETWORKDAYS(TODAY(),[End],S.DDL_DEQClosed)))
Networkdays = NETWORKDAYS([Start ↓],[End],S.DDL_DEQClosed)
mm/dd/yy
Subject
Your name
Your message
DEQ Closed
To restore any cell under columns G or H to default, place cursor in cell then enter "=AA" followed by the cell address. EXAMPLE: =AAH13 would restore the default EQC meeting.
9/26/13
Subject - what is 107Bf21?
Andrea
9/26/13
Subject - what is 107Bf21?
Andrea
10/23/13
Start Date
Andrea Curtis
The date the DA approves a concept development shouldn't affect subsequent dates in the schedule . The date that a DA approves concept development could be months before we begin work on the rulemaking.
10/23/13
Indicate Entry
Andrea Curtis
Highlight or otherwise indicate when a cell needs us to enter a date
10/23/13
Indicate Entry
Andrea Curtis
Highlight or otherwise indicate when a cell needs us to enter a date
10/23/13
Monthly report
Andrea Curtis
Add monthly report dates, in addition to EQC meeting dates.

## ConditionalFormat (hidden)
|  | Example | Calculation | Applies to | Last row
Column I: Section Separator codes
T | Section title | White on Teal | =IF($AAE4="T",TRUE) | =$B$4:$ZZ$474
Y | Highlight for section title | Teal on Yellow | =IF($AAE4="Y",TRUE) | "
W |  | White on white | =IF($AAE4="W",TRUE) | "
0 OR 1 | Indicates task involved/not involved | White on white | =IF($AAE4=0,TRUE) | "
Office Closure |  | See DDL worksheet | S.DDL_DEQClosed is the "holiday" table in WORKDAY function
|  | Office Closure date | =IF(WORKDAY($G20-1,1,S.DDL_DEQClosed)<>$G20,TRUE) | $G$20:$G$480 (or last row)
|  | Office Closure date | =IF(WORKDAY($H20-1,1,S.DDL_DEQClosed)<>$H20,TRUE) | $H$20:$H$480 (or last row)
|  | Date has past | =IF(WORKDAY($G10-1,1,S.DDL_DEQClosed)<>$G10,TRUE) | $G$10:$G$480 (or last row)
|  | " | =IF(WORKDAY($H10-1,1,S.DDL_DEQClosed)<>$H10,TRUE) | $H$10:$H$480 (or last row)
Gantt
| An 'X' in $J10 identifies the row as for Gantt to format | Workday | =AND($J10<>"X",$G10<=L$7,$H10>=K$7) | $K10:$AHC$450
|  | Weekend | =IF(OR(WEEKDAY(K$7)=1,WEEKDAY(K$7)=7),TRUE) | $K10:$AHC$450
|  | Closed | =IF(ISERROR(VLOOKUP(K$7,S.DDL_DEQClosed,1,FALSE)),0,1) | $K10:$AHC$450
S.LastCellGantt
s.LastCellschedule

## AddToPlan (hidden)
How a Division Administrator adds a new proposal to the rolling rulemaking plan
| Start | Notify | Train | Draft | Approve | Prepare | Inform
Program è | Identify need * legislation, court order, federal requirements, fees, easier to do business * DEQ intitiated through environmental soultions | If approved to develop concept for inclusion on DEQ Rulemaking Plan | SharePoint, Rule_Development, CONSIDERATIONS & RESOURCES, records management | CONSIDERATIONS, RESOURCES, Overview of Key Dates | Concept for inclusion on DEQ Rulemaking Plan | If division approves adding concept to DEQ Rulemaking Plan | Focusing on communication materials
| ê |  | 2 hours | 8 hours
|  |  |  | Team Collaboration |  | Team Collaboration
Lead staff |  |  | Attend, learn, share | Complete 1st workbook drafts using what you know now |  | Prepare DA communication to EMT/EQC assistant
Lead manager | Discuss need with DA and program managers | Assign staff to work with DRC/ARC on concept development | Attend, learn, share | Add information you know | Present RESOURCES & CONSIDERATIONS summary to DA & program managers | Help prepare and approve DA communication
Rules coordinators (DRC, ARC) |  | ARC Establish SharePoint, Rule_Development sites schedule training | Facilitate, learn, share | Provided guidance and review |  | ARC Add to plan. Prepare summary pdf for DA communication
Division administrator (DA) | Approve initial work to develop concept - discuss potential with EMT | Notify DRC and ARC |  |  | Approve/reject concept addition to plan. Inform lead staff, DRC, ARC |  | EMT/EQC Assistant using communication materials adapted to personal style
EMT | Offer initial ideas about connections, cautions | [5 empty] | Offer advice, indicate interest
EQC assistant | [6 empty] | Add to monthly Director's Report. Advise DRC/ARC re: EQC involvement

## Names
Names entered on this worksheet will become part of the Schedule of Tasks
| Enter first name |  | CodeName | Title
Lead staff | AndreaRW |  | LRAPA | Incorporate Lane Regional Air Protection Agency Rules into State Implementation Plan | i
Lead manager | MargaretMGR |  | ACDPFE
Division Administrator | Andy |  |  | \\deqhq1\Rule_Development\2013 Plan\AQ-RM-ACDPfeeIncrease-Andrea Curtis
OCO Communications | WilliamK |  |  | \\deqhq1\Rule_Development\2013 Plan\AQ-RM-ACDPfeeIncrease-Andrea Curtis
Division Rules Coordinator | AndreaDRC |  |  | Update Air Contaminant Discharge Permit Fees
Agency Rules Coordinator | Maggie
EQC Assistant | Stephanie
State Implementation Plan Coordinator | AndreaSIP
Web Master | Michele
Fiscal staff | Robin
Budget analyst | MargaretBGT
Assistant Attorney General | LarryK
Legislative liaison | MargaretLEG
Support staff | SavvySupport | <<<<<<<< | If support staff is not available, include Lead staff's name
Time Accounting | RobertB
Director | Dick
Hearings Officer | CarrieAnn
DA Assistant | Carol
Chief Public Affairs Officer | JoanieS

## HearingAndAdDates
S.RulemakingTitle | 2013-10-24
Hearings |  | Notes
LRAPA | 2014-01-13
-blank - | -blank -
-blank - | -blank -
-blank - | -blank -
-blank - | -blank -
-blank - | -blank -
-blank - | -blank -
-blank - | -blank -
Newspaper Advertisements
NOTICE.AD01.OREGONIAN | 2013-12-11
NOTICE.AD02.REGISTERGUARD | 2013-12-11
NOTICE.AD03.[INSERT NAME PUBLICATION] | 2013-12-11
NOTICE.AD04.[INSERT NAME PUBLICATION] | 2013-12-11
NOTICE.AD05.[INSERT NAME PUBLICATION] | 2013-12-11
NOTICE.AD06.[INSERT NAME PUBLICATION] | 2013-12-11
NOTICE.AD07.[INSERT NAME PUBLICATION] | 2013-12-11
NOTICE.AD08.[INSERT NAME PUBLICATION] | 2013-12-11