## CodeName.ScheduleOfTasks
| Overview of Key Dates | [6 empty] | T
| GHGTemp |  |  |  | Start ↓ | End |  | B
[5 empty] | 2014-12-05 | 2015-02-03 |  | B | 2014-12-05 | 2015-02-03 |  | Last row = 866
Y
| To restore any cell under columns G or H to default, place cursor in cell then enter "=A" followed by the cell address. EXAMPLE: =AG13 would restore the default Start of Advisory Committee. | [6 empty] | 0 |  | Dir. Date Used in Calcs
| Director added to DEQ Rulemaking Plan | Y | [5 empty] | 1 |  | 0
0
| TEMPORARY Rulemaking | T |  |  |  |  | 30 | 1 |  |  |  | TEMPORARY Rulemaking
0
| Rule proposal complexity (1=Minimal, 2= Moderate, 3=Complex) | 2 |  |  |  |  | 30 | 1
0
| Advisory Committee - not involved | N | i |  | 2014-05-02 | 0 | 0 | 0 | 0 | 0 |  | Advisory Committee - not involved
0
| Fees - not involved | N |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fees - not involved
| -blank- | N | i | 0 |  |  | 0 | 0 |  |  |  | -blank-
| -blank- |  |  | 30 |  | 0 | 30 | 0 |  | 0 |  | -blank-
0
| State Implementation Plan for AQ rules - not involved | N |  | 0 |  |  | 0 | 0 |  |  |  | State Implementation Plan for AQ rules - not involved
| -blank- |  |  |  |  | 0 |  | 0 |  | 0 |  | -blank-
| -blank- |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  | -blank-
[8 empty] | 0 |  |  | `
| Public Notice - not required for TEMPORARY rules - APA | N |  | Adj | 0 | 0 |  | 0 | 0 | 0 | Best practice | Public Notice - not required for TEMPORARY rules - APA
| -blank- |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | -blank-
| -blank- |  |  | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | -blank-
| -blank- |  |  | 5 | 0 | 0 | 7 | 0 | 0 | 0 | 5 | -blank-
| -blank |  |  |  |  | 0 |  | 0 |  | 0 |  | -blank
| -blank- | Drop down list > |  |  |  | 2014-10-01 |  | 0 |  | 0 |  | -blank-
1
| Public Comment and Testimony - not involved | Y |  |  | 0 | 0 | 0 | 1 | 0 | 0 |  | Public Comment and Testimony - not involved
| -blank- |  |  |  |  | 1900-01-01 |  | 1 |  | 1900-01-01 |  | -blank-
| ERROR: All hearings must be noticed |  |  |  |  | 0 |  | 0 |  | 0 |  | ERROR: All hearings must be noticed
| -blank- |  |  |  |  | 0 |  | 1 |  | 0 |  | -blank-
1
| EQC Preparation |  |  |  | 2014-08-06 | 2014-09-29 |  | 1 | 0 | 2014-09-29 |  | =IF(S.Notice.Involved="N","-blank-",IF(S.EQC.SubmitStaffRpt-S.Notice.CloseComment<45,"ERROR - Staff report due before Close of public comment.","Close public comment - best practice, 3 days after last hearing"))
1
| No EQC involvement before Action Item meeting |  |  |  | Option 1 ↓ | Option 2 ↓ |  | 1 |  |  |  | No EQC involvement before Action Item meeting
| No Director's report requested | N | i |  | 0 | 0 |  | 0 | 0 | 0 |  | No Director's report requested
| No information item requested | N | i |  | 0 | 0 | 0 | 0 | 0 | 0 |  | No information item requested
| No facilitated hearing requested | N |  |  | 0 | 2014-10-22 |  | 0 | 0 | 0 |  | No facilitated hearing requested
1
| Rule publication - submit TEMPORARY staff report |  |  |  |  | 2014-09-29 | 37 | 1 |  | 2014-09-29 |  | Rule publication - submit TEMPORARY staff report
| EQC meeting - TEMPORARY Rulemaking Action Item | Drop down list > |  |  |  | 2014-11-05 |  | 1 |  | #N/A |  | EQC meeting - TEMPORARY Rulemaking Action Item
[7 empty] | -55 | 1 | < +/- calendar days adjustment
[7 empty] | 134 | 1 | < calendar days added
1
| Post EQC Activities |  |  |  | 2014-11-05 | 2015-02-03 |  | 1 | 2014-11-05 | 2015-02-03
| SOS - file rules |  |  |  |  | 2014-11-07 |  | 1 |  | 2014-11-07
| DAS - fees not involved |  |  |  |  | 2014-11-10 |  | 0 |  | 2014-11-10 |  | DAS - fees not involved
| Rules become effective select 'Y' if effective upon filing > | Y |  |  |  | 2014-11-07 |  | 1 |  | 2014-11-07
| EPA - SIP not involved |  |  |  |  | 0 |  | 0 |  | 0 |  | EPA - SIP not involved
Planning
| GHGTemp |  |  |  | Start | End |  | B
[5 empty] | 2014-08-06 | 2014-08-06 |  | B | 0 | 2014-08-06 | 2014-05-02
Y
| Review version history to help maintain rulemaking record > | i | [5 empty] | W
| KEY PEOPLE | [6 empty] | 1
| Subject expert, core team member - Jerry | [6 empty] | 1 |  |  |  | Subject expert, core team member - Jerry
| * member of core team - project manager | [6 empty] | 1
| * responsible for: | [6 empty] | 1
| - meeting program's rulemaking goals | [6 empty] | 1
| - meeting subject expert's tasks identified in this Schedule | [6 empty] | 1
| - engaging rules group lead, core team and RESOURCES appropriately | [6 empty] | 1
| - ensuring technical and programatice accuracy of completed work products | [6 empty] | 1
| * leads: | [6 empty] | 1
| - research and analysis for rulemaking | [6 empty] | 1
| - drafting work products | [6 empty] | 1
| - core team meetings | [6 empty] | 1
| * briefs: | [6 empty] | 1
| - core team and management about delays and complications as needed | [6 empty] | 0
| - Lydia & Lydia as needed | [6 empty] | 0 |  |  |  | - Lydia & Lydia as needed
| Sponsoring manager, core team member - Leah | [6 empty] | 1 |  |  |  | Sponsoring manager, core team member - Leah
| * member of core team - subject direction | [6 empty] | 1
| * responsible for approving external work product as: | [6 empty] | 1
| - meeting program and section goals | [6 empty] | 1
| - being accurate both technically & programmatically | [6 empty] | 1
| - meeting sponsoring manager's task deadlines in this Schedule | [6 empty] | 1
| * leads extra review cycles for Lydia as needed | [6 empty] | 0 |  |  |  | * leads extra review cycles for Lydia as needed
| * briefs: | [6 empty] | 1
| - core team and management about delays and complications as needed | [6 empty] | 0 |  |  |  | * briefs core team, Lydia & Lydia as needed
| - Lydia & Lydia as needed | [6 empty] | 0 |  |  |  | - Lydia & Lydia as needed
| Rules group lead, core team member - AndreaG | [6 empty] | 1 |  |  |  | Rules group lead, core team member - AndreaG
| * member of core team - rulemaking best practices | [6 empty] | 1
| * responsible for: | [6 empty] | 1
| - quality of public rulemaking documents | [6 empty] | 1
| - fiscal and economic impact analysis | [6 empty] | 0 |  |  |  | * keeps Lydia informed about risks, progress & potential delays
| * leads rule publication work: | [6 empty] | 1
| - establish SharePoint sub site, Rule_Developmant drive and archival spaces | [6 empty] | 1
| - establish/maintain Web page, URLs, online comment form, University student Outlook account | [6 empty] | 1
| - engages Rule Publications (SIP coordinator, public affairs consultant, EQC assistant) | [6 empty] | 1
| assistant) as needed for edits, style guide, grammar, plain English, organization, clarity and tone | [6 empty] | 1
| clarity and tone | [6 empty] | 1
| - reconciles Rule Publications edits that do not affect subject content | [6 empty] | 1
| * authenticates SOS & LC submittals, files notice, fiscal & rules | [6 empty] | 0 |  |  |  | * keeps Lydia informed about risks, progress & potential delays
| * briefs: | [6 empty] | 1
| - core team and management about delays and complications as needed | [6 empty] | 0 |  |  |  | * briefs core team, Lydia & Lydia as needed
| - team & Lydia as needed | [6 empty] | 0 |  |  |  | - team & Lydia as needed
| Program Support Staff - Jerry | [6 empty] | 1 |  |  |  | Program Support Staff - Jerry
| Assistant DA - Lydia | [6 empty] | 1 |  |  |  | Assistant DA - Lydia
| DA - Lydia | [6 empty] | 1 |  |  |  | DA - Lydia
| GENERAL INFORMATION | [6 empty] | 1
| Q-Time number = ????? | [6 empty] | 0
| SharePoint - collaboration place for working documents | [6 empty] | 0
| http://deqsps/programs/rulemaking/PROGRAM/GHGTempdefault.aspx | [6 empty] | 0 |  |  |  | http://deqsps/programs/rulemaking/PROGRAM/GHGTempdefault.aspx
| Rules Development - non collaborative work | [6 empty] | 0
| \\deqhq1\Rule_Development\Currrent Plan\GHGTemp.aspx | [6 empty] | 0 |  |  |  | \\deqhq1\Rule_Development\Currrent Plan\GHGTemp.aspx
| URLs | [6 empty] | 0
| Online public comment form | [6 empty] | 0
| http://www.oregon.gov/deq/RulesandRegulations/Pages/comments/GHGTemp.aspx | [6 empty] | 0 |  |  |  | http://www.oregon.gov/deq/RulesandRegulations/Pages/comments/GHGTemp.aspx
| External Web page | [6 empty] | 0
| http://www.oregon.gov/deq/RulesandRegulations/Pages/2014/GHGTemp.aspx | [6 empty] | 0 |  |  |  | http://www.oregon.gov/deq/RulesandRegulations/Pages/2014/GHGTemp.aspx
| University Student Comment Account | [6 empty] | 0
| Comment-GHGTemp@deq.state.or.us | [6 empty] | 0 |  |  |  | Comment-GHGTemp@deq.state.or.us
1
| CONCEPT DEVELOPMENT | i | [5 empty] | 1
| Leah discusses developing concept for DEQ Rulemaking Plan with Lydia |  | x |  |  | 0 |  | 1 |  | 0 |  | Leah discusses developing concept for DEQ Rulemaking Plan with Lydia
| Lydia approves concept development work |  | x |  |  | 0 |  | 1 |  | 0 |  | Lydia approves concept development work
| Leah |  | x |  |  |  |  | 1 |  |  |  | Leah
| * assigns subject expert for the rulemaking |  | x |  |  | 0 |  | 1 |  | 0 |  | * assigns subject expert for the rulemaking
| (reminder - add work to workplans as needed) | [6 empty] | 1 |  |  |  | (reminder - add work to workplans as needed)
| * identify existing Q-Time number for concept development work |  |  |  |  | 0 |  | 1 |  | 0 |  | * identify existing Q-Time number for concept development work
| Q-Time number = | [6 empty] | 1 |  |  |  | * identify existing Q-Time number for concept development work
| Maggie | [6 empty] | 1 |  |  |  | Maggie
| * adds to Rules Idea list and shares information with Rules Group |  | x |  |  | 0 |  | 1 |  | 0
| * establishes Rule_Development site | i | x |  |  |  |  | 1
| * establishes SharePoint sub site | i | x |  |  |  |  | 1
| * schedules work session | [6 empty] | 1
| Leah & Jerry participates in work session. Topics include: |  |  |  |  | 0 |  | 1 |  | 0 |  | Leah & Jerry participates in work session. Topics include:
| * roles and responsibilities | [6 empty] | 1
| * records management | [6 empty] | 1
| - naming conventions | [6 empty] | 1
| - SharePoint | i | [5 empty] | 1
| - shared Rule _Development drive | i | [5 empty] | 1
| * overview of work products | [6 empty] | 1
| - Rules and Regulations Web page | i | [5 empty] | 1
| - INVITATION.TO.COMMENT (blank in folder 4) | [6 empty] | 0
| - RULES.REDLINE | [6 empty] | 1
| - NOTICE (blank in folder 4) | [6 empty] | 0
| - FEE.ANALYSIS (blank in folder 3) | [6 empty] | 0
| - STAFF.RPT.Temporary (blank in folder 6) | [6 empty] | 1 |  |  |  | - STAFF.RPT.Temporary (blank in folder 6)
| * work products for this phase (templates preloaded to SharePoint folder 1): | [6 empty] | 1
| - Overview of Key Dates at top of this SCHEDULE | [6 empty] | 1
| - initial draft RESOURCES workbook | [6 empty] | 1
| - initial draft CONSIDERATIONS workbook | [6 empty] | 1
| Jerry drafts: |  | x |  | 0 | 0 |  | 1 | 0 | 0 |  | Jerry drafts:
| * RESOURCES workbook identifies rulemaking and implementation needs | [6 empty] | 1
| * CONSIDERATIONS workbook reflects scope of work accurately | [6 empty] | 1
| * CONSIDERATIONS workbook identifies potential risks accurately | [6 empty] | 1
| Jerry gets consenus from Leah & AndreaG on workbooks |  | x |  |  | 0 |  | 1 |  | 0 |  | Jerry gets consenus from Leah & AndreaG on workbooks
| Leah shares concept with Lydia and may stop/delay/advance concept |  | x |  |  | 0 |  | 1 |  | 0 |  | Leah shares concept with Lydia and may stop/delay/advance concept
| Lydia shares concept with Lydia and may stop/delay/advance concept |  | x |  |  | 0 |  | 1 |  | 0 |  | Lydia shares concept with Lydia and may stop/delay/advance concept
| If advanced, Leah emails AndreaG to indicate her approval |  | x |  |  | 0 |  | 1 |  | 0 |  | If advanced, Leah emails AndreaG to indicate her approval
| Maggie: | i |  |  |  | 0 |  | 1 |  | 0 |  | Maggie:
| * leads Rules Group prioritization using CONSIDERATIONS and RESOURCES data that | [6 empty] | 1
| compares to other concepts, rulemakings in progress and Rules Group work load | [6 empty] | 1
| * shares priority list and factors with Leah & Jerry |  |  |  |  | 0 |  | 1 |  | 0 |  | * shares priority list and factors with Leah & Jerry
| * adjusts factors as needed | [6 empty] | 1
| * shares priority listing with Leah & AndreaG |  |  |  |  | 0 |  | 1 |  | 0 |  | * shares priority listing with Leah & AndreaG
| If prioritized and resourced: | [6 empty] | 1 |  |  |  | Dick:
| Maggie develops work papers and Leadership Team draft email for Dick | i |  |  | 0 | 0 |  | 1 | 0 | 0 |  | Maggie develops work papers and Leadership Team draft email for Dick
| Dick: | [6 empty] | 1 |  |  |  | Dick:
| * adapts email and approves moving forward, sends email |  |  |  |  | 0 |  | 1 |  | 0
| To: Leadership Team describing addition to DEQ Rulemaking Plan | [6 empty] | 1 |  |  |  | To: Leadership Team describing addition to DEQ Rulemaking Plan
| To: StephanieC to include in monthly Director's Report | [6 empty] | 1 |  |  |  | To: StephanieC to include in monthly Director's Report
| (Dick asks EQC how they want to be involved with rulemaking) | [6 empty] | 1 |  |  |  | (Dick asks EQC how they want to be involved with rulemaking)
| (StephanieC informs team about EQC involvement by email) | [6 empty] | 1 |  |  |  | (StephanieC informs team about EQC involvement by email)
| Cc… Leah, Jerry, AndreaG | [6 empty] | 1 |  |  |  | Cc… Leah, Jerry, AndreaG
| AndreaG: | [6 empty] | 1 |  |  |  | AndreaG:
| * selects 'A' if approved, 'P' if postponed, 'R' if rejected | A | [5 empty] | 1
| * saves email Rule_Development ¦ 1-Planning ¦ APPROVAL.ToMoveForward.pdf | i | [5 empty] | 1 |  |  |  | * saves email Rule_Development ¦ 1-Planning ¦ APPROVAL.ToMoveForward.pdf
[8 empty] | 0 |  |  | `
| START RULEMAKING IF DICK ADDS TO PLAN | [6 empty] | 1
| Leah, Jerry & AndreaG decide whether to expand team 'Y' to expand > | N | x |  |  | 0 |  | 1 |  | 0 |  | Leah, Jerry & AndreaG decide whether to expand team 'Y' to expand >
| Leah works with MargaretO obtains unique Q-Time number(s) |  | x |  |  | 0 |  | 1 |  | 0 |  | Leah works with MargaretO obtains unique Q-Time number(s)
| for this rulemaking fromRobertB | [6 empty] | 1 |  |  |  | for this rulemaking fromRobertB
| Leah is responsible for: | [6 empty] | 1 |  |  |  | Leah is responsible for:
| * getting new team members' manager approval | [6 empty] | 0
| * adding rulemaking to work plans as appropriate | [6 empty] | 0
| * program team members meet agreed upon dates in this SCHEDULE | [6 empty] | 1
| AndreaG drafts SCHEDULE: |  | x |  |  | 0 |  | 1 |  | 0 |  | AndreaG drafts SCHEDULE:
| Jerry & AndreaG refine & agree on draft schedule: |  | x |  |  | 0 |  | 1 |  | 0 |  | Jerry & AndreaG refine & agree on draft schedule:
| Jerry schedules/holds team meeting(s) for consensus on: |  | x |  | 0 | 0 |  | 1 | 0 | 0 |  | Jerry schedules/holds team meeting(s) for consensus on:
| * RESOURCES workbook identifies rulemaking and implementation needs | [6 empty] | 1
| * CONSIDERATIONS workbook reflects scope of work accurately | [6 empty] | 1
| * CONSIDERATIONS workbook identifies potential risks accurately | [6 empty] | 1
| * SCHEDULE of tasks and deadlines | [6 empty] | 1
[8 empty] | 0 |  |  | `
| COMMUNICATIONS PLANNING | [6 empty] | 1
| Jerry schedules/holds meeting with Leah and |  | x |  | 0 | 0 |  | 1 | 0 | 0 |  | Jerry schedules/holds meeting with Leah and
| BrianW and AndreaG to discuss/determine need for: | [6 empty] | 1 |  |  |  | BrianW and AndreaG to discuss/determine need for:
| - Communications Plan 'Y' to develop | N | [5 empty] | 0 |  |  | N
| - Message Map 'Y' to develop | Y | [5 empty] | 1
| - Newspaper advertisements 'Y' to develop | Y | [5 empty] | 1
| - Newspaper release 'Y' to develop | N | [5 empty] | 0
| - Program Web page 'Y' to develop | N | [5 empty] | 0
| - Information Meetings before hearing 'Y' to develop | N | [5 empty] | 0
[8 empty] | 0 |  |  | `
| COMMUNICATIONS OPTION | [6 empty] | 1
| Jerry leads communication option review and approval loops for: | [6 empty] | 1 |  |  |  | Jerry leads communication option review and approval loops for:
| * drafting COMMUNICATION.PLAN with BrianW using information | i |  |  | 0 | 0 |  | 0 | 0 | 0 |  | * drafting COMMUNICATION.PLAN with BrianW using information
| from CONSIDERATIONS and RESOURCES workbooks | [6 empty] | 0
| * drafting MESSAGE.MAP with BrianW | i |  |  | 0 | 0 |  | 1 | 0 | 0 |  | * drafting MESSAGE.MAP with BrianW
| * drafting PROGRAM.WEB.PAGE content with team and Michele |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | * drafting PROGRAM.WEB.PAGE content with team and Michele
| Leah: | [6 empty] | 1 |  |  |  | Leah:
| * shares content with Lydia and approves content: |  |  |  | 0 | 0 |  | 1 | 0 | 0 |  | * shares content with Lydia and approves content:
| 1st loop - team modifies content to get to approval |  |  |  | 0 | 0 |  | 1 | 0 | 0
| 2nd loop - team modifies content to get to approval | N |  |  | 0 | 0 |  | 0 | 0 | 0
| 3rd loop - team modifies content to get to approval | N |  |  | 0 | 0 |  | 0 | 0 | 0
| Final loop - team modifies content to get to approval | N |  |  | 0 | 0 |  | 0 | 0 | 0
| Jerry leads program Web page development: |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02 |  | Jerry leads program Web page development:
| * submits Web Request for program Web page | [6 empty] | 0
` | * verifies Web content meets team expectations | [6 empty] | 0
| * works with Michele to make adjustments | [6 empty] | 0 |  |  |  | * works with Michele to make adjustments
[8 empty] | 0 |  |  | `
| PREPLANNING FOR HEARINGS | [6 empty] | 1
| Team identifies hearing locations, dates and times |  | Hearing Table |  |  |  |  | 1 |  |  |  | Team identifies hearing locations, dates and times
|  |  | # |  | Date | Time |  | 1 |  |  |  | Jerry enters hearings locations, dates and times:
| Portland | Y | 1 |  | 0 | 6 p.m. |  | 1 | 0 | 5 p.m.
| Enter city name | N | 2 |  | 0 | 6 p.m. |  | 0 | 0 | 6 p.m.
| Enter city name | N | 3 |  | 0 | 6 p.m. |  | 0 | 0 | 6 p.m.
| Enter city name | N | 4 |  | 0 | 6 p.m. |  | 0 | 0 | 6 p.m.
| Enter city name | N | 5 |  | 0 | 6 p.m. |  | 0 | 0 | 6 p.m.
| Enter city name | N | 6 |  | 0 | 6 p.m. |  | 0 | 0 | 6 p.m.
| Enter city name | N | 7 |  | 0 | 6 p.m. |  | 0 | 0 | 6 p.m.
| Enter city name | N |  |  | 0 | 6 p.m. |  | 0 | 0 | 6 p.m.
| Last hearing: |  |  |  | 0 |  |  | 1 | 0
| Jerry reserves venues/equipment for hearings |  |  |  | 0 | 0 |  | 1 | 0 | 0 |  | Jerry reserves venues/equipment for hearings
| Jerry identifies hearings officer(s) on HearingAndAdDates TAB | i | [5 empty] | 1 |  |  |  | Jerry identifies hearings officer(s) on HearingAndAdDates TAB
| NEWSPAPER ADVERTISEMENTS | [6 empty] | 0
| Jerry works with Jerry: |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | Jerry works with Jerry:
| * to identify publications and publication dates | [6 empty] | 0
|  | Publication Table | [5 empty] | 0
|  | # | Publication |  |  | Pub Date |  | 0
| NOTICE.AD1Oregonian | 1 | Oregonian |  |  | 0 |  | 0 |  | 0 |  | NOTICE.AD1Oregonian
| NOTICE.AD2None | 2 | None |  |  | 0 |  | 0 |  | 0 |  | NOTICE.AD2None
| NOTICE.AD3None | 3 | None |  |  | 0 |  | 0 |  | 0 |  | NOTICE.AD3None
| NOTICE.AD4None | 4 | None |  |  | 0 |  | 0 |  | 0 |  | NOTICE.AD4None
| NOTICE.AD5None | 5 | None |  |  | 0 |  | 0 |  | 0 |  | NOTICE.AD5None
| NOTICE.AD6None | 6 | None |  |  | 0 |  | 0 |  | 0 |  | NOTICE.AD6None
| NOTICE.AD7None | 7 | None |  |  | 0 |  | 0 |  | 0 |  | NOTICE.AD7None
| NOTICE.AD8None | 8 | None |  |  | 0 |  | 0 |  | 0 |  | NOTICE.AD8None
| * develops an AD.STANDARD for each hearing if required | i | [5 empty] | 0
| * develops AD.LEGAL for each hearing if required | i | [5 empty] | 0
| * saves as NOTICE.AD.Hearing1, etc. on Rule_Development folder 4 | [6 empty] | 0
| * determines when ADs need to be submitted to contractor | Ad to contractor > |  |  |  | 0 |  | 0 |  | 0
| * shares contents of HearingAndAdDates TAB with Leah | i |  |  | 0 | 0 |  | 0 | 0 | 0 |  | * shares contents of HearingAndAdDates TAB with Leah
| * obtains Leah's email approval |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | * obtains Leah's email approval
[8 empty] | 0 |  |  | `
| EQC FACILITATED HEARINGS | [6 empty] | 0
| Jerry: | [6 empty] | 0 |  |  |  | Jerry:
| * observe EQC quorum notification requirements (ORS 192.630) | i | [5 empty] | 0
| * identifies EQC facilitated hearing, coordinate with commissioner: | [6 empty] | 0
| MEden@neea.org | N |  |  |  | 2014-10-15 |  | 0 |  | 0
| JoKRanch@hotmail.com | N |  |  |  | 2014-10-15 |  | 0
| EdArmstrong2@gmail.com | N |  |  |  | 2014-10-22 |  | 0
| MorganRider@gmail.com | N |  |  |  | 2014-10-22 |  | 0
| cjohnson@eou.edu | N |  |  |  | 2014-10-22 |  | 0
[8 empty] | 0 |  |  | `
| PREPARE TO DRAFT RULES | [6 empty] | 1
| Jerry coordinates with Team to: |  | x |  | 0 | 0 |  | 1 | 0 | 0 |  | Jerry coordinates with Team to:
| * determine need for a crosswalk |  | x |  |  |  |  | 1
| * identify rules to amend or repeal |  | x |  |  |  |  | 1
| * identify requirements that need rules adoption |  | x |  |  |  |  | 1
| * identify land use rules | i | x |  |  |  |  | 1
| * identify SIP rules | i | x |  |  |  |  | 1
| Jerry: | [6 empty] | 1 |  |  |  | Jerry:
| * obtains starting rules from Oregon State Archives | i | x |  |  | 0 |  | 1 |  | 0
| * owns pristine draft of proposed rules and maintains it on | [6 empty] | 1
| Rule_Development¦1-Planning using the name¦STARTING.RULES | [6 empty] | 1
| only Jerry works on rules at this location to ensure the | [6 empty] | 1 |  |  |  | only Jerry works on rules at this location to ensure the
| redline/strikethrough remains consistent and that no reviewer | [6 empty] | 1
| copied text from other locations or turned track changes off | [6 empty] | 1
| * uploads copy of STARTING.RULES to SharePoint¦1-Planning |  | X |  |  |  |  | 1
| All contributors & reviewers work on draft rules on SharePoint | [6 empty] | 1
| * requests Maggie provide numbers for new rules/divisions |  | x |  |  | 0 |  | 1 |  | 0 |  | * requests Maggie provide numbers for new rules/divisions
| Maggie: | [6 empty] | 1 |  |  |  | Maggie:
| * obtains, verifies, provides previously unused rule numbers |  | x |  |  | 0 |  | 1 |  | 0 |  | Maggie obtains, verifies, provides previously unused numbers
| * identifies rules that may be involved in other rulemakings |  | x |  |  | 0 |  | 1 |  | 0 |  | Maggie identifies rules that may be involved in other rulemakings
| * coordinates with AndreaG to identify SIP rules |  |  |  |  | 0 |  | 0 | 0 | 0 |  | * coordinates with AndreaG to identify SIP rules
| * requests all planning emails for the Rule Record and saves in | i |  |  |  | 0 |  | 1 |  | 0 |  | Jerry gathers all planning emails for the Rule Record and saves as:
| Rule_Development¦1-Planning¦EMAILS.Planning.pdf | [6 empty] | 1
Advisory Committee - not involved
| GHGTemp |  |  |  | Start | End |  | B
[5 empty] | 2014-05-02 | 0 |  | B | 2014-05-02 | 0
Y
| Review version history to help maintaining rulemaking record | i | [5 empty] | W
| Jerry holds/leads team meeting to: |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02 |  | Jerry holds/leads team meeting to:
| * review | [6 empty] | 0
| - advisory committee Q-Card | i | [5 empty] | 0
| - Public Involvement Resources, discuss when to engage BrianW | i | [5 empty] | 0 |  |  |  | - Public Involvement Resources, discuss when to engage BrianW
| - review committee Web page template | [6 empty] | 0
| - review and discuss required committee meeting sign up list | [6 empty] | 0
| * discuss | [6 empty] | 0
| - public Meeting Laws | i | [5 empty] | 0 |  |  |  | May be required in future
| - EQC quorum notification requirements (ORS 192.630) | i | [5 empty] | 0 |  |  |  | * Oregon Transparency law (not required for Advisory Committees) | i
| - need for optional committee Web page | [6 empty] | 0
| - need for optional committee charter | [6 empty] | 0
| * identify | [6 empty] | 0
| - lists of persons potentially affected by proposed rules | i | [5 empty] | 0
| - lists of persons who may have special interest in rulemaking | [6 empty] | 0
| - potential committee members | [6 empty] | 0
| - potential meeting dates and venues | [6 empty] | 0
| Jerry coordinates with team to: |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02 |  | Jerry coordinates with team to:
| * develop AC.ROSTER (blank in folder 4) | [6 empty] | 0
| * add EQC members to Cc. list for ALL committee communications | [6 empty] | 0
| MEden@neea.org | [6 empty] | 0
| JoKRanch@hotmail.com | [6 empty] | 0
| EdArmstrong2@gmail.com | [6 empty] | 0
| MorganRider@gmail.com | [6 empty] | 0
| cjohnson@eou.edu | [6 empty] | 0
| * reserve potential meeting dates and venues | [6 empty] | 0
| * draft committee AC.INVITATION (links to GovDelivery/Web pages) |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| * draft content for optional committee Web page | Y |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| * draft optional AC.CHARTER | Y |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| * emails lists above to invite them to sign up to receive meeting notices | i | [5 empty] | 0
| Leah shares draft roster and invitation with Lydia |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02 |  | Leah shares draft roster and invitation with Lydia
| Team addresses any concerns and validates accuracy of how addressed |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| Leah approves potential advisory committee roster |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02 |  | Leah approves potential advisory committee roster
| Team: | [6 empty] | 0
| * makes initial voice contact with potential committee members |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| * finalizes AC.ROSTER based on responses |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| Jerry: | [6 empty] | 0 |  |  |  | Jerry:
| * submits optional Committee Web page template attached to Web Request | i |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| * submits Web Request at anytime when Committee Web page needs updating | [6 empty] | 0
| * sends invitation to potential committee members who agreed to serve |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| * maintains advisory committee record | [6 empty] | 0
| Meeting 1 | Y |  |  | 2014-06-05 | 9.00 a,m |  | 0 | 2014-05-16
| Team identifies meeting roles | [6 empty] | 0
| Jerry coordinates or drafts: |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02 |  | Jerry coordinates or drafts:
| * AC.AGENDA.06.05.14 | i | [5 empty] | 0 |  |  |  | * AC.AGENDA.06.05.14
| * AC.NOTIFICATION.06.05.14 | [6 empty] | 0 |  |  |  | * AC.NOTIFICATION.06.05.14
| Jerry obtains team approval of agenda and notification |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02 |  | Jerry obtains team approval of agenda and notification
| Jerry (about 14 working days before meeting:) |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02 |  | Jerry (about 14 working days before meeting:)
| * adds meeting to DEQ Online Calendar (password = dudeman) | i | [5 empty] | 0
| * sends GovDelivery meeting notice and Web page link | [6 empty] | 0
| * releases unneeded venues | [6 empty] | 0 |  |  |  | )&", gets team agreement"
| Team assigns custom task here |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| Team assigns custom task here |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| Team assigns custom task here |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| Team assigns custom task here |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| START OPTION - Presentation Select option > | Y | [5 empty] | 0
| Enter staff name here | [6 empty] | 0
| * drafts optional AC.PRESENTATION.06.05.14 | i |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02 |  | * drafts optional AC.PRESENTATION.06.05.14
| Enter staff name here | [6 empty] | 0
| * involves stakeholder presenters, if any |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| Team approves presentation materials |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| Jerry submits Web Request to post materials | i | [5 empty] | 0 |  |  |  | Jerry submits Web Request to post materials
| Team practices presentation | [6 empty] | 0
| Team facilitates/holds meeting |  |  |  |  | 2014-06-05 |  | 0 |  | 2014-06-05
| Jerry drafts AC.MINUTES 06.05.14 | i |  |  | 2014-06-05 | 2014-06-05 |  | 0 | 2014-06-05 | 2014-06-05 |  | Jerry drafts AC.MINUTES 06.05.14
| Team holds debrief meeting |  |  |  | 2014-06-05 | 2014-06-05 |  | 0 | 2014-06-05 | 2014-06-05
| Meeting 2 | Y |  |  | 2014-06-26 | 9.00 a.m. |  | 0 | 2014-06-05
| Team identifies meeting roles |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| Jerry coordinates or drafts: | [6 empty] | 0 |  |  |  | Jerry coordinates or drafts:
| * AC.AGENDA.06.05.14, gets team agreement | i |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12 |  | * AC.AGENDA.06.05.14, gets team agreement
| * AC.NOTIFICATION.06.05.14 |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12 |  | * AC.NOTIFICATION.06.05.14
| * adds meeting to DEQ Online Calendar (password = dudeman) | i |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| * releases unneeded venues |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| Team assigns custom task here |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| Team assigns custom task here |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| Team assigns custom task here |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| Team assigns custom task here |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| START OPTION - Presentation Select option > | Y | [5 empty] | 0
| Enter staff name here | [6 empty] | 0
| * drafts optional AC.PRESENTATION.06.05.14 | i |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12 |  | * drafts optional AC.PRESENTATION.06.05.14
| Enter staff name here | [6 empty] | 0
| * involves stakeholder presenters, if any |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| Team approves presentation materials |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| Jerry submits Web Request to post materials | i |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12 |  | Jerry submits Web Request to post materials
| Team practices presentation |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| Jerry sends meeting notice with link to Web page |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12 |  | Jerry sends meeting notice with link to Web page
| Team facilitates/holds meeting |  | Set above at Meeting 2 title |  |  | 2014-06-26 |  | 0 |  | 2014-06-26
| Jerry drafts AC.MINUTES 06.05.14 | i |  | 1 | 2014-06-26 | 2014-06-26 |  | 0 | 2014-06-26 | 2014-06-26 |  | Jerry drafts AC.MINUTES 06.05.14
| Team holds debrief meeting |  |  | 1 | 2014-06-26 | 2014-06-26 |  | 0 | 2014-06-26 | 2014-06-26
| Meeting 3 | Y |  |  | 2014-07-30 | 9.00 a.m. |  | 0 | 2014-06-26
| Team identifies meeting roles |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Jerry coordinates or drafts: | [6 empty] | 0 |  |  |  | Jerry coordinates or drafts:
| * AC.AGENDA.06.05.14, gets team agreement | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * AC.AGENDA.06.05.14, gets team agreement
| * AC.NOTIFICATION.06.05.14 |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * AC.NOTIFICATION.06.05.14
| * adds meeting to DEQ Online Calendar (password = dudeman) | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| * releases unneeded venues |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| START OPTION - Presentation Select option > | Y | [5 empty] | 0
| Enter staff name here | [6 empty] | 0
| * drafts optional AC.PRESENTATION.06.05.14 | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * drafts optional AC.PRESENTATION.06.05.14
| Enter staff name here | [6 empty] | 0
| * involves stakeholder presenters, if any |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team approves presentation materials |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Jerry submits Web Request to post materials | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | Jerry submits Web Request to post materials
| Team practices presentation |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Jerry sends meeting notice with link to Web page |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | Jerry sends meeting notice with link to Web page
| Team facilitates/holds meeting |  | Set above at Meeting 3 title |  |  | 2014-07-30 |  | 0 |  | 2014-07-30
| Jerry drafts AC.MINUTES06.05.14 | i |  | 1 | 2014-06-05 | 2014-06-05 |  | 0 | 2014-07-30 | 2014-06-05 |  | Jerry drafts AC.MINUTES06.05.14
| Team holds debrief meeting |  |  | 1 | 2014-06-05 | 2014-06-05 |  | 0 | 2014-07-30 | 2014-06-05
| Meeting 4 | N |  |  | 2014-07-30 | 6:00 p.m. |  | 0 | 2014-07-30
| Team identifies meeting roles |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Jerry coordinates or drafts: | [6 empty] | 0 |  |  |  | Jerry coordinates or drafts:
| * AC.AGENDA.06.05.14, gets team agreement | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * AC.AGENDA.06.05.14, gets team agreement
| * AC.NOTIFICATION.06.05.14 |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * AC.NOTIFICATION.06.05.14
| * adds meeting to DEQ Online Calendar (password = dudeman) | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| * releases unneeded venues |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| START OPTION - Presentation Select option > | Y | [5 empty] | 0
| Enter staff name here | [6 empty] | 0
| * drafts optional AC.PRESENTATION.06.05.14 | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * drafts optional AC.PRESENTATION.06.05.14
| Enter staff name here | [6 empty] | 0
| * involves stakeholder presenters, if any |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team approves presentation materials |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Jerry submits Web Request to post materials | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | Jerry submits Web Request to post materials
| Team practices presentation |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Jerry sends meeting notice with link to Web page |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | Jerry sends meeting notice with link to Web page
| Team facilitates/holds meeting |  | Set above at Meeting 4 title |  |  | 2014-07-30 |  | 0 |  | 2014-07-30
| Jerry drafts AC.MINUTES06.05.14 | i |  | 1 | 2014-07-30 | 2014-07-30 |  | 0 | 2014-07-30 | 2014-07-30 |  | Jerry drafts AC.MINUTES06.05.14
| Team holds debrief meeting |  |  | 1 | 2014-07-30 | 2014-07-30 |  | 0 | 2014-07-30 | 2014-07-30
| Meeting 5 | N |  |  | 2014-07-30 | 6:00 p.m. |  | 0 | 2014-07-30
| Team identifies meeting roles |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Jerry coordinates or drafts: | [6 empty] | 0 |  |  |  | Jerry coordinates or drafts:
| * AC.AGENDA.06.05.14, gets team agreement | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * AC.AGENDA.06.05.14, gets team agreement
| * AC.NOTIFICATION.06.05.14 |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * AC.NOTIFICATION.06.05.14
| * adds meeting to DEQ Online Calendar (password = dudeman) | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| * releases unneeded venues |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| START OPTION - Presentation Select option > | Y | [5 empty] | 0
| Enter staff name here | [6 empty] | 0
| * drafts optional AC.PRESENTATION.06.05.14 | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * drafts optional AC.PRESENTATION.06.05.14
| Enter staff name here | [6 empty] | 0
| * involves stakeholder presenters, if any |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team approves presentation materials |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Jerry submits Web Request to post materials | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | Jerry submits Web Request to post materials
| Team practices presentation |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Jerry sends meeting notice with link to Web page |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | Jerry sends meeting notice with link to Web page
| Team facilitates/holds meeting |  | Set above at Meeting 5 title |  |  | 2014-07-30 |  | 0 |  | 2014-07-30
| Jerry drafts AC.MINUTES06.05.14 | i |  | 1 | 2014-07-30 | 2014-07-30 |  | 0 | 2014-07-30 | 2014-07-30 |  | Jerry drafts AC.MINUTES06.05.14
| Team holds debrief meeting |  |  | 1 | 2014-07-30 | 2014-07-30 |  | 0 | 2014-07-30 | 2014-07-30
| Jerry gathers all advisory committee emails for the Rule Record and saves as: | i |  |  | 2014-05-02 | 0 |  | 0 | 2014-05-02 | 0 |  | Jerry gathers all advisory committee emails for the Rule Record and saves as:
| Rule_Development¦3-FeesApproval¦EMAILS.Fees.pdf | [6 empty] | 0
| Fees - not involved | [10 empty] | Fees - not involved
[5 empty] | Start | End |  | B
[5 empty] | 0 | 0 |  | B | 0 | 0
Y
| Review version history to help maintaining rulemaking record > | i | [5 empty] | W
| Jerry: | [6 empty] | 0 |  |  |  | Jerry:
| * devlopes Fee Approval Packet, resources: team and MargaretO | i |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | * devlopes Fee Approval Packet, resources: team and MargaretO
| Fee Approval Packet includes: | [6 empty] | 0
| blank row | [6 empty] | 0 |  |  |  | blank row
| blank row | [6 empty] | 0 |  |  |  | blank row
| blank line | i | [5 empty] | 0 |  |  |  | blank line
| blank row | i | [5 empty] | 0 |  |  |  | blank row
| * requests Maggie's review for sufficiency, tone, plain English, style guide |  |  | 4 | 0 | 1900-01-04 |  | 0 | 0 | 1900-01-04 |  | * requests Maggie's review for sufficiency, tone, plain English, style guide
| considering documents will become part of Notice and EQC packets | [6 empty] | 0
| * initiates Leah's Fee Approval Packet review, addresses suggestions |  |  |  |  | 1900-01-04 |  | 0 |  | 1900-01-04 |  | * initiates Leah's Fee Approval Packet review, addresses suggestions
| 1st loop of Leah's Fee Approval Packet review and approval |  |  | -4 | 1900-01-04 | 0 |  | 0 | 1900-01-04 | 0 |  | 1st loop of Leah's Fee Approval Packet review and approval
| 2nd loop of Leah's Fee Approval Packet review and approval | N |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2nd loop of Leah's Fee Approval Packet review and approval
| 3rd loop of Leah's Fee Approval Packet review and approval | N |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 3rd loop of Leah's Fee Approval Packet review and approval
| 4th loop of Leah's Fee Approval Packet review and approval | N |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 4th loop of Leah's Fee Approval Packet review and approval
| AndreaG coordinates: | [6 empty] | 0 |  |  |  | AndreaG coordinates:
| * sending EMAIL.DAS.APPROVAL with Fee Approval Packet attached |  |  |  |  | 0 |  | 0 |  | 0
| - in Outlook, request delivery and read receipts | [6 empty] | 0
| - save receipts to Rule_Dev.¦3-Fee.Approval¦PROOF.DAS.REQUEST.pdf | [6 empty] | 0
| * following up on status about 15 days after sending |  |  |  |  | 0 |  | 0 |  | 0
| DAS sends Jerry response |  |  |  |  | 0 |  | 0 |  | 0 |  | DAS sends Jerry response
| If denied, Jerry coordinates addressing DAS response |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | If denied, Jerry coordinates addressing DAS response
| 1st loop of Leah's approval of response to DAS denial |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1st loop of Leah's approval of response to DAS denial
| 2nd loop of Leah's approval of response to DAS denial | N |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2nd loop of Leah's approval of response to DAS denial
| 3rd loop of Leah's approval of response to DAS denial | N |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 3rd loop of Leah's approval of response to DAS denial
| 4th loop of Leah's approval of response to DAS denial | N |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 4th loop of Leah's approval of response to DAS denial
| If approved, Jerry scans and files DAS.PART1.pdf |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | If approved, Jerry scans and files DAS.PART1.pdf
| Next step happens under 4-Public Notice section | [6 empty] | 0
| Jerry gathers all fee emails for the Rule Record and saves as: | i |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Jerry gathers all fee emails for the Rule Record and saves as:
| Rule_Development¦3-FeesApproval¦EMAILS.Fees.pdf | [6 empty] | 0
Public Notice - not required for TEMPORARY rules - APA
| GHGTemp |  |  |  | Start | End
[5 empty] | 0 | 0 |  | 0 | 0 | 0
1900-04-20
| Review version history to help maintain rulemaking record > | i
| DRAFT NOTICE PACKET | [6 empty] | 0
| Jerry leads drafting of Notice Packet with core team |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | Jerry leads drafting of Notice Packet with core team
| Notice Packet includes: | [6 empty] | 0
| * INVITATION.TO.COMMENT (develop after Notice is stable ) | [6 empty] | 0
| * PROPOSED.RULES | [6 empty] | 0
| * NOTICE | [6 empty] | 0
| - Overview | [6 empty] | 0
| - Statement of Need | [6 empty] | 0
| - Rules affected, authorities, supporting documents | [6 empty] | 0
| - Fee Analysis | [6 empty] | 0
| - Statement of fiscal and economic impact | [6 empty] | 0
| - Federal relationship | [6 empty] | 0
| - Land use | [6 empty] | 0 |  | 0
| - Stakeholder and public involvement | [6 empty] | 0
| * SUPPORTING.DOCS - optional | [6 empty] | 0
| Jerry asks RESOURCES for help and input, especially: |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | Jerry asks RESOURCES for help and input, especially:
| This is information gathering - not a review | [6 empty] | 0
| * Advisory Commiitee not involved |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | * Advisory Commiitee not involved
| * Affected staff, including regional staff, for contributions |  |  |  | 0 | 0 |  | 0 | 0 | 0
| * SIP not involved |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | * SIP not involved
| * Leah for direction and subject consultation, especially to ensure drafts: |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | * Leah for direction and subject consultation, especially to ensure drafts:
| - meet program goals for rulemaking | [6 empty] | 0
| - align with section, division and agency goals | [6 empty] | 0
| * AndreaG for rulemaking best practices consultation |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | * AndreaG for rulemaking best practices consultation
| -blank- |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | -blank-
| * PaulG, if needed for legal consultation |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | * PaulG, if needed for legal consultation
| * Enter custom resource here |  |  |  | 0 | 0 |  | 0 | 0 | 0
| * Enter custom resource here |  |  |  | 0 | 0 |  | 0 | 0 | 0
| * Enter custom resource here |  |  |  | 0 | 0 |  | 0 | 0 | 0
| Jerry continually refines draft Notice Packet to consider RESOURCES input |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | Jerry continually refines draft Notice Packet to consider RESOURCES input
| * validates approach with RESOURCES an needed | [6 empty] | 0
| * verifies/adjusts prevously scheduled briefing & review with Lydia | [6 empty] | 0 |  |  |  | * verifies/adjusts prevously scheduled briefing & review with Lydia
| * asks PaulG for legal sufficiency if warranted | [6 empty] | 0 |  |  |  | * asks PaulG for legal sufficiency if warranted
| * addresses PaulG concerns and discusses with Leah as needed | [6 empty] | 0 |  |  |  | * addresses PaulG concerns and discusses with Leah as needed
| * informs Leah about the approach, issues and potential delays | [6 empty] | 0 |  |  |  | * informs Leah about the approach, issues and potential delays
| * raises unanticipated rulemaking risks to appropriate level | [6 empty] | 0
| * raises unanticipated rule implementation risks to appropriate level | [6 empty] | 0
| * informs AndreaG about potential delays for and develop contingency, if needed | [6 empty] | 0 |  |  |  | * informs AndreaG about potential delays for and develop contingency, if needed
| Jerry asks subject contributors, including Leah for consensus on |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | Jerry asks subject contributors, including Leah for consensus on
| completeness and accuracy of technical and program content | [6 empty] | 0
| Jerry verifies draft rules to ensure: | [6 empty] | 0 |  |  |  | Jerry verifies draft rules to ensure:
| * they are current compared to Oregon State Archives | i | [5 empty] | 0
| * they consider other rulemakings that may affect subject rules | [6 empty] | 0
| * statutory authorities are correct for each rule | [6 empty] | 0
| * statutes implemented are correct for each rules | [6 empty] | 0
| * SIP rules are not involved | [6 empty] | 0 |  |  |  | * SIP rules are not involved
| KEEP MANAGEMENT INFORMED | [6 empty] | 0
| Jerry asks Carol to schedule future time on Lydia's calendar for: | Schedule by |  |  |  | 0 |  | 0 |  | 0 |  | Jerry asks Carol to schedule future time on Lydia's calendar for:
| * Lydia briefing meeting with Jerry, Leah and AndreaG | Meeting will be |  |  |  | 0 |  | 0 |  | 0 |  | * Lydia briefing meeting with Jerry, Leah and AndreaG
| * time on Lydia's calendar to review Notice Packet during preview week | Review begins on |  |  |  | 0 |  | 0 |  | 0 |  | * time on Lydia's calendar to review Notice Packet during preview week
| Jerry schedules time on Leah calendar to review Notice Packet | [6 empty] | 0 |  |  |  | Jerry schedules time on Leah calendar to review Notice Packet
| Jerry keeps Leah informed about progress | Review begins on |  |  |  | 0 |  | 0 |  | 0 |  | Jerry keeps Leah informed about progress
| Leah keeps Lydia informed about progress | [6 empty] | 0 |  |  |  | Leah keeps Lydia informed about progress
| Lydia keeps Lydia informed about potential risks & delays | [6 empty] | 0 |  |  |  | Lydia keeps Lydia informed about potential risks & delays
| AndreaG keeps Lydia informed about risks & progress | [6 empty] | 0 |  |  |  | AndreaG keeps Lydia informed about risks & progress
| CUSTOM SEQUENCE | [6 empty] | 0
| Name initiator and subject for custom review loop 1 | N |  |  | 0 | 0 |  | 0 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 0 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 0 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 0 | 0 | 0
| Name initiator and subject for custom review loop 2 | N |  |  | 0 | 0 |  | 0 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 0 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 0 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 0 | 0 | 0
| Name initiator and subject for custom review loop 3 | N |  |  | 0 | 0 |  | 0 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 0 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 0 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 0 | 0 | 0
0
| PREPARE FOR MANAGEMENT REVIEW | [6 empty] | 0
| Leah looks at Notice Packet ensure: |  |  |  | Sponsoring Manager's Work Period |  |  | 0 |  |  |  | Leah looks at Notice Packet ensure:
| * work products meets rulemaking goals |  |  |  | 0 | 0 |  | 0 | 0 | 0
| * work products are accurate - programmatically and technically |  |  |  | Due | Complete by |  | 0
| * documents are complete - all comments addressed & no outstanding issues | [6 empty] | 0
| Leah: | [6 empty] | 0 |  |  |  | Leah:
| * does not need to duplicate Rule Publication work below | [6 empty] | 0
| * notifies Jerry when complete | [6 empty] | 0 |  |  |  | * notifies Jerry when complete
| Jerry: |  |  |  | 1900-01-01 | 0 |  | 0 | 1900-01-01 | 0 |  | Jerry:
| * addresses Leah's technical concerns | [6 empty] | 0 |  |  |  | * addresses Leah's technical concerns
| * submits Notice and Proposed Rules to Rule Publication (AndreaG) | [6 empty] | 0 |  |  |  | * submits Notice and Proposed Rules to Rule Publication (AndreaG)
| AndreaG leads initial Rule Publication work that includes: |  |  |  | Rule Publication Work Period |  |  | 0 |  |  |  | AndreaG leads initial Rule Publication work that includes:
| * establishing rule's Web page, comment form, URLs, University student account |  |  |  | 0 | 0 |  | 0 | 0 | 0
| * determining fiscal and economic impact analysis sufficiency |  |  |  | Due | Complete by |  | 0
| * performing preliminary work on final review checklist | i | [5 empty] | 0
| * obtaining/consolidating BrianW, StephanieC & AndreaG edits as needed | [6 empty] | 0 |  |  |  | * obtaining/consolidating BrianW, StephanieC & AndreaG edits as needed
| including style guide, grammar, plain English, organization, clarity, tone | [6 empty] | 0
| * accepting all style guide and format edits | [6 empty] | 0
| Jerry & AndreaG prepare drafts for preview |  |  |  | 1900-01-01 | 1900-01-04 |  | 0 | 1900-01-01 | 1900-01-04 |  | Jerry & AndreaG prepare drafts for preview
| Leah approves moving forward with Notice and Proposed Rules |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | Leah approves moving forward with Notice and Proposed Rules
| 2nd loop of Leah's Notice Packet review and approval | N |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 2nd loop of Leah's Notice Packet review and approval
| 3rd loop of Leah's Notice Packet review and approval | N |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 3rd loop of Leah's Notice Packet review and approval
| 4th loop of Leah's Notice Packet review and approval | N |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 4th loop of Leah's Notice Packet review and approval
| Jerry & AndreaG address any concerns that may block Leah's approval |  |  |  | 1900-01-05 | 0 |  | 0 | 1900-01-05 | 0 |  | Jerry & AndreaG address any concerns that may block Leah's approval
| PREVIEW PERIOD | [6 empty] | 0
| AndreaG drafts EMAIL.PREVIEW - instructions in template: | i |  |  |  | 0 |  | 0 |  | 0 |  | AndreaG drafts EMAIL.PREVIEW - instructions in template:
| * sends draft to Lydia before briefing, copies Jerry & Leah | [6 empty] | 0 |  |  |  | * sends draft to Lydia before briefing, copies Jerry & Leah
| Jerry, Leah & AndreaG: | [6 empty] | 0 |  |  |  | Jerry, Leah & AndreaG:
| * brief Lydia |  |  |  | Meeting > | 0 |  | 0 |  | 0 |  | * brief Lydia
| * remind Lydia this is also her review/approval period | [6 empty] | 0 |  |  |  | * remind Lydia this is also her review/approval period
| Lydia personalizes and sends EMAIL.PREVIEW |  |  |  | Preview Period |  |  | 0 |  |  |  | Lydia personalizes and sends EMAIL.PREVIEW
| To… Dick, Lydia, Leadership Team & StephanieC |  |  |  | Start | End |  | 0 |  |  |  | To… Dick, Lydia, Leadership Team & StephanieC
| Cc…to all contributing and affected staff |  |  |  | 0 | 0 |  | 0 | 0 | 0
[5 empty] | allow 7-14 days |  |  | 0
0
| Jerry: |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | Jerry:
| * saves EMAIL.PREVIEW.pdf to Rule_Development¦4-Notice | i | [5 empty] | 0
| * talks with Leah, decides how to address any feedback from preview | [6 empty] | 0 |  |  |  | * talks with Leah, decides how to address any feedback from preview
| * modifies documents as needed | [6 empty] | 0
| * verifies PROPOSED.RULES are still based on current compilation | [6 empty] | 0
| * finalizes Notice Packet with Leah | [6 empty] | 0 |  |  |  | * finalizes Notice Packet with Leah
| Leah: | [6 empty] | 0 |  |  |  | Leah:
| * determines whether Lydia needs a second review 'Y' if 2nd review needed> | Y |  |  | 0 | 0 |  | 0 | 0 | 0 |  | * determines whether Lydia needs a second review 'Y' if 2nd review needed>
| * manages Lydia's 2nd review and approval | [6 empty] | 0 |  |  |  | * manages Lydia's 2nd review and approval
| * emails approval to move forward with Notice to Jerry & AndreaG |  |  |  |  | #NUM! |  | 0 |  | #NUM! |  | * emails approval to move forward with Notice to Jerry & AndreaG
| AndreaG, depending on input from preview, leads Rule Publication work that: |  |  |  | #NUM! |  |  | 0 | #NUM! |  |  | AndreaG, depending on input from preview, leads Rule Publication work that:
| * compares work products pre/post preview and determines need for additional edits | [6 empty] | 0
| * consolidates Rule Publication edits | [6 empty] | 0
| * verifies/clarifies additional edits with Jerry & Leah as warranted | [6 empty] | 0 |  |  |  | * verifies/clarifies additional edits with Jerry & Leah as warranted
| Leah emails Jerry & AndreaG approval to publish notice | Approval to publish notice |  |  |  | #NUM! |  | 0 |  | #NUM! |  | Leah emails Jerry & AndreaG approval to publish notice
| Jerry: | [6 empty] | 0 |  |  |  | Jerry:
| * saves email as Rule_Development¦4-Notice¦MGR.APPROVAL.Notice.pdf | [6 empty] | 0
| NOTIFICATIONS | [6 empty] | 0
| Jerry: | [6 empty] | 0 |  |  |  | Jerry:
| * submits of Notice to EPA |  |  |  |  | #NUM! |  | 0 |  | #NUM!
| AndreaG works with Rule Publication to: |  |  |  | #NUM! |  |  | 0 | #NUM! |  |  | AndreaG works with Rule Publication to:
| * establishes Outlook comment box for University students with Jerry as owner | [6 empty] | 0 |  |  |  | * establishes Outlook comment box for University students with Jerry as owner
| * establishes Rulemaking Activities Web page for proposed rule | i | [5 empty] | 0
| * establishes online public comment form | [6 empty] | 0
| * completes final review checklist | i | [5 empty] | 0
| * authenticates SOS/LC submittals | [6 empty] | 0
| * submits notice to SOS for publication in Oregon Bulletin | i | [5 empty] | 0
| * emails DAS notification of fees that don't require DAS approval | [6 empty] | 0
| * saves all evidence on Rule_Development ¦ 4-Notice using naming conventions | i | [5 empty] | 0
| Jerry leads: | [6 empty] | 0 |  |  |  | Jerry leads:
| * submitting newspaper notices to contractor |  | Set under Planning |  |  | 0 |  | 0 |  | 0 |  | * modifies documents as needed
| * adding hearings to DEQ online calendar | i | [5 empty] | 0
| * creating an auto reply to Outlook account for University students | i | [5 empty] | 0
| * validating Web page, comment form and Outlook account | [6 empty] | 0 |  |  |  | * validates Web page, comment form, hearing date accuracy with Jerry
| * opening public comment by notifying agency rulemaking list that includes: |  |  |  |  | 0 |  | 0 |  | 0
| - GovDelivery | [6 empty] | 0
| - advisory committee | [6 empty] | 0
| - program-specific list | [6 empty] | 0
| * verifying newspaper advertisements are correct | [6 empty] | 0
| * obtaining copies of affidavits of publication from Accounting | [6 empty] | 0
| * saves all evidence, lists and affidavits on Rule_Development ¦ 4-Notice | i | [5 empty] | 0
` | Jerry drafts EMAIL.NOTICE.TO.KEY.LEGISLATORS - instruction in template: | i |  |  |  | 0 |  | 0 | 0 | 0 |  | Jerry drafts EMAIL.NOTICE.TO.KEY.LEGISLATORS - instruction in template:
| * sends draft to MargaretO to: | [6 empty] | 0 |  |  |  | * sends draft to MargaretO to:
| MargaretO: | [6 empty] | 0 |  |  |  | MargaretO:
| * determines key legislators requiring ORS 183.335(5) notification | i | [5 empty] | 0
| * adapts email as needed | [6 empty] | 0
| * emails to recipients with Return Receipt (redirects receipt to Jerry) |  |  |  |  | 0 |  | 0 | ` | 0 |  | * emails to recipients with Return Receipt (redirects receipt to Jerry)
| * copies Jerry | [6 empty] | 0 |  |  |  | * copies Jerry
| * saves receipts under Rule_Development¦4-Notice using naming conventions | [6 empty] | 0
| AndreaG & Michele maintain Rukemaking Activities Web page |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | AndreaG & Michele maintain Rukemaking Activities Web page
| Jerry gathers andsaves all emails on | i |  |  | 0 | 0 |  | 0 | 0 | 0 |  | Jerry gathers andsaves all emails on
| * Rule_Development¦4-Notice using naming conventions | [6 empty] | 0
W
| Public Comment and Testimony - not involved | [6 empty] | T
[5 empty] | Start | End |  | B
[5 empty] | 0 | 0 |  | B | 0 | 0
Y
| Review version history to help maintaining rulemaking record > | i | [5 empty] | W
| Jerry verifies venues and equipment, gathers supplies | i |  |  | 0 | 0 |  | 0 | 0 | 0 |  | Jerry verifies venues and equipment, gathers supplies
| Team does not plan to hold information meeting | [6 empty] | 0 |  |  |  | Team does not plan to hold information meeting
| Jerry: |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | Jerry:
| * develops INFO.MEETING.TEXT | [6 empty] | 0 | 0 | 0
| * modifies MESSAGE.MAP | i | [5 empty] | 0 | 0 | 0
| * develops INFO.PRESENTATION | [6 empty] | 0 | 0 | 0
| * practices presentation | [6 empty] | 0 | 0 | 0
| * makes presentation adjustments | [6 empty] | 0 | 0 | 0
| * initiates Leah's review/approval, addresses suggestions |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | * initiates Leah's review/approval, addresses suggestions
| 1st loop Leah reviews/approves optional presentation |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 1st loop Leah reviews/approves optional presentation
| 2nd loop Leah reviews/approves optional presentation | N |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 2nd loop Leah reviews/approves optional presentation
| 3rd loop Leah reviews/approves optional presentation | N |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 3rd loop Leah reviews/approves optional presentation
| 4th loop Leah reviews/approves optional presentation | N |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 4th loop Leah reviews/approves optional presentation
| Hearings Officers: | [6 empty] | 1
| * reviews responsibilities of hearings officer |  |  |  | 0 | 0 |  | 0 | 0 | 0
| * develops introductory and logistics script | i |  |  | 0 | 0 |  | 0 | 0 | 0
| * holds the following hearings with assigned team: | [6 empty] | 0 |  |  |  | * holds the following hearings with assigned team:
| 1. Portland hearing |  |  |  |  | 0 |  | 0 |  | 0 |  | 1. Portland hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.1.mp3 | [6 empty] | 0
| 2. Enter city name hearing |  |  |  |  | 0 |  | 0 |  | 0 |  | 2. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.2.mp3 | [6 empty] | 0
| 3. Enter city name hearing |  |  |  |  | 0 |  | 0 |  | 0 |  | 3. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.3.mp3 | [6 empty] | 0
| 4. Enter city name hearing |  |  |  |  | 0 |  | 0 |  | 0 |  | 4. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.4.mp3 | [6 empty] | 0
| 5. Enter city name hearing |  |  |  |  | 0 |  | 0 |  | 0 |  | 5. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.5.mp3 | [6 empty] | 0
| 6. Enter city name hearing |  |  |  |  | 0 |  | 0 |  | 0 |  | 6. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.6.mp3 | [6 empty] | 0
| 7. Enter city name hearing |  |  |  |  | 0 |  | 0 |  | 0 |  | 7. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.7.mp3 | [6 empty] | 0
| 8. Enter city name hearing |  |  |  |  | 0 |  | 0 |  | 0 |  | 8. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.8.mp3 | [6 empty] | 0
| Jerry, for comments not received through online form: |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Jerry, for comments not received through online form:
| * stamps DEQ receipt date on mailed comments | [6 empty] | 0
| * adds commenter and comment to COMMENTS | [6 empty] | 0
| * scans and links comments by ID###.pdf - optional | [6 empty] | 0
|  |  | Close public comment |  |  | 0 |  | 0 |  | 0
| Jerry: |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Jerry:
| * saves online public comment information to COMMENTS | [6 empty] | 0
| * coordinates with team to: | [6 empty] | 0
| - develop category titles to bundle similar comments | [6 empty] | 0
| - organize comments into categories | [6 empty] | 0
| - draft DEQ responses to each categories of comments | [6 empty] | 0
| * leads team work finalizing DEQ responses to public comment | [6 empty] | 0
| DO NOT MAIL TO COMMENTERS UNTIL STAFF REPORT IS FINALIZED | [6 empty] | `
| Jerry asks Maggie for Rule Publication work | i |  |  |  | 1900-01-01 |  | 0 |  | 1900-01-01 |  | Jerry asks Maggie for Rule Publication work
| Maggie coordinates Rule Publication work: |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | Maggie coordinates Rule Publication work:
| * edits for plain English, style guide and tone | [6 empty] | 0
| since this will become part of the EQC Packet | [6 empty] | 0
| * contacts Jerry with questions, clarifications and suggestions | [6 empty] | 0 |  |  |  | * contacts Jerry with questions, clarifications and suggestions
| * notifies Jerry when complete | [6 empty] | 0 |  |  |  | * notifies Jerry when complete
| Jerry: | [6 empty] | 0 |  |  |  | Jerry:
| * shares comments/responses to comments with Leah & Lydia |  |  |  |  | 0 |  | 0 |  | 0 |  | * shares comments/responses to comments with Leah & Lydia
| 1st loop - team modifies responses to get to approval |  |  |  | 0 | 0 |  | 0 | 0 | 0
| 2nd loop - team modifies responses to get to approval | N |  |  | 0 | 0 |  | 0 | 0 | 0
| 3rd loop - team modifies responses to get to approval | N |  |  | 0 | 0 |  | 0 | 0 | 0
| Final loop - team modifies responses to get to approval | N |  |  | 0 | 0 |  | 0 | 0 | 0
| Jerry: | [6 empty] | 0 |  |  |  | Jerry:
| * gathers emails ABOUT comments, not actual comments, for Rule Record | i |  |  |  | 0 |  | 0 |  | 0
| * saves them as Rule_Development¦5-PublicComment...¦EMAIL.Comment.pdf | [6 empty] | 0
W
| EQC Preparation | [6 empty] | T
[5 empty] | Start | End |  | B
[5 empty] | 2014-08-06 | 2014-09-29 |  | B | 2014-08-06 | 2014-09-29
Y
| Review version history to help maintaining rulemaking record > | i | [5 empty] | W
| No EQC involvement prior to Action Item meeting | [6 empty] | 1 |  |  |  | No EQC involvement prior to Action Item meeting
| * no Director's Report |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | * no Director's Report
| * no EQC Information Item | i |  |  | 0 | 0 |  | 0 | 0 | 0 |  | * no EQC Information Item
| * blank row |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | * blank row
| Jerry develops STAFF.RPT.Temporary (preloaded in folder 6 by: |  | x |  | 2014-08-06 | 2014-09-02 |  | 1 | 2014-08-06 | 2014-09-29 |  | Jerry develops STAFF.RPT.Temporary (preloaded in folder 6 by:
| * selecting EQC recommendation in staff report |  | x |  |  |  |  | 1
| No NOTICE for this rulemaking | [6 empty] | 0 |  |  |  | No NOTICE for this rulemaking
| inserting message into header according to instructions in staff report: | [6 empty] | 0
| - Statement of need | [6 empty] | 0
| - Federal relationships | [6 empty] | 0
| - Fiscal impact statement | [6 empty] | 0
| - Fees | [6 empty] | 0
| - Land use | [6 empty] | 0
| - NAME OTHER SECTION UNCHANGED SINCE PUBLIC NOTICE REVIEW | [6 empty] | 0
| - NAME OTHER SECTION UNCHANGED SINCE PUBLIC NOTICE REVIEW | [6 empty] | 0
| * verifies PROPOSED.RULES use latest compilation compared | i | x |  | 2014-08-06 | 2014-09-29 |  | 1 | 2014-08-06 | 2014-09-29
| compared to Oregon State Archives | [6 empty] | 1
| * coordinates work on STAFF.RPT.Temporary sections: | [6 empty] | 1 |  |  |  | * coordinates work on STAFF.RPT.Temporary sections:
| - may update the following as needed, highlight changes since Notice: | [6 empty] | 1
| > change past tense to present tense throughout document as appropriate | [6 empty] | 1
| > Overview section |  | x |  |  |  |  | 1
| > Background (optional) section |  | x |  |  |  |  | 1
| > Rules affected, authorities, supporting documentation |  | x |  |  |  |  | 1
| > Stakeholder involvement section |  | x |  |  |  |  | 1
| - draft Implementation section |  | x |  |  |  |  | 1
| - Insert Summary of comments and DEQ responses | [6 empty] | 1
| > inserts message above to indicate previous reviews | [6 empty] | 1
| - Commenters | [6 empty] | 1
| * finalizes draft of EQC Packet: |  |  |  | 2014-08-06 | 2014-09-02 |  | 1 | 2014-08-06 | 2014-09-29
| - STAFF.RPT.Temporary |  | x |  |  |  |  | 1 |  |  |  | - STAFF.RPT.Temporary
| - PROPOSED.RULES |  | x |  |  |  |  | 1
| - SUPPORTING.DOCUMENTS | [6 empty] | 1
| * notifies AndreaG that Staff Report is ready for Rule Publication work | [6 empty] | 1 |  |  |  | * notifies AndreaG that Staff Report is ready for Rule Publication work
| AndreaG leads initial Rule Publication work that includes: |  |  |  | Rule Publication Work Period |  |  | 1 |  |  |  | AndreaG leads initial Rule Publication work that includes:
| * comparing Notice to EQC Staff Report to determine what needs review |  | x |  | 2014-09-03 | 2014-09-17 |  | 1 | 0 | 2014-09-12
| * obtaining/consolidating BrianW, StephanieC & AndreaG edits if needed | [6 empty] | 1 |  |  |  | * obtaining/consolidating BrianW, StephanieC & AndreaG edits if needed
| including style guide, grammar, plain English, organization, clarity, tone | [6 empty] | 1
| * accepting all style guide and format edits | [6 empty] | 1
| * contacts Jerry with questions or modifications and when work is complete | [6 empty] | 1 |  |  |  | * contacts Jerry with questions or modifications and when work is complete
| AndreaG lets Jerry know when work is complete | [6 empty] | 1 |  | 2014-09-18 |  | AndreaG lets Jerry know when work is complete
| Jerry prepares EQC Staff Report and initiates reviews |  | x |  | 2014-08-06 | 2014-09-02 |  | 1 | 2014-09-19 | 2014-08-11 |  | Jerry prepares EQC Staff Report and initiates reviews
| - PaulG, if needed |  | x |  | 2014-08-06 | 2014-09-02 |  | 1 | 2014-08-06 | 2014-09-29 |  | - PaulG, if needed
| - Enter custom reviewer and action |  |  |  | 2014-08-06 | 2014-09-29 |  | 1 | 2014-08-06 | 2014-09-29
| - Enter custom reviewer and action |  |  |  | 2014-08-06 | 2014-09-29 |  | 1 | 2014-08-06 | 2014-09-29
| - Enter custom reviewer and perspective |  |  |  | 2014-08-06 | 2014-09-29 |  | 1 | 2014-08-06 | 2014-09-29
| Enter custom review loop 1 | Y |  |  | 2014-09-02 | 2014-09-02 |  | 1 | 2014-09-02 | 2014-09-02
| * enter custom action word and reviewer |  |  |  | 2014-09-02 | 2014-09-02 |  | 1 | 2014-09-02 | 2014-09-02
| * enter custom action word and reviewer |  |  |  | 2014-09-02 | 2014-09-02 |  | 1 | 2014-09-02 | 2014-09-02
| * enter custom action word and reviewer |  |  |  | 2014-09-02 | 2014-09-02 |  | 1 | 2014-09-02 | 2014-09-02
| Name initiator and subject for custom review loop 2 | Y |  |  | 2014-09-02 | 2014-09-02 |  | 1 | 2014-09-02 | 2014-09-02
| * enter custom action word and reviewer |  |  |  | 2014-09-02 | 2014-09-02 |  | 1 | 2014-09-02 | 2014-09-02
| * enter custom action word and reviewer |  |  |  | 2014-09-02 | 2014-09-02 |  | 1 | 2014-09-02 | 2014-09-02
| * enter custom action word and reviewer |  |  |  | 2014-09-02 | 2014-09-02 |  | 1 | 2014-09-02 | 2014-09-02
| Name initiator and subject for custom review loop 3 | Y |  |  | 2014-09-02 | 2014-09-02 |  | 1 | 2014-09-02 | 2014-09-02
| * enter custom action word and reviewer |  |  |  | 2014-09-02 | 2014-09-02 |  | 1 | 2014-09-02 | 2014-09-02
| * enter custom action word and reviewer |  |  |  | 2014-09-02 | 2014-09-02 |  | 1 | 2014-09-02 | 2014-09-02
| * enter custom action word and reviewer |  |  |  | 2014-09-02 | 2014-09-02 |  | 1 | 2014-09-02 | 2014-09-02
| Jerry: | [6 empty] | 1 |  |  |  | Jerry:
| * discusses need for 1¦1 commissioners briefings with Leah & Lydia | N |  |  | 0 | 0 |  | 0 | 0 | 0 |  | * discusses need for 1¦1 commissioners briefings with Leah & Lydia
| Enter name of staff who will brief each commissioner - | MEden@neea.org | [5 empty] | 0
| Enter name of staff who will brief each commissioner - | JoKRanch@hotmail.com | [5 empty] | 0
| Enter name of staff who will brief each commissioner - | EdArmstrong2@gmail.com | [5 empty] | 0
| Enter name of staff who will brief each commissioner - | MorganRider@gmail.com | [5 empty] | 0
| Enter name of staff who will brief each commissioner - | cjohnson@eou.edu | [5 empty] | 0
| * obtains approval to publish EQC Packet from: | [6 empty] | 1
| - Leah for lead manager approval |  | x |  | 2014-09-19 | 2014-09-19 |  | 1 | 2014-08-06 | 2014-09-29 |  | - Leah for lead manager approval
| - Lydia for division administrator approval |  | x |  | 2014-09-22 | 2014-09-24 |  | 1 | 2014-08-06 | 2014-09-29 |  | - Lydia for division administrator approval
| * notifies the following according to division's best practice |  | x |  | 2014-09-22 | 2014-11-04 |  | 1 | 2014-08-06 | 2014-11-04
| - staff contributors | [6 empty] | 1
| - key stakeholders | [6 empty] | 1
| - advisory committee members | [6 empty] | 0
| - commenters | [6 empty] | 0
| - interested parties (optional) | [6 empty] | 1
| * leads team development of EQC presentation |  | x |  | 2014-09-24 | 2014-11-04 |  | 1 | 2014-09-24 | 2014-11-04
| * coordinates presentation practices |  | x |  | 2014-11-04 | 2014-11-04 |  | 1 | 2014-11-04 | 2014-11-04
| * makes any presentation adjustments |  | x |  | 2014-11-04 | 2014-11-04 |  | 1 | 2014-11-04 | 2014-11-04
| Presentation team ATTENDS EQC MEETING |  |  |  | 0 | 2014-11-05 |  | 1 |  | 2014-11-05
| Jerry collects emails about EQC preparations for Rule Record and saves as: | i |  |  | 2014-11-05 | 2014-11-05 |  | 1 | 2014-11-05 | 2014-11-05 |  | Jerry collects emails about EQC preparations for Rule Record and saves as:
| Rule_Development¦6-EQCPreparation¦EMAILS.EQC.Prep.pdf | [6 empty] | 1
W
| Post EQC | [6 empty] | T
[5 empty] | Start | End |  | B
[5 empty] | 2014-11-05 | 2015-02-03 |  | B | 2014-11-05 | 2015-02-03
Y
| Review version history to help maintaining rulemaking record > | i | [5 empty] | W
| Work shifts from SharePoint to Rule_Development | [6 empty] | 0
| Jerry: | [6 empty] | 1 |  |  |  | Jerry:
| * prepares/saves documents to Rule_Development¦7-PostEQC |  |  |  |  | 2014-11-05 |  | 1 |  | 2014-11-05
| - ADDENDUM.TO.STAFF.RPT (if presented to EQC) | [6 empty] | 1
| - RULES.docx (clean version) |  | x |  |  |  |  | 1
| - REDLINE.docx (showing changes in strikethrough and underscore) |  | x |  |  |  |  | 1
| - TABLES.340-###-####.docx (1 .docx per rule contains ALL tables in rule) |  | x |  |  |  |  | 1
| - TABLES.340-###-####.docx (1 .docx per rule contains ALL tables in rule) | [6 empty] | 1
| * emails Maggie to affirm EQC action and document readiness | [6 empty] | 1 |  |  |  | * emails Maggie to affirm EQC action and document readiness
| * emails optional STAKEHOLDER.NOTIFICATION of EQC action | Y | x |  |  | 2014-11-05 |  | 1 |  | 2014-11-05
| * coordinates EPA.SIP.SUBMITAL with AndreaG |  |  |  |  | 2014-11-05 |  | 0 |  | 2014-11-05 |  | * coordinates EPA.SIP.SUBMITAL with AndreaG
| * coordinates AC.THANK.YOU email or letter with Leah | i |  |  |  | 0 |  | 0 |  | 0 |  | * coordinates AC.THANK.YOU email or letter with Leah
| * coordinates AC.SURVEY with Leah | i |  |  |  | 0 |  | 0 |  | 0 |  | * coordinates AC.SURVEY with Leah
| * coordinates optional discussion on project evaluation, lessons learned |  |  |  |  | 2014-11-05 |  | 1 |  | 2014-11-05
| AndreaG: | [6 empty] | 1 |  |  |  | AndreaG:
| * no DAS involvement |  |  |  |  | 0 |  | 0 |  | 0 |  | * no DAS involvement
| * no DAS involvement |  |  |  |  | 0 |  | 0 |  | 0 |  | * no DAS involvement
| * no DAS involvement |  |  |  |  | 0 |  | 0 |  | 0 |  | * no DAS involvement
| * no DAS involvement |  |  |  |  | 0 |  | 0 |  | 0 |  | * no DAS involvement
| Maggie: | [6 empty] | 1 |  |  |  | Maggie:
| * prepares and e-files ADOPTED RULES with Secretary of State | i |  |  |  | 2014-11-07 |  | 1 |  | 2014-11-07
| EFFECTIVE DATE |  |  |  |  | 2014-11-07 |  | 1 |  | 2014-11-07
| * shuttles Legislative Counsel notification by return receipt | i |  |  |  | 2014-11-07 |  | 1 |  | 2014-11-07
| - Certificate.SOS-Stamped.pdf | [6 empty] | 1
| - Redline.LC.pdf | [6 empty] | 1
| - self-addressed envelope, fold underside of flap over a 2nd certificate" | [6 empty] | 1
| write "Please date stamp certificate and return." on underside of flap | [6 empty] | 1
| * combine/save following PDFs as Rule_Development¦7-PostEQC | i |  |  |  | 2014-11-07 |  | 1 |  | 2014-11-07
| ¦CERTIFICATE.SOS.LC.Documentation.pdf | [6 empty] | 1
| 1 Certificate.SOS-stamped.pdf | [6 empty] | 1
| 1a Justification.SOS.Stamped.pdf | [6 empty] | 1 |  |  |  | 1a Justification.SOS.Stamped.pdf
| 2 Rules.SOS.pdf | [6 empty] | 1
| 2a 340-### Tables.SOS.pdf | [6 empty] | 1
| 2b 340-### Tables.SOS.pdf | [6 empty] | 1
| 3 HousingCosts.SOS.pdf | [6 empty] | 1
| 4 Authorization.SOS.pdf | [6 empty] | 1
| 5 Certificate.LC-stamped.pdf | [6 empty] | 1
| 6 Redline.LC.pdf | [6 empty] | 1
| 7 ShuttleTracking.LC.pdf | [6 empty] | 1
| * coordinates with Jerry to: | i |  | 1 | 2014-11-07 | 2014-11-07 |  | 1 | 2014-11-07 | 2014-11-07 |  | * coordinates with Jerry to:
| - archive records | i | [5 empty] | 1
| - retire SharePoint | [6 empty] | 1
| - close Outlook account |  |  |  |  | 2014-11-07 |  | 1 |  | 2014-11-07
| - update Web page | [6 empty] | 1
| Jerry: | [6 empty] | 1 |  |  |  | Jerry:
| * gathers emails about post EQC activities for the Rule Record and saves as: |  |  | 1 | 2014-11-07 | 2014-11-07 |  | 1 | 2014-11-07 | 2014-11-07
| Rule_Development¦7-PostEQC¦EMAILS.PostEQC.pdf | [6 empty] | 1
| * verifies accuracy of rules published in Oregon Bulletin |  |  | 1 | 2014-11-24 | 2014-11-24 |  | 1 | 2014-11-24 | 2014-11-24
| If errors, Jerry works with Maggie to correct and selects 'Y' > | Y |  | 1 | 2014-11-24 | 2014-11-24 |  | 1 | 2014-11-24 | 2014-11-24 |  | If errors, Jerry works with Maggie to correct and selects 'Y' >
| AndreaG submits SIP to EPA within 60 days AFTER adoption |  |  | 32 | 2014-11-05 | 2014-12-22 |  | 1 | 2014-11-05 | 2014-12-22 |  | AndreaG submits SIP to EPA within 60 days AFTER adoption
| Jerry: | [6 empty] | 1 |  |  |  | Jerry:
| * places all physical records in archival box - do not print electronic records |  |  | 58 | 2014-11-07 | 2015-02-03 |  | 1 | 2014-11-07 | 2015-02-03
| * labels the box by SOS certificate and order number "DEQ ##-yyyy" |  |  |  |  | 2015-02-03 |  | 1 | 0 | 2015-02-03
| * delivers archival box to Maggie |  |  |  |  | 2015-02-03 |  | 1 | 0 | 2015-02-03 |  | * delivers archival box to Maggie
| AndreaG coordinates retiring Q-Time number(s) with RobertB |  |  | 1 | 2014-11-07 | 2014-11-07 |  | 1 | 2014-11-07 | 2014-11-07 |  | AndreaG coordinates retiring Q-Time number(s) with RobertB
| At the close of the rulemaking records, Maggie archives the record | [6 empty] | 1 |  |  |  | At the close of the rulemaking records, Maggie archives the record
| FROM: \\deqhq1\Rule_Development | i | [5 empty] | 1
| TO: \\deqhq1\Rule_Archives | [6 empty] | 1
| TEAM CELEBRATES |  |  | 58 | 2014-11-07 | 2015-02-03 |  | 1 | 2014-11-07 | 2015-02-03
| Jerry takes a vacation | [6 empty] | 1 |  |  |  | Jerry takes a vacation
$H$866
B
Note on B591: PCAdmin: move one day forward
mm/dd/yy
Subject
Your name
Your message
DEQ Closed

## ConditionalFormat (hidden)
|  | Example | Calculation | Applies to | Last row
Column I: Section Separator codes
T | Section title | White on Teal | =IF($AAE4="T",TRUE) | =$B$4:$ZZ$474
Y | Highlight for section title | Teal on Yellow | =IF($AAE4="Y",TRUE) | "
W |  | White on white | =IF($AAE4="W",TRUE) | "
0 OR 1 | Indicates task involved/not involved | White on white | =IF($AAE4=0,TRUE) | "
Office Closure |  | See DDL worksheet | S.DDL_DEQClosed is the "holiday" table in WORKDAY function
|  | Office Closure date | =IF(WORKDAY($G20-1,1,S.DDL_DEQClosed)<>$G20,TRUE) | $G$20:$G$480 (or last row)
|  | Office Closure date | =IF(WORKDAY($H20-1,1,S.DDL_DEQClosed)<>$H20,TRUE) | $H$20:$H$480 (or last row)
|  | Date has past | =IF(WORKDAY($G10-1,1,S.DDL_DEQClosed)<>$G10,TRUE) | $G$10:$G$480 (or last row)
|  | " | =IF(WORKDAY($H10-1,1,S.DDL_DEQClosed)<>$H10,TRUE) | $H$10:$H$480 (or last row)
Gantt
| An 'X' in $J10 identifies the row as for Gantt to format | Workday | =AND($J10<>"X",$G10<=L$7,$H10>=K$7) | $K10:$AHC$450
|  | Weekend | =IF(OR(WEEKDAY(K$7)=1,WEEKDAY(K$7)=7),TRUE) | $K10:$AHC$450
|  | Closed | =IF(ISERROR(VLOOKUP(K$7,S.DDL_DEQClosed,1,FALSE)),0,1) | $K10:$AHC$450
S.LastCellGantt
s.LastCellschedule

## AddToPlan (hidden)
How a Division Administrator adds a new proposal to the rolling rulemaking plan
| Start | Notify | Train | Draft | Approve | Prepare | Inform
Program è | Identify need * legislation, court order, federal requirements, fees, easier to do business * DEQ intitiated through environmental soultions | If approved to develop concept for inclusion on DEQ Rulemaking Plan | SharePoint, Rule_Development, CONSIDERATIONS & RESOURCES, records management | CONSIDERATIONS, RESOURCES, Overview of Key Dates | Concept for inclusion on DEQ Rulemaking Plan | If division approves adding concept to DEQ Rulemaking Plan | Focusing on communication materials
| ê |  | 2 hours | 8 hours
|  |  |  | Team Collaboration |  | Team Collaboration
Lead staff |  |  | Attend, learn, share | Complete 1st workbook drafts using what you know now |  | Prepare DA communication to EMT/EQC assistant
Lead manager | Discuss need with DA and program managers | Assign staff to work with DRC/ARC on concept development | Attend, learn, share | Add information you know | Present RESOURCES & CONSIDERATIONS summary to DA & program managers | Help prepare and approve DA communication
Rules coordinators (DRC, ARC) |  | ARC Establish SharePoint, Rule_Development sites schedule training | Facilitate, learn, share | Provided guidance and review |  | ARC Add to plan. Prepare summary pdf for DA communication
Division administrator (DA) | Approve initial work to develop concept - discuss potential with EMT | Notify DRC and ARC |  |  | Approve/reject concept addition to plan. Inform lead staff, DRC, ARC |  | EMT/EQC Assistant using communication materials adapted to personal style
EMT | Offer initial ideas about connections, cautions | [5 empty] | Offer advice, indicate interest
EQC assistant | [6 empty] | Add to monthly Director's Report. Advise DRC/ARC re: EQC involvement

## AQ.CFPp2.Calendar (hidden)
Greenhouse gas permitting |  |  |  | GHGTemp
starting |  |  |  | 2014-12-05 | [6 empty] | 2014-12-08 | [6 empty] | 2014-12-15 | [6 empty] | 2014-12-22 | [6 empty] | 2014-12-29 | [6 empty] | 2015-01-05 | [6 empty] | 2015-01-12 | [6 empty] | 2015-01-19
2014-12-05 |  |  |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Adjust start date +/- from today |  |  | 0 | - | - | - | - | 2014-12-05 | 2014-12-06 | 2014-12-07 | 2014-12-08 | 2014-12-09 | 2014-12-10 | 2014-12-11 | 2014-12-12 | 2014-12-13 | 2014-12-14 | 2014-12-15 | 2014-12-16 | 2014-12-17 | 2014-12-18 | 2014-12-19 | 2014-12-20 | 2014-12-21 | 2014-12-22 | 2014-12-23 | 2014-12-24 | 2014-12-25 | 2014-12-26 | 2014-12-27 | 2014-12-28 | 2014-12-29 | 2014-12-30 | 2014-12-31 | 2015-01-01 | 2015-01-02 | 2015-01-03 | 2015-01-04 | 2015-01-05 | 2015-01-06 | 2015-01-07 | 2015-01-08 | 2015-01-09 | 2015-01-10 | 2015-01-11 | 2015-01-12 | 2015-01-13 | 2015-01-14 | 2015-01-15 | 2015-01-16 | 2015-01-17 | 2015-01-18 | 2015-01-19 | 2015-01-20 | 2015-01-21 | 2015-01-22 | 2015-01-23 | 2015-01-24 | 2015-01-25
| Start | End
Add to DEQ Rulemaking Plan |  |  | 0
Establish Q-time numbers | 0 | 0 | 1
Setup shared sites | 0 | 0 | 1
Kickoff worksession | 0 | 0 | 1
Planning Sequence |  |  | 0
Draft workbooks | 0 | 0 | 1
Communications Meeting | 0 | 0 | 1
Rules Sequence | 0 | 2015-02-03 | 0
@ Start | 0 | 0 | 1
@ Notice | 0 | 0 | 1
@ EQC Preparation | 0 | 0 | 1
@ Filing | 0 | 0 | 1
SIP Sequence |  |  | 1
@ Notice EPA/SIP 180 days | 0 | 0 | 1
@ Notice: EPA/SIP 45 days | #NAME? | #NAME? | #NAME?
@ Post EQC: Submit to EPA | 0 | 0 | 1
Fee Sequence |  |  | 0
@ Fee Approval: Part 1 to DAS | 0 | 0 | 1
@ Post EQC: Part 2 to DAS | 2014-11-10 | 2014-11-10 | 1
@ Notice Email DAS for exempt fees | 0 | 0 | 1
Advisory Committee Sequence |  |  | 0
Invitation | 2014-05-02 | 2014-05-02 | 1
Meeting 1 | 2014-06-05 | 2014-06-05 | 1
Meeting 2 | 2014-06-26 | 2014-06-26 | 1
Meeting 3 | 2014-07-30 | 2014-07-30 | 1
Meeting 4 | 2014-07-30 | 2014-07-30 | 1
Meeting 5 | 2014-07-30 | 2014-07-30 | 1
Involve EQC Sequence |  |  | 0
Directors Report 1 | 0 | 0 | 1
Directors Report 2 | 0 | 0 | 1
Info Item 1 | 0 | 0 | 1
Info Item 2 | 0 | 0 | 1
Notice Sequence |  |  | 0
EPA/SIP 180 days | 0 | 0 | 1
EPA/SIP 45 days | #NAME? | #NAME? | #NAME?
Involve DEQ RESOURCES | #REF! | #REF! | #REF!
Send Ad to contract services | 0 | 0 | 1
Manager approval | #NUM! | #NUM! | #NUM!
Open/Close Comment | 1900-01-01 | 0 | 1
DA briefing schedule/meeting | 0 | 0 | 1
Email DAS for exempt fees | 0 | 0 | 1
Preview period | 0 | 0 | 1
SOS Bulletin submit/publish | 0 | 2014-10-01 | 1
Hearing: first/last | 0 | 0 | 1
EQC Preparation Sequence |  |  | 0
EQC Meeting | 2014-11-05 | 2014-11-05 | 1
Post EQC Sequence |  |  | 0
Filing/effective | 2014-11-07 | 2014-11-07 | 1
Part 2 to DAS | 2014-11-10 | 2014-11-10 | 1
Submit to EPA | 0 | 0 | 1
1
1

## GetStarted
Title | CodeName
Greenhouse gas permitting | GHGTemp | i
Names entered under this area will become part of the Schedule of Tasks and Partnershup Agreement
| Enter first name for Schedule | Enter full name for Agreement | Division | Program | Pronoun
Subject Expert | Jerry | Jerry Ebersole | OP | Air Quality Planning | his
Sponsoring Partner | Leah | Leah Feldon | OP | Air Quality Planning | her
Sponsoring Partner's Manager | Lydia | Lydia Emer | OP | Operations Division Administrator | her
Rules Group Partner | AndreaG | Andrea Gartenbaum | OP | Agency Rules | her
Standardization (ARC) | Maggie
Public Affairs Representative | BrianW
EQC Assistant | StephanieC |  |  | GET STARTED
State Implementation Plan Coordinator | AndreaG |  |  | Enter names and codes on this worksheet
Web Master | Michele
FiscalReviewer | Maggie |  |  | ON SCHEDULE
Budget analyst | MargaretO |  |  | Enter Title in header
Assistant Attorney General | PaulG |  |  | Enter start date in G6
Legislative liaison | MargaretO |  |  | When Directors adds to plan, enter date in G9
Support staff | Jerry | <<<<< If support staff is not available, include Lead staff's name |  | Select Y/N options in C9:C50
Time Accounting | RobertB |  |  | All banner dates set on Overview of Key dates
Director | Dick |  |  | Drop down lists
Hearings Officer | HearingOfficer |  |  | EQC optional involvement G39:H41
Division Administrator - Rules | Lydia |  |  | SOS Bulletin H31
Division Administrator - Program | Lydia |  |  | EQC meeting H44
DA Assistant | Carol
Chief Public Affairs Officer | N/A
Media Manager
Jennifer | WQ
Wendy | LQ
Uri | AQ
Budget Analyst
AdamC | WQ
SandraM | LQ
MargaretO | AQ
Legislative Liason
KarenT | WQ
TomR | LQ
MargaretO | AQ

## HearingAndAdDates (hidden)
Greenhouse gas permitting |  |  |  | 2014-12-05
Hearings
|  |  | Hearings Officer | Notes
City | Date | Time
Portland | 0 | 6 p.m. | 6 p.m.
-blank - | -blank - | -blank - | -blank -
-blank - | -blank - | -blank - | -blank -
-blank - | -blank - | -blank - | -blank -
-blank - | -blank - | -blank - | -blank -
-blank - | -blank - | -blank - | -blank -
-blank - | -blank - | -blank - | -blank -
-blank - | -blank - | -blank - | -blank -
Newspaper Advertisements
NOTICE.AD1Oregonian | 0
NOTICE.AD2None | 0
NOTICE.AD3None | 0
NOTICE.AD4None | 0
NOTICE.AD5None | 0
NOTICE.AD6None | 0
NOTICE.AD7None | 0
NOTICE.AD8None | 0

## DDLs
DDLs called from ScheduleTasks
1 | 2 | 3 | 4 | 5 | 6
DDL_EQCMeeting | EQCStaffRptDue | EQCMaterialsDue | Days to next | Next | Last
2013-03-20 | 2013-02-11 | 2013-03-13 | 91 | 2013-06-19 | 2012-12-16 | When updating EQC table, leave rows for previous year.
2013-06-19 | 2013-05-10 | 2013-06-12 | 63 | 2013-08-21 | 2013-03-20
2013-08-21 | 2013-07-16 | 2013-08-14 | 56 | 2013-10-16 | 2013-06-19
2013-10-16 | 2013-09-10 | 2013-10-09 | 56 | 2013-12-11 | 2013-08-21
2013-12-11 | 2013-11-01 | 2013-12-04 | 99 | 2014-03-20 | 2013-10-16
2014-03-20 | 2014-02-13 | 2014-02-24 | 293 | 2015-01-07 | 2012-12-16 |  | 2014-01-24
2014-06-18 | 2014-05-12 | 2014-05-26 | 70 | 2014-08-27 | 2013-08-29 |  | 2014-03-20
2014-08-27 | 2014-07-24 | 2014-08-04 | 70 | 2014-11-05 | 2014-06-18 |  | 2014-06-18
2014-11-05 | 2014-09-29 | 2014-10-13 | 63 | 2015-01-07 | 2014-08-27 |  | 2014-08-20
2015-01-07 | 2014-12-02 | 2014-12-10 | 67 | 2015-03-15 | 2014-11-05 |  | 2014-10-22
2015-03-15 | 2015-02-02 | 2015-03-05 | 94 | 2015-06-17 | 2015-01-07 |  | 2014-12-17
2015-06-17 | 2015-05-07 | 2015-06-05 | 63 | 2015-08-19 | 2015-03-15 |  | 2015-03-18
2015-08-19 | 2015-07-09 | 2015-08-07 | 63 | 2015-10-21 | 2015-06-17 |  | 2015-06-17
2015-10-21 | 2015-09-10 | 2015-10-09 | 56 | 2015-12-16 | 2015-08-19 |  | 2015-08-19
2015-12-16 | 2015-11-05 | 2015-12-04 | 98 | 2016-03-23 | 2015-10-21 |  | 2015-10-21
2016-03-23 | 2016-02-11 | 2016-03-11 | 91 | 2016-06-22 | 2015-12-16 |  | 2015-12-16
2016-06-22 | 2016-05-12 | 2016-06-10 | 56 | 2016-08-17 | 2016-03-23 |  | 2016-03-23
2016-08-17 | 2016-07-07 | 2016-08-05 | 63 | 2016-10-19 | 2016-06-22 |  | 2016-06-22
2016-10-19 | 2016-09-08 | 2016-10-07 | 63 | 2016-12-21 | 2016-08-17
2016-12-21 | 2016-11-10 | 2016-12-09 | 91 | 2017-03-22 | 2016-10-19
2017-03-22 | 2017-02-09 | 2017-03-10 | 91 | 2017-06-21 | 2016-12-21
2017-06-21 | 2017-05-11 | 2017-06-09 | 91
http://www.leg.state.or.us/ors/187.html
DEQClosed | [7 empty] | LEGAL HOLIDAYS 187.010 Legal holidays; acts deferred to next business day; effect on labor agreements. (1) The following days are legal holidays in this state: (a) Each Sunday. (b) New Year’s Day on January 1. (c) Martin Luther King, Jr.’s Birthday on the third Monday in January. (d) Presidents Day, for the purpose of commemorating Presidents Washington and Lincoln, on the third Monday in February. (e) Memorial Day on the last Monday in May. (f) Independence Day on July 4. (g) Labor Day on the first Monday in September. (h) Veterans Day on November 11. (i) Thanksgiving Day on the fourth Thursday in November. (j) Christmas Day on December 25. (2) Each time a holiday, other than Sunday, listed in subsection (1) of this section falls on Sunday, the succeeding Monday shall be a legal holiday. Each time a holiday listed in subsection (1) of this section falls on Saturday, the preceding Friday shall be a legal holiday. (3) Any act authorized, required or permitted to be performed on a holiday as designated in this section may be performed on the next succeeding business day; and no liability or loss of rights of any kind shall result from such delay. (4) In enumerating legal holidays in subsection (1) of this section, the Legislative Assembly does not intend to limit or otherwise affect public or private collective bargaining or collective bargaining agreements. [Amended by 1955 c.4 §1; 1969 c.455 §1; 1973 c.51 §1; 1975 c.633 §1; 1977 c.135 §1; 1977 c.321 §1; 1985 c.518 §1] 187.020 Additional legal holidays. In addition to those specified in ORS 187.010, the following days are legal holidays in this state: (1) Every day appointed by the Governor as a holiday. (2) Every day appointed by the President of the United States as a day of mourning, rejoicing or other special observance only when the Governor also appoints that day as a holiday. [Amended by 1969 c.455 §2; 1975 c.633 §2; 1977 c.135 §2; 1977 c.321 §2; 1985 c.518 §2]
2013-01-01 | New Year | 2013-01-01
2013-01-18 | furlough | 2013-01-18
2013-01-21 | MLK Jr. | 2013-01-21
2013-02-18 | Presidents | 2013-02-18
2013-04-19 | furlough | 2013-04-19
2013-05-24 | furlough | 2013-05-24
2013-05-27 | Memorial | 2013-05-27
2013-07-04 | Independence | 2013-07-04
2013-09-02 | Labor | 2013-09-02
2013-11-11 | Veterans | 2013-11-11
2013-11-28 | Thanksgiving | 2013-11-28
2013-12-25 | Christmas | 2013-12-25
2014-01-01 | New Year | 2014-01-01
2014-01-20 | MLK Jr. | 2014-01-20
2014-02-17 | Presidents | 2014-02-17
2014-05-26 | Memorial | 2014-05-26
2014-07-04 | Independence | 2014-07-04
2014-09-02 | Labor | 2014-09-02
2014-11-11 | Veterans | 2014-11-11
2014-11-27 | Thanksgiving | 2014-11-27
2014-12-25 | Christmas | 2014-12-25
2015-01-01 | New Year | 2015-01-01
2015-01-19 | MLK Jr. | 2015-01-19
2015-02-16 | Presidents | 2015-02-16
2015-05-25 | Memorial | 2015-05-25
2015-07-03 | Independence | 2015-07-03
2015-09-07 | Labor | 2015-09-07
2015-11-11 | Veterans | 2015-11-11
2015-11-26 | Thanksgiving | 2015-11-26
2015-12-25 | Christmas | 2015-12-25
2016-01-01 | New Year | 2016-01-01
2016-01-18 | MLK Jr. | 2016-01-18
2016-02-15 | Presidents | 2016-02-15
2016-05-30 | Memorial | 2016-05-30
2016-07-04 | Independence | 2016-07-04
2016-09-05 | Labor | 2016-09-05
2016-11-11 | Veterans | 2016-11-11
2016-11-24 | Thanksgiving | 2016-11-24
2016-12-26 | Christmas | 2016-12-26
2017-01-02 | New Year | 2017-01-02
2017-01-16 | MLK Jr. | 2017-01-16
2017-02-20 | Presidents | 2017-02-20
2017-05-29 | Memorial | 2017-05-29
2017-07-04 | Independence | 2017-07-04
2017-09-04 | Labor | 2017-09-04
2017-11-10 | Veterans | 2017-11-10
2017-11-23 | Thanksgiving | 2017-11-23
2017-12-25 | Christmas | 2017-12-25
2018-01-01 | New Year | 2018-01-01
Called from ScheduleTasks
DDL_Bulletin | VL_Bulletin
2013-01-01 | 2012-12-14 | 2012-12-14
2013-02-01 | 2013-01-15 | 2013-01-15
2013-03-01 | 2013-02-15 | 2013-02-15
2013-04-01 | 2013-03-15 | 2013-03-15
2013-05-01 | 2013-04-15 | 2013-04-15
2013-06-01 | 2013-05-15 | 2013-05-15
2013-07-01 | 2013-06-14 | 2013-06-14
2013-08-01 | 2013-07-15 | 2013-07-15
2013-09-01 | 2013-08-15 | 2013-08-15
2013-10-01 | 2013-09-13 | 2013-09-13
2013-11-01 | 2013-10-15 | 2013-10-15
2013-12-01 | 2013-11-15 | 2013-11-15
2014-01-01 | 2013-12-13 | 2013-12-13
2014-02-01 | 2014-01-15 | 2014-01-15
2014-03-01 | 2014-02-14 | 2014-02-14
2014-04-01 | 2014-03-14 | 2014-03-14
2014-05-01 | 2014-04-15 | 2014-04-15
2014-06-01 | 2014-05-15 | 2014-05-15
2014-07-01 | 2014-06-13 | 2014-06-13
2014-08-01 | 2014-07-15 | 2014-07-15
2014-09-01 | 2014-08-15 | 2014-08-15
2014-10-01 | 2014-09-15 | 2014-09-15
2014-11-01 | 2014-10-15 | 2014-10-15
2014-12-01 | 2014-11-14 | 2014-11-14
2015-01-01 | 2014-12-15 | 2014-12-15
2015-02-01 | 2015-01-15 | 2015-01-15
2015-03-01 | 2015-02-13 | 2015-02-13
2015-04-01 | 2015-03-13 | 2015-03-13
2015-05-01 | 2015-04-15 | 2015-04-15
2015-06-01 | 2015-05-15 | 2015-05-15
2015-07-01 | 2015-06-15 | 2015-06-15
2015-08-01 | 2015-07-15 | 2015-07-15
2015-09-01 | 2015-08-15 | 2015-08-15
2015-10-01 | 2015-09-15 | 2015-09-15
2015-11-01 | 2015-10-15 | 2015-10-15
2015-12-01 | 2015-11-13 | 2015-11-13
2016-01-01 | 2015-12-15 | 2015-12-15
2016-02-01 | 2016-01-15 | 2016-01-15
2016-03-01 | 2016-02-15 | 2016-02-15
2016-04-01 | 2016-03-15 | 2016-03-15
2016-05-01 | 2016-04-15 | 2016-04-15
2016-06-01 | 2016-05-13 | 2016-05-13
2016-07-01 | 2016-06-15 | 2016-06-15
2016-08-01 | 2016-07-15 | 2016-07-15
2016-09-01 | 2016-08-15 | 2016-08-15
2016-10-01 | 2016-09-15 | 2016-09-15
2016-11-01 | 2016-10-14 | 2016-10-14
2016-12-01 | 2016-11-15 | 2016-11-15
2017-01-01 | 2016-12-15 | 2016-12-15
2017-02-01 | 2017-01-13 | 2017-01-13
2017-03-01 | 2017-02-15 | 2017-02-15
2017-04-01 | 2017-03-15 | 2017-03-15
2017-05-01 | 2017-04-14 | 2017-04-14
2017-06-01 | 2017-05-15 | 2017-05-15
2017-07-01 | 2017-06-15 | 2017-06-15
2017-08-01 | 2017-07-14 | 2017-07-14
2017-09-01 | 2017-08-15 | 2017-08-15
2017-10-01 | 2017-09-15 | 2017-09-15
2017-11-01 | 2017-10-13 | 2017-10-13
2017-12-01 | 2017-11-15 | 2017-11-15
2018-01-01 | 2017-12-15 | 2017-12-15
2018-02-01 | 2018-01-15 | 2018-01-15
2018-03-01 | 2018-02-15 | 2018-02-15
2018-04-01 | 2018-03-14 | 2018-03-14
2018-05-01 | 2018-04-13 | 2018-04-13
2018-06-01 | 2018-05-15 | 2018-05-15
2018-07-01 | 2018-06-15 | 2018-06-15
2018-08-01 | 2018-07-13 | 2018-07-13
2018-09-01 | 2018-08-15 | 2018-08-15
2018-10-01 | 2018-09-14 | 2018-09-14
2018-11-01 | 2018-10-15 | 2018-10-15
2018-12-01 | 2018-11-15 | 2018-11-15
2019-01-01 | 2018-12-14 | 2018-12-14
2019-02-01 | 2019-01-15 | 2019-01-15
2019-03-01 | 2019-02-15 | 2019-02-15
2019-04-01 | 2019-03-15 | 2019-03-15
2019-05-01 | 2019-04-15 | 2019-04-15
2019-06-01 | 2019-05-15 | 2019-05-15
2019-07-01 | 2019-06-14 | 2019-06-14
2019-08-01 | 2019-07-15 | 2019-07-15
2019-09-01 | 2019-08-15 | 2019-08-15
2019-10-01 | 2019-09-13 | 2019-09-13
2019-11-01 | 2019-10-15 | 2019-10-15
2019-12-01 | 2019-11-15 | 2019-11-15
2020-01-01 | 2019-12-13 | 2019-12-13
2020-02-01 | 2020-01-15 | 2020-01-15
2020-03-01 | 2020-02-14 | 2020-02-14
2020-04-01 | 2020-03-13 | 2020-03-13
2020-05-01 | 2020-04-15 | 2020-04-15
2020-06-01 | 2020-05-15 | 2020-05-15
2020-07-01 | 2020-06-15 | 2020-06-15
2020-08-01 | 2020-07-15 | 2020-07-15
2020-09-01 | 2020-08-14 | 2020-08-14
2020-10-01 | 2020-09-15 | 2020-09-15
2020-11-01 | 2020-10-15 | 2020-10-15
2020-12-01 | 2020-11-13 | 2020-11-13
2021-01-01 | 2020-12-15 | 2020-12-15
2021-02-01 | 2021-01-15 | 2021-01-15
2021-03-01 | 2021-02-15 | 2021-02-15
2021-04-01 | 2021-03-15 | 2021-03-15
2021-05-01 | 2021-04-15 | 2021-04-15
2021-06-01 | 2021-05-14 | 2021-05-14
2021-07-01 | 2021-06-15 | 2021-06-15
2021-08-01 | 2021-07-15 | 2021-07-15
2021-09-01 | 2021-08-13 | 2021-08-13
2021-10-01 | 2021-09-15 | 2021-09-15
2021-11-01 | 2021-10-15 | 2021-10-15
2021-12-01 | 2021-11-15 | 2021-11-15
Called from ScheduleTasks
| Newapapers | EQC Facilitated Hearing
Oregonian
EastOregon
RegisterGuard
MailTribune
KlamathHerald
LaGrandeObserver
JournalOfCommerce
None
Other
Formulas:
Next = [DDL_EQCMeeting]+[Days to next]
Last = [DDL_EQCMeeting]-[Days to next, row above]
EQCStaffRptDue = WORKDAY([DDL_EQCMeeting]-40,-1,S.DDL_DEQClosed)
EQCMaterialsDue = WORKDAY([DDL_EQCMeeting]-9,-1,S.DDL_DEQClosed)
EQCMaterialsDue = [DDL_EQCMeeting]

## PartnershipAgreement (hidden)
INTERIM RULEMAKING PARTNERSHIP AGREEMENT
Greenhouse gas permitting
Code: GHGTemp
Description
Enter short description from CONSIDERATIONS
Objectives
Enter objectives from CONSIDERATIONS
Assumptions and Contraints
Enter assumption and contraints identified in CONSIDERATIONS
Managing Partners
Changes to this agreement require the approval and signature of both Partners. A change in scope and missed deadlines may result in re-prioritizing this rulemaking.
| Sponsoring Partner | Leah Feldon, OP: Air Quality Planning
| Subject Expert | Jerry Ebersole, OP: Air Quality Planning
| Rules Group Partner | Andrea Gartenbaum, OP: Agency Rules
Deliverables
Activity Sequence – Add to DEQ Rulemaking Plan
Deadline | Responsibility for Meeting Deadline | Deliverable | Purpose | Recipiant | Done
0 | Rules Group Partner: Andrea Gartenbaum | Shared drive Draft workbooks | Worksession | Leah Feldon | N
0 | Sponsoring Partner: Leah Feldon | Draft workbooks CONSIDERATIONS RESOURCES | Input | Lydia Emer and AndreaG | N
0 | Sponsoring Partner's Manager: Lydia | Draft workbooks with edits CONSIDERATIONS RESOURCES | Input | Leah and AndreaG | N
| Rules Group Partner: AndreaG | Updated Rulemaking Projects Priorities list | Determine capacity Prioritize rulemakings Validate with Leah | Rules Group | N
| Rules Group Partner: AndreaG | Proposed addition to DEQ Rulemaking Plan | Approve, postpone, reject | Dick | N
Activity Sequence - Planning for Director-approved rulemaking priorities
Deadline | Resonsibility for Meeting Deadline | Deliverable | Purpose | Recipient | Done
| Sponsoring Partner: Leah | Refine workbooks Considerations Resources Schedule | Input, notification | People identified in RESOURCES workbook | N
| Sponsoring Partner: Leah | Communications Plan | Input, advice | People identified in RESOURCES workbook | N
Activity Sequence - Notice Packet
Invitation to Comment
Notice
Proposed Rules
Supporting Documents
Deadline | Resonsibility for Meeting Deadline | Deliverable | Purpose | Recipient | Done
#REF! | Sponsoring Partner: Leah | Draft notice & rules | Input, notification | People identified in RESOURCES workbook | N
#REF! | People identified in RESOURCES workbook | Input | Expand knowledge | Leah | N
| Sponsoring Partner: Leah | Draft notice & rules | Input, advice, review | AndreaG | N
| Rules Group Partner: AndreaG | Draft notice & rules | Initial review to ensure standardization, organization, preliminary review of fiscal and economic impact statement, small business analysis | Leah | N
| Sponsoring Partner: Leah | Notice Packet | Confirm adequacy of rulemaking materials | AndreaG | N
0 | Sponsoring Partner: Leah | Notice Packet Preview Email: LT, EQC Assistant, RESOURCES | Inform | Lydia | N
0 | Sponsoring Partner's Manager: Lydia | Notice Packet | Review and approval | Leah
| Division Administrator Lydia | Notice Packet with edits; Approval | Approval | Leah
| Sponsoring Partner's Manager: Lydia | Final Notice Packet | OK to publish | AndreaG
| Rules Group Partner: AndreaG | Final minor edit | Publication ready | Web staff
| Sponsoring Partner: Leah | Confirm accuracy of published rules | Inform | AndreaG
| Sponsoring Partner: Leah | List of hearing participants and their roles; Finalized hearing materials and presentation | Input, advice, review | #NAME?
Activity Sequence – Publication
Deadline | Responsibility for Meeting Deadline | Deliverable | Purpose | Recipient | Done
| Sponsoring Partner: Leah | Approved Newspaper ad(s), Notification lists, Notice content (legislators email, GovDelivery and Interested Parties) | Input, advice, review | AndreaG | N
| Rules Group Partner: AndreaG | Activate Web page, Online comment form. Submit Newspaper ad, SOS Notice, Notification Lists, DAS | Publication | Carol, Legislative staff and Web staff | N
Activity Sequence – EQC Packet
Staff Report
Proposed Rules
Deadline | Responsibility for Meeting Deadline | Deliverable | Purpose | Recipient | Done
| Sponsoring Partner: Leah | EQC Packet | Input, notification | People identified in RESOURCES workbook | N
| Rules Group Partner: AndreaG | EQC Packet | Input, advice, review | Leah | N
| EPA, DOJ | EQC Packet | Review as needed | Leah | N
| Sponsoring Partner: Leah | EQC Packet - finalized | Review and approval | Lydia | N
| Division Administrator: Lydia | EQC Packet with edits, Approval | Approval | Leah | N
| Sponsoring Partner: Leah | Final EQC Packet | OK to publish | AndreaG | N
| Rules Group Partner: AndreaG | Final minor edit | EQC ready | StephanieC | N
Activity Sequence – EQC Presentation
Deadline | Responsibility for Meeting Deadline | Deliverable | Purpose | Send to | Done
| Sponsoring Partner: Leah | List of EQC presenters, their roles and responsibilities; Final EQC Presentation | Input, advice, review | AndreaG | N
| Rules Group Partner: AndreaG | Presentation with minor edit | EQC ready | StephanieC | N
| Rules Group Partner: AndreaG | Update Web page, Online comment form. SOS Filing, DAS, Legislative Counsel | Rules become effective | SOS; Legislative Counsel; DAS | N
Activity Sequence – Rulemaking Record
Deadline | Responsibility for Meeting Deadline | Deliverable | Purpose | Send to | Done
| Sponsoring Partner: Leah | Confirm accuracy of published rules Submit supporting documents for record | Inform | AndreaG | N
| Rules Group Partner: AndreaG | Archive records; Retire SharePoint; Close Outlook account; Update Web page | Complete rulemaking |  | N
Activity Sequence - Rule Development
Deadline | Resonsibility for Meeting Deadline | Deliverable | Purpose | Send to | Done
Sponsoring Manager
Leah Feldon, OP: Air Quality Planning DATE
Rules Group Partner
Andrea Gartenbaum, OP: Agency Rules DATE

## OwnConsultInform (hidden)
Owns program and regulatory content
Manages subject expert
Identifies and remedies training gaps in basic skills for subject expert (e.g. MS Office products, project management, research techniques, written and oral communication, presentation skills, and SharePoint)
Maintains pristine rules in redline/strikeout
Responsible for achieving program intent and requirements (e.g. federal requirements for program delegation)
Responsible for high quality research and analysis by the program
Responsible for high quality and timeliness of program deliverables
Owns best practices
Assists sponsoring manager in finding expertise
Trains subject expert on rulemaking knowledge
Advises subject expert on rulemaking best practices, including advisory committees and fiscal analysis
Guides subject expert through all work products
Develops DEQ’s message with subject expert (e.g. Plain English, Style Guide, Tone, Clarity, OR Rulemaking requirements, DEQ best practices, web presence)
Performs fiscal review
Facilitates input by Communications staff and Legislative staff
Determines adequacy of rulemaking materials
Responsible for adhering rulemaking to best practices
Responsible for meeting regulatory requirements for rulemaking