## CodeName.ScheduleOfTasks
| Overview of Key Dates | [6 empty] | T
| GPLMP |  |  |  | Start ↓ | End |  | B
[5 empty] | 2014-08-13 | 2015-04-07 |  | B | 2014-08-13 | 2015-04-07 |  | Last row = 866
| & | [6 empty] | Y
| To restore any cell under columns G or H to default, place cursor in cell then enter "=A" followed by the cell address. EXAMPLE: =AG13 would restore the default Start of Advisory Committee. | [6 empty] | 0 |  | Dir. Date Used in Calcs
| Director added to DEQ Rulemaking Plan | Y |  |  | 2014-06-30 |  |  | 1 |  | 2014-06-30
0
| PERMANENT Rulemaking | P |  |  |  |  | 60 | 1 |  |  |  | PERMANENT Rulemaking
0
| Rule proposal complexity (1=Minimal, 2= Moderate, 3=Complex) | 2 |  |  |  |  | 30 | 1
0
| Advisory Committee - not involved | N | i |  | 2014-05-02 | 0 | 0 | 0 | 0 | 0 |  | Advisory Committee - not involved
0
| Fees - not involved | N |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fees - not involved
| -blank- | N | i | 0 |  |  | 0 | 0 |  |  |  | -blank-
| -blank- |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  | -blank-
0
| State Implementation Plan (AQ rules) | Y |  | 112 |  |  | 112 | 1 |  |  |  | State Implementation Plan (AQ rules)
| EPA - submit SIP Development Plan 6 months before comment period opens |  |  |  |  | 2014-04-16 |  | 1 |  | 2014-04-16 |  | EPA - submit SIP Development Plan 6 months before comment period opens
| EPA - submit at least 45 days before submitting notice to Rules Publications |  |  | 45 |  | 2014-07-16 | 45 | 1 |  | 2014-07-16 |  | EPA - submit at least 45 days before submitting notice to Rules Publications
[8 empty] | 0 |  |  | `
| Public Notice | Y |  | Adj | 2014-06-30 | 2014-11-21 |  | 1 | 2014-06-30 | 2014-11-21 | Best practice | Public Notice
| Due to DavidC - approval to submit Notice Packet to Rule Publication |  |  | 5 | 2014-08-26 |  | 10 | 1 | #NUM! | #NUM! | 7 | Due to DavidC - approval to submit Notice Packet to Rule Publication
| Due to Rule Publication (AndreaG) - final edits and validations |  |  | 10 |  | 2014-09-10 | 14 | 1 | 2014-08-29 | 2014-09-10 | 14 | Due to Rule Publication (AndreaG) - final edits and validations
| Due to Uri for input and approval to publish Notice Packet |  |  | 7 | 2014-09-24 | 2014-10-01 | 7 | 1 | 2014-09-24 | 2014-10-01 | 5 | Due to Uri for input and approval to publish Notice Packet
| SOS - submit on workday no later than 15th of month BEFORE Bulletin |  |  |  |  | 2014-10-15 |  | 1 |  | 2014-10-15 |  | SOS - submit on workday no later than 15th of month BEFORE Bulletin
| SOS - Oregon Bulletin always publishes on the 1st of month | Drop down list > |  |  |  | 2014-11-01 |  | 1 |  | 2014-10-01 |  | SOS - Oregon Bulletin always publishes on the 1st of month
1
| Public Comment and Testimony | Y |  |  | 2014-10-15 | 2014-12-02 | 7 | 1 | 2014-10-15 | 2014-12-02 |  | Public Comment and Testimony
| Open public comment |  |  |  |  | 2014-10-16 |  | 1 |  | 2014-10-16 |  | Open public comment
| Hold 1st hearing at least 30 days AFTER open comment - EPA SIP requirement |  |  |  |  | 2014-11-18 |  | 1 |  | 2014-11-17 |  | Hold 1st hearing at least 30 days AFTER open comment - EPA SIP requirement
| Close public comment - DEQ best practice, 3 days after last hearing |  |  |  |  | 2014-11-21 |  | 1 |  | 2014-11-21 |  | Close public comment - DEQ best practice, 3 days after last hearing
1
| EQC Preparation |  |  |  | 2014-10-15 | 2014-12-02 |  | 1 | 2014-10-15 | 2014-12-02 |  | =IF(S.Notice.Involved="N","-blank-",IF(S.EQC.SubmitStaffRpt-S.Notice.CloseComment<45,"ERROR - Staff report due before Close of public comment.","Close public comment - best practice, 3 days after last hearing"))
1
| Involvement before Rulemaking Action Item |  |  |  | Option 1 ↓ | Option 2 ↓ |  | 1 |  |  |  | Involvement before Rulemaking Action Item
| Director's Report - some material comes from monthly status report | Y | i |  | 2014-07-01 | 2014-07-01 |  | 1 | 2014-06-30 | 2014-06-30 |  | Director's Report - some material comes from monthly status report
| No information item requested | N | i |  | 0 | 0 | 0 | 0 | 0 | 0 |  | No information item requested
| No facilitated hearing requested | N |  |  | 0 | 2014-10-22 |  | 0 | 0 | 0 |  | No facilitated hearing requested
1
| Rule Publication - submit PERMANENT staff report |  |  |  |  | 2014-12-02 | 36 | 1 |  | 2014-12-02 |  | Rule Publication - submit PERMANENT staff report
| EQC meeting - PERMANENT Rulemaking Action Item | Drop down list > |  |  |  | 2015-01-07 |  | 1 |  | 2015-03-15 |  | EQC meeting - PERMANENT Rulemaking Action Item
[7 empty] | -55 | 1 | < +/- calendar days adjustment
[7 empty] | 321 | 1 | < calendar days added
1
| Post EQC Activities |  |  |  | 2015-01-07 | 2015-04-07 |  | 1 | 2015-01-07 | 2015-04-07
| SOS - file rules |  |  |  |  | 2015-01-09 |  | 1 |  | 2015-01-09
| DAS - fees not involved |  |  |  |  | 2015-01-12 |  | 0 |  | 2015-01-12 |  | DAS - fees not involved
| Rules become effective select 'Y' if effective upon filing > | Y |  |  |  | 2015-01-09 |  | 1 |  | 2015-01-09
| EPA - goal to submit SIP within 60 days of adoption |  |  |  |  | 2015-03-09 |  | 1 |  | 2015-03-09 |  | EPA - goal to submit SIP within 60 days of adoption
Planning
| GPLMP |  |  |  | Start | End |  | B
[5 empty] | 2014-06-30 | 2014-08-11 |  | B | 2014-06-30 | 2014-08-11 | 2014-06-30
Y
| Review version history to help maintain rulemaking record > | i | [5 empty] | W
| KEY PEOPLE | [6 empty] | 1
| Subject expert, core team member - Brian | [6 empty] | 1 |  |  |  | Subject expert, core team member - Brian
| * member of core team - project manager | [6 empty] | 1
| * responsible for: | [6 empty] | 1
| - meeting program's rulemaking goals | [6 empty] | 1
| - meeting subject expert's tasks identified in this Schedule | [6 empty] | 1
| - engaging rules group lead, core team and RESOURCES appropriately | [6 empty] | 1
| - ensuring completed work products are accurate - technically & programmatically | [6 empty] | 1
| * leads: | [6 empty] | 1
| - research/analysis for rulemaking | [6 empty] | 1
| - drafting of work products | [6 empty] | 1
| * briefs: | [6 empty] | 1
| - core team and management about delays and complications as needed | [6 empty] | 1
| - Uri & Wendy as needed | [6 empty] | 1 |  |  |  | - Uri & Wendy as needed
| Sponsoring manager, core team member - DavidC | [6 empty] | 1 |  |  |  | Sponsoring manager, core team member - DavidC
| * member of core team - subject direction | [6 empty] | 1
| * responsible for: | [6 empty] | 1
| - approving work and external work products as: | [6 empty] | 1
| > meeting program and section goals | [6 empty] | 1
| > being accurate both technically & programmatically | [6 empty] | 1
| > meeting sponsoring manager's task deadlines identified in this Schedule | [6 empty] | 1
| * leads: | [6 empty] | 1
| - extra review cycles for Uri as needed | [6 empty] | 1 |  |  |  | - extra review cycles for Uri as needed
| * briefs: | [6 empty] | 1
| - core team and management about delays and complications as needed | [6 empty] | 1 |  |  |  | * briefs core team, Uri & Wendy as needed
| - Uri & Wendy as needed | [6 empty] | 1 |  |  |  | - Uri & Wendy as needed
| Rules group lead, core team member - AndreaG | [6 empty] | 1 |  |  |  | Rules group lead, core team member - AndreaG
| * member of core team - rulemaking best practices | [6 empty] | 1
| * responsible for: | [6 empty] | 1
| - quality of public rulemaking documents | [6 empty] | 1
| - fiscal and economic impact analysis | [6 empty] | 1 |  |  |  | * keeps Uri informed about risks, progress & potential delays
| * leads rule publication work: | [6 empty] | 1
| - establish SharePoint sub site, Rule_Development drive and archival spaces | [6 empty] | 1
| - establish/maintain Web page, URLs, online comment form, University student Outlook account | [6 empty] | 1
| - engages Rule Publications (SIP coordinator, public affairs consultant, EQC assistant) | [6 empty] | 1
| as needed for edits, style guide, grammar, plain English, organization, clarity and tone | [6 empty] | 1
| - reconciles Rule Publications edits that do not affect subject content | [6 empty] | 1
| * authenticates SOS & LC submittals, files notice, fiscal & rules | [6 empty] | 1 |  |  |  | * keeps Uri informed about risks, progress & potential delays
| * briefs: | [6 empty] | 1
| - core team and management about delays and complications as needed | [6 empty] | 1 |  |  |  | * briefs core team, Uri & Wendy as needed
| - team & Lydia as needed | [6 empty] | 1 |  |  |  | - team & Lydia as needed
| Program Support Staff - Brian | [6 empty] | 1 |  |  |  | Program Support Staff - Brian
| Assistant DA - Uri | [6 empty] | 1 |  |  |  | Assistant DA - Uri
| DA - Wendy | [6 empty] | 1 |  |  |  | DA - Wendy
| GENERAL INFORMATION | [6 empty] | 1
| Q-Time number = ????? | [6 empty] | 1
| SharePoint - collaboration place for working documents | [6 empty] | 1
| http://deqsps/programs/rulemaking/aq/gplimited/default.aspx | [6 empty] | 1 |  |  |  | http://deqsps/programs/rulemaking/aq/ppu/docs/Forms/byCategory.aspx
| Rules Development - non collaborative work | [6 empty] | 1
| \\deqhq1\Rule_Development\Currrent Plan\AQ-RM-GrantsPassLMP-Brian Finneran\1-Planning | [6 empty] | 1 |  |  |  | \\deqhq1\Rule_Development\Currrent Plan\AQ-RM-GrantsPassLMP-Brian Finneran\1-Planning
| URLs | [6 empty] | 1
| Online public comment form | [6 empty] | 1
| http://www.oregon.gov/deq/RulesandRegulations/Pages/comments/GPLMP.aspx | [6 empty] | 1 |  |  |  | http://www.oregon.gov/deq/RulesandRegulations/Pages/comments/GPLMP.aspx
| External Web page | [6 empty] | 1
| http://www.oregon.gov/deq/RulesandRegulations/Pages/2014/GPLMP.aspx | [6 empty] | 1 |  |  |  | http://www.oregon.gov/deq/RulesandRegulations/Pages/2014/GPLMP.aspx
| University Student Comment Account | [6 empty] | 1
| Comment-GPLMP@deq.state.or.us | [6 empty] | 1 |  |  |  | Comment-GPLMP@deq.state.or.us
1
| CONCEPT DEVELOPMENT | i | [5 empty] | 1
| DavidC discusses developing concept for DEQ Rulemaking Plan with Uri |  | x |  |  | 2014-06-30 |  | 1 |  | 2014-06-30 |  | DavidC discusses developing concept for DEQ Rulemaking Plan with Uri
| Uri approves concept development work |  | X |  |  | 2014-06-30 |  | 1 |  | 2014-06-30 |  | Uri approves concept development work
| DavidC | [6 empty] | 1 |  |  |  | DavidC
| * assigns subject expert for the rulemaking |  | X |  |  | 2014-06-30 |  | 1 |  | 2014-06-30 |  | * assigns subject expert for the rulemaking
| (reminder - add work to workplans as needed) | [6 empty] | 1 |  |  |  | (reminder - add work to workplans as needed)
| * identify existing Q-Time number for concept development work |  | X |  |  | 2014-06-30 |  | 1 |  | 2014-06-30 |  | * identify existing Q-Time number for concept development work
| Q-Time number = | [6 empty] | 1 |  |  |  | * identify existing Q-Time number for concept development work
| Maggie | [6 empty] | 1 |  |  |  | Maggie
| * adds to Rules Idea list and shares information with Rules Group |  | X |  |  | 2014-06-30 |  | 1 |  | 2014-06-30
| * establishes Rule_Development site | i | X |  |  |  |  | 1
| * establishes SharePoint sub site | i | X |  |  |  |  | 1
| * schedules work session |  | X |  |  |  |  | 1
| DavidC & Brian participates in work session. Topics include: |  | X |  |  | 2014-06-30 |  | 1 |  | 2014-06-30 |  | DavidC & Brian participates in work session. Topics include:
| * roles and responsibilities | [6 empty] | 1
| * records management | [6 empty] | 1
| - naming conventions | [6 empty] | 1
| - SharePoint | i | [5 empty] | 1
| - shared Rule _Development drive | i | [5 empty] | 1
| * overview of work products | [6 empty] | 1
| - Rules and Regulations Web page | i | [5 empty] | 1
| - INVITATION.TO.COMMENT (blank in folder 4) | [6 empty] | 1
| - RULES.REDLINE | [6 empty] | 1
| - NOTICE (blank in folder 4) | [6 empty] | 1
| - FEE.ANALYSIS (blank in folder 3) | [6 empty] | 0
| - STAFF.RPT.Permanent (blank in folder 6) | [6 empty] | 1 |  |  |  | - STAFF.RPT.Permanent (blank in folder 6)
| * work products for this phase (templates preloaded to SharePoint folder 1): | [6 empty] | 1
| - Overview of Key Dates at top of this SCHEDULE | [6 empty] | 1
| - initial draft RESOURCES workbook | [6 empty] | 1
| - initial draft CONSIDERATIONS workbook | [6 empty] | 1
| Brian drafts: |  | x |  | 2014-06-30 | 2014-06-30 |  | 1 | 2014-06-30 | 2014-06-30 |  | Brian drafts:
| * RESOURCES workbook identifies rulemaking and implementation needs | [6 empty] | 1
| * CONSIDERATIONS workbook reflects scope of work accurately | [6 empty] | 1
| * CONSIDERATIONS workbook identifies potential risks accurately | [6 empty] | 1
| Brian gets consenus from DavidC & AndreaG on workbooks |  | X |  |  | 2014-06-30 |  | 1 |  | 2014-06-30 |  | Brian gets consenus from DavidC & AndreaG on workbooks
| DavidC shares concept with Uri and may stop/delay/advance concept |  | x |  |  | 2014-06-30 |  | 1 |  | 2014-06-30 |  | DavidC shares concept with Uri and may stop/delay/advance concept
| Uri shares concept with Wendy and may stop/delay/advance concept |  | x |  |  | 2014-06-30 |  | 1 |  | 2014-06-30 |  | Uri shares concept with Wendy and may stop/delay/advance concept
| If advanced, DavidC emails AndreaG to indicate her approval |  | x |  |  | 2014-06-30 |  | 1 |  | 2014-06-30 |  | If advanced, DavidC emails AndreaG to indicate her approval
| Maggie: | i | x |  |  | 0 |  | 1 |  | 0 |  | Maggie:
| * leads Rules Group prioritization using CONSIDERATIONS and RESOURCES data that |  | x |  |  |  |  | 1
| compares to other concepts, rulemakings in progress and Rules Group work load |  | x |  |  |  |  | 1
| * shares priority list and factors with DavidC & Brian |  | X |  |  | 2014-06-30 |  | 1 |  | 2014-06-30 |  | * shares priority list and factors with DavidC & Brian
| * adjusts factors as needed |  | x |  |  |  |  | 1
| * shares priority listing with DavidC & AndreaG |  | X |  |  | 2014-06-30 |  | 1 |  | 2014-06-30 |  | * shares priority listing with DavidC & AndreaG
| If prioritized and resourced: | [6 empty] | 1 |  |  |  | Dick:
| Maggie develops work papers and Leadership Team draft email for Dick | i |  |  | 2014-06-30 | 2014-06-30 |  | 1 | 2014-06-30 | 2014-06-30 |  | Maggie develops work papers and Leadership Team draft email for Dick
| Dick: | [6 empty] | 1 |  |  |  | Dick:
| * adapts email and approves moving forward, sends email |  |  |  |  | 2014-06-30 |  | 1 |  | 2014-06-30
| To: Leadership Team describing addition to DEQ Rulemaking Plan | [6 empty] | 1 |  |  |  | To: Leadership Team describing addition to DEQ Rulemaking Plan
| To: StephanieC to include in monthly Director's Report | [6 empty] | 1 |  |  |  | To: StephanieC to include in monthly Director's Report
| (Dick asks EQC how they want to be involved with rulemaking) | [6 empty] | 1 |  |  |  | (Dick asks EQC how they want to be involved with rulemaking)
| (StephanieC informs team about EQC involvement by email) | [6 empty] | 1 |  |  |  | (StephanieC informs team about EQC involvement by email)
| Cc… DavidC, Brian, AndreaG | [6 empty] | 1 |  |  |  | Cc… DavidC, Brian, AndreaG
| AndreaG: | [6 empty] | 1 |  |  |  | AndreaG:
| * selects 'A' if approved, 'P' if postponed, 'R' if rejected | A | X |  |  |  |  | 1
| * saves email Rule_Development ¦ 1-Planning ¦ APPROVAL.ToMoveForward.pdf | i | [5 empty] | 1 |  |  |  | * saves email Rule_Development ¦ 1-Planning ¦ APPROVAL.ToMoveForward.pdf
[8 empty] | 0 |  |  | `
| START RULEMAKING IF DICK ADDS TO PLAN | [6 empty] | 1
| DavidC, Brian & AndreaG decide whether to expand team 'Y' to expand > | N | x |  |  | 2014-06-30 |  | 1 |  | 2014-06-30 |  | DavidC, Brian & AndreaG decide whether to expand team 'Y' to expand >
| DavidC works with MargaretO obtains unique Q-Time number(s) |  |  |  |  | 2014-06-30 |  | 1 |  | 2014-06-30 |  | DavidC works with MargaretO obtains unique Q-Time number(s)
| for this rulemaking fromRobertB | [6 empty] | 1 |  |  |  | for this rulemaking fromRobertB
| DavidC is responsible for: | [6 empty] | 1 |  |  |  | DavidC is responsible for:
| * getting new team members' manager approval | [6 empty] | 0
| * adding rulemaking to work plans as appropriate | [6 empty] | 0
| * program team members meet agreed upon dates in this SCHEDULE | [6 empty] | 1
| AndreaG drafts SCHEDULE: |  |  |  |  | 2014-06-30 |  | 1 |  | 2014-06-30 |  | AndreaG drafts SCHEDULE:
| Brian & AndreaG refine & agree on draft schedule: |  |  |  |  | 2014-06-30 |  | 1 |  | 2014-06-30 |  | Brian & AndreaG refine & agree on draft schedule:
| Brian schedules/holds team meeting(s) for consensus on: |  |  |  | 2014-06-30 | 2014-06-30 |  | 1 | 2014-06-30 | 2014-06-30 |  | Brian schedules/holds team meeting(s) for consensus on:
| * RESOURCES workbook identifies rulemaking and implementation needs | [6 empty] | 1
| * CONSIDERATIONS workbook reflects scope of work accurately | [6 empty] | 1
| * CONSIDERATIONS workbook identifies potential risks accurately | [6 empty] | 1
| * SCHEDULE of tasks and deadlines | [6 empty] | 1
[8 empty] | 0 |  |  | `
| COMMUNICATIONS PLANNING | [6 empty] | 1
| Brian schedules/holds meeting with DavidC and |  | X |  | 2014-06-30 | 2014-06-30 |  | 1 | 2014-06-30 | 2014-06-30 |  | Brian schedules/holds meeting with DavidC and
| BrianW and AndreaG to discuss/determine need for: | [6 empty] | 1 |  |  |  | BrianW and AndreaG to discuss/determine need for:
| - Communications Plan 'Y' to develop | N | [5 empty] | 0 |  |  | N
| - Message Map 'Y' to develop | N | [5 empty] | 0
| - Newspaper advertisements 'Y' to develop | Y | [5 empty] | 1
| - Newspaper release 'Y' to develop | N | [5 empty] | 0
| - Program Web page 'Y' to develop | N | [5 empty] | 0
| - Information Meetings before hearing 'Y' to develop | N | [5 empty] | 0
[8 empty] | 0 |  |  | `
| COMMUNICATIONS OPTION | [6 empty] | 0
| Brian leads communication option review and approval loops for: | [6 empty] | 0 |  |  |  | Brian leads communication option review and approval loops for:
| * drafting COMMUNICATION.PLAN with BrianW using information | i |  |  | 2014-06-30 | 2014-06-30 |  | 0 | 2014-06-30 | 2014-06-30 |  | * drafting COMMUNICATION.PLAN with BrianW using information
| from CONSIDERATIONS and RESOURCES workbooks | [6 empty] | 0
| * drafting MESSAGE.MAP with BrianW | i |  |  | 2014-06-30 | 2014-06-30 |  | 0 | 2014-06-30 | 2014-06-30 |  | * drafting MESSAGE.MAP with BrianW
| * drafting PROGRAM.WEB.PAGE content with team and Michele |  |  |  | 2014-06-30 | 2014-06-30 |  | 0 | 2014-06-30 | 2014-06-30 |  | * drafting PROGRAM.WEB.PAGE content with team and Michele
| DavidC: | [6 empty] | 0 |  |  |  | DavidC:
| * shares content with Uri and approves content: |  |  |  | 2014-06-30 | 2014-06-30 |  | 0 | 2014-06-30 | 2014-06-30 |  | * shares content with Uri and approves content:
| 1st loop - team modifies content to get to approval |  |  |  | 2014-06-30 | 2014-06-30 |  | 0 | 2014-06-30 | 2014-06-30
| 2nd loop - team modifies content to get to approval | N |  |  | 0 | 0 |  | 0 | 0 | 0
| 3rd loop - team modifies content to get to approval | N |  |  | 0 | 0 |  | 0 | 0 | 0
| Final loop - team modifies content to get to approval | N |  |  | 0 | 0 |  | 0 | 0 | 0
| Brian leads program Web page development: |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02 |  | Brian leads program Web page development:
| * submits Web Request for program Web page | [6 empty] | 0
` | * verifies Web content meets team expectations | [6 empty] | 0
| * works with Michele to make adjustments | [6 empty] | 0 |  |  |  | * works with Michele to make adjustments
[8 empty] | 0 |  |  | `
| PREPLANNING FOR HEARINGS | [6 empty] | 1
| Team identifies hearing locations, dates and times |  | Hearing Table |  |  |  |  | 1 |  |  |  | Team identifies hearing locations, dates and times
|  |  | # |  | Date | Time |  | 1 |  |  |  | Brian enters hearings locations, dates and times:
| Grants Pass | Y | 1 |  | 2014-11-18 | 6 p.m. |  | 1 | 2014-11-18 | 5 p.m.
|  | N | 2 |  | 0 | 6 p.m. |  | 0 | 0 | 6 p.m.
| Enter city name | N | 3 |  | 0 | 6 p.m. |  | 0 | 0 | 6 p.m.
| Enter city name | N | 4 |  | 0 | 6 p.m. |  | 0 | 0 | 6 p.m.
| Enter city name | N | 5 |  | 0 | 6 p.m. |  | 0 | 0 | 6 p.m.
| Enter city name | N | 6 |  | 0 | 6 p.m. |  | 0 | 0 | 6 p.m.
| Enter city name | N | 7 |  | 0 | 6 p.m. |  | 0 | 0 | 6 p.m.
| Enter city name | N |  |  | 0 | 6 p.m. |  | 0 | 0 | 6 p.m.
| Last hearing: |  |  |  | 2014-11-18 |  |  | 1 | 2014-11-18
| Brian reserves venues/equipment for hearings |  |  |  | 2014-06-30 | 2014-09-22 |  | 1 | 2014-06-30 | 2014-09-22 |  | Brian reserves venues/equipment for hearings
| Brian identifies hearings officer(s) on HearingAndAdDates TAB | i | [5 empty] | 1 |  |  |  | Brian identifies hearings officer(s) on HearingAndAdDates TAB
| NEWSPAPER ADVERTISEMENTS | [6 empty] | 1
| Brian: |  |  |  | 2014-06-30 | 2014-09-22 |  | 1 | 2014-06-30 | 2014-09-22 |  | Brian:
| * to identify publications and publication dates | [6 empty] | 1
|  | Publication Table | [5 empty] | 1
|  | # | Publication |  |  | Pub Date |  | 1
| NOTICE.AD1Oregonian | 1 | Oregonian |  |  | 2014-10-16 |  | 1 |  | 2014-10-16 |  | NOTICE.AD1Oregonian
| NOTICE.AD2Other | 2 | Other |  |  | 2014-10-16 |  | 1 |  | 2014-10-16 |  | NOTICE.AD2Other
| NOTICE.AD3None | 3 | None |  |  | 2014-10-16 |  | 1 |  | 2014-10-16 |  | NOTICE.AD3None
| NOTICE.AD4None | 4 | None |  |  | 2014-10-16 |  | 1 |  | 2014-10-16 |  | NOTICE.AD4None
| NOTICE.AD5None | 5 | None |  |  | 2014-10-16 |  | 1 |  | 2014-10-16 |  | NOTICE.AD5None
| NOTICE.AD6None | 6 | None |  |  | 2014-10-16 |  | 1 |  | 2014-10-16 |  | NOTICE.AD6None
| NOTICE.AD7None | 7 | None |  |  | 2014-10-16 |  | 1 |  | 2014-10-16 |  | NOTICE.AD7None
| NOTICE.AD8None | 8 | None |  |  | 2014-10-16 |  | 1 |  | 2014-10-16 |  | NOTICE.AD8None
| * develops an AD.STANDARD for each hearing if required | i | [5 empty] | 1
| * develops AD.LEGAL for each hearing if required | i | [5 empty] | 1
| * saves as NOTICE.AD.Hearing1, etc. on Rule_Development folder 4 | [6 empty] | 1
| * determines when ADs need to be submitted to contractor | Ad to contractor > |  |  |  | 2014-10-02 |  | 1 |  | 2014-10-02
| * shares contents of HearingAndAdDates TAB with DavidC | i |  |  | 2014-06-30 | 2014-09-26 |  | 1 | 2014-06-30 | 2014-09-26 |  | * shares contents of HearingAndAdDates TAB with DavidC
| * obtains DavidC's email approval |  |  |  | 2014-06-30 | 2014-09-26 |  | 1 | 2014-06-30 | 2014-09-26 |  | * obtains DavidC's email approval
[8 empty] | 0 |  |  | `
| EQC FACILITATED HEARINGS | [6 empty] | 0
| Brian: | [6 empty] | 0 |  |  |  | Brian:
| * observe EQC quorum notification requirements (ORS 192.630) | i | [5 empty] | 0
| * identifies EQC facilitated hearing, coordinate with commissioner: | [6 empty] | 0
| MEden@neea.org | N |  |  |  | 2014-10-15 |  | 0 |  | 0
| JoKRanch@hotmail.com | N |  |  |  | 2014-10-15 |  | 0
| EdArmstrong2@gmail.com | N |  |  |  | 2014-10-22 |  | 0
| MorganRider@gmail.com | N |  |  |  | 2014-10-22 |  | 0
| cjohnson@eou.edu | N |  |  |  | 2014-10-22 |  | 0
[8 empty] | 0 |  |  | `
| PREPARE TO DRAFT RULES | [6 empty] | 1
| Brian coordinates with Team to: |  |  |  | 2014-06-30 | 2014-06-30 |  | 1 | 2014-06-30 | 2014-06-30 |  | Brian coordinates with Team to:
| * determine need for a crosswalk | [6 empty] | 1
| * identify rules to amend or repeal | [6 empty] | 1
| * identify requirements that need rules adoption | [6 empty] | 1
| * identify land use rules | i | [5 empty] | 1
| * identify SIP rules | i | [5 empty] | 1
| Brian: | [6 empty] | 1 |  |  |  | Brian:
| * obtains starting rules from Oregon State Archives | i |  |  |  | 2014-06-30 |  | 1 |  | 2014-06-30
| * owns pristine draft of proposed rules and maintains it on | [6 empty] | 1
| Rule_Development¦1-Planning using the name¦STARTING.RULES | [6 empty] | 1
| only Brian works on rules at this location to ensure the | [6 empty] | 1 |  |  |  | only Brian works on rules at this location to ensure the
| redline/strikethrough remains consistent and that no reviewer | [6 empty] | 1
| copied text from other locations or turned track changes off | [6 empty] | 1
| * uploads copy of STARTING.RULES to SharePoint¦1-Planning | [6 empty] | 1
| All contributors & reviewers work on draft rules on SharePoint | [6 empty] | 1
| * requests Maggie provide numbers for new rules/divisions |  |  |  |  | 2014-06-30 |  | 1 |  | 2014-06-30 |  | * requests Maggie provide numbers for new rules/divisions
| Maggie: | [6 empty] | 1 |  |  |  | Maggie:
| * obtains, verifies, provides previously unused rule numbers |  |  |  |  | 2014-06-30 |  | 1 |  | 2014-06-30 |  | Maggie obtains, verifies, provides previously unused numbers
| * identifies rules that may be involved in other rulemakings |  |  |  |  | 2014-06-30 |  | 1 |  | 2014-06-30 |  | Maggie identifies rules that may be involved in other rulemakings
| * coordinates with AndreaG to identify SIP rules |  |  |  |  | 0 |  | 1 | 2014-06-30 | 0 |  | * coordinates with AndreaG to identify SIP rules
| * requests all planning emails for the Rule Record and saves in | i |  |  |  | 2014-06-30 |  | 1 |  | 2014-06-30 |  | Brian gathers all planning emails for the Rule Record and saves as:
| Rule_Development¦1-Planning¦EMAILS.Planning.pdf | [6 empty] | 1
Advisory Committee - not involved
| GPLMP |  |  |  | Start | End |  | B
[5 empty] | 2014-05-02 | 0 |  | B | 2014-05-02 | 0
Y
| Review version history to help maintaining rulemaking record | i | [5 empty] | W
| Brian holds/leads team meeting to: |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02 |  | Brian holds/leads team meeting to:
| * review | [6 empty] | 0
| - advisory committee Q-Card | i | [5 empty] | 0
| - Public Involvement Resources, discuss when to engage BrianW | i | [5 empty] | 0 |  |  |  | - Public Involvement Resources, discuss when to engage BrianW
| - review committee Web page template | [6 empty] | 0
| - review and discuss required committee meeting sign up list | [6 empty] | 0
| * discuss | [6 empty] | 0
| - public Meeting Laws | i | [5 empty] | 0 |  |  |  | May be required in future
| - EQC quorum notification requirements (ORS 192.630) | i | [5 empty] | 0 |  |  |  | * Oregon Transparency law (not required for Advisory Committees) | i
| - need for optional committee Web page | [6 empty] | 0
| - need for optional committee charter | [6 empty] | 0
| * identify | [6 empty] | 0
| - lists of persons potentially affected by proposed rules | i | [5 empty] | 0
| - lists of persons who may have special interest in rulemaking | [6 empty] | 0
| - potential committee members | [6 empty] | 0
| - potential meeting dates and venues | [6 empty] | 0
| Brian coordinates with team to: |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02 |  | Brian coordinates with team to:
| * develop AC.ROSTER (blank in folder 4) | [6 empty] | 0
| * add EQC members to Cc. list for ALL committee communications | [6 empty] | 0
| MEden@neea.org | [6 empty] | 0
| JoKRanch@hotmail.com | [6 empty] | 0
| EdArmstrong2@gmail.com | [6 empty] | 0
| MorganRider@gmail.com | [6 empty] | 0
| cjohnson@eou.edu | [6 empty] | 0
| * reserve potential meeting dates and venues | [6 empty] | 0
| * draft committee AC.INVITATION (links to GovDelivery/Web pages) |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| * draft content for optional committee Web page | Y |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| * draft optional AC.CHARTER | Y |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| * emails lists above to invite them to sign up to receive meeting notices | i | [5 empty] | 0
| DavidC shares draft roster and invitation with Uri |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02 |  | DavidC shares draft roster and invitation with Uri
| Team addresses any concerns and validates accuracy of how addressed |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| DavidC approves potential advisory committee roster |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02 |  | DavidC approves potential advisory committee roster
| Team: | [6 empty] | 0
| * makes initial voice contact with potential committee members |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| * finalizes AC.ROSTER based on responses |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| Brian: | [6 empty] | 0 |  |  |  | Brian:
| * submits optional Committee Web page template attached to Web Request | i |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| * submits Web Request at anytime when Committee Web page needs updating | [6 empty] | 0
| * sends invitation to potential committee members who agreed to serve |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| * maintains advisory committee record | [6 empty] | 0
| Meeting 1 | Y |  |  | 2014-06-05 | 9.00 a.m. |  | 0 | 2014-05-16
| Team identifies meeting roles | [6 empty] | 0
| Brian coordinates or drafts: |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02 |  | Brian coordinates or drafts:
| * AC.AGENDA.06.05.14 | i | [5 empty] | 0 |  |  |  | * AC.AGENDA.06.05.14
| * AC.NOTIFICATION.06.05.14 | [6 empty] | 0 |  |  |  | * AC.NOTIFICATION.06.05.14
| Brian obtains team approval of agenda and notification |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02 |  | Brian obtains team approval of agenda and notification
| Brian (about 14 working days before meeting:) |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02 |  | Brian (about 14 working days before meeting:)
| * adds meeting to DEQ Online Calendar (password = dudeman) | i | [5 empty] | 0
| * sends GovDelivery meeting notice and Web page link | [6 empty] | 0
| * releases unneeded venues | [6 empty] | 0 |  |  |  | )&", gets team agreement"
| Team assigns custom task here |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| Team assigns custom task here |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| Team assigns custom task here |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| Team assigns custom task here |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| START OPTION - Presentation Select option > | Y | [5 empty] | 0
| Enter staff name here | [6 empty] | 0
| * drafts optional AC.PRESENTATION.06.05.14 | i |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02 |  | * drafts optional AC.PRESENTATION.06.05.14
| Enter staff name here | [6 empty] | 0
| * involves stakeholder presenters, if any |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| Team approves presentation materials |  |  |  | 2014-05-02 | 2014-05-02 |  | 0 | 2014-05-02 | 2014-05-02
| Brian submits Web Request to post materials | i | [5 empty] | 0 |  |  |  | Brian submits Web Request to post materials
| Team practices presentation | [6 empty] | 0
| Team facilitates/holds meeting |  |  |  |  | 2014-06-05 |  | 0 |  | 2014-06-05
| Brian drafts AC.MINUTES 06.05.14 | i |  |  | 2014-06-05 | 2014-06-05 |  | 0 | 2014-06-05 | 2014-06-05 |  | Brian drafts AC.MINUTES 06.05.14
| Team holds debrief meeting |  |  |  | 2014-06-05 | 2014-06-05 |  | 0 | 2014-06-05 | 2014-06-05
| Meeting 2 | Y |  |  | 2014-06-26 | 9.00 a.m. |  | 0 | 2014-06-05
| Team identifies meeting roles |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| Brian coordinates or drafts: | [6 empty] | 0 |  |  |  | Brian coordinates or drafts:
| * AC.AGENDA.06.05.14, gets team agreement | i |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12 |  | * AC.AGENDA.06.05.14, gets team agreement
| * AC.NOTIFICATION.06.05.14 |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12 |  | * AC.NOTIFICATION.06.05.14
| * adds meeting to DEQ Online Calendar (password = dudeman) | i |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| * releases unneeded venues |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| Team assigns custom task here |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| Team assigns custom task here |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| Team assigns custom task here |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| Team assigns custom task here |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| START OPTION - Presentation Select option > | Y | [5 empty] | 0
| Enter staff name here | [6 empty] | 0
| * drafts optional AC.PRESENTATION.06.05.14 | i |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12 |  | * drafts optional AC.PRESENTATION.06.05.14
| Enter staff name here | [6 empty] | 0
| * involves stakeholder presenters, if any |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| Team approves presentation materials |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| Brian submits Web Request to post materials | i |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12 |  | Brian submits Web Request to post materials
| Team practices presentation |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| Brian sends meeting notice with link to Web page |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12 |  | Brian sends meeting notice with link to Web page
| Team facilitates/holds meeting |  | Set above at Meeting 2 title |  |  | 2014-06-26 |  | 0 |  | 2014-06-26
| Brian drafts AC.MINUTES 06.05.14 | i |  | 1 | 2014-06-26 | 2014-06-26 |  | 0 | 2014-06-26 | 2014-06-26 |  | Brian drafts AC.MINUTES 06.05.14
| Team holds debrief meeting |  |  | 1 | 2014-06-26 | 2014-06-26 |  | 0 | 2014-06-26 | 2014-06-26
| Meeting 3 | Y |  |  | 2014-07-30 | 9.00 a.m. |  | 0 | 2014-06-26
| Team identifies meeting roles |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Brian coordinates or drafts: | [6 empty] | 0 |  |  |  | Brian coordinates or drafts:
| * AC.AGENDA.06.05.14, gets team agreement | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * AC.AGENDA.06.05.14, gets team agreement
| * AC.NOTIFICATION.06.05.14 |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * AC.NOTIFICATION.06.05.14
| * adds meeting to DEQ Online Calendar (password = dudeman) | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| * releases unneeded venues |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| START OPTION - Presentation Select option > | Y | [5 empty] | 0
| Enter staff name here | [6 empty] | 0
| * drafts optional AC.PRESENTATION.06.05.14 | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * drafts optional AC.PRESENTATION.06.05.14
| Enter staff name here | [6 empty] | 0
| * involves stakeholder presenters, if any |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team approves presentation materials |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Brian submits Web Request to post materials | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | Brian submits Web Request to post materials
| Team practices presentation |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Brian sends meeting notice with link to Web page |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | Brian sends meeting notice with link to Web page
| Team facilitates/holds meeting |  | Set above at Meeting 3 title |  |  | 2014-07-30 |  | 0 |  | 2014-07-30
| Brian drafts AC.MINUTES06.05.14 | i |  | 1 | 2014-06-05 | 2014-06-05 |  | 0 | 2014-07-30 | 2014-06-05 |  | Brian drafts AC.MINUTES06.05.14
| Team holds debrief meeting |  |  | 1 | 2014-06-05 | 2014-06-05 |  | 0 | 2014-07-30 | 2014-06-05
| Meeting 4 | N |  |  | 2014-07-30 | 6:00 p.m. |  | 0 | 2014-07-30
| Team identifies meeting roles |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Brian coordinates or drafts: | [6 empty] | 0 |  |  |  | Brian coordinates or drafts:
| * AC.AGENDA.06.05.14, gets team agreement | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * AC.AGENDA.06.05.14, gets team agreement
| * AC.NOTIFICATION.06.05.14 |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * AC.NOTIFICATION.06.05.14
| * adds meeting to DEQ Online Calendar (password = dudeman) | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| * releases unneeded venues |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| START OPTION - Presentation Select option > | Y | [5 empty] | 0
| Enter staff name here | [6 empty] | 0
| * drafts optional AC.PRESENTATION.06.05.14 | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * drafts optional AC.PRESENTATION.06.05.14
| Enter staff name here | [6 empty] | 0
| * involves stakeholder presenters, if any |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team approves presentation materials |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Brian submits Web Request to post materials | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | Brian submits Web Request to post materials
| Team practices presentation |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Brian sends meeting notice with link to Web page |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | Brian sends meeting notice with link to Web page
| Team facilitates/holds meeting |  | Set above at Meeting 4 title |  |  | 2014-07-30 |  | 0 |  | 2014-07-30
| Brian drafts AC.MINUTES06.05.14 | i |  | 1 | 2014-07-30 | 2014-07-30 |  | 0 | 2014-07-30 | 2014-07-30 |  | Brian drafts AC.MINUTES06.05.14
| Team holds debrief meeting |  |  | 1 | 2014-07-30 | 2014-07-30 |  | 0 | 2014-07-30 | 2014-07-30
| Meeting 5 | N |  |  | 2014-07-30 | 6:00 p.m. |  | 0 | 2014-07-30
| Team identifies meeting roles |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Brian coordinates or drafts: | [6 empty] | 0 |  |  |  | Brian coordinates or drafts:
| * AC.AGENDA.06.05.14, gets team agreement | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * AC.AGENDA.06.05.14, gets team agreement
| * AC.NOTIFICATION.06.05.14 |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * AC.NOTIFICATION.06.05.14
| * adds meeting to DEQ Online Calendar (password = dudeman) | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| * releases unneeded venues |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| START OPTION - Presentation Select option > | Y | [5 empty] | 0
| Enter staff name here | [6 empty] | 0
| * drafts optional AC.PRESENTATION.06.05.14 | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * drafts optional AC.PRESENTATION.06.05.14
| Enter staff name here | [6 empty] | 0
| * involves stakeholder presenters, if any |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team approves presentation materials |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Brian submits Web Request to post materials | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | Brian submits Web Request to post materials
| Team practices presentation |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Brian sends meeting notice with link to Web page |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | Brian sends meeting notice with link to Web page
| Team facilitates/holds meeting |  | Set above at Meeting 5 title |  |  | 2014-07-30 |  | 0 |  | 2014-07-30
| Brian drafts AC.MINUTES06.05.14 | i |  | 1 | 2014-07-30 | 2014-07-30 |  | 0 | 2014-07-30 | 2014-07-30 |  | Brian drafts AC.MINUTES06.05.14
| Team holds debrief meeting |  |  | 1 | 2014-07-30 | 2014-07-30 |  | 0 | 2014-07-30 | 2014-07-30
| Brian gathers all advisory committee emails for the Rule Record and saves as: | i |  |  | 2014-05-02 | 0 |  | 0 | 2014-05-02 | 0 |  | Brian gathers all advisory committee emails for the Rule Record and saves as:
| Rule_Development¦3-FeesApproval¦EMAILS.Fees.pdf | [6 empty] | 0
| Fees - not involved | [10 empty] | Fees - not involved
[5 empty] | Start | End |  | B
[5 empty] | 0 | 0 |  | B | 0 | 0
Y
| Review version history to help maintaining rulemaking record > | i | [5 empty] | W
| Brian: | [6 empty] | 0 |  |  |  | Brian:
| * devlopes Fee Approval Packet, resources: team and MargaretO | i |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | * devlopes Fee Approval Packet, resources: team and MargaretO
| Fee Approval Packet includes: | [6 empty] | 0
| blank row | [6 empty] | 0 |  |  |  | blank row
| blank row | [6 empty] | 0 |  |  |  | blank row
| blank line | i | [5 empty] | 0 |  |  |  | blank line
| blank row | i | [5 empty] | 0 |  |  |  | blank row
| * requests Maggie's review for sufficiency, tone, plain English, style guide |  |  | 4 | 0 | 1900-01-04 |  | 0 | 0 | 1900-01-04 |  | * requests Maggie's review for sufficiency, tone, plain English, style guide
| considering documents will become part of Notice and EQC packets | [6 empty] | 0
| * initiates DavidC's Fee Approval Packet review, addresses suggestions |  |  |  |  | 1900-01-04 |  | 0 |  | 1900-01-04 |  | * initiates DavidC's Fee Approval Packet review, addresses suggestions
| 1st loop of DavidC's Fee Approval Packet review and approval |  |  | -4 | 1900-01-04 | 0 |  | 0 | 1900-01-04 | 0 |  | 1st loop of DavidC's Fee Approval Packet review and approval
| 2nd loop of DavidC's Fee Approval Packet review and approval | N |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2nd loop of DavidC's Fee Approval Packet review and approval
| 3rd loop of DavidC's Fee Approval Packet review and approval | N |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 3rd loop of DavidC's Fee Approval Packet review and approval
| 4th loop of DavidC's Fee Approval Packet review and approval | N |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 4th loop of DavidC's Fee Approval Packet review and approval
| AndreaG coordinates: | [6 empty] | 0 |  |  |  | AndreaG coordinates:
| * sending EMAIL.DAS.APPROVAL with Fee Approval Packet attached |  |  |  |  | 0 |  | 0 |  | 0
| - in Outlook, request delivery and read receipts | [6 empty] | 0
| - save receipts to Rule_Dev.¦3-Fee.Approval¦PROOF.DAS.REQUEST.pdf | [6 empty] | 0
| * following up on status about 15 days after sending |  |  |  |  | 0 |  | 0 |  | 0
| DAS sends Brian response |  |  |  |  | 0 |  | 0 |  | 0 |  | DAS sends Brian response
| If denied, Brian coordinates addressing DAS response |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | If denied, Brian coordinates addressing DAS response
| 1st loop of DavidC's approval of response to DAS denial |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1st loop of DavidC's approval of response to DAS denial
| 2nd loop of DavidC's approval of response to DAS denial | N |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2nd loop of DavidC's approval of response to DAS denial
| 3rd loop of DavidC's approval of response to DAS denial | N |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 3rd loop of DavidC's approval of response to DAS denial
| 4th loop of DavidC's approval of response to DAS denial | N |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 4th loop of DavidC's approval of response to DAS denial
| If approved, Brian scans and files DAS.PART1.pdf |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | If approved, Brian scans and files DAS.PART1.pdf
| Next step happens under 4-Public Notice section | [6 empty] | 0
| Brian gathers all fee emails for the Rule Record and saves as: | i |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Brian gathers all fee emails for the Rule Record and saves as:
| Rule_Development¦3-FeesApproval¦EMAILS.Fees.pdf | [6 empty] | 0
Public Notice
| GPLMP |  |  |  | Start | End
[5 empty] | 2014-06-30 | 2014-11-21 |  | 1 | 2014-06-30 | 2014-11-21
1900-04-20
| Review version history to help maintain rulemaking record > | i
| DRAFT NOTICE PACKET | [6 empty] | 1
| Brian leads drafting of Notice Packet with core team |  |  |  | 2014-06-30 | 2014-08-22 |  | 1 | 2014-06-30 | 2014-08-22 |  | Brian leads drafting of Notice Packet with core team
| Notice Packet includes: | [6 empty] | 1
| * INVITATION.TO.COMMENT (develop after Notice is stable ) | [6 empty] | 1
| * PROPOSED.RULES | [6 empty] | 1
| * NOTICE | [6 empty] | 1
| - Overview | [6 empty] | 1
| - Statement of Need | [6 empty] | 1
| - Rules affected, authorities, supporting documents | [6 empty] | 1
| - Fee Analysis | [6 empty] | 1
| - Statement of fiscal and economic impact | [6 empty] | 1
| - Federal relationship | [6 empty] | 1
| - Land use | [6 empty] | 1 |  | 0
| - Stakeholder and public involvement | [6 empty] | 1
| * SUPPORTING.DOCS - optional | [6 empty] | 1
| Brian asks RESOURCES for help and input, especially: |  |  |  | 2014-06-30 | 2014-08-22 |  | 1 | 2014-06-30 | 2014-08-22 |  | Brian asks RESOURCES for help and input, especially:
| This is information gathering - not a review | [6 empty] | 1
| * Advisory Commiitee not involved |  |  |  | 2014-06-30 | 2014-08-22 |  | 1 | 2014-06-30 | 2014-08-22 |  | * Advisory Commiitee not involved
| * Affected staff, including regional staff, for contributions |  |  |  | 2014-06-30 | 2014-08-22 |  | 1 | 2014-06-30 | 2014-08-22
| * AndreaG, for SIP consultation |  |  |  | 2014-06-30 | 2014-08-22 |  | 1 | 2014-06-30 | 2014-08-22 |  | * AndreaG, for SIP consultation
| * DavidC for direction and subject consultation, especially to ensure drafts: |  |  |  | 2014-06-30 | 2014-08-22 |  | 1 | 2014-06-30 | 2014-08-22 |  | * DavidC for direction and subject consultation, especially to ensure drafts:
| - meet program goals for rulemaking | [6 empty] | 1
| - align with section, division and agency goals | [6 empty] | 1
| * AndreaG for rulemaking best practices consultation |  |  |  | 2014-06-30 | 2014-08-22 |  | 1 | 2014-06-30 | 2014-08-22 |  | * AndreaG for rulemaking best practices consultation
| -blank- |  |  |  | 2014-06-30 | 2014-08-22 |  | 1 | 2014-06-30 | 2014-08-22 |  | -blank-
| * PaulG, if needed for legal consultation |  |  |  | 2014-06-30 | 2014-08-22 |  | 1 | 2014-06-30 | 2014-08-22 |  | * PaulG, if needed for legal consultation
| * Enter custom resource here |  |  |  | 2014-06-30 | 2014-08-22 |  | 1 | 2014-06-30 | 2014-08-22
| * Enter custom resource here |  |  |  | 2014-06-30 | 2014-08-22 |  | 1 | 2014-06-30 | 2014-08-22
| * Enter custom resource here |  |  |  | 2014-06-30 | 2014-08-22 |  | 1 | 2014-06-30 | 2014-08-22
| Brian continually refines draft Notice Packet to consider RESOURCES input |  |  |  | 2014-06-30 | 2014-08-22 |  | 1 | 2014-06-30 | 2014-08-22 |  | Brian continually refines draft Notice Packet to consider RESOURCES input
| * validates approach with RESOURCES an needed | [6 empty] | 1
| * verifies/adjusts prevously scheduled briefing & review with Uri | [6 empty] | 1 |  |  |  | * verifies/adjusts prevously scheduled briefing & review with Uri
| * asks PaulG for legal sufficiency if warranted | [6 empty] | 1 |  |  |  | * asks PaulG for legal sufficiency if warranted
| * addresses PaulG concerns and discusses with DavidC as needed | [6 empty] | 1 |  |  |  | * addresses PaulG concerns and discusses with DavidC as needed
| * informs DavidC about the approach, issues and potential delays | [6 empty] | 1 |  |  |  | * informs DavidC about the approach, issues and potential delays
| * raises unanticipated rulemaking risks to appropriate level | [6 empty] | 1
| * raises unanticipated rule implementation risks to appropriate level | [6 empty] | 1
| * informs AndreaG about potential delays for and develop contingency, if needed | [6 empty] | 1 |  |  |  | * informs AndreaG about potential delays for and develop contingency, if needed
| Brian asks subject contributors, including DavidC for consensus on |  |  |  | 2014-06-30 | 2014-08-22 |  | 1 | 2014-06-30 | 2014-08-22 |  | Brian asks subject contributors, including DavidC for consensus on
| completeness and accuracy of technical and program content | [6 empty] | 1
| Brian verifies draft rules to ensure: | [6 empty] | 1 |  |  |  | Brian verifies draft rules to ensure:
| * they are current compared to Oregon State Archives | i | [5 empty] | 1
| * they consider other rulemakings that may affect subject rules | [6 empty] | 1
| * statutory authorities are correct for each rule | [6 empty] | 1
| * statutes implemented are correct for each rules | [6 empty] | 1
| * SIP note is at bottom of all SIP rules | [6 empty] | 1 |  |  |  | * SIP note is at bottom of all SIP rules
| KEEP MANAGEMENT INFORMED | [6 empty] | 1
| Brian asks Carol to schedule future time on Uri's calendar for: | Schedule by |  |  |  | 2014-07-25 |  | 1 |  | 2014-07-25 |  | Brian asks Carol to schedule future time on Uri's calendar for:
| * Uri briefing meeting with Brian, DavidC and AndreaG | Meeting will be |  |  |  | 2014-09-23 |  | 1 |  | 2014-09-23 |  | * Uri briefing meeting with Brian, DavidC and AndreaG
| * time on Uri's calendar to review Notice Packet during preview week | Review begins on |  |  |  | 2014-09-24 |  | 1 |  | 2014-09-24 |  | * time on Uri's calendar to review Notice Packet during preview week
| Brian schedules time on DavidC calendar to review Notice Packet | [6 empty] | 1 |  |  |  | Brian schedules time on DavidC calendar to review Notice Packet
| Brian keeps DavidC informed about progress | Review begins on |  |  |  | 2014-08-26 |  | 1 |  | 2014-08-26 |  | Brian keeps DavidC informed about progress
| DavidC keeps Uri informed about progress | [6 empty] | 1 |  |  |  | DavidC keeps Uri informed about progress
| Uri keeps Wendy informed about potential risks & delays | [6 empty] | 1 |  |  |  | Uri keeps Wendy informed about potential risks & delays
| AndreaG keeps Lydia informed about risks & progress | [6 empty] | 1 |  |  |  | AndreaG keeps Lydia informed about risks & progress
| CUSTOM SEQUENCE | [6 empty] | 1
| Name initiator and subject for custom review loop 1 | N |  |  | 0 | 0 |  | 0 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 0 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 0 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 0 | 0 | 0
| Name initiator and subject for custom review loop 2 | N |  |  | 0 | 0 |  | 0 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 0 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 0 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 0 | 0 | 0
| Name initiator and subject for custom review loop 3 | N |  |  | 0 | 0 |  | 0 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 0 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 0 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 0 | 0 | 0
1
| PREPARE FOR MANAGEMENT REVIEW | [6 empty] | 1
| DavidC looks at Notice Packet ensure: |  |  |  | Sponsoring Manager's Work Period |  |  | 1 |  |  |  | DavidC looks at Notice Packet ensure:
| * work products meets rulemaking goals |  |  |  | 2014-08-26 | 0 |  | 1 | 2014-08-26 | 0
| * work products are accurate - programmatically and technically |  |  |  | Due | Complete by |  | 1
| * documents are complete - all comments addressed & no outstanding issues | [6 empty] | 1
| DavidC: | [6 empty] | 1 |  |  |  | DavidC:
| * does not need to duplicate Rule Publication work below | [6 empty] | 1
| * notifies Brian when complete | [6 empty] | 1 |  |  |  | * notifies Brian when complete
| Brian: |  |  |  | 1900-01-01 | #NUM! |  | 1 | 1900-01-01 | #NUM! |  | Brian:
| * addresses DavidC's technical concerns | [6 empty] | 1 |  |  |  | * addresses DavidC's technical concerns
| * submits Notice and Proposed Rules to Rule Publication (AndreaG) | [6 empty] | 1 |  |  |  | * submits Notice and Proposed Rules to Rule Publication (AndreaG)
| AndreaG leads initial Rule Publication work that includes: |  |  |  | Rule Publication Work Period |  |  | 1 |  |  |  | AndreaG leads initial Rule Publication work that includes:
| * establishing rule's Web page, comment form, URLs, University student account |  |  |  | 0 | 2014-09-10 |  | 1 | 0 | 2014-09-10
| * determining fiscal and economic impact analysis sufficiency |  |  |  | Due | Complete by |  | 1
| * performing preliminary work on final review checklist | i | [5 empty] | 1
| * obtaining/consolidating BrianW, StephanieC & AndreaG edits as needed | [6 empty] | 1 |  |  |  | * obtaining/consolidating BrianW, StephanieC & AndreaG edits as needed
| including style guide, grammar, plain English, organization, clarity, tone | [6 empty] | 1
| * accepting all style guide and format edits | [6 empty] | 1
| Brian & AndreaG prepare drafts for preview |  |  |  | 2014-09-11 | 2014-09-16 |  | 1 | 2014-09-11 | 2014-09-16 |  | Brian & AndreaG prepare drafts for preview
| DavidC approves moving forward with Notice and Proposed Rules |  |  |  | 2014-09-17 | 2014-09-18 |  | 1 | 2014-09-17 | 2014-09-18 |  | DavidC approves moving forward with Notice and Proposed Rules
| 2nd loop of DavidC's Notice Packet review and approval | N |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 2nd loop of DavidC's Notice Packet review and approval
| 3rd loop of DavidC's Notice Packet review and approval | N |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 3rd loop of DavidC's Notice Packet review and approval
| 4th loop of DavidC's Notice Packet review and approval | N |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 4th loop of DavidC's Notice Packet review and approval
| Brian & AndreaG address any concerns that may block DavidC's approval |  |  |  | #NUM! | #NUM! |  | 1 | #NUM! | #NUM! |  | Brian & AndreaG address any concerns that may block DavidC's approval
| PREVIEW PERIOD | [6 empty] | 1
| AndreaG drafts EMAIL.PREVIEW - instructions in template: | i |  |  |  | #NUM! |  | 1 |  | #NUM! |  | AndreaG drafts EMAIL.PREVIEW - instructions in template:
| * sends draft to Uri before briefing, copies Brian & DavidC | [6 empty] | 1 |  |  |  | * sends draft to Uri before briefing, copies Brian & DavidC
| Brian, DavidC & AndreaG: | [6 empty] | 1 |  |  |  | Brian, DavidC & AndreaG:
| * brief Uri |  |  |  | Meeting > | 2014-09-23 |  | 1 |  | 2014-09-23 |  | * brief Uri
| * remind Uri this is also his review/approval period | [6 empty] | 1 |  |  |  | * remind Uri this is also his review/approval period
| Uri personalizes and sends EMAIL.PREVIEW |  |  |  | Preview Period |  |  | 1 |  |  |  | Uri personalizes and sends EMAIL.PREVIEW
| To… Dick, Wendy, Leadership Team & StephanieC |  |  |  | Start | End |  | 1 |  |  |  | To… Dick, Wendy, Leadership Team & StephanieC
| Cc…to all contributing and affected staff |  |  |  | 2014-09-24 | 2014-10-01 |  | 1 | 2014-09-24 | 2014-10-01
[5 empty] | allow 7-14 days |  |  | 1
1
| Brian: |  |  |  | 2014-09-24 | 2014-10-06 |  | 1 | 2014-09-24 | 2014-10-06 |  | Brian:
| * saves EMAIL.PREVIEW.pdf to Rule_Development¦4-Notice | i | [5 empty] | 1
| * talks with DavidC, decides how to address any feedback from preview | [6 empty] | 1 |  |  |  | * talks with DavidC, decides how to address any feedback from preview
| * modifies documents as needed | [6 empty] | 1
| * verifies PROPOSED.RULES are still based on current compilation | [6 empty] | 1
| * finalizes Notice Packet with DavidC | [6 empty] | 1 |  |  |  | * finalizes Notice Packet with DavidC
| DavidC: | [6 empty] | 1 |  |  |  | DavidC:
| * determines whether Uri needs a second review 'Y' if 2nd review needed> | N |  |  | 0 | 2014-10-06 |  | 0 | 0 | 2014-10-06 |  | * determines whether Uri needs a second review 'Y' if 2nd review needed>
| * manages Uri's 2nd review and approval | [6 empty] | 0 |  |  |  | * manages Uri's 2nd review and approval
| * emails approval to move forward with Notice to Brian & AndreaG |  |  |  |  | 2014-10-07 |  | 1 |  | 2014-10-07 |  | * emails approval to move forward with Notice to Brian & AndreaG
| AndreaG, depending on input from preview, leads Rule Publication work that: |  |  |  | 2014-10-08 |  |  | 1 | 2014-10-08 |  |  | AndreaG, depending on input from preview, leads Rule Publication work that:
| * compares work products pre/post preview and determines need for additional edits | [6 empty] | 1
| * consolidates Rule Publication edits | [6 empty] | 1
| * verifies/clarifies additional edits with Brian & DavidC as warranted | [6 empty] | 1 |  |  |  | * verifies/clarifies additional edits with Brian & DavidC as warranted
| DavidC emails Brian & AndreaG approval to publish notice | Approval to publish notice |  |  |  | 2014-10-13 |  | 1 |  | 2014-10-13 |  | DavidC emails Brian & AndreaG approval to publish notice
| Brian: | [6 empty] | 1 |  |  |  | Brian:
| * saves email as Rule_Development¦4-Notice¦MGR.APPROVAL.Notice.pdf | [6 empty] | 1
| NOTIFICATIONS | [6 empty] | 1
| Brian: | [6 empty] | 1 |  |  |  | Brian:
| * submits of Notice to EPA |  |  |  |  | 2014-10-13 |  | 1 |  | 2014-10-13
| AndreaG works with Rule Publication to: |  |  |  | 2014-10-08 |  |  | 1 | 2014-10-08 |  |  | AndreaG works with Rule Publication to:
| * establishes Outlook comment box for University students with Brian as owner | [6 empty] | 1 |  |  |  | * establishes Outlook comment box for University students with Brian as owner
| * establishes Rulemaking Activities Web page for proposed rule | i | [5 empty] | 1
| * establishes online public comment form | [6 empty] | 1
| * completes final review checklist | i | [5 empty] | 1
| * authenticates SOS/LC submittals | [6 empty] | 1
| * submits notice to SOS for publication in Oregon Bulletin | i | [5 empty] | 1
| * emails DAS notification of fees that don't require DAS approval | [6 empty] | 0
| * saves all evidence on Rule_Development ¦ 4-Notice using naming conventions | i | [5 empty] | 1
| Brian leads: | [6 empty] | 1 |  |  |  | Brian leads:
| * submitting newspaper notices to contractor |  | Set under Planning |  |  | 2014-10-02 |  | 1 |  | 2014-10-02 |  | * modifies documents as needed
| * adding hearings to DEQ online calendar | i | [5 empty] | 1
| * creating an auto reply to Outlook account for University students | i | [5 empty] | 1
| * validating Web page, comment form and Outlook account | [6 empty] | 1 |  |  |  | * validates Web page, comment form, hearing date accuracy with Brian
| * opening public comment by notifying agency rulemaking list that includes: |  |  |  |  | 2014-10-16 |  | 1 |  | 2014-10-16
| - GovDelivery | [6 empty] | 1
| - advisory committee | [6 empty] | 1
| - program-specific list | [6 empty] | 1
| * verifying newspaper advertisements are correct | [6 empty] | 1
| * obtaining copies of affidavits of publication from Accounting | [6 empty] | 1
| * saves all evidence, lists and affidavits on Rule_Development ¦ 4-Notice | i | [5 empty] | 1
` | Brian drafts EMAIL.NOTICE.TO.KEY.LEGISLATORS - instruction in template: | i |  |  |  | 2014-10-09 |  | 1 | 2014-09-26 | 2014-10-09 |  | Brian drafts EMAIL.NOTICE.TO.KEY.LEGISLATORS - instruction in template:
| * sends draft to MargaretO to: | [6 empty] | 1 |  |  |  | * sends draft to MargaretO to:
| MargaretO: | [6 empty] | 1 |  |  |  | MargaretO:
| * determines key legislators requiring ORS 183.335(5) notification | i | [5 empty] | 1
| * adapts email as needed | [6 empty] | 1
| * emails to recipients with Return Receipt (redirects receipt to Brian) |  |  |  |  | 2014-10-16 |  | 1 | ` | 2014-10-16 |  | * emails to recipients with Return Receipt (redirects receipt to Brian)
| * copies Brian | [6 empty] | 1 |  |  |  | * copies Brian
| * saves receipts under Rule_Development¦4-Notice using naming conventions | [6 empty] | 1
| AndreaG & Michele maintain Rukemaking Activities Web page |  |  |  | 2014-10-16 | 2014-11-21 |  | 1 | 2014-10-16 | 2014-11-21 |  | AndreaG & Michele maintain Rukemaking Activities Web page
| Brian gathers andsaves all emails on | i |  |  | 2014-06-30 | 2014-11-21 |  | 1 | 2014-06-30 | 2014-11-21 |  | Brian gathers andsaves all emails on
| * Rule_Development¦4-Notice using naming conventions | [6 empty] | 1
W
| Public Comment and Testimony | [6 empty] | T
[5 empty] | Start | End |  | B
[5 empty] | 2014-06-30 | 2014-12-02 |  | B | 2014-06-30 | 2014-12-02
Y
| Review version history to help maintaining rulemaking record > | i | [5 empty] | W
| Brian verifies venues and equipment, gathers supplies | i |  |  | 2014-10-15 | 2014-11-18 |  | 1 | 2014-10-15 | 2014-11-18 |  | Brian verifies venues and equipment, gathers supplies
| Team does not plan to hold information meeting | [6 empty] | 0 |  |  |  | Team does not plan to hold information meeting
| Brian: |  |  |  | 2014-10-15 | 2014-10-15 |  | 1 | 2014-10-15 | 2014-10-15 |  | Brian:
| * develops INFO.MEETING.TEXT | [6 empty] | 0 | 0 | 0
| * modifies MESSAGE.MAP | i | [5 empty] | 0 | 0 | 0
| * develops INFO.PRESENTATION | [6 empty] | 0 | 0 | 0
| * practices presentation | [6 empty] | 0 | 0 | 0
| * makes presentation adjustments | [6 empty] | 0 | 0 | 0
| * initiates DavidC's review/approval, addresses suggestions |  |  |  | 2014-10-15 | 2014-10-15 |  | 0 | 2014-10-15 | 2014-10-15 |  | * initiates DavidC's review/approval, addresses suggestions
| 1st loop DavidC reviews/approves optional presentation |  |  |  | 2014-10-15 | 2014-10-15 |  | 0 | 2014-10-15 | 2014-10-15 |  | 1st loop DavidC reviews/approves optional presentation
| 2nd loop DavidC reviews/approves optional presentation | N |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 2nd loop DavidC reviews/approves optional presentation
| 3rd loop DavidC reviews/approves optional presentation | N |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 3rd loop DavidC reviews/approves optional presentation
| 4th loop DavidC reviews/approves optional presentation | N |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 4th loop DavidC reviews/approves optional presentation
| Hearings Officers: | [6 empty] | 1
| * reviews responsibilities of hearings officer |  |  |  | 2014-10-15 | 2014-11-18 |  | 1 | 2014-10-15 | 2014-11-18
| * develops introductory and logistics script | i |  |  | 2014-10-15 | 2014-11-18 |  | 1 | 2014-10-15 | 2014-11-18
| * holds the following hearings with assigned team: | [6 empty] | 1 |  |  |  | * holds the following hearings with assigned team:
| 1. Grants Pass hearing |  |  |  |  | 2014-11-18 |  | 1 |  | 2014-11-18 |  | 1. Grants Pass hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.1.mp3 | [6 empty] | 1
| 2. hearing |  |  |  |  | 0 |  | 0 |  | 0 |  | 2. hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.2.mp3 | [6 empty] | 0
| 3. Enter city name hearing |  |  |  |  | 0 |  | 0 |  | 0 |  | 3. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.3.mp3 | [6 empty] | 0
| 4. Enter city name hearing |  |  |  |  | 0 |  | 0 |  | 0 |  | 4. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.4.mp3 | [6 empty] | 0
| 5. Enter city name hearing |  |  |  |  | 0 |  | 0 |  | 0 |  | 5. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.5.mp3 | [6 empty] | 0
| 6. Enter city name hearing |  |  |  |  | 0 |  | 0 |  | 0 |  | 6. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.6.mp3 | [6 empty] | 0
| 7. Enter city name hearing |  |  |  |  | 0 |  | 0 |  | 0 |  | 7. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.7.mp3 | [6 empty] | 0
| 8. Enter city name hearing |  |  |  |  | 0 |  | 0 |  | 0 |  | 8. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.8.mp3 | [6 empty] | 0
| Brian, for comments not received through online form: |  |  | 10 | 2014-11-18 | 2014-12-02 |  | 1 | 2014-11-18 | 2014-12-02 |  | Brian, for comments not received through online form:
| * stamps DEQ receipt date on mailed comments | [6 empty] | 1
| * adds commenter and comment to COMMENTS | [6 empty] | 1
| * scans and links comments by ID###.pdf - optional | [6 empty] | 1
|  |  | Close public comment |  |  | 2014-11-21 |  | 1 |  | 2014-11-21
| Brian: |  |  | 4 | 2014-11-18 | 2014-11-21 |  | 1 | 2014-11-18 | 2014-11-21 |  | Brian:
| * saves online public comment information to COMMENTS | [6 empty] | 1
| * coordinates with team to: | [6 empty] | 1
| - develop category titles to bundle similar comments | [6 empty] | 1
| - organize comments into categories | [6 empty] | 1
| - draft DEQ responses to each categories of comments | [6 empty] | 1
| * leads team work finalizing DEQ responses to public comment | [6 empty] | 1
| DO NOT MAIL TO COMMENTERS UNTIL ALL STAFF REPORT IS FINALIZED | [6 empty] | `
| Brian asks Maggie for Rule Publication work | i |  |  |  | 2014-11-24 |  | 1 |  | 2014-11-24 |  | Brian asks Maggie for Rule Publication work
| Maggie coordinates Rule Publication work: |  |  |  | 2014-11-24 | 2014-11-24 |  | 1 | 2014-11-24 | 2014-11-24 |  | Maggie coordinates Rule Publication work:
| * edits for plain English, style guide and tone | [6 empty] | 1
| since this will become part of the EQC Packet | [6 empty] | 1
| * contacts Brian with questions, clarifications and suggestions | [6 empty] | 1 |  |  |  | * contacts Brian with questions, clarifications and suggestions
| * notifies Brian when complete | [6 empty] | 1 |  |  |  | * notifies Brian when complete
| Brian: | [6 empty] | 1 |  |  |  | Brian:
| * shares comments/responses to comments with DavidC & Uri |  |  |  |  | 2014-11-24 |  | 1 |  | 2014-11-24 |  | * shares comments/responses to comments with DavidC & Uri
| 1st loop - team modifies responses to get to approval |  |  |  | 2014-11-24 | 2014-11-24 |  | 1 | 2014-11-24 | 2014-11-24
| 2nd loop - team modifies responses to get to approval | N |  |  | 0 | 0 |  | 0 | 0 | 0
| 3rd loop - team modifies responses to get to approval | N |  |  | 0 | 0 |  | 0 | 0 | 0
| Final loop - team modifies responses to get to approval | N |  |  | 0 | 0 |  | 0 | 0 | 0
| Brian: | [6 empty] | 1 |  |  |  | Brian:
| * gathers emails ABOUT comments, not actual comments, for Rule Record | i |  |  |  | 2014-11-24 |  | 1 |  | 2014-11-24
| * saves them as Rule_Development¦5-PublicComment...¦EMAIL.Comment.pdf | [6 empty] | 1
W
| EQC Preparation | [6 empty] | T
[5 empty] | Start | End |  | B
[5 empty] | 2014-10-15 | 2014-12-02 |  | B | 2014-10-15 | 2014-12-02
Y
| Review version history to help maintaining rulemaking record > | i | [5 empty] | W
| Brian: | [6 empty] | 1 |  |  |  | Brian:
| * drafts content of Director's Report to EQC |  |  |  | 2014-10-15 | 2014-12-02 |  | 1 | 2014-10-15 | 2014-12-02 |  | * drafts content of Director's Report to EQC
| * no EQC Information Item | i |  |  | 0 | 0 |  | 0 | 0 | 0 |  | * no EQC Information Item
| * leads EQC material review |  |  |  | 2014-10-15 | 2014-12-02 |  | 1 | 2014-10-15 | 2014-12-02 |  | * leads EQC material review
| Brian develops STAFF.RPT.Permanent preloaded in folder 6 by: |  |  |  | 2014-10-15 | 2014-12-02 |  | 1 | 2014-10-15 | 2014-12-02 |  | Brian develops STAFF.RPT.Permanent preloaded in folder 6 by:
| * selecting EQC recommendation in staff report | [6 empty] | 1
| * integrating NOTICE into STAFF REPORT.Permanent by | [6 empty] | 1 |  |  |  | * integrating NOTICE into STAFF REPORT.Permanent by
| inserting message into header according to instructions in staff report: | [6 empty] | 1
| - Statement of need | [6 empty] | 1
| - Federal relationships | [6 empty] | 1
| - Fiscal impact statement | [6 empty] | 1
| - Fees | [6 empty] | 1
| - Land use | [6 empty] | 1
| - NAME OTHER SECTION UNCHANGED SINCE PUBLIC NOTICE REVIEW | [6 empty] | 1
| - NAME OTHER SECTION UNCHANGED SINCE PUBLIC NOTICE REVIEW | [6 empty] | 1
| * verifies PROPOSED.RULES use latest compilation compared | i |  |  | 2014-10-15 | 2014-12-02 |  | 1 | 2014-10-15 | 2014-12-02
| compared to Oregon State Archives | [6 empty] | 1
| * coordinates work on STAFF.RPT.Permanent sections: | [6 empty] | 1 |  |  |  | * coordinates work on STAFF.RPT.Permanent sections:
| - may update the following as needed, highlight changes since Notice: | [6 empty] | 1
| > change past tense to present tense throughout document as appropriate | [6 empty] | 1
| > Overview section | [6 empty] | 1
| > Background (optional) section | [6 empty] | 1
| > Rules affected, authorities, supporting documentation | [6 empty] | 1
| > Stakeholder involvement section | [6 empty] | 1
| - draft Implementation section | [6 empty] | 1
| - Insert Summary of comments and DEQ responses | [6 empty] | 1
| > inserts message above to indicate previous reviews | [6 empty] | 1
| - Commenters | [6 empty] | 1
| * finalizes draft of EQC Packet: |  |  |  | 2014-10-15 | 2014-12-02 |  | 1 | 2014-10-15 | 2014-12-02
| - STAFF.RPT.Permanent | [6 empty] | 1 |  |  |  | - STAFF.RPT.Permanent
| - PROPOSED.RULES | [6 empty] | 1
| - SUPPORTING.DOCUMENTS | [6 empty] | 1
| * notifies AndreaG that Staff Report is ready for Rule Publication work | [6 empty] | 1 |  |  |  | * notifies AndreaG that Staff Report is ready for Rule Publication work
| AndreaG leads initial Rule Publication work that includes: |  |  |  | Rule Publication Work Period |  |  | 1 |  |  |  | AndreaG leads initial Rule Publication work that includes:
| * comparing Notice to EQC Staff Report to determine what needs review |  |  |  | 0 | 1900-01-09 |  | 1 | 0 | 1900-01-09
| * obtaining/consolidating BrianW, StephanieC & AndreaG edits if needed | [6 empty] | 1 |  |  |  | * obtaining/consolidating BrianW, StephanieC & AndreaG edits if needed
| including style guide, grammar, plain English, organization, clarity, tone | [6 empty] | 1
| * accepting all style guide and format edits | [6 empty] | 1
| * contacts Brian with questions or modifications and when work is complete | [6 empty] | 1 |  |  |  | * contacts Brian with questions or modifications and when work is complete
| AndreaG lets Brian know when work is complete | [6 empty] | 1 |  | 1900-01-10 |  | AndreaG lets Brian know when work is complete
| Brian prepares EQC Staff Report and initiates reviews |  |  |  | 2014-10-15 | 2014-12-02 |  | 1 | 2014-10-15 | 2014-12-02 |  | Brian prepares EQC Staff Report and initiates reviews
| - PaulG, if needed |  |  |  | 2014-10-15 | 2014-12-02 |  | 1 | 2014-10-15 | 2014-12-02 |  | - PaulG, if needed
| - Enter custom reviewer and action |  |  |  | 2014-10-15 | 2014-12-02 |  | 1 | 2014-10-15 | 2014-12-02
| - Enter custom reviewer and action |  |  |  | 2014-10-15 | 2014-12-02 |  | 1 | 2014-10-15 | 2014-12-02
| - Enter custom reviewer and perspective |  |  |  | 2014-10-15 | 2014-12-02 |  | 1 | 2014-10-15 | 2014-12-02
| Enter custom review loop 1 | Y |  |  | 2014-12-02 | 2014-12-02 |  | 1 | 2014-12-02 | 2014-12-02
| * enter custom action word and reviewer |  |  |  | 2014-12-02 | 2014-12-02 |  | 1 | 2014-12-02 | 2014-12-02
| * enter custom action word and reviewer |  |  |  | 2014-12-02 | 2014-12-02 |  | 1 | 2014-12-02 | 2014-12-02
| * enter custom action word and reviewer |  |  |  | 2014-12-02 | 2014-12-02 |  | 1 | 2014-12-02 | 2014-12-02
| Name initiator and subject for custom review loop 2 | Y |  |  | 2014-12-02 | 2014-12-02 |  | 1 | 2014-12-02 | 2014-12-02
| * enter custom action word and reviewer |  |  |  | 2014-12-02 | 2014-12-02 |  | 1 | 2014-12-02 | 2014-12-02
| * enter custom action word and reviewer |  |  |  | 2014-12-02 | 2014-12-02 |  | 1 | 2014-12-02 | 2014-12-02
| * enter custom action word and reviewer |  |  |  | 2014-12-02 | 2014-12-02 |  | 1 | 2014-12-02 | 2014-12-02
| Name initiator and subject for custom review loop 3 | Y |  |  | 2014-12-02 | 2014-12-02 |  | 1 | 2014-12-02 | 2014-12-02
| * enter custom action word and reviewer |  |  |  | 2014-12-02 | 2014-12-02 |  | 1 | 2014-12-02 | 2014-12-02
| * enter custom action word and reviewer |  |  |  | 2014-12-02 | 2014-12-02 |  | 1 | 2014-12-02 | 2014-12-02
| * enter custom action word and reviewer |  |  |  | 2014-12-02 | 2014-12-02 |  | 1 | 2014-12-02 | 2014-12-02
| Brian: | [6 empty] | 1 |  |  |  | Brian:
| * discusses need for 1¦1 commissioners briefings with DavidC & Uri | N |  |  | 0 | 0 |  | 0 | 0 | 0 |  | * discusses need for 1¦1 commissioners briefings with DavidC & Uri
| Enter name of staff who will brief each commissioner - | MEden@neea.org | [5 empty] | 0
| Enter name of staff who will brief each commissioner - | JoKRanch@hotmail.com | [5 empty] | 0
| Enter name of staff who will brief each commissioner - | EdArmstrong2@gmail.com | [5 empty] | 0
| Enter name of staff who will brief each commissioner - | MorganRider@gmail.com | [5 empty] | 0
| Enter name of staff who will brief each commissioner - | cjohnson@eou.edu | [5 empty] | 0
| * obtains approval to publish EQC Packet from: | [6 empty] | 1
| - DavidC for lead manager approval |  |  |  | 2014-10-15 | 2014-12-02 |  | 1 | 2014-10-15 | 2014-12-02 |  | - DavidC for lead manager approval
| - Uri for division administrator approval |  |  |  | 2014-10-15 | 2014-12-02 |  | 1 | 2014-10-15 | 2014-12-02 |  | - Uri for division administrator approval
| * notifies the following according to division's best practice |  |  |  | 2014-10-15 | 2015-01-06 |  | 1 | 2014-10-15 | 2015-01-06
| - staff contributors | [6 empty] | 1
| - key stakeholders | [6 empty] | 1
| - advisory committee members | [6 empty] | 0
| - commenters | [6 empty] | 1
| - interested parties (optional) | [6 empty] | 1
| * leads team development of EQC presentation |  |  |  | 2014-12-02 | 2015-01-06 |  | 1 | 2014-12-02 | 2015-01-06
| * coordinates presentation practices |  |  |  | 2015-01-06 | 2015-01-06 |  | 1 | 2015-01-06 | 2015-01-06
| * makes any presentation adjustments |  |  |  | 2015-01-06 | 2015-01-06 |  | 1 | 2015-01-06 | 2015-01-06
| Presentation team ATTENDS EQC MEETING |  |  |  | 0 | 2015-01-07 |  | 1 |  | 2015-01-07
| Brian collects emails about EQC preparations for Rule Record and saves as: | i |  |  | 2015-01-07 | 2015-01-07 |  | 1 | 2015-01-07 | 2015-01-07 |  | Brian collects emails about EQC preparations for Rule Record and saves as:
| Rule_Development¦6-EQCPreparation¦EMAILS.EQC.Prep.pdf | [6 empty] | 1
W
| Post EQC | [6 empty] | T
[5 empty] | Start | End |  | B
[5 empty] | 2015-01-07 | 2015-04-07 |  | B | 2015-01-07 | 2015-04-07
Y
| Review version history to help maintaining rulemaking record > | i | [5 empty] | W
| Work shifts from SharePoint to Rule_Development | [6 empty] | 1
| Brian: | [6 empty] | 1 |  |  |  | Brian:
| * prepares/saves documents to Rule_Development¦7-PostEQC |  |  |  |  | 2015-01-07 |  | 1 |  | 2015-01-07
| - ADDENDUM.TO.STAFF.RPT (if presented to EQC) | [6 empty] | 1
| - RULES.docx (clean version) | [6 empty] | 1
| - REDLINE.docx (showing changes in strikethrough and underscore) | [6 empty] | 1
| - TABLES.340-###-####.docx (1 .docx per rule contains ALL tables in rule) | [6 empty] | 1
| - TABLES.340-###-####.docx (1 .docx per rule contains ALL tables in rule) | [6 empty] | 1
| * emails Maggie to affirm EQC action and document readiness | [6 empty] | 1 |  |  |  | * emails Maggie to affirm EQC action and document readiness
| * emails optional STAKEHOLDER.NOTIFICATION of EQC action | Y |  |  |  | 2015-01-07 |  | 1 |  | 2015-01-07
| * coordinates EPA.SIP.SUBMITAL with AndreaG |  |  |  |  | 2015-01-07 |  | 1 |  | 2015-01-07 |  | * coordinates EPA.SIP.SUBMITAL with AndreaG
| * coordinates AC.THANK.YOU email or letter with DavidC | i |  |  |  | 0 |  | 0 |  | 0 |  | * coordinates AC.THANK.YOU email or letter with DavidC
| * coordinates AC.SURVEY with DavidC | i |  |  |  | 0 |  | 0 |  | 0 |  | * coordinates AC.SURVEY with DavidC
| * coordinates optional discussion on project evaluation, lessons learned |  |  |  |  | 2015-01-07 |  | 1 |  | 2015-01-07
| AndreaG: | [6 empty] | 1 |  |  |  | AndreaG:
| * no DAS involvement |  |  |  |  | 0 |  | 0 |  | 0 |  | * no DAS involvement
| * no DAS involvement |  |  |  |  | 0 |  | 0 |  | 0 |  | * no DAS involvement
| * no DAS involvement |  |  |  |  | 0 |  | 0 |  | 0 |  | * no DAS involvement
| * no DAS involvement |  |  |  |  | 0 |  | 0 |  | 0 |  | * no DAS involvement
| Maggie: | [6 empty] | 1 |  |  |  | Maggie:
| * prepares and e-files ADOPTED RULES with Secretary of State | i |  |  |  | 2015-01-09 |  | 1 |  | 2015-01-09
| EFFECTIVE DATE |  |  |  |  | 2015-01-09 |  | 1 |  | 2015-01-09
| * shuttles Legislative Counsel notification by return receipt | i |  |  |  | 2015-01-09 |  | 1 |  | 2015-01-09
| - Certificate.SOS-Stamped.pdf | [6 empty] | 1
| - Redline.LC.pdf | [6 empty] | 1
| - self-addressed envelope, fold underside of flap over a 2nd certificate" | [6 empty] | 1
| write "Please date stamp certificate and return." on underside of flap | [6 empty] | 1
| * combine/save following PDFs as Rule_Development¦7-PostEQC | i |  |  |  | 2015-01-09 |  | 1 |  | 2015-01-09
| ¦CERTIFICATE.SOS.LC.Documentation.pdf | [6 empty] | 1
| 1 Certificate.SOS-stamped.pdf | [6 empty] | 1
| reserved for temporary rules | [6 empty] | 0 |  |  |  | reserved for temporary rules
| 2 Rules.SOS.pdf | [6 empty] | 1
| 2a 340-### Tables.SOS.pdf | [6 empty] | 1
| 2b 340-### Tables.SOS.pdf | [6 empty] | 1
| 3 HousingCosts.SOS.pdf | [6 empty] | 1
| 4 Authorization.SOS.pdf | [6 empty] | 1
| 5 Certificate.LC-stamped.pdf | [6 empty] | 1
| 6 Redline.LC.pdf | [6 empty] | 1
| 7 ShuttleTracking.LC.pdf | [6 empty] | 1
| * coordinates with Brian to: | i |  | 1 | 2015-01-09 | 2015-01-09 |  | 1 | 2015-01-09 | 2015-01-09 |  | * coordinates with Brian to:
| - archive records | i | [5 empty] | 1
| - retire SharePoint | [6 empty] | 1
| - close Outlook account |  |  |  |  | 2015-01-09 |  | 1 |  | 2015-01-09
| - update Web page | [6 empty] | 1
| Brian: | [6 empty] | 1 |  |  |  | Brian:
| * gathers emails about post EQC activities for the Rule Record and saves as: |  |  | 1 | 2015-01-09 | 2015-01-09 |  | 1 | 2015-01-09 | 2015-01-09
| Rule_Development¦7-PostEQC¦EMAILS.PostEQC.pdf | [6 empty] | 1
| * verifies accuracy of rules published in Oregon Bulletin |  |  | 1 | 2015-01-26 | 2015-01-26 |  | 1 | 2015-01-26 | 2015-01-26
| If errors, Brian works with Maggie to correct and selects 'Y' > | Y |  | 1 | 2015-01-26 | 2015-01-26 |  | 1 | 2015-01-26 | 2015-01-26 |  | If errors, Brian works with Maggie to correct and selects 'Y' >
| AndreaG submits SIP to EPA within 60 days AFTER adoption |  |  | 32 | 2015-01-07 | 2015-02-23 |  | 1 | 2015-01-07 | 2015-02-23 |  | AndreaG submits SIP to EPA within 60 days AFTER adoption
| Brian: | [6 empty] | 1 |  |  |  | Brian:
| * places all physical records in archival box - do not print electronic records |  |  | 61 | 2015-01-09 | 2015-04-07 |  | 1 | 2015-01-09 | 2015-04-07
| * labels the box by SOS certificate and order number "DEQ ##-yyyy" |  |  |  |  | 2015-04-07 |  | 1 | 0 | 2015-04-07
| * delivers archival box to Maggie |  |  |  |  | 2015-04-07 |  | 1 | 0 | 2015-04-07 |  | * delivers archival box to Maggie
| AndreaG coordinates retiring Q-Time number(s) with RobertB |  |  | 1 | 2015-01-09 | 2015-01-09 |  | 1 | 2015-01-09 | 2015-01-09 |  | AndreaG coordinates retiring Q-Time number(s) with RobertB
| At the close of the rulemaking records, Maggie archives the record | [6 empty] | 1 |  |  |  | At the close of the rulemaking records, Maggie archives the record
| FROM: \\deqhq1\Rule_Development | i | [5 empty] | 1
| TO: \\deqhq1\Rule_Archives | [6 empty] | 1
| TEAM CELEBRATES |  |  | 61 | 2015-01-09 | 2015-04-07 |  | 1 | 2015-01-09 | 2015-04-07
| Brian takes a vacation | [6 empty] | 1 |  |  |  | Brian takes a vacation
$H$866
B
Note on AK31: AGarten: Changed EPA requirement to EPA SIP requirement
Note on AK105: AGarten: Fix. Should be address for SharePoint work
Note on AK107: AGarten: Fix. Should be address for Rules Development - non collaborative work. Should we add a folder for this, to keep people out of the other folders on rules development?
Note on AK112: AGarten: Change the year from 2013 to 2014
Note on AK114: AGarten: change commas to periods
Note on AK183: AGarten: typo
Note on AH229: AGarten: I updated this formula. The end date of this task should be a couple weeks before the Notice is submitted to SOS
Note on B230: AGarten: Revise for clarity
Note on C230: AGarten: this link to the hearing and ad tab doesn't work if the tab is hidden.
Note on AH233: AGarten: This step needs to happen earlier. I changed it from 2 days to 18 days before the notice is published
Note on AK233: AGarten: Changed for Jill's rulemaking. Removed part of formula since Jill doesn't have a support person.
Note on H236: AGarten: Verify date works with newspaper. Newspapers are not published every day of the week.
Note on AH249: AGarten: Changed from H233 to =IF(AF249=0,,IF(S.Notice.AD.Involved="N",,WORKDAY(S.Notice.OpenComment,-10,S.DDL_DEQClosed)))
Note on B250: AGarten: Revise for clarity
Note on C250: AGarten: this link to the hearing and ad tab doesn't work if the tab is hidden
Note on AH250: AGarten: Changed from 2 days to 13 days
Note on AH251: AGarten: Changed from 2 days to 13 days
Note on H332: AGarten: Fixed punctuation
Note on B509: AGarten: spelling
Note on AG593: AGarten: I changed this. I think it's linked to wrong date. Should be linked to S.Notice.Submit.ToADA in AG25
Note on B607: AGarten: Increase height or add row to display the last word of this responsibility
Note on AH610: AGarten: I changed days from 5 to 3 because this approval should come from Leah before our SOS submittal work begins.
Note on C618: AGarten: Change hyperlink to http://www.oregon.gov/deq/RulesandRegulations/Pages/proposedrule.aspx
Note on C624: AGarten: Change hyperlink to \\deqhq1\Rule_Development\Currrent Plan
Note on B630: AGarten: Currently, GovDelivery performed by one person for all of AQ. Not sure the subject expert should perform GovDelivery. Training issue.
Note on C636: AGarten: Change hyperlink to
Note on AH637: AGarten: I changed -2days to -5days to allow adequate time for review
Note on AH642: AGarten: I changed this formula. It needs to be the date we open the comment period, not IF(AF642=0,,WORKDAY(S.Notice.OpenComment,-2,S.DDL_DEQClosed))
Note on B699: AGarten: Change from "ALL REVIEWS ARE COMPLETE" to "staff report is finalized"
Note on C700: AGarten: fix typo
Note on B716: AGarten: The dates in this section need more work. It needs to be clear when the staff report is due to the director's office, and the reviewer periods should auto populate based on that deadline or the close of comment deadline
Note on B727: AGarten: This is a change from current practice. Do we want the subject expert to do this instead of the rule lead?
Note on B747: AGarten: what does this mean?
Note on G755: AGarten: these dates need work
Note on AH760: AGarten: delete
Note on AG761: AGarten: Change from =WORKDAY(H755,2,S.DDL_DEQClosed) to =S.EQC.BANNER.Begin
Note on AH761: AGarten: Changed from =WORKDAY(G761+2,1,S.DDL_DEQClosed) to =S.EQC.SubmitStaffRpt
DEQ Closed

## ConditionalFormat (hidden)
|  | Example | Calculation | Applies to | Last row
Column I: Section Separator codes
T | Section title | White on Teal | =IF($AAE4="T",TRUE) | =$B$4:$ZZ$474
Y | Highlight for section title | Teal on Yellow | =IF($AAE4="Y",TRUE) | "
W |  | White on white | =IF($AAE4="W",TRUE) | "
0 OR 1 | Indicates task involved/not involved | White on white | =IF($AAE4=0,TRUE) | "
Office Closure |  | See DDL worksheet | S.DDL_DEQClosed is the "holiday" table in WORKDAY function
|  | Office Closure date | =IF(WORKDAY($G20-1,1,S.DDL_DEQClosed)<>$G20,TRUE) | $G$20:$G$480 (or last row)
|  | Office Closure date | =IF(WORKDAY($H20-1,1,S.DDL_DEQClosed)<>$H20,TRUE) | $H$20:$H$480 (or last row)
|  | Date has past | =IF(WORKDAY($G10-1,1,S.DDL_DEQClosed)<>$G10,TRUE) | $G$10:$G$480 (or last row)
|  | " | =IF(WORKDAY($H10-1,1,S.DDL_DEQClosed)<>$H10,TRUE) | $H$10:$H$480 (or last row)
Gantt
| An 'X' in $J10 identifies the row as for Gantt to format | Workday | =AND($J10<>"X",$G10<=L$7,$H10>=K$7) | $K10:$AHC$450
|  | Weekend | =IF(OR(WEEKDAY(K$7)=1,WEEKDAY(K$7)=7),TRUE) | $K10:$AHC$450
|  | Closed | =IF(ISERROR(VLOOKUP(K$7,S.DDL_DEQClosed,1,FALSE)),0,1) | $K10:$AHC$450
S.LastCellGantt
s.LastCellschedule

## AddToPlan (hidden)
How a Division Administrator adds a new proposal to the rolling rulemaking plan
| Start | Notify | Train | Draft | Approve | Prepare | Inform
Program è | Identify need * legislation, court order, federal requirements, fees, easier to do business * DEQ intitiated through environmental soultions | If approved to develop concept for inclusion on DEQ Rulemaking Plan | SharePoint, Rule_Development, CONSIDERATIONS & RESOURCES, records management | CONSIDERATIONS, RESOURCES, Overview of Key Dates | Concept for inclusion on DEQ Rulemaking Plan | If division approves adding concept to DEQ Rulemaking Plan | Focusing on communication materials
| ê |  | 2 hours | 8 hours
|  |  |  | Team Collaboration |  | Team Collaboration
Lead staff |  |  | Attend, learn, share | Complete 1st workbook drafts using what you know now |  | Prepare DA communication to EMT/EQC assistant
Lead manager | Discuss need with DA and program managers | Assign staff to work with DRC/ARC on concept development | Attend, learn, share | Add information you know | Present RESOURCES & CONSIDERATIONS summary to DA & program managers | Help prepare and approve DA communication
Rules coordinators (DRC, ARC) |  | ARC Establish SharePoint, Rule_Development sites schedule training | Facilitate, learn, share | Provided guidance and review |  | ARC Add to plan. Prepare summary pdf for DA communication
Division administrator (DA) | Approve initial work to develop concept - discuss potential with EMT | Notify DRC and ARC |  |  | Approve/reject concept addition to plan. Inform lead staff, DRC, ARC |  | EMT/EQC Assistant using communication materials adapted to personal style
EMT | Offer initial ideas about connections, cautions | [5 empty] | Offer advice, indicate interest
EQC assistant | [6 empty] | Add to monthly Director's Report. Advise DRC/ARC re: EQC involvement

## AQ.CFPp2.Calendar (hidden)
Grants Pass Limited Maintenance Plans for CO and PM10 |  |  |  | GPLMP
starting |  |  |  | 2014-08-13 | [6 empty] | 2014-08-18 | [6 empty] | 2014-08-25 | [6 empty] | 2014-09-01 | [6 empty] | 2014-09-08 | [6 empty] | 2014-09-15 | [6 empty] | 2014-09-22 | [6 empty] | 2014-09-29
2014-08-13 |  |  |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Adjust start date +/- from today |  |  | 0 | - | - | 2014-08-13 | 2014-08-14 | 2014-08-15 | 2014-08-16 | 2014-08-17 | 2014-08-18 | 2014-08-19 | 2014-08-20 | 2014-08-21 | 2014-08-22 | 2014-08-23 | 2014-08-24 | 2014-08-25 | 2014-08-26 | 2014-08-27 | 2014-08-28 | 2014-08-29 | 2014-08-30 | 2014-08-31 | 2014-09-01 | 2014-09-02 | 2014-09-03 | 2014-09-04 | 2014-09-05 | 2014-09-06 | 2014-09-07 | 2014-09-08 | 2014-09-09 | 2014-09-10 | 2014-09-11 | 2014-09-12 | 2014-09-13 | 2014-09-14 | 2014-09-15 | 2014-09-16 | 2014-09-17 | 2014-09-18 | 2014-09-19 | 2014-09-20 | 2014-09-21 | 2014-09-22 | 2014-09-23 | 2014-09-24 | 2014-09-25 | 2014-09-26 | 2014-09-27 | 2014-09-28 | 2014-09-29 | 2014-09-30 | 2014-10-01 | 2014-10-02 | 2014-10-03 | 2014-10-04 | 2014-10-05
| Start | End
Add to DEQ Rulemaking Plan |  |  | 0
Establish Q-time numbers | 0 | 2014-06-30 | 1
Setup shared sites | 2014-06-30 | 2014-06-30 | 1
Kickoff worksession | 2014-06-30 | 2014-06-30 | 1
Planning Sequence |  |  | 0
Draft workbooks | 2014-06-30 | 2014-06-30 | 1
Communications Meeting | 2014-06-30 | 2014-06-30 | 1
Rules Sequence | 2014-06-30 | 2015-04-07 | 0
@ Start | 0 | 0 | 1
@ Notice | 2014-06-30 | 0 | 1
@ EQC Preparation | 0 | 0 | 1
@ Filing | 0 | 0 | 1
SIP Sequence |  |  | 1
@ Notice EPA/SIP 180 days | 2014-04-16 | 2014-04-16 | 1
@ Notice: EPA/SIP 45 days | #NAME? | #NAME? | #NAME?
@ Post EQC: Submit to EPA | 2015-03-09 | 2015-03-09 | 0
Fee Sequence |  |  | 0
@ Fee Approval: Part 1 to DAS | 0 | 0 | 1
@ Post EQC: Part 2 to DAS | 2015-01-12 | 2015-01-12 | 0
@ Notice Email DAS for exempt fees | 0 | 0 | 1
Advisory Committee Sequence |  |  | 0
Invitation | 2014-05-02 | 2014-05-02 | 1
Meeting 1 | 2014-06-05 | 2014-06-05 | 1
Meeting 2 | 2014-06-26 | 2014-06-26 | 1
Meeting 3 | 2014-07-30 | 2014-07-30 | 1
Meeting 4 | 2014-07-30 | 2014-07-30 | 1
Meeting 5 | 2014-07-30 | 2014-07-30 | 1
Involve EQC Sequence |  |  | 0
Directors Report 1 | 2014-07-01 | 2014-07-01 | 1
Directors Report 2 | 2014-07-01 | 2014-07-01 | 1
Info Item 1 | 0 | 0 | 1
Info Item 2 | 0 | 0 | 1
Notice Sequence |  |  | 0
EPA/SIP 180 days | 2014-04-16 | 2014-04-16 | 1
EPA/SIP 45 days | #NAME? | #NAME? | #NAME?
Involve DEQ RESOURCES | #REF! | #REF! | #REF!
Send Ad to contract services | 2014-10-02 | 2014-10-02 | 0
Manager approval | 2014-10-07 | 2014-10-07 | 0
Open/Close Comment | 2014-10-16 | 2014-11-21 | 0
DA briefing schedule/meeting | 2014-09-23 | 2014-09-23 | 0
Email DAS for exempt fees | 0 | 0 | 1
Preview period | 2014-09-24 | 2014-10-01 | 0
SOS Bulletin submit/publish | 2014-10-15 | 2014-11-01 | 0
Hearing: first/last | 2014-11-18 | 2014-11-18 | 0
EQC Preparation Sequence |  |  | 0
EQC Meeting | 2015-01-07 | 2015-01-07 | 0
Post EQC Sequence |  |  | 0
Filing/effective | 2015-01-09 | 2015-01-09 | 0
Part 2 to DAS | 2015-01-12 | 2015-01-12 | 0
Submit to EPA | 2015-03-09 | 2015-03-09 | 0
1
1

## GetStarted
Title | CodeName
Grants Pass Limited Maintenance Plans for CO and PM10 | GPLMP | i
Names entered under this area will become part of the Schedule of Tasks and Partnershup Agreement
| Enter first name for Schedule | Enter full name for Agreement | Division | Program | Pronoun
Subject Expert | Brian | Brian Finneran | OP | Air Quality Planning | her
Sponsoring Partner | DavidC | David Collier | OP | Air Quality Planning | her
Sponsoring Partner's Manager | Uri | Uri Papish | OP | Air Quality Deputy Administrator | his
Rules Group Partner | AndreaG | Andrea Gartenbaum | OP | Agency Rules | her
Standardization (ARC) | Maggie
Public Affairs Representative | BrianW
EQC Assistant | StephanieC |  |  | GET STARTED
State Implementation Plan Coordinator | AndreaG |  |  | Enter names and codes on this worksheet
Web Master | Michele
FiscalReviewer | Maggie |  |  | ON SCHEDULE
Budget analyst | MargaretO |  |  | Enter Title in header
Assistant Attorney General | PaulG |  |  | Enter start date in G6
Legislative liaison | MargaretO |  |  | When Directors adds to plan, enter date in G9
Support staff | Brian | <<<<< If support staff is not available, include Lead staff's name |  | Select Y/N options in C9:C50
Time Accounting | RobertB |  |  | All banner dates set on Overview of Key dates
Director | Dick |  |  | Drop down lists
Hearings Officer | HearingOfficer |  |  | EQC optional involvement G39:H41
Division Administrator - Rules | Lydia |  |  | SOS Bulletin H31
Division Administrator - Program | Wendy |  |  | EQC meeting H44
DA Assistant | Carol
Chief Public Affairs Officer | N/A
Media Manager
Jennifer | WQ
Wendy | LQ
Uri | AQ
Budget Analyst
AdamC | WQ
SandraM | LQ
MargaretO | AQ
Legislative Liason
KarenT | WQ
TomR | LQ
MargaretO | AQ

## HearingAndAdDates (hidden)
Grants Pass Limited Maintenance Plans for CO and PM10 |  |  |  | 2014-08-13
Hearings
|  |  | Hearings Officer | Notes
City | Date | Time
Grants Pass | 2014-11-18 | 6 p.m. | 6 p.m.
-blank - | -blank - | -blank - | -blank -
-blank - | -blank - | -blank - | -blank -
-blank - | -blank - | -blank - | -blank -
-blank - | -blank - | -blank - | -blank -
-blank - | -blank - | -blank - | -blank -
-blank - | -blank - | -blank - | -blank -
-blank - | -blank - | -blank - | -blank -
Newspaper Advertisements
NOTICE.AD1Oregonian | 2014-10-16
NOTICE.AD2Other | 2014-10-16
NOTICE.AD3None | 2014-10-16
NOTICE.AD4None | 2014-10-16
NOTICE.AD5None | 2014-10-16
NOTICE.AD6None | 2014-10-16
NOTICE.AD7None | 2014-10-16
NOTICE.AD8None | 2014-10-16

## DDLs
DDLs called from ScheduleTasks
1 | 2 | 3 | 4 | 5 | 6
DDL_EQCMeeting | EQCStaffRptDue | EQCMaterialsDue | Days to next | Next | Last
2013-03-20 | 2013-02-11 | 2013-03-13 | 91 | 2013-06-19 | 2012-12-16 | When updating EQC table, leave rows for previous year.
2013-06-19 | 2013-05-10 | 2013-06-12 | 63 | 2013-08-21 | 2013-03-20
2013-08-21 | 2013-07-16 | 2013-08-14 | 56 | 2013-10-16 | 2013-06-19
2013-10-16 | 2013-09-10 | 2013-10-09 | 56 | 2013-12-11 | 2013-08-21
2013-12-11 | 2013-11-01 | 2013-12-04 | 99 | 2014-03-20 | 2013-10-16
2014-03-20 | 2014-02-13 | 2014-02-24 | 293 | 2015-01-07 | 2012-12-16 |  | 2014-01-24
2014-06-18 | 2014-05-12 | 2014-05-26 | 70 | 2014-08-27 | 2013-08-29 |  | 2014-03-20
2014-08-27 | 2014-07-24 | 2014-08-04 | 70 | 2014-11-05 | 2014-06-18 |  | 2014-06-18
2014-11-05 | 2014-09-29 | 2014-10-13 | 63 | 2015-01-07 | 2014-08-27 |  | 2014-08-20
2015-01-07 | 2014-12-02 | 2014-12-10 | 67 | 2015-03-15 | 2014-11-05 |  | 2014-10-22
2015-03-15 | 2015-02-02 | 2015-03-05 | 94 | 2015-06-17 | 2015-01-07 |  | 2014-12-17
2015-06-17 | 2015-05-07 | 2015-06-05 | 63 | 2015-08-19 | 2015-03-15 |  | 2015-03-18
2015-08-19 | 2015-07-09 | 2015-08-07 | 63 | 2015-10-21 | 2015-06-17 |  | 2015-06-17
2015-10-21 | 2015-09-10 | 2015-10-09 | 56 | 2015-12-16 | 2015-08-19 |  | 2015-08-19
2015-12-16 | 2015-11-05 | 2015-12-04 | 98 | 2016-03-23 | 2015-10-21 |  | 2015-10-21
2016-03-23 | 2016-02-11 | 2016-03-11 | 91 | 2016-06-22 | 2015-12-16 |  | 2015-12-16
2016-06-22 | 2016-05-12 | 2016-06-10 | 56 | 2016-08-17 | 2016-03-23 |  | 2016-03-23
2016-08-17 | 2016-07-07 | 2016-08-05 | 63 | 2016-10-19 | 2016-06-22 |  | 2016-06-22
2016-10-19 | 2016-09-08 | 2016-10-07 | 63 | 2016-12-21 | 2016-08-17
2016-12-21 | 2016-11-10 | 2016-12-09 | 91 | 2017-03-22 | 2016-10-19
2017-03-22 | 2017-02-09 | 2017-03-10 | 91 | 2017-06-21 | 2016-12-21
2017-06-21 | 2017-05-11 | 2017-06-09 | 91
http://www.leg.state.or.us/ors/187.html
DEQClosed | [7 empty] | LEGAL HOLIDAYS 187.010 Legal holidays; acts deferred to next business day; effect on labor agreements. (1) The following days are legal holidays in this state: (a) Each Sunday. (b) New Year’s Day on January 1. (c) Martin Luther King, Jr.’s Birthday on the third Monday in January. (d) Presidents Day, for the purpose of commemorating Presidents Washington and Lincoln, on the third Monday in February. (e) Memorial Day on the last Monday in May. (f) Independence Day on July 4. (g) Labor Day on the first Monday in September. (h) Veterans Day on November 11. (i) Thanksgiving Day on the fourth Thursday in November. (j) Christmas Day on December 25. (2) Each time a holiday, other than Sunday, listed in subsection (1) of this section falls on Sunday, the succeeding Monday shall be a legal holiday. Each time a holiday listed in subsection (1) of this section falls on Saturday, the preceding Friday shall be a legal holiday. (3) Any act authorized, required or permitted to be performed on a holiday as designated in this section may be performed on the next succeeding business day; and no liability or loss of rights of any kind shall result from such delay. (4) In enumerating legal holidays in subsection (1) of this section, the Legislative Assembly does not intend to limit or otherwise affect public or private collective bargaining or collective bargaining agreements. [Amended by 1955 c.4 §1; 1969 c.455 §1; 1973 c.51 §1; 1975 c.633 §1; 1977 c.135 §1; 1977 c.321 §1; 1985 c.518 §1] 187.020 Additional legal holidays. In addition to those specified in ORS 187.010, the following days are legal holidays in this state: (1) Every day appointed by the Governor as a holiday. (2) Every day appointed by the President of the United States as a day of mourning, rejoicing or other special observance only when the Governor also appoints that day as a holiday. [Amended by 1969 c.455 §2; 1975 c.633 §2; 1977 c.135 §2; 1977 c.321 §2; 1985 c.518 §2]
2013-01-01 | New Year | 2013-01-01
2013-01-18 | furlough | 2013-01-18
2013-01-21 | MLK Jr. | 2013-01-21
2013-02-18 | Presidents | 2013-02-18
2013-04-19 | furlough | 2013-04-19
2013-05-24 | furlough | 2013-05-24
2013-05-27 | Memorial | 2013-05-27
2013-07-04 | Independence | 2013-07-04
2013-09-02 | Labor | 2013-09-02
2013-11-11 | Veterans | 2013-11-11
2013-11-28 | Thanksgiving | 2013-11-28
2013-12-25 | Christmas | 2013-12-25
2014-01-01 | New Year | 2014-01-01
2014-01-20 | MLK Jr. | 2014-01-20
2014-02-17 | Presidents | 2014-02-17
2014-05-26 | Memorial | 2014-05-26
2014-07-04 | Independence | 2014-07-04
2014-09-02 | Labor | 2014-09-02
2014-11-11 | Veterans | 2014-11-11
2014-11-27 | Thanksgiving | 2014-11-27
2014-12-25 | Christmas | 2014-12-25
2015-01-01 | New Year | 2015-01-01
2015-01-19 | MLK Jr. | 2015-01-19
2015-02-16 | Presidents | 2015-02-16
2015-05-25 | Memorial | 2015-05-25
2015-07-03 | Independence | 2015-07-03
2015-09-07 | Labor | 2015-09-07
2015-11-11 | Veterans | 2015-11-11
2015-11-26 | Thanksgiving | 2015-11-26
2015-12-25 | Christmas | 2015-12-25
2016-01-01 | New Year | 2016-01-01
2016-01-18 | MLK Jr. | 2016-01-18
2016-02-15 | Presidents | 2016-02-15
2016-05-30 | Memorial | 2016-05-30
2016-07-04 | Independence | 2016-07-04
2016-09-05 | Labor | 2016-09-05
2016-11-11 | Veterans | 2016-11-11
2016-11-24 | Thanksgiving | 2016-11-24
2016-12-26 | Christmas | 2016-12-26
2017-01-02 | New Year | 2017-01-02
2017-01-16 | MLK Jr. | 2017-01-16
2017-02-20 | Presidents | 2017-02-20
2017-05-29 | Memorial | 2017-05-29
2017-07-04 | Independence | 2017-07-04
2017-09-04 | Labor | 2017-09-04
2017-11-10 | Veterans | 2017-11-10
2017-11-23 | Thanksgiving | 2017-11-23
2017-12-25 | Christmas | 2017-12-25
2018-01-01 | New Year | 2018-01-01
Called from ScheduleTasks
DDL_Bulletin | VL_Bulletin
2013-01-01 | 2012-12-14 | 2012-12-14
2013-02-01 | 2013-01-15 | 2013-01-15
2013-03-01 | 2013-02-15 | 2013-02-15
2013-04-01 | 2013-03-15 | 2013-03-15
2013-05-01 | 2013-04-15 | 2013-04-15
2013-06-01 | 2013-05-15 | 2013-05-15
2013-07-01 | 2013-06-14 | 2013-06-14
2013-08-01 | 2013-07-15 | 2013-07-15
2013-09-01 | 2013-08-15 | 2013-08-15
2013-10-01 | 2013-09-13 | 2013-09-13
2013-11-01 | 2013-10-15 | 2013-10-15
2013-12-01 | 2013-11-15 | 2013-11-15
2014-01-01 | 2013-12-13 | 2013-12-13
2014-02-01 | 2014-01-15 | 2014-01-15
2014-03-01 | 2014-02-14 | 2014-02-14
2014-04-01 | 2014-03-14 | 2014-03-14
2014-05-01 | 2014-04-15 | 2014-04-15
2014-06-01 | 2014-05-15 | 2014-05-15
2014-07-01 | 2014-06-13 | 2014-06-13
2014-08-01 | 2014-07-15 | 2014-07-15
2014-09-01 | 2014-08-15 | 2014-08-15
2014-10-01 | 2014-09-15 | 2014-09-15
2014-11-01 | 2014-10-15 | 2014-10-15
2014-12-01 | 2014-11-14 | 2014-11-14
2015-01-01 | 2014-12-15 | 2014-12-15
2015-02-01 | 2015-01-15 | 2015-01-15
2015-03-01 | 2015-02-13 | 2015-02-13
2015-04-01 | 2015-03-13 | 2015-03-13
2015-05-01 | 2015-04-15 | 2015-04-15
2015-06-01 | 2015-05-15 | 2015-05-15
2015-07-01 | 2015-06-15 | 2015-06-15
2015-08-01 | 2015-07-15 | 2015-07-15
2015-09-01 | 2015-08-15 | 2015-08-15
2015-10-01 | 2015-09-15 | 2015-09-15
2015-11-01 | 2015-10-15 | 2015-10-15
2015-12-01 | 2015-11-13 | 2015-11-13
2016-01-01 | 2015-12-15 | 2015-12-15
2016-02-01 | 2016-01-15 | 2016-01-15
2016-03-01 | 2016-02-15 | 2016-02-15
2016-04-01 | 2016-03-15 | 2016-03-15
2016-05-01 | 2016-04-15 | 2016-04-15
2016-06-01 | 2016-05-13 | 2016-05-13
2016-07-01 | 2016-06-15 | 2016-06-15
2016-08-01 | 2016-07-15 | 2016-07-15
2016-09-01 | 2016-08-15 | 2016-08-15
2016-10-01 | 2016-09-15 | 2016-09-15
2016-11-01 | 2016-10-14 | 2016-10-14
2016-12-01 | 2016-11-15 | 2016-11-15
2017-01-01 | 2016-12-15 | 2016-12-15
2017-02-01 | 2017-01-13 | 2017-01-13
2017-03-01 | 2017-02-15 | 2017-02-15
2017-04-01 | 2017-03-15 | 2017-03-15
2017-05-01 | 2017-04-14 | 2017-04-14
2017-06-01 | 2017-05-15 | 2017-05-15
2017-07-01 | 2017-06-15 | 2017-06-15
2017-08-01 | 2017-07-14 | 2017-07-14
2017-09-01 | 2017-08-15 | 2017-08-15
2017-10-01 | 2017-09-15 | 2017-09-15
2017-11-01 | 2017-10-13 | 2017-10-13
2017-12-01 | 2017-11-15 | 2017-11-15
2018-01-01 | 2017-12-15 | 2017-12-15
2018-02-01 | 2018-01-15 | 2018-01-15
2018-03-01 | 2018-02-15 | 2018-02-15
2018-04-01 | 2018-03-14 | 2018-03-14
2018-05-01 | 2018-04-13 | 2018-04-13
2018-06-01 | 2018-05-15 | 2018-05-15
2018-07-01 | 2018-06-15 | 2018-06-15
2018-08-01 | 2018-07-13 | 2018-07-13
2018-09-01 | 2018-08-15 | 2018-08-15
2018-10-01 | 2018-09-14 | 2018-09-14
2018-11-01 | 2018-10-15 | 2018-10-15
2018-12-01 | 2018-11-15 | 2018-11-15
2019-01-01 | 2018-12-14 | 2018-12-14
2019-02-01 | 2019-01-15 | 2019-01-15
2019-03-01 | 2019-02-15 | 2019-02-15
2019-04-01 | 2019-03-15 | 2019-03-15
2019-05-01 | 2019-04-15 | 2019-04-15
2019-06-01 | 2019-05-15 | 2019-05-15
2019-07-01 | 2019-06-14 | 2019-06-14
2019-08-01 | 2019-07-15 | 2019-07-15
2019-09-01 | 2019-08-15 | 2019-08-15
2019-10-01 | 2019-09-13 | 2019-09-13
2019-11-01 | 2019-10-15 | 2019-10-15
2019-12-01 | 2019-11-15 | 2019-11-15
2020-01-01 | 2019-12-13 | 2019-12-13
2020-02-01 | 2020-01-15 | 2020-01-15
2020-03-01 | 2020-02-14 | 2020-02-14
2020-04-01 | 2020-03-13 | 2020-03-13
2020-05-01 | 2020-04-15 | 2020-04-15
2020-06-01 | 2020-05-15 | 2020-05-15
2020-07-01 | 2020-06-15 | 2020-06-15
2020-08-01 | 2020-07-15 | 2020-07-15
2020-09-01 | 2020-08-14 | 2020-08-14
2020-10-01 | 2020-09-15 | 2020-09-15
2020-11-01 | 2020-10-15 | 2020-10-15
2020-12-01 | 2020-11-13 | 2020-11-13
2021-01-01 | 2020-12-15 | 2020-12-15
2021-02-01 | 2021-01-15 | 2021-01-15
2021-03-01 | 2021-02-15 | 2021-02-15
2021-04-01 | 2021-03-15 | 2021-03-15
2021-05-01 | 2021-04-15 | 2021-04-15
2021-06-01 | 2021-05-14 | 2021-05-14
2021-07-01 | 2021-06-15 | 2021-06-15
2021-08-01 | 2021-07-15 | 2021-07-15
2021-09-01 | 2021-08-13 | 2021-08-13
2021-10-01 | 2021-09-15 | 2021-09-15
2021-11-01 | 2021-10-15 | 2021-10-15
2021-12-01 | 2021-11-15 | 2021-11-15
Called from ScheduleTasks
| Newapapers | EQC Facilitated Hearing
Oregonian
EastOregon
RegisterGuard
MailTribune
KlamathHerald
LaGrandeObserver
JournalOfCommerce
None
Other
Formulas:
Next = [DDL_EQCMeeting]+[Days to next]
Last = [DDL_EQCMeeting]-[Days to next, row above]
EQCStaffRptDue = WORKDAY([DDL_EQCMeeting]-40,-1,S.DDL_DEQClosed)
EQCMaterialsDue = WORKDAY([DDL_EQCMeeting]-9,-1,S.DDL_DEQClosed)
EQCMaterialsDue = [DDL_EQCMeeting]

## PartnershipAgreement (hidden)
INTERIM RULEMAKING PARTNERSHIP AGREEMENT
Grants Pass Limited Maintenance Plans for CO and PM10
Code: GPLMP
Description
Enter short description from CONSIDERATIONS
Objectives
Enter objectives from CONSIDERATIONS
Assumptions and Contraints
Enter assumption and contraints identified in CONSIDERATIONS
Managing Partners
Changes to this agreement require the approval and signature of both Partners. A change in scope and missed deadlines may result in re-prioritizing this rulemaking.
| Sponsoring Partner | David Collier, OP: Air Quality Planning
| Subject Expert | Brian Finneran, OP: Air Quality Planning
| Rules Group Partner | Andrea Gartenbaum, OP: Agency Rules
Deliverables
Activity Sequence – Add to DEQ Rulemaking Plan
Deadline | Responsibility for Meeting Deadline | Deliverable | Purpose | Recipiant | Done
2014-06-30 | Rules Group Partner: Andrea Gartenbaum | Shared drive Draft workbooks | Worksession | David Collier | N
2014-06-30 | Sponsoring Partner: David Collier | Draft workbooks CONSIDERATIONS RESOURCES | Input | Uri Papish and AndreaG | N
2014-06-30 | Sponsoring Partner's Manager: Uri | Draft workbooks with edits CONSIDERATIONS RESOURCES | Input | DavidC and AndreaG | N
| Rules Group Partner: AndreaG | Updated Rulemaking Projects Priorities list | Determine capacity Prioritize rulemakings Validate with DavidC | Rules Group | N
| Rules Group Partner: AndreaG | Proposed addition to DEQ Rulemaking Plan | Approve, postpone, reject | Dick | N
Activity Sequence - Planning for Director-approved rulemaking priorities
Deadline | Resonsibility for Meeting Deadline | Deliverable | Purpose | Recipient | Done
| Sponsoring Partner: DavidC | Refine workbooks Considerations Resources Schedule | Input, notification | People identified in RESOURCES workbook | N
| Sponsoring Partner: DavidC | Communications Plan | Input, advice | People identified in RESOURCES workbook | N
Activity Sequence - Notice Packet
Invitation to Comment
Notice
Proposed Rules
Supporting Documents
Deadline | Resonsibility for Meeting Deadline | Deliverable | Purpose | Recipient | Done
#REF! | Sponsoring Partner: DavidC | Draft notice & rules | Input, notification | People identified in RESOURCES workbook | N
#REF! | People identified in RESOURCES workbook | Input | Expand knowledge | DavidC | N
| Sponsoring Partner: DavidC | Draft notice & rules | Input, advice, review | AndreaG | N
| Rules Group Partner: AndreaG | Draft notice & rules | Initial review to ensure standardization, organization, preliminary review of fiscal and economic impact statement, small business analysis | DavidC | N
| Sponsoring Partner: DavidC | Notice Packet | Confirm adequacy of rulemaking materials | AndreaG | N
2014-09-24 | Sponsoring Partner: DavidC | Notice Packet Preview Email: LT, EQC Assistant, RESOURCES | Inform | Uri | N
2014-10-01 | Sponsoring Partner's Manager: Uri | Notice Packet | Review and approval | DavidC
| Division Administrator Wendy | Notice Packet with edits; Approval | Approval | DavidC
| Sponsoring Partner's Manager: Uri | Final Notice Packet | OK to publish | AndreaG
| Rules Group Partner: AndreaG | Final minor edit | Publication ready | Web staff
| Sponsoring Partner: DavidC | Confirm accuracy of published rules | Inform | AndreaG
| Sponsoring Partner: DavidC | List of hearing participants and their roles; Finalized hearing materials and presentation | Input, advice, review | #NAME?
Activity Sequence – Publication
Deadline | Responsibility for Meeting Deadline | Deliverable | Purpose | Recipient | Done
| Sponsoring Partner: DavidC | Approved Newspaper ad(s), Notification lists, Notice content (legislators email, GovDelivery and Interested Parties) | Input, advice, review | AndreaG | N
| Rules Group Partner: AndreaG | Activate Web page, Online comment form. Submit Newspaper ad, SOS Notice, Notification Lists, DAS | Publication | Carol, Legislative staff and Web staff | N
Activity Sequence – EQC Packet
Staff Report
Proposed Rules
Deadline | Responsibility for Meeting Deadline | Deliverable | Purpose | Recipient | Done
| Sponsoring Partner: DavidC | EQC Packet | Input, notification | People identified in RESOURCES workbook | N
| Rules Group Partner: AndreaG | EQC Packet | Input, advice, review | DavidC | N
| EPA, DOJ | EQC Packet | Review as needed | DavidC | N
| Sponsoring Partner: DavidC | EQC Packet - finalized | Review and approval | Uri | N
| Division Administrator: Wendy | EQC Packet with edits, Approval | Approval | DavidC | N
| Sponsoring Partner: DavidC | Final EQC Packet | OK to publish | AndreaG | N
| Rules Group Partner: AndreaG | Final minor edit | EQC ready | StephanieC | N
Activity Sequence – EQC Presentation
Deadline | Responsibility for Meeting Deadline | Deliverable | Purpose | Send to | Done
| Sponsoring Partner: DavidC | List of EQC presenters, their roles and responsibilities; Final EQC Presentation | Input, advice, review | AndreaG | N
| Rules Group Partner: AndreaG | Presentation with minor edit | EQC ready | StephanieC | N
| Rules Group Partner: AndreaG | Update Web page, Online comment form. SOS Filing, DAS, Legislative Counsel | Rules become effective | SOS; Legislative Counsel; DAS | N
Activity Sequence – Rulemaking Record
Deadline | Responsibility for Meeting Deadline | Deliverable | Purpose | Send to | Done
| Sponsoring Partner: DavidC | Confirm accuracy of published rules Submit supporting documents for record | Inform | AndreaG | N
| Rules Group Partner: AndreaG | Archive records; Retire SharePoint; Close Outlook account; Update Web page | Complete rulemaking |  | N
Activity Sequence - Rule Development
Deadline | Resonsibility for Meeting Deadline | Deliverable | Purpose | Send to | Done
Sponsoring Manager
David Collier, OP: Air Quality Planning DATE
Rules Group Partner
Andrea Gartenbaum, OP: Agency Rules DATE

## OwnConsultInform (hidden)
Owns program and regulatory content
Manages subject expert
Identifies and remedies training gaps in basic skills for subject expert (e.g. MS Office products, project management, research techniques, written and oral communication, presentation skills, and SharePoint)
Maintains pristine rules in redline/strikeout
Responsible for achieving program intent and requirements (e.g. federal requirements for program delegation)
Responsible for high quality research and analysis by the program
Responsible for high quality and timeliness of program deliverables
Owns best practices
Assists sponsoring manager in finding expertise
Trains subject expert on rulemaking knowledge
Advises subject expert on rulemaking best practices, including advisory committees and fiscal analysis
Guides subject expert through all work products
Develops DEQ’s message with subject expert (e.g. Plain English, Style Guide, Tone, Clarity, OR Rulemaking requirements, DEQ best practices, web presence)
Performs fiscal review
Facilitates input by Communications staff and Legislative staff
Determines adequacy of rulemaking materials
Responsible for adhering rulemaking to best practices
Responsible for meeting regulatory requirements for rulemaking