## 2013 Plan Schedule (hidden)
DEQ Rulemaking |  |  |  |  | 2026-08-05
Schedule of Tasks | [8 empty] | google
for developing the 2013 DEQ Rulemaking Plan | [8 empty] | EMT plan approval | 2012-11-08
About this worksheet
Welcome to DEQ's annual solicitation of rulemaking concepts. The schedule below identifies the tasks, the owner of the task and target dates for completing the task.
|  | Purpose | The process experts use this space to develop and communicate the schedule for developing DEQ’s annual rulemaking plan.
|  | Steps | The schedule steps through:
1. Gathering rulemaking concepts (administrator, managers.)
2. Assigning resources to draft Considerations and Resources.
3. Determining if the concept meets the section, program, divisional, regional priorities for the upcoming year.
Owners
ARC Agency rules coordinator |  |  | 4. Drafting Considerations and Resources.
DD Deputy director
EMT Executive Management Team |  |  | 5. Approving concepts presented on Considerations and Resources for inclusion on the draft rulemaking plan (administrator.)
LA Lead administrator
LM Lead manager
RC Rules coordinators |  |  | 6. Comparing all DEQ Considerations and Resources information presented on draft plan (EMT.)
Nicole Vick - AQ
Chris Clipper - WQ
Maggie Vandehey - MSD/OCE/LQ |  |  | 7. Approving DEQ resources to work on this proposals by including it on the annual DEQ Rulemaking Plan.
SE Subject expert
|  | Audience | Subject expert, lead managers and administrators, rules coordinator and executive management team
Tasks for developing plan | [6 empty] | #NAME? | #NAME? | #NAME? | #NAME?
|  |  | Workdays |  | Calendar Days |  |  |  | add least amount of time - leisurely
Task |  | Owner | Task | Today> | Task | Today> | Start | End
Kickoff DEQ's annual rulemaking plan cycle |  | DD, EMT | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Solicit rulemaking concept |  | LA, LM | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Prioritize and approve division concepts |  | LA, LM, RC | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? |  | LA
Identify/notify subject expert |  | LM | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Rough draft Considerations worksheet | > | SE | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Rough draft Resources worksheet | > | SE | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Refine rough draft - team work session |  | SE, LM, RC | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Brief lead administrator |  | SE, LM, RC | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Review |  | LA | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Loop as needed
Approve draft, notify RC |  | LA | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Check in approved workbooks |  | RC | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Notify SE, LM, ARC |  | RC | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Draft consolidated 2013 Rulemaking Plan |  | ARC | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Review and modify draft contribution |  | RC | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Consensus review of 2013 DEQ Rulemaking Plan |  | LA, LM, OCO | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Loop as needed
Submit draft 2013 plan to EMT assistant |  | ARC | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Prepare EMT presentation |  | ARC, LA | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Review draft 2013 DEQ Rulemaking Plan |  | EMT | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
EMT MEETING |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Archive concept version, move approved concept workbooks to Rule_Development and active rulmaking on SharePoint as version 1.0 |  | RC
Formulas:
Workdays = NETWORKDAYS([Start],[End],deqclosed)
Today> = NETWORKDAYS(TODAY(),[End])
Today> = [End]-TODAY()
add least amount of time - leisurely = WORKDAY([End, row above],1,deqclosed)
mm/dd/yy
Subject
Your name
Your message

## Sheet1 (hidden)
PEARSON Lisa * BAM Analysts; ROCCO Ken G
MASON Palmer; WESTBROOK Esther; ROICK Tom; GINSBURG Andy; OLIPHANT Margaret; ROYS Jim; LAWRENCE Richard; SHIN Sohng; STEVENS-SCHWENGER Joanie

## DDLs (hidden)
DDLs called from Resources
R.DDL_HighMedLow | VL_HighMedLow
does not apply | 0
very low | 2
low | 4
medium | 6
high | 8
very high | 10
Called from Resources
R.DDL_DEQResourcesInvolved | R.VL_DEQResourcesInvolved | Minimum | Max
0 hours | 0 | 0 | 0
>0 <4 hours | 1 | 0 | 4
=>4 <41 hours | 2 | 4 | 41
=>40 <81 hours | 3 | 40 | 81
=>80 <161 hours | 4 | 80 | 161
=>160 <301hours | 5 | 160 | 301
=>300 <501 hours | 6 | 300 | 501
=>500 <1001 hours | 7 | 500 | 1001
=>1000 <1501 hours | 8 | 1000 | 1501
=>1500 <2001 hours | 9 | 1500 | 2001
=>2000 hours | 10 | 2000 | ~
Called from Resources
R.DDL_DEQStaffRank
STAFF
MANAGER
ADMINISTRATOR
Called from Resources

## Summary
| DEQ Rulemaking |  | 2026-08-05
AQ permitting program updates
Summary of this workbook
1 | Project record |  | Estimated hours
2 | Risks |  | Low | High | Resource risks
3 | Core Team |  | 1624 | 2284 | Organizational | Medium | 3 | Medium
4 | Advisors |  | 84 | 203 | Capability | Low | 1 | Low
5 | Interested Staff |  | 44 | 126 | Skills and Experience | Low | 1 | Low
6 | Other Divisions |  | 0 | 0
7 | Regions |  | 648 | 1308
8 | Financial Services |  | 0 | 8
9 | Communications and Outreach |  | 4 | 61
10 | Organizational Services |  | 0 | 0 | Resources identified | 26
11 | Technical Services |  | 40 | 89
12 | Compliance and Enforcement |  | 0 | 0
13 | LEAD |  | 0 | 0
14 | Intergovernmental |  | 0 | 0
15 | Custom Participants |  | 0 | 0
| Total hours |  | 2444 | 4079
2012 DEQ avg. staff cost per hour |  |  | X $58 | X $58
| Estimated cost |  | 141752 | 236582
Note on M2: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
Resources
mm/dd/yy
Subject
Jill Inahara 06/27/12
Your message

## ExecutiveSummary (hidden)
| DEQ Rulemaking | [8 empty] | 2026-08-05
|  | Executive Summary | [6 empty] | Hyperlink to concept on SharePoint
#NAME?
| #NAME? | [19 empty] | #NAME?
Draft Scope
Brief description of rule proposal
#NAME?
| Ideal |  |  |  | Reality |  |  |  | Consequences
| What we want to happen. |  |  |  | What we are trying to change. |  |  |  | What will happen if we don't change.
| #REF! |  |  |  | #REF! |  |  |  | #REF!
Schedule | [5 empty] | legislative session
| #NAME? |  |  |  | #NAME? |  |  |  | #NAME?
| Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 |  |  |  | Q4
| #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME?
| #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME?
| #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME?
| #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME?
| #NAME? Q3: Requirements | [9 empty] | #NAME?
| #NAME? Q1: The proposed rules involve; #NAME? Q2: Involved; #NAME? Q3: New; #NAME? Q4: Expanded; #NAME? Q1: Reduced | [9 empty] | #NAME?
| #NAME? Q1: Compliance; #NAME? Q2: #REF!; #NAME? Q3: #REF!; #NAME? Q4: #REF!; #NAME? Q1: #REF! | [9 empty] | #NAME?
| #NAME? Q1: Penalties; #NAME? Q2: #REF!; #NAME? Q3: #REF!; #NAME? Q4: #REF!; #NAME? Q1: #REF! | [9 empty] | #NAME?
| #NAME? Q1: #REF!; #NAME? Q2: #REF!; #NAME? Q3: #REF!; #NAME? Q4: #REF!; #NAME? Q1: #REF! | [9 empty] | #NAME?
| Permits, certifications, licenses, registrations |  |  |  |  | #REF! | #REF! | #REF! | #REF! | Affected parties
| #NAME? Q1: Fees; #NAME? Q2: #NAME?; #NAME? Q3: #REF!; #NAME? Q4: #REF!; #NAME? Q1: #REF! |  |  |  |  | Previously unregulated
| #NAME? Q1: An advisory committee; #NAME? Q2: #NAME?; #NAME? Q3: Affected | [9 empty] | #NAME?
| #NAME? Q1: State Implemenation Plan; #NAME? Q2: #NAME?; #NAME? Q4: #REF!; #NAME? Q3: #REF! |  |  |  |  | #REF!
| #NAME? Q1: Land use rules; #NAME? Q2: #NAME?; #NAME? Q4: #REF!; #NAME? Q3: #REF! |  |  |  |  | #REF! |  |  |  |  | #NAME?
| #NAME? Q1: Public notice; #NAME? Q2: #NAME?; #NAME? Q4: #REF!; #NAME? Q3: #REF! |  |  |  |  | #REF!
| #NAME? Q1: Hearings; #NAME? Q2: #NAME?; #NAME? Q4: #REF!; #NAME? Q3: #REF! |  |  |  |  | #REF! |  |  |  |  | #NAME?
| #NAME? Q4: #REF!; #NAME? Q3: #REF! |  |  |  |  | #REF!
| Stakeholder risks | [9 empty] | low → high
| People involved |  |  |  | #REF! |  |  | Estimated interest |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | #REF! | #REF! | #REF!
| Complexity |  |  |  | #REF! | [16 empty] | #REF! | #REF!
| Draft Resources | [6 empty] | Draft Considerations
| Through the resources worksheet, the rule design team starts identifying rulemaking and implementation resources, drafting tasks and estimating hours. | [6 empty] | Through the considerations worksheet, the rule design team starts documenting aspects of the project to consider. The team identifies risks associated with the consideration in the categories below. These risks can help determine what DEQ skills are needed for a successful outcome, the right stakeholder involvement and should be discussed in the communications plan.
Resource risks
| Organizational |  |  |  | #NAME?
| Capability |  |  |  | #NAME? | [15 empty] | #NAME? | #NAME?
| Skills and Experience |  |  |  | #NAME? | [15 empty] | #NAME? | #NAME?
[21 empty] | #NAME? | #NAME?
Range in hours
| Group |  |  |  | Min | Max |  |  |  |  | low → high 1: Risk rating low → high | Risk | Charter | Message | Proposal
| #NAME? |  |  |  | #NAME? | #NAME? |  | 1. Program |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | #NAME? | #NAME? | #NAME? | #NAME?
| #NAME? |  |  |  | #NAME? | #NAME? |  | 2. Technology |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | #NAME? | #NAME? | #NAME? | #NAME?
| #NAME? |  |  |  | #NAME? | #NAME? |  | 3. Timing |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | #NAME? | #NAME? | #NAME? | #NAME?
| #NAME? |  |  |  | #NAME? | #NAME? |  | 4. Policy |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | #NAME? | #NAME? | #NAME? | #NAME?
| #NAME? |  |  |  | #NAME? | #NAME? |  | 5. Environmental |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | #NAME? | #NAME? | #NAME? | #NAME?
| #NAME? |  |  |  | #NAME? | #NAME? |  | 6. Fiscal |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | #NAME? | #NAME? | #NAME? | #NAME?
| #NAME? |  |  |  | #NAME? | #NAME? |  | 7. Legal |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | #NAME? | #NAME? | #NAME? | #NAME?
| #NAME? |  |  |  | #NAME? | #NAME? |  | 8. Political |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | #NAME? | #NAME? | #NAME? | #NAME?
| #NAME? |  |  |  | #NAME? | #NAME? |  | 9. Implementation |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | #NAME? | #NAME? | #NAME? | #NAME?
| #NAME? |  |  |  | #NAME? | #NAME?
| #NAME? |  |  |  | #NAME? | #NAME?
| #NAME? |  |  |  | #NAME? | #NAME?
| Total estimated hours between |  |  |  | #NAME? | #NAME?
@ 2012 average DEQ rate of $58/hr
[5 empty] | #NAME? | #NAME?
Note on Y4: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
6/1/2012
About the summary
Agency Rules Coordinator
The Considerations and Resources worksheets populate this Executive Summary. Make any modifications on those worksheets.
The audience for this summary is ultimately the Executive Management Team.

## 1ProjectRecord
⧀ Go to Content
| 1 | Project record |  | AQ permitting program updates | 2012 - Average DEQ hourly cost | 58
|  | Project name |  | AQ permitting program updates
Go to Q-Time |  | Q-time for devloping this plan |  | 43063: 2013 Rulemaking: AQ Permitting Updates
|  | Q-time for NAME PURPOSE |  | #####: RM-AaaaAaaa-2013
|  | Q-time for NAME PURPOSE |  | #####: RM-AaaaAaaa-2013
|  | Q-time for NAME PURPOSE |  | #####: RM-AaaaAaaa-2013
Best practices: maintaining rulemaking record
|  | Start each email Subject line with |  | RM-AQPerm
|  | Email folder |  | RM-AQPerm@deq.state.or.us
|  | Electronic record: SharePoint |  | http://deqsps/programs/rulemaking/aq/ppu/default.aspx
|  | Electronic record: Rules Development |  | \\deqhq1\Rule_Development\2013 Plan
|  | Physical record | Pre filing | Enter location of record
|  |  | Post filing | Central rulemaking file, then SOS Archives
|  | Rule design team email group |  | RM-AaaaAaaaTeam
|  | Project number (PCA) |  | P#####: RM-AaaaAaaa
|  | Advisory Committee email group |  | None
|  | Public comment email box |  | Comment-AaaaAaaa@dep.state.or.us
Please suggest process improvements to the Project record worksheet.
More instruction on this page would be helpful. Why are there so many Q-time for NAME PURPOSE's?
Note on Y3: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
mm/dd/yy
Subject
Jill Inahara - 06/28/12

## 2Risks
⧀ Go to Content
Risk Management | 2 | DEQ resource risks | AQ permitting program updates
on Q-net |  | a. Organizational |  |  |  | Days Added to schedule
|  | Limited impact on operations or staff | Some impact on operations, retraining, transfer or reassigning staff | Significant impact on operations, restructuring, potential for high profile failure | R.2aOrgRisk
3
Optional discussion
on Q-net |  | b. Capability |  |  |  | Days Added to schedule
|  | Program/DEQ has extensive experience with previous comparable outputs | Program/DEQ has experience with comparable projects but this project has new complexities | No previous experience with this type of proposal | R.2bOrgRisk
1
Optional discussion
on Q-net |  | c. Skills and experience |  |  |  | Days Added to schedule
|  | Fully resourced, skilled management and team, no recruitment or specialist training | Key skills and experience in place but recruitment or training required | Key skills or experience not in place, recruitment or extensive training required | R.2cOrgRisk
1
Optional discussion
Please suggest process improvements to the DEQ resource risks worksheet.
Go to Top
mm/dd/yy
Subject
Your name
Your message
6/21/12
What we envision
Agency Rules Group
The rules group:
• Hopes this worksheet will help you to start thinking about potential resource risks.
• Anticipates this workbook will evolve as we get input from the teams and decision makers.
• Plans to update the template for this workbook once a year after considering information entered into the yellow “improvement” boxes and any messages that point to them. See the example below.
Low
Medium
High
Low
Medium
High
Low
Medium
High

## 3CoreTeam
⧀ Go to Content
| 3 | Core Team | AQ permitting program updates | [10 empty] | R.3StaffCount | R.3LowHrs | R.3HighHrs
[11 empty] | Estimated range |  |  | 4 | 1624 | 2284
|  | Number of staff involved | 4 | Hours | [6 empty] | 1,624-2,284 |  |  | 1,624-2,284 | R.3LowDollars | R.3HighDollars
|  | DEQ 2012 average hourly $ | 58 | Staff cost | [6 empty] | $94,192-132,472 |  |  | $94,192-132,472 | 94192 | 132472
MESSAGE
Do we need an advisory committee or do we use existing Round Table? Need to meet requirements of public meetings laws when they apply and not. See C3Stakeholders U10. Need to confirm how Trainee will charge time and if approved.
Subject Expert (SE)
Role and Responsibilities
The subject expert works with the lead manager and rules coordinator (team) to develop the concept in the Considerations and Resources workbooks by: • Working with the rules coordinator to meet shared responsibilities listed under Rule Coordinator section below • Developing the rough draft using what she or he: - Knows now, or - Can readily find out • Participating in the team work session to refine the draft • Participating in briefing the lead administrator • Reconciling the lead administrator’s comments with the draft workbooks
|  | Name | Select hours | Workload indicator
|  | Jill Inahara | =>1500 <2001 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 9 | 1500 | 2001
Lead Manager
Role and Responsibilities
The lead manager is a contributing member on the team who will be: • Consulting with the lead administrator and approving the initial work on the Considerations and Resources workbooks • Notifying the subject expert to develop the workbooks in rough draft • Stopping/delaying work if the rough draft is out of sync with current section or program priorities • Raising potential issues to the lead administrator • Participating in team work sessions to refine the workbooks • Reviewing and approving the release of the workbooks to the lead administrator • Participating in briefing the lead administrator • Reviews the 2013 DEQ Rulemaking Plan to ensure concept accuracy • Participates in the EMT’s 2013 DEQ Annual Plan review
|  | Name | Select hours | Workload indicator 1: Workload indicator
|  | Tom Roick/Uri Papish | =>80 <161 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 4 | 80 | 161
on Q-net |  | Lead Administrator
Role and Responsibilities
The lead administrator: • In consultation with the lead manager, approves initial work on the Considerations and Resources worksheets. • Ensures the program manager and the team has adequate and appropriate resources • Advises the team as needed • Reviews, approves, denies or delays concept for consistency with cross-program and divisional priorities • Leads the EMT presentation for this concept during the plan review
|  | Name | Select hours | Workload indicator 1: Workload indicator
|  | Andy Ginsburg | =>40 <81 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 3 | 40 | 81
on Q-net |  | Rules Coordinator
Role and Responsibilities
The rules coordinator is the expert on the rulemaking process. The RC is responsible for helping the subject expert in: • Developing and maintaining the: - Blueprint and SharePoint site - Schedule • Engaging DEQ resources • Reviewing all written materials and editing for: - plain English - DEQ Style Guide • Ensuring that each plan has all required reviews and approvals before: - Submitting to the regional or division administrator - Checking in workbooks for adding to the consolidated DEQ plan
|  | Name | Select hours | Workload indicator 1: Workload indicator
|  | Nicole Vick | =>4 <41 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 2 | 4 | 41
Project Assistant
Role and Responsibilities
The Project Assistant is responsible for helping the rulemaking team in: • Helping team maintain advisory committee list, minutes and agendas • Scheduling meeting rooms and equipment • Managing iLinc, conference call-in numbers, mailings and GovDelivery • Working with team to maintain physical and electronic records
|  | Name | Select hours | Workload indicator 1: Workload indicator
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 0 | 0 | 0
Facilitator
Role and Responsibilities
Helps team maintain advisory committee list, minutes and agendas. Schedules meeting rooms and equipment. Responsible for iLinc, conference call-in numbers, mailings and GovDelivery. Works with team to maintain physical and electronic records.
|  | Name | Select hours | Workload indicator 1: Workload indicator
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 0 | 0 | 0
Custom Role
Role and Responsibilities
|  | Name | Select hours | Workload indicator 1: Workload indicator
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 0 | 0 | 0
Please suggest process improvements to the Core Team worksheet.
Go to Top
Note on V2: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
mm/dd/yy
Subject
Your name
Your message

## 4Advisors
⧀ Go to Content
Go to DEQ | 4 | Advisors | AQ permitting program updates | [10 empty] | R.4StaffCount | R.4LowHrs | R.4HighHrs
[11 empty] | Estimated range |  |  | 3 | 84 | 203
|  | Number of staff involved | 3 | Hours | [6 empty] | 84-203 |  |  | 84-203 | R.4LowDollars | R.4HighDollars
|  | DEQ 2012 average hourly $ | 58 | Staff cost | [6 empty] | $4,872-11,774 |  |  | $4,872-11,774 | 4872 | 11774
MESSAGE
Go to DOJ |  | DOJ
Role and Responsibilities
If needed, DOJ provides legal advice to ensure legal sufficiency, defensibility and enforceability and to determine if we are within our authority and consistent with statute.
|  | Name | Select hours | Workload indicator
|  | Paul Garrahan | =>40 <81 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 3 | 40 | 81
on SOS |  | Agency Rules Coordinator
Role and Responsibilities
ARC provides advice on DEQ best practices; ensures documents meet rulemaking procedural requirements; reviews DAS fee submittals; reviews, approves, and submits SOS notice and filing.
|  | Name | Select hours | Workload indicator 1: Workload indicator
|  | Maggie Vandehey | =>40 <81 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 3 | 40 | 81
on Q-net |  | State Implementation Plan Coordinator
Role and Responsibilities
The SIP coordinator is responsible for helping the subject expert meet federal requirements that include timelines, EPA review, public notice process, SIP numbering and submissions.
|  | Name | Select hours | Workload indicator 1: Workload indicator
|  | Nicole Vick | =>4 <41 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 2 | 4 | 41
Custom Advisor A
Role and Responsibilities
|  | Name | Select hours | Workload indicator 1: Workload indicator
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 0 | 0 | 0
Custom Advisor B
Role and Responsibilities
|  | Name | Select hours | Workload indicator 1: Workload indicator
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 0 | 0 | 0
Please suggest process improvements to the Advisors worksheet.
Go to Top
Note on V2: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
mm/dd/yy
Subject
Your name
Your message

## 5InterestedStaff
⧀ Go to Content
| 5 | Interested Staff | AQ permitting program updates | [10 empty] | R.5StaffCount | R.5LowHrs | R.5HighHrs
[11 empty] | Estimated range |  |  | 3 | 44 | 126
|  | Number of staff involved | 3 | Hours | [6 empty] | 44-126 |  |  | 44-126 | R.5LowDollars | R.5HighDollars
|  | DEQ 2012 average hourly $ | 58 | Staff cost | [6 empty] | $2,552-7,308 |  |  | $2,552-7,308 | 2552 | 7308
MESSAGE
on Q-net |  | Environmental Quality Commission
Area of interest
|  | Name | Select hours | Workload indicator
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 0 | 0 | 0
AQ Trainee
Area of interest
Training opportunity
|  | Name | Select hours | Workload indicator 1: Workload indicator
|  | Rachel Sakata | =>40 <81 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 3 | 40 | 81
Regional Manager
Area of interest
General updates
|  | Name | Select hours | Workload indicator 1: Workload indicator
|  | Linda Hayes-Gorman | >0 <4 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 1 | 0 | 4
Planning Manager
Area of interest
General updates and review
|  | Name | Select hours | Workload indicator 1: Workload indicator
|  | David Collier | =>4 <41 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 2 | 4 | 41
Interested Staff D
Area of interest
|  | Name | Select hours | Workload indicator 1: Workload indicator
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 0 | 0 | 0
Please suggest process improvements to the Interested Staff worksheet.
Examples would be helpful.
Go to Top
Note on V2: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
mm/dd/yy
Subject
Your name
Your message

## 6OtherDivisions
⧀ Go to Content
on Q-net | 6 | Other Divisions | AQ permitting program updates | [11 empty] | R.6StaffCount | R.6LowHrs | R.6HighHrs
[11 empty] | Estimated range |  |  |  | 0 | 0 | 0
|  | Number of staff involved | 0 | Hours | [6 empty] | 0 |  |  |  | 0 | R.6LowDollars | R.6HighDollars
|  | DEQ 2012 average hourly $ | 58 | Staff cost | [6 empty] | $0 |  |  |  | $0 | 0 | 0
MESSAGE
#NAME?
on Q-net |  | Land Quality
Development
|  | Name | Select hours | Workload indicator | [9 empty] | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
on Q-net |  | Water Quality
Development
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
on Q-net |  | Air Quality
Development
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
on Q-net |  | Management Service - not separately listed
Development
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Please suggest process improvements to the Other Divisions worksheet.
Go to Top
Note on V2: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
mm/dd/yy
Subject
Your name
Your message

## 7Regions
⧀ Go to Content
on Q-net | 7 | Regions | AQ permitting program updates
[11 empty] | Estimated range |  |  |  | R.7StaffCount | R.7LowHrs | R.7HighHrs
|  | Number of staff involved | 8 | Hours | [6 empty] | 648-1,308 |  |  |  | 8 | 648 | 1308
|  | DEQ 2012 average hourly $ | 58 | Staff cost | [6 empty] | $37,584-75,864 |  |  |  | 648-1,308 | R.7LowDollars | R.7HighDollars
|  | MESSAGE | [12 empty] | $37,584-75,864 | 37584 | 75864
on Q-net |  | Eastern Region
Development
Fisher & Calkins: Help with development of rules; Bailey: NSR/PSD rulemaking team and Source Sampling Manual/Continuous Monitoring Manual
|  | Name | Select hours | Workload indicator | [9 empty] | Level involved
|  | Mark Fisher (core team) | =>160 <301hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | STAFF | 5 | 160 | 301
|  | Larry Calkins | =>4 <41 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | STAFF | 2 | 4 | 41
|  | Mark Bailey | =>40 <81 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | MANAGER | 3 | 40 | 81
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
Help with writing implementation guidance
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  | Mark Fisher (core team) | =>80 <161 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | STAFF | 4 | 80 | 161
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
on Q-net |  | Western Region
Development
Help with development of rules
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  | Gary Andes/Karen White-Fallon (core team) | =>160 <301hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | STAFF | 5 | 160 | 301
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
Help with writing implementation guidance
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  | Gary Andes/Karen White-Fallon (core team) | =>4 <41 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | STAFF | 2 | 4 | 41
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
on Q-net |  | Northwest Region
Development
Help with development of rules
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  | George Davis (core team) | =>160 <301hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | STAFF | 5 | 160 | 301
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
Help with writing implementation guidance
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  | George Davis (core team) | =>40 <81 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | STAFF | 3 | 40 | 81
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Please suggest process improvements to the Regions worksheet. | bar: Workload indicator 5 5 5 5 to Workload indicator 10 10 10 10
Go to Top
Note on V2: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
mm/dd/yy
Subject
Your name
Your message

## 8FinancialServices
⧀ Go to Content
| 8 | Financial Services | AQ permitting program updates
[11 empty] | Estimated range |  |  |  | R.8StaffCount | R.8LowHrs | R.8HighHrs
|  | Number of staff involved | 2 | Hours | [6 empty] | 0-8 |  |  |  | 2 | 0 | 8
|  | DEQ 2012 average hourly $ | 58 | Staff cost | [6 empty] | $0-464 |  |  |  | 0-8 | R.8LowDollars | R.8HighDollars
|  | MESSAGE | [12 empty] | $0-464 | 0 | 464
on Q-net |  | Budget
Development
Fiscal Impact Statement review
|  | Name | Select hours | Workload indicator | [9 empty] | Level involved
|  | Robin Williams | >0 <4 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | STAFF | 1 | 0 | 4
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
on Q-net |  | Accounting
Development
Development of Q-time and project numbers, and time accounting
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  | Robert Beall | >0 <4 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | STAFF | 1 | 0 | 4
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
on Q-net |  | Contracts
Development
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Please suggest process improvements to the Financial Services worksheet. | bar: Workload indicator 3 3 3 3 to Workload indicator 10 10 10 10
Go to Top
Note on V2: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
mm/dd/yy
Subject
Your name
Your message

## 9OCO
⧀ Go to Content
on Q-net | 9 | Communications and Outreach | AQ permitting program updates
[11 empty] | Estimated range |  |  |  | R.9StaffCount | R.9LowHrs | R.9HighHrs
|  | Number of staff involved | 6 | Hours | [6 empty] | 4-61 |  |  |  | 6 | 4 | 61
|  | DEQ 2012 average hourly $ | 58 | Staff cost | [6 empty] | $232-3,538 |  |  |  | 4-61 | R.9LowDollars | R.9HighDollars
|  | MESSAGE | [12 empty] | $232-3,538 | 232 | 3538
on Q-net |  | Communications Strategies | [15 empty] | drop down ⧁
Development
Public notice document review and communication plan strategy
|  | Name | Select hours | Workload indicator | [9 empty] | Level involved
|  | William Knight | =>4 <41 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | STAFF | 2 | 4 | 41
|  | Joanie Stevens-Schwenger (editor) | >0 <4 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | MANAGER | 1 | 0 | 4
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
on Q-net |  | Public Information Representative
Development
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
Potential messaging for Lakeview
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  | William Knight | >0 <4 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | STAFF | 1 | 0 | 4
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
on Q-net |  | Web Communications
Development
Posting program page and required public notice documents to proposed rulemaking page.
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  | AQ Web person | >0 <4 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | STAFF | 1 | 0 | 4
|  | Elle Kozlowski | >0 <4 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | STAFF | 1 | 0 | 4
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
Post to adopted rules page and archive notices to Q-Net.
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  | Elle Kozlowski | >0 <4 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | STAFF | 1 | 0 | 4
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Please suggest process improvements to the Communications and Outreach worksheet. | bar: Workload indicator 9 9 9 9 to Workload indicator 10 10 10 10
Go to Top
Note on V2: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
mm/dd/yy
Subject
Your name
Your message

## 10OrgServices
⧀ Go to Content
| 10 | Organizational Services | AQ permitting program updates | [11 empty] | R.10StaffCount | R.10LowHrs | R.10HighHrs
[11 empty] | Estimated range |  |  |  | 0 | 0 | 0
|  | Number of staff involved | 0 | Hours | [6 empty] | 0 |  |  |  | 0 | R.10LowDollars | R.10HighDollars
|  | DEQ 2012 average hourly $ | 58 | Staff cost | [6 empty] | $0 |  |  |  | $0 | 0 | 0
MESSAGE
on Q-net |  | Human Resources
Development
|  | Name | Select hours | Workload indicator | [9 empty] | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
on Q-net |  | Policy and Procedures
on DAS |  | Development
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
on Q-net |  | Health and Safety
Development
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
on Q-net |  | Training
Development
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
See 7Regions under Implementation.
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Please suggest process improvements to the Organizational Services worksheet. | bar: Workload indicator 6 6 6 6 to Workload indicator 10 10 10 10
Go to Top
Note on V2: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
mm/dd/yy
Subject
Your name
Your message

## 11TechServices
⧀ Go to Content
on Q-net | 11 | Technical Services | AQ permitting program updates | [11 empty] | R.11StaffCount | R.11LowHrs | R.11HighHrs
[11 empty] | Estimated range |  |  |  | 3 | 40 | 89
|  | Number of staff involved | 3 | Hours | [6 empty] | 40-89 |  |  |  | 40-89 | R.11LowDollars | R.11HighDollars
|  | DEQ 2012 average hourly $ | 58 | Staff cost | [6 empty] | $2,320-5,162 |  |  |  | $2,320-5,162 | 2320 | 5162
MESSAGE
need to identify who would assist with template revisions, need to review permitting database
Divisional Technical
Development
Modeling reviewer, review permitting database for aluminum and ferronickel
|  | Name | Select hours | Workload indicator | [9 empty] | Level involved
|  | Phil Allen (NSR/PSD rulemaking team) | =>40 <81 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | STAFF | 3 | 40 | 81
|  | Brian Fields (update TRAACS) | >0 <4 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | STAFF | 1 | 0 | 4
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
on Q-net |  | Information Technology
Development
Update permitting templates
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  | Janice Leber | >0 <4 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | STAFF | 1 | 0 | 4
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
on Q-net |  | Business Systems Development
Development
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Please suggest process improvements to the Technical Services worksheet. | bar: Workload indicator 4 4 4 4 to Workload indicator 10 10 10 10
Go to Top
Note on V2: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
mm/dd/yy
Subject
Your name
Your message

## 12OCE
⧀ Go to Content
on Q-net | 12 | Compliance & Enforcement | AQ permitting program updates
[11 empty] | Estimated range |  |  |  | R.12StaffCount | R.12LowHrs | R.12HighHrs
|  | Number of staff involved | 0 | Hours | [6 empty] | 0 |  |  |  | 0 | 0 | 0
|  | DEQ 2012 average hourly $ | 58 | Staff cost | [6 empty] | $0 |  |  |  | 0 | R.12LowDollars | R.12HighDollars
|  | MESSAGE | [12 empty] | $0 | 0 | 0
Jenny Root to review ????
Compliance and Enforcement - not separately listed
Development
|  | Name | Select hours | Workload indicator | [9 empty] | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Please suggest process improvements to the Compliance & Enforcement worksheet.
Go to Top
Note on V3: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
mm/dd/yy
Subject
Your name
Your message

## 13LEAD
⧀ Go to Content
on Q-net | 13 | LEAD | AQ permitting program updates
|  | Laboratory and Environmental Assessment Division | [12 empty] | R.13StaffCount | R.13LowHrs | R.13HighHrs
[11 empty] | Estimated range |  |  |  | 0 | 0 | 0
|  | Number of staff involved | 0 | Hours | [6 empty] | 0 |  |  |  | 0 | R.13LowDollars | R.13HighDollars
|  | DEQ 2012 average hourly $ | 58 | Staff cost | [6 empty] | $0 |  |  |  | $0 | 0 | 0
MESSAGE
on Q-net |  | Monitoring
Development
|  | Name | Select hours | Workload indicator | [9 empty] | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Analytical testing
Development
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
on Q-net |  | Quality Assurance
Development
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Please suggest process improvements to the LEAD worksheet.
Go to Top
Note on V2: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
mm/dd/yy
Subject
Your name
Your message

## 14Intergovernmental
⧀ Go to Content
| 14 | Intergovernmental | AQ permitting program updates | [11 empty] | R.14StaffCount | R.14LowHrs | R.14HighHrs
[11 empty] | Estimated range |  |  |  | 0 | 0 | 0
|  | Number of staff involved | 0 | Hours | [6 empty] | 0 |  |  |  | 0 | R.14LowDollars | R.14HighDollars
|  | DEQ 2012 average hourly $ | 58 | Staff cost | [6 empty] | $0 |  |  |  | $0 | 0 | 0
MESSAGE
LRARA may consider aligning their titles with OARs.
Go to LRAPA |  | LRAPA
Development
Oregon DEQ to advise of permitting updates
|  | Name | Select hours | Workload indicator | [9 empty] | Level involved
|  | Max Heuftle | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | STAFF | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Go to EPA |  | EPA Region 10
Development
Reviewing and provide advice and SIP coordination
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  | Justin Spenillo | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | STAFF | 0 | 0 | 0
|  | Dave Bray | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | MANAGER | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Municipalities
Development
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
See map |  | Counties
Development
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Go to SDAO |  | Special Districts
Development
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
on Q-net |  | Tribal Government Relations
Development
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Please suggest process improvements to the Intergovernmental worksheet. | bar: Workload indicator 4 4 4 4 to Workload indicator 10 10 10 10
Go to Top
Note on W2: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
mm/dd/yy
Subject
Your name
Your message

## 15CustomParticipants
⧀ Go to Content
Go to Work Groups | 15 | Custom Participants | AQ permitting program updates | [11 empty] | R.15StaffCount | R.15LowHrs | R.15HighHrs
[11 empty] | Estimated range |  |  |  | 0 | 0 | 0
|  | Number of staff involved | 0 | Hours | [6 empty] | 0 |  |  |  | 0 | R.15LowDollars | R.15HighDollars
|  | DEQ 2012 average hourly $ | 58 | Staff cost | [6 empty] | $0 |  |  |  | $0 | 0 | 0
MESSAGE
Enter custom party here
Development
|  | Name | Select hours | Workload indicator | [9 empty] | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Enter custom party here
Development
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Enter custom party here
Development
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Enter custom party here
Development
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Enter custom party here
Development
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Implementation
|  | Name | Select hours | Workload indicator 1 1 1 1: Workload indicator | Level involved
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
|  |  | 0 hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 0 | 0 | 0
Please suggest process improvements to the Custom Participants worksheet. | bar: Workload indicator 4 4 4 4 to Workload indicator 10 10 10 10
Go to Top
Note on X2: WORKING WITH THE MESSAGE BOX Make a copy Click your mouse button inside the yellow message box below then press Ctrl + C. Click on a cell near the subject matter of your message the press Ctrl + V. Resize the message Click inside the message box and with squares appear around the parameter. Grab (click the mouse button and continue holding it down) one of the squares and resize to fit your message. Adding text Click inside the message box to enter the date, subject, your name and message. Point to the subject matter Grab a yellow triangle on the arrowed line and point it to the exact location. Relocating the message Grab the box close to the border. When four arrows appear under the cursor, click and hold down the mouse button and move the box to the new location.
mm/dd/yy
Subject
Your name
Your message