## AQPerm.ScheduleOfTasks
Overview of Key Dates
| AQPerm |  |  |  | Start ↓ | End
[5 empty] | 2014-01-02 | 2015-06-09 |  |  | 2014-10-06 | 2015-06-09 |  | Last row = 910
| To restore any cell under columns G or H to default, place cursor in cell then enter "=A" followed by the cell address. EXAMPLE: =AG13 would restore the default Start of Advisory Committee. | [6 empty] | 0 |  | Dir. Date Used in Calcs
| Director added to DEQ Rulemaking Plan | Y |  |  | 2014-01-02 |  |  | 1 |  | 2014-01-02
| PERMANENT Rulemaking | P |  |  |  |  | 60 | 1 |  |  |  | PERMANENT Rulemaking
| Rule proposal complexity (1=Minimal, 2= Moderate, 3=Complex) | 3 |  |  |  |  | 60 | 1
| Advisory Committee | Y | i |  | 2014-01-02 | 2015-01-29 | 21 | 1 | 2014-01-02 | 2015-01-29 |  | Advisory Committee
| Fees - not involved | N |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fees - not involved
| -blank- | Y | i | 0 |  |  | 0 | 0 |  |  |  | -blank-
| -blank- |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  | -blank-
0
| State Implementation Plan (AQ rules) | Y |  | 112 |  |  | 112 | 1 |  |  |  | State Implementation Plan (AQ rules)
| EPA - submit SIP Development Plan 6 months before comment period opens |  |  |  |  | 2013-12-16 |  | 1 |  | 2013-12-16 |  | EPA - submit SIP Development Plan 6 months before comment period opens
| EPA - submit at least 45 days before submittig notice to SOS |  |  | 45 |  | 2014-04-11 | 45 | 1 |  | 2014-04-11 |  | EPA - submit at least 45 days before submittig notice to SOS
[8 empty] | 0 |  |  | `
| Public Notice | Y |  | Adj | 2014-01-02 | 2014-09-15 |  | 1 | 2014-01-02 | 2014-09-15 | Best practice | Public Notice
| Due to Leah - approval to submit Notice Packet to Rule Publication |  |  | 10 | 2014-04-04 | 2014-04-15 | 10 | 1 | 2014-04-04 | 2014-04-15 | 7 | Due to Leah - approval to submit Notice Packet to Rule Publication
| Due to Rule Publication (AndreaG) - final edits and validations |  |  | 14 | 2014-04-25 | 2014-05-09 | 21 | 1 | 2014-04-25 | 2014-05-09 | 14 | Due to Rule Publication (AndreaG) - final edits and validations
| Due to Lydia for input and approval to publish Notice Packet |  |  | 5 | 2014-05-23 | 2014-05-30 | 7 | 1 | 2014-05-23 | 2014-05-30 | 5 | Due to Lydia for input and approval to publish Notice Packet
| SOS - submit on workday no later than 15th of month BEFORE Bulletin |  |  |  |  | 2014-06-13 |  | 1 |  | 2014-06-13 |  | SOS - submit on workday no later than 15th of month BEFORE Bulletin
| SOS - Oregon Bulletin always publishes on the 1st of month | Drop down list > |  |  |  | 2014-07-01 |  | 1 |  | 2014-12-01 |  | SOS - Oregon Bulletin always publishes on the 1st of month
| Public Comment and Testimony | N |  |  | 2014-06-13 | 2015-01-29 | 14 | 1 | 2014-06-13 | 2015-01-29 |  | Public Comment and Testimony
| Open public comment |  |  |  |  | 2014-06-16 |  | 1 |  | 2014-06-16 |  | Open public comment
| Hold 1st hearing at least 30 days AFTER open comment - EPA SIP requirement | Y |  |  |  | 2014-07-16 |  | 1 |  | 2014-07-16 |  | Hold 1st hearing at least 30 days AFTER open comment - EPA SIP requirement
| Close public comment - DEQ best practice, 3 days after last hearing |  |  |  |  | 2014-09-15 |  | 1 |  | 2014-07-21 |  | Close public comment - DEQ best practice, 3 days after last hearing
| EQC Preparation |  |  |  | 2014-06-13 | 2015-01-29 |  | 1 | 2014-06-13 | 2015-01-29 |  | =IF(S.Notice.Involved="N","-blank-",IF(S.EQC.SubmitStaffRpt-S.Notice.CloseComment<45,"ERROR - Staff report due before Close of public comment.","Close public comment - best practice, 3 days after last hearing"))
| Involvement before Rulemaking Action Item |  |  |  | Option 1 ↓ | Option 2 ↓ |  | 1 |  |  |  | Involvement before Rulemaking Action Item
| Director's Report - some material comes from monthly status report | Y | i |  |  |  |  | 1 | 2014-01-02 | 2014-01-02 |  | Director's Report - some material comes from monthly status report
| Information Item - a presentation to update the EQC | Y | i |  | 2015-01-07 | 2015-01-07 | 21 | 1 | 2015-01-07 | 2015-01-07 |  | Information Item - a presentation to update the EQC
| No facilitated hearing requested | N |  |  | 0 | 0 |  | 0 | 0 | 0 |  | No facilitated hearing requested
| Rule Publication - submit PERMANENT staff report |  |  |  |  | 2015-01-29 | 41 | 1 |  | 2015-01-29 |  | Rule Publication - submit PERMANENT staff report
| EQC meeting - PERMANENT Rulemaking Action Item | Drop down list > |  |  |  | 2015-03-11 |  | 1 |  | 2015-01-07 |  | EQC meeting - PERMANENT Rulemaking Action Item
[7 empty] | -55 | 1 | < +/- calendar days adjustment
[7 empty] | 412 | 1 | < calendar days added
| Post EQC Activities |  |  |  | 2015-03-11 | 2015-06-09 |  | 1 | 2015-03-11 | 2015-06-09
| SOS - file rules |  |  |  |  | 2015-03-13 |  | 1 |  | 2015-03-13
| DAS - fees not involved |  |  |  |  | 2015-03-16 |  | 0 |  | 2015-03-16 |  | DAS - fees not involved
| Rules become effective select 'Y' if effective upon filing > | Y |  |  |  | 2015-03-13 |  | 1 |  | 2015-03-13
| EPA - goal to submit SIP within 60 days of adoption |  |  |  |  | 2015-05-11 |  | 1 |  | 2015-05-11 |  | EPA - goal to submit SIP within 60 days of adoption
Planning
| AQPerm |  |  |  | Start | End
[5 empty] | 2014-01-02 | 2014-02-11 |  |  | 2014-01-02 | 2014-02-11 | 2014-01-02
| Review version history to help maintain rulemaking record > | i
| KEY PEOPLE | [6 empty] | 1
| Subject expert, core team member - Jill | [6 empty] | 1 |  |  |  | Subject expert, core team member - Jill
| * member of core team - project manager | [6 empty] | 1
| * responsible for: | [6 empty] | 1
| - meeting program's rulemaking goals | [6 empty] | 1
| - meeting subject expert's tasks identified in this Schedule | [6 empty] | 1
| - engaging rules group lead, core team and RESOURCES appropriately | [6 empty] | 1
| - ensuring technical and programatic accuracy of completed work products | [6 empty] | 1
| * leads: | [6 empty] | 1
| - research and analysis for rulemaking | [6 empty] | 1
| - drafting work products | [6 empty] | 1
| - core team meetings | [6 empty] | 1
| * briefs: | [6 empty] | 1
| - core team and management about delays and complications as needed | [6 empty] | 1
| - Lydia & Lydia as needed | [6 empty] | 1 |  |  |  | - Lydia & Lydia as needed
| Sponsoring manager, core team member - Leah | [6 empty] | 1 |  |  |  | Sponsoring manager, core team member - Leah
| * member of core team - subject direction | [6 empty] | 1
| * responsible for approving external work product as: | [6 empty] | 1
| - meeting program and section goals | [6 empty] | 1
| - being accurate both technically & programmatically | [6 empty] | 1
| - meeting sponsoring manager's task deadlines in this Schedule | [6 empty] | 1
| * leads extra review cycles for Lydia as needed | [6 empty] | 1 |  |  |  | * leads extra review cycles for Lydia as needed
| * briefs: | [6 empty] | 1
| - core team and management about delays and complications as needed | [6 empty] | 1 |  |  |  | * briefs core team, Lydia & Lydia as needed
| - Lydia & Lydia as needed | [6 empty] | 1 |  |  |  | - Lydia & Lydia as needed
| Rules group lead, core team member - AndreaG | [6 empty] | 1 |  |  |  | Rules group lead, core team member - AndreaG
| * member of core team - rulemaking best practices | [6 empty] | 1
| * responsible for: | [6 empty] | 1
| - quality of public rulemaking documents | [6 empty] | 1
| - fiscal and economic impact analysis | [6 empty] | 1 |  |  |  | * keeps Lydia informed about risks, progress & potential delays
| * leads rule publication work: | [6 empty] | 1
| - establish SharePoint sub site, Rule_Development drive and archival spaces | [6 empty] | 1
| - establish/maintain Web page, URLs, online comment form, University student Outlook account | [6 empty] | 1
| - engages Rule Publications (SIP coordinator, public affairs consultant, EQC assistant) | [6 empty] | 1
| assistant) as needed for edits, style guide, grammar, plain English, organization, clarity and tone | [6 empty] | 1
| clarity and tone | [6 empty] | 1
| - reconciles Rule Publications edits that do not affect subject content | [6 empty] | 1
| * authenticates SOS & LC submittals, files notice, fiscal & rules | [6 empty] | 1 |  |  |  | * keeps Lydia informed about risks, progress & potential delays
| * briefs: | [6 empty] | 1
| - core team and management about delays and complications as needed | [6 empty] | 1 |  |  |  | * briefs core team, Lydia & Lydia as needed
| - team & Lydia as needed | [6 empty] | 1 |  |  |  | - team & Lydia as needed
| Program Support Staff - Jill | [6 empty] | 1 |  |  |  | Program Support Staff - Jill
| Assistant DA - Lydia | [6 empty] | 1 |  |  |  | Assistant DA - Lydia
| DA - Lydia | [6 empty] | 1 |  |  |  | DA - Lydia
| GENERAL INFORMATION | [6 empty] | 1
| Q-Time number = 43777 | [6 empty] | 1
| SharePoint - collaboration place for working documents | [6 empty] | 1
| http://deqsps/programs/rulemaking/PROGRAM/AQPermdefault.aspx | [6 empty] | 1 |  |  |  | http://deqsps/programs/rulemaking/PROGRAM/AQPermdefault.aspx
| Rules Development - non collaborative work | [6 empty] | 1
| \\deqhq1\Rule_Development\Currrent Plan\AQPerm.aspx | [6 empty] | 1 |  |  |  | \\deqhq1\Rule_Development\Currrent Plan\AQPerm.aspx
| URLs | [6 empty] | 1
| Online public comment form | [6 empty] | 1
| http://www.oregon.gov/deq/RulesandRegulations/Pages/comments/AQPerm.aspx | [6 empty] | 1 |  |  |  | http://www.oregon.gov/deq/RulesandRegulations/Pages/comments/AQPerm.aspx
| External Web page | [6 empty] | 1
| http://www.oregon.gov/deq/RulesandRegulations/Pages/2014/AQPerm.aspx | [6 empty] | 1 |  |  |  | http://www.oregon.gov/deq/RulesandRegulations/Pages/2014/AQPerm.aspx
| University Student Comment Account | [6 empty] | 1
| Comment-AQPerm@deq.state.or.us | [6 empty] | 1 |  |  |  | Comment-AQPerm@deq.state.or.us
| CONCEPT DEVELOPMENT | i | [5 empty] | 1
| Leah discusses developing concept for DEQ Rulemaking Plan with Lydia |  |  |  |  | 2014-01-02 |  | 1 |  | 2014-01-02 |  | Leah discusses developing concept for DEQ Rulemaking Plan with Lydia
| Lydia approves concept development work |  |  |  |  | 2014-01-02 |  | 1 |  | 2014-01-02 |  | Lydia approves concept development work
| Leah | [6 empty] | 1 |  |  |  | Leah
| * assigns subject expert for the rulemaking |  |  |  |  | 2014-01-02 |  | 1 |  | 2014-01-02 |  | * assigns subject expert for the rulemaking
| (reminder - add work to workplans as needed) | [6 empty] | 1 |  |  |  | (reminder - add work to workplans as needed)
| * identify existing Q-Time number for concept development work |  |  |  |  | 2014-01-02 |  | 1 |  | 2014-01-02 |  | * identify existing Q-Time number for concept development work
| Q-Time number = | [6 empty] | 1 |  |  |  | * identify existing Q-Time number for concept development work
| Maggie | [6 empty] | 1 |  |  |  | Maggie
| * adds to Rules Idea list and shares information with Rules Group |  |  |  |  | 2014-01-02 |  | 1 |  | 2014-01-02
| * establishes Rule_Development site | i | [5 empty] | 1
| * establishes SharePoint sub site | i | [5 empty] | 1
| * schedules work session | [6 empty] | 1
| Leah & Jill participates in work session. Topics include: |  |  |  |  | 2014-01-02 |  | 1 |  | 2014-01-02 |  | Leah & Jill participates in work session. Topics include:
| * roles and responsibilities | [6 empty] | 1
| * records management | [6 empty] | 1
| - naming conventions | [6 empty] | 1
| - SharePoint | [6 empty] | 1
| - shared Rule _Development drive | [6 empty] | 1
| * overview of work products | [6 empty] | 1
| - Rules and Regulations Web page | i | [5 empty] | 1
| - INVITATION.TO.COMMENT (blank in folder 4) | i | [5 empty] | 1
| - PROPOSED.RULES | [6 empty] | 1
| - NOTICE (blank in folder 4) | i | [5 empty] | 1
| - FEE.ANALYSIS (blank in folder 3) | i | [5 empty] | 0
| - STAFF.RPT.Permanent (blank in folder 6) | i | [5 empty] | 1 |  |  |  | - STAFF.RPT.Permanent (blank in folder 6)
| * work products for this phase (templates preloaded to SharePoint folder 1): | [6 empty] | 1
| - Overview of Key Dates at top of this SCHEDULE | [6 empty] | 1
| - initial draft RESOURCES workbook | [6 empty] | 1
| - initial draft CONSIDERATIONS workbook | [6 empty] | 1
| Jill drafts: |  |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02 |  | Jill drafts:
| * RESOURCES workbook identifies rulemaking and implementation needs | [6 empty] | 1
| * CONSIDERATIONS workbook reflects scope of work accurately | [6 empty] | 1
| * CONSIDERATIONS workbook identifies potential risks accurately | [6 empty] | 1
| Jill gets consenus from Leah & AndreaG on workbooks |  |  |  |  | 2014-01-02 |  | 1 |  | 2014-01-02 |  | Jill gets consenus from Leah & AndreaG on workbooks
| Leah shares concept with Lydia and may stop/delay/advance concept |  |  |  |  | 2014-01-02 |  | 1 |  | 2014-01-02 |  | Leah shares concept with Lydia and may stop/delay/advance concept
| Lydia shares concept with Lydia and may stop/delay/advance concept |  |  |  |  | 2014-01-02 |  | 1 |  | 2014-01-02 |  | Lydia shares concept with Lydia and may stop/delay/advance concept
| If advanced, Leah emails AndreaG to indicate approval |  |  |  |  | 2014-01-02 |  | 1 |  | 2014-01-02 |  | If advanced, Leah emails AndreaG to indicate approval
| Maggie: |  |  |  |  | 0 |  | 1 |  | 0 |  | Maggie:
| * leads Rules Group prioritization using CONSIDERATIONS and RESOURCES data that | [6 empty] | 1
| compares to other concepts, rulemakings in progress and Rules Group work load | [6 empty] | 1
| * shares priority list and factors with Leah & Jill |  |  |  |  | 2014-01-02 |  | 1 |  | 2014-01-02 |  | * shares priority list and factors with Leah & Jill
| * adjusts factors as needed | [6 empty] | 1
| * shares priority listing with Leah & AndreaG |  |  |  |  | 2014-01-02 |  | 1 |  | 2014-01-02 |  | * shares priority listing with Leah & AndreaG
| If prioritized and resourced: | [6 empty] | 1 |  |  |  | Dick:
| Maggie develops work papers and Leadership Team draft email for Dick | i |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02 |  | Maggie develops work papers and Leadership Team draft email for Dick
| Dick: | [6 empty] | 1 |  |  |  | Dick:
| * adapts email and approves moving forward, sends email |  |  |  |  | 2014-01-02 |  | 1 |  | 2014-01-02
| To: Leadership Team describing addition to DEQ Rulemaking Plan | [6 empty] | 1 |  |  |  | To: Leadership Team describing addition to DEQ Rulemaking Plan
| To: StephanieC to include in monthly Director's Report | [6 empty] | 1 |  |  |  | To: StephanieC to include in monthly Director's Report
| (Dick asks EQC how they want to be involved with rulemaking) | [6 empty] | 1 |  |  |  | (Dick asks EQC how they want to be involved with rulemaking)
| (StephanieC informs team about EQC involvement by email) | [6 empty] | 1 |  |  |  | (StephanieC informs team about EQC involvement by email)
| Cc… Leah, Jill, AndreaG | [6 empty] | 1 |  |  |  | Cc… Leah, Jill, AndreaG
| AndreaG: | [6 empty] | 1 |  |  |  | AndreaG:
| * selects 'A' if approved, 'P' if postponed, 'R' if rejected | A | [5 empty] | 1
| * saves email Rule_Development ¦ 1-Planning ¦ APPROVAL.ToMoveForward.pdf | i | [5 empty] | 1 |  |  |  | * saves email Rule_Development ¦ 1-Planning ¦ APPROVAL.ToMoveForward.pdf
`
| START RULEMAKING IF DICK ADDS TO PLAN | [6 empty] | 1
| Leah, Jill & AndreaG decide whether to expand team 'Y' to expand > | N |  |  |  | 2014-01-02 |  | 1 |  | 2014-01-02 |  | Leah, Jill & AndreaG decide whether to expand team 'Y' to expand >
| Leah works with Maggie obtains unique Q-Time number(s) |  |  |  |  | 2014-01-02 |  | 1 |  | 2014-01-02 |  | Leah works with Maggie obtains unique Q-Time number(s)
| for this rulemaking fromRobertB | [6 empty] | 1 |  |  |  | for this rulemaking fromRobertB
| Leah is responsible for: | [6 empty] | 1 |  |  |  | Leah is responsible for:
| * getting new team members' manager approval | [6 empty] | 0
| * adding rulemaking to work plans as appropriate | [6 empty] | 0
| * program team members meet agreed upon dates in this SCHEDULE | [6 empty] | 1
| AndreaG drafts SCHEDULE: |  |  |  |  | 2014-01-02 |  | 1 |  | 2014-01-02 |  | AndreaG drafts SCHEDULE:
| Jill & AndreaG refine & agree on draft schedule: |  |  |  |  | 2014-01-02 |  | 1 |  | 2014-01-02 |  | Jill & AndreaG refine & agree on draft schedule:
| Jill schedules/holds team meeting(s) for consensus on: |  |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02 |  | Jill schedules/holds team meeting(s) for consensus on:
| * RESOURCES workbook identifies rulemaking and implementation needs | [6 empty] | 1
| * CONSIDERATIONS workbook reflects scope of work accurately | [6 empty] | 1
| * CONSIDERATIONS workbook identifies potential risks accurately | [6 empty] | 1
| * SCHEDULE of tasks and deadlines | [6 empty] | 1
`
| COMMUNICATIONS PLANNING | [6 empty] | 1
| Jill schedules/holds meeting with Leah and |  |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02 |  | Jill schedules/holds meeting with Leah and
| BrianW and AndreaG to discuss/determine need for: | [6 empty] | 1 |  |  |  | BrianW and AndreaG to discuss/determine need for:
| - Communications Plan 'Y' to develop | N | [5 empty] | 0 |  |  | N
| - Message Map 'Y' to develop | N | [5 empty] | 0
| - Newspaper advertisements 'Y' to develop | Y | [5 empty] | 1
| - Newspaper release 'Y' to develop | N | [5 empty] | 0
| - Program Web page 'Y' to develop | N | [5 empty] | 0
| - Information Meetings before hearing 'Y' to develop | N | [5 empty] | 0
`
| COMMUNICATIONS OPTION | [6 empty] | 0
| Jill leads communication option review and approval loops for: | [6 empty] | 0 |  |  |  | Jill leads communication option review and approval loops for:
| * drafting COMMUNICATION.PLAN with BrianW using information | i |  |  | 2014-01-02 | 2014-01-02 |  | 0 | 2014-01-02 | 2014-01-02 |  | * drafting COMMUNICATION.PLAN with BrianW using information
| from CONSIDERATIONS and RESOURCES workbooks | [6 empty] | 0
| * drafting MESSAGE.MAP with BrianW | i |  |  | 2014-01-02 | 2014-01-02 |  | 0 | 2014-01-02 | 2014-01-02 |  | * drafting MESSAGE.MAP with BrianW
| * drafting PROGRAM.WEB.PAGE content with team and Michele |  |  |  | 2014-01-02 | 2014-01-02 |  | 0 | 2014-01-02 | 2014-01-02 |  | * drafting PROGRAM.WEB.PAGE content with team and Michele
| Leah: | [6 empty] | 0 |  |  |  | Leah:
| * shares content with Lydia and approves content: |  |  |  | 2014-01-02 | 2014-01-02 |  | 0 | 2014-01-02 | 2014-01-02 |  | * shares content with Lydia and approves content:
| 1st loop - team modifies content to get to approval |  |  |  | 2014-01-02 | 2014-01-02 |  | 0 | 2014-01-02 | 2014-01-02
| 2nd loop - team modifies content to get to approval | N |  |  | 0 | 0 |  | 0 | 0 | 0
| 3rd loop - team modifies content to get to approval | N |  |  | 0 | 0 |  | 0 | 0 | 0
| Final loop - team modifies content to get to approval | N |  |  | 0 | 0 |  | 0 | 0 | 0
| Jill leads program Web page development: |  |  |  | 2014-01-02 | 2014-01-02 |  | 0 | 2014-01-02 | 2014-01-02 |  | Jill leads program Web page development:
| * submits Web Request for program Web page | [6 empty] | 0
` | * verifies Web content meets team expectations | [6 empty] | 0
| * works with Michele to make adjustments | [6 empty] | 0 |  |  |  | * works with Michele to make adjustments
`
| PREPLANNING FOR HEARINGS | [6 empty] | 1
| Team identifies hearing locations, dates and times |  | Hearing Table |  |  |  |  | 1 |  |  |  | Team identifies hearing locations, dates and times
|  |  | # |  | Date | Time |  | 1 |  |  |  | Jill enters hearings locations, dates and times:
| Portland | Y | 1 |  | 2014-07-16 | 6 p.m. |  | 1 | 2014-07-16 | 5 p.m.
| Enter city name | N | 2 |  | 0 | 6 p.m. |  | 0 | 0 | 6 p.m.
| Enter city name | N | 3 |  | 0 | 6 p.m. |  | 0 | 0 | 6 p.m.
| Enter city name | N | 4 |  | 0 | 6 p.m. |  | 0 | 0 | 6 p.m.
| Enter city name | N | 5 |  | 0 | 6 p.m. |  | 0 | 0 | 6 p.m.
| Enter city name | N | 6 |  | 0 | 6 p.m. |  | 0 | 0 | 6 p.m.
| Enter city name | N | 7 |  | 0 | 6 p.m. |  | 0 | 0 | 6 p.m.
| Enter city name | N |  |  | 0 | 6 p.m. |  | 0 | 0 | 6 p.m.
| Last hearing: |  |  |  | 2014-07-16 |  |  | 1 | 2014-07-16
| Jill reserves venues/equipment for hearings |  |  |  | 2014-01-02 | 2014-07-16 |  | 1 | 2014-01-02 | 2014-07-16 |  | Jill reserves venues/equipment for hearings
| Jill identifies hearings officer(s) on HearingAndAdDates TAB | i | [5 empty] | 1 |  |  |  | Jill identifies hearings officer(s) on HearingAndAdDates TAB
| NEWSPAPER ADVERTISEMENTS | [6 empty] | 1
| Jill works with Jill: |  |  |  | 2014-01-02 | 2014-05-20 |  | 1 | 2014-01-02 | 2014-05-20 |  | Jill works with Jill:
| * to identify publications and publication dates | [6 empty] | 1
|  | Publication Table | [5 empty] | 1
|  | # | Publication |  |  | Pub Date |  | 1
| NOTICE.AD1Oregonian | 1 | Oregonian |  |  | 2014-06-16 |  | 1 |  | 2014-06-16 |  | NOTICE.AD1Oregonian
| NOTICE.AD2None | 2 | None |  |  | 2014-06-16 |  | 1 |  | 2014-06-16 |  | NOTICE.AD2None
| NOTICE.AD3None | 3 | None |  |  | 2014-06-16 |  | 1 |  | 2014-06-16 |  | NOTICE.AD3None
| NOTICE.AD4None | 4 | None |  |  | 2014-06-16 |  | 1 |  | 2014-06-16 |  | NOTICE.AD4None
| NOTICE.AD5None | 5 | None |  |  | 2014-06-16 |  | 1 |  | 2014-06-16 |  | NOTICE.AD5None
| NOTICE.AD6None | 6 | None |  |  | 2014-06-16 |  | 1 |  | 2014-06-16 |  | NOTICE.AD6None
| NOTICE.AD7None | 7 | None |  |  | 2014-06-16 |  | 1 |  | 2014-06-16 |  | NOTICE.AD7None
| NOTICE.AD8None | 8 | None |  |  | 2014-06-16 |  | 1 |  | 2014-06-16 |  | NOTICE.AD8None
| * develops an AD.STANDARD for each hearing if required | e | [5 empty] | 1
| * develops AD.LEGAL for each hearing if required | t | [5 empty] | 1
| * saves as NOTICE.AD.Hearing1, etc. on Rule_Development folder 4 | [6 empty] | 1
| * determines when ADs need to be submitted to contractor | Ad to contractor > |  |  |  | 2014-06-02 |  | 1 |  | 2014-06-02
| * shares contents of HearingAndAdDates TAB with Leah | i |  |  | 2014-01-02 | 2014-05-27 |  | 1 | 2014-01-02 | 2014-05-27 |  | * shares contents of HearingAndAdDates TAB with Leah
| * obtains Leah's email approval |  |  |  | 2014-01-02 | 2014-05-27 |  | 1 | 2014-01-02 | 2014-05-27 |  | * obtains Leah's email approval
`
| EQC FACILITATED HEARINGS | [6 empty] | 0
| Jill: | [6 empty] | 0 |  |  |  | Jill:
| * observe EQC quorum notification requirements (ORS 192.630) | i | [5 empty] | 0
| * identifies EQC facilitated hearing, coordinate with commissioner: | [6 empty] | 0
| MEden@neea.org | N |  |  |  | 2014-10-15 |  | 0 |  | 0
| JoKRanch@hotmail.com | N |  |  |  | 2014-10-15 |  | 0
| EdArmstrong2@gmail.com | N |  |  |  | 2014-10-22 |  | 0
| MorganRider@gmail.com | N |  |  |  | 2014-10-22 |  | 0
| cjohnson@eou.edu | N |  |  |  | 2014-10-22 |  | 0
`
| PREPARE TO DRAFT RULES | [6 empty] | 1
| Jill coordinates with Team to: |  |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02 |  | Jill coordinates with Team to:
| * determine need for a crosswalk | [6 empty] | 1
| * identify rules to amend or repeal | [6 empty] | 1
| * identify requirements that need rules adoption | [6 empty] | 1
| * identify land use rules | i | [5 empty] | 1
| * identify SIP rules | [6 empty] | 1
| Jill: | [6 empty] | 1 |  |  |  | Jill:
| * obtains starting rules from Oregon State Archives | i |  |  |  | 2014-01-02 |  | 1 |  | 2014-01-02
| * owns pristine draft of proposed rules and maintains it on | [6 empty] | 1
| Rule_Development¦1-Planning using the name¦STARTING.RULES | [6 empty] | 1
| only Jill works on rules at this location to ensure the | [6 empty] | 1 |  |  |  | only Jill works on rules at this location to ensure the
| redline/strikethrough remains consistent and that no reviewer | [6 empty] | 1
| copied text from other locations or turned track changes off | [6 empty] | 1
| * uploads copy of STARTING.RULES to SharePoint¦1-Planning | [6 empty] | 1
| All contributors & reviewers work on draft rules on SharePoint | [6 empty] | 1
| * requests Maggie provide numbers for new rules/divisions |  |  |  |  | 2014-01-02 |  | 1 |  | 2014-01-02 |  | * requests Maggie provide numbers for new rules/divisions
| Maggie: | [6 empty] | 1 |  |  |  | Maggie:
| * obtains, verifies, provides previously unused rule numbers |  |  |  |  | 2014-01-02 |  | 1 |  | 2014-01-02 |  | Maggie obtains, verifies, provides previously unused numbers
| * identifies rules that may be involved in other rulemakings |  |  |  |  | 2014-01-02 |  | 1 |  | 2014-01-02 |  | Maggie identifies rules that may be involved in other rulemakings
| * coordinates with AndreaG to identify SIP rules |  |  |  |  | 0 |  | 1 | 2014-01-02 | 0 |  | * coordinates with AndreaG to identify SIP rules
| * requests all planning emails for the Rule Record and saves in | i |  |  |  | 2014-01-02 |  | 1 |  | 2014-01-02 |  | Jill gathers all planning emails for the Rule Record and saves as:
| Rule_Development¦1-Planning¦EMAILS.Planning.pdf | [6 empty] | 1
Advisory Committee
| AQPerm |  |  |  | Start | End
[5 empty] | 2014-01-02 | 2015-01-29 |  |  | 2014-01-02 | 2015-01-29
| Review version history to help maintaining rulemaking record | i
| Jill holds/leads team meeting to: |  |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02 |  | Jill holds/leads team meeting to:
| * review | [6 empty] | 1
| - advisory committee Q-Card | i | [5 empty] | 1
| - Public Involvement Resources, discuss when to engage BrianW | i | [5 empty] | 1 |  |  |  | - Public Involvement Resources, discuss when to engage BrianW
| - review committee Web page template | i | [5 empty] | 1
| - review and discuss required committee meeting sign up list | i | [5 empty] | 1
* discuss
| - public Meeting Laws | i | [5 empty] | 1 |  |  |  | May be required in future
| - EQC quorum notification requirements (ORS 192.630) | i | [5 empty] | 1 |  |  |  | * Oregon Transparency law (not required for Advisory Committees) | i
| - need for optional committee Web page | [6 empty] | 1
| - need for optional committee charter | [6 empty] | 1
| * identify | [6 empty] | 1
| - lists of persons potentially affected by proposed rules | [6 empty] | 1
| - lists of persons who may have special interest in rulemaking | [6 empty] | 1
| - potential committee members | [6 empty] | 1
| - potential meeting dates and venues | [6 empty] | 1
| Jill coordinates with team to: |  |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02 |  | Jill coordinates with team to:
| * develop AC.ROSTER (blank in folder 4) | [6 empty] | 1
| * add EQC members to Cc. list for ALL committee communications | [6 empty] | 1
| MEden@neea.org | [6 empty] | 1
| JoKRanch@hotmail.com | [6 empty] | 1
| EdArmstrong2@gmail.com | [6 empty] | 1
| MorganRider@gmail.com | [6 empty] | 1
| cjohnson@eou.edu | [6 empty] | 1
| * reserve potential meeting dates and venues | [6 empty] | 1
| * draft committee AC.INVITATION (links to GovDelivery/Web pages) |  |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02
| * draft content for optional committee Web page | Y |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02
| * draft optional AC.CHARTER | Y |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02
| * emails lists above to invite them to sign up to receive meeting notices | i | [5 empty] | 1
| Leah shares draft roster and invitation with Lydia |  |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02 |  | Leah shares draft roster and invitation with Lydia
| Team addresses any concerns and validates accuracy of how addressed |  |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02
| Leah approves potential advisory committee roster |  |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02 |  | Leah approves potential advisory committee roster
| Team: | [6 empty] | 1
| * makes initial voice contact with potential committee members |  |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02
| * finalizes AC.ROSTER based on responses |  |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02
| Jill: | [6 empty] | 1 |  |  |  | Jill:
| * submits optional Committee Web page template attached to Web Request | i |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02
| * submits Web Request at anytime when Committee Web page needs updating | [6 empty] | 1
| * sends invitation to potential committee members who agreed to serve |  |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02
| * maintains advisory committee record | [6 empty] | 1
| Meeting 1 | Y |  |  | 2014-06-05 | 9.00 am |  | 1 | 2014-01-16
| Team identifies meeting roles | [6 empty] | 1
| Jill coordinates or drafts: |  |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02 |  | Jill coordinates or drafts:
| * AC.AGENDA.06.05.14 | i | [5 empty] | 1 |  |  |  | * AC.AGENDA.06.05.14
| * AC.NOTIFICATION.06.05.14 | [6 empty] | 1 |  |  |  | * AC.NOTIFICATION.06.05.14
| Jill obtains team approval of agenda and notification |  |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02 |  | Jill obtains team approval of agenda and notification
| Jill (about 14 working days before meeting:) |  |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02 |  | Jill (about 14 working days before meeting:)
| * adds meeting to DEQ Online Calendar (password = dudeman) | i | [5 empty] | 1
| * sends GovDelivery meeting notice and Web page link | [6 empty] | 1
| * releases unneeded venues | [6 empty] | 1 |  |  |  | )&", gets team agreement"
| Team assigns custom task here |  |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02
| Team assigns custom task here |  |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02
| Team assigns custom task here |  |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02
| Team assigns custom task here |  |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02
| START OPTION - Presentation Select option > | Y | [5 empty] | 1
| Enter staff name here | [6 empty] | 1
| * drafts optional AC.PRESENTATION.06.05.14 |  |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02 |  | * drafts optional AC.PRESENTATION.06.05.14
| Enter staff name here | [6 empty] | 1
| * involves stakeholder presenters, if any |  |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02
| Team approves presentation materials |  |  |  | 2014-01-02 | 2014-01-02 |  | 1 | 2014-01-02 | 2014-01-02
| Jill submits Web Request to post materials | i | [5 empty] | 1 |  |  |  | Jill submits Web Request to post materials
| Team practices presentation | [6 empty] | 1
| Team facilitates/holds meeting |  |  |  |  | 2014-06-05 |  | 1 |  | 2014-06-05
| Jill drafts AC.MINUTES 06.05.14 | i |  |  | 2014-06-05 | 2014-06-05 |  | 1 | 2014-06-05 | 2014-06-05 |  | Jill drafts AC.MINUTES 06.05.14
| Team holds debrief meeting |  |  |  | 2014-06-05 | 2014-06-05 |  | 1 | 2014-06-05 | 2014-06-05
| Meeting 2 | N |  |  | 2014-06-26 | 9.00 a.m. |  | 0 | 2014-06-05
| Team identifies meeting roles |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| Jill coordinates or drafts: | [6 empty] | 0 |  |  |  | Jill coordinates or drafts:
| * AC.AGENDA.06.05.14, gets team agreement | i |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12 |  | * AC.AGENDA.06.05.14, gets team agreement
| * AC.NOTIFICATION.06.05.14 |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12 |  | * AC.NOTIFICATION.06.05.14
| * adds meeting to DEQ Online Calendar (password = dudeman) | i |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| * releases unneeded venues |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| Team assigns custom task here |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| Team assigns custom task here |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| Team assigns custom task here |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| Team assigns custom task here |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| START OPTION - Presentation Select option > | Y | [5 empty] | 0
| Enter staff name here | [6 empty] | 0
| * drafts optional AC.PRESENTATION.06.05.14 | i |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12 |  | * drafts optional AC.PRESENTATION.06.05.14
| Enter staff name here | [6 empty] | 0
| * involves stakeholder presenters, if any |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| Team approves presentation materials |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| Jill submits Web Request to post materials | i |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12 |  | Jill submits Web Request to post materials
| Team practices presentation |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12
| Jill sends meeting notice with link to Web page |  |  | 1 | 2014-06-12 | 2014-06-12 |  | 0 | 2014-06-12 | 2014-06-12 |  | Jill sends meeting notice with link to Web page
| Team facilitates/holds meeting |  | Set above at Meeting 2 title |  |  | 2014-06-26 |  | 0 |  | 2014-06-26
| Jill drafts AC.MINUTES 06.05.14 | i |  | 1 | 2014-06-26 | 2014-06-26 |  | 0 | 2014-06-26 | 2014-06-26 |  | Jill drafts AC.MINUTES 06.05.14
| Team holds debrief meeting |  |  | 1 | 2014-06-26 | 2014-06-26 |  | 0 | 2014-06-26 | 2014-06-26
| Meeting 3 | N |  |  | 2014-07-30 | 9.00 a.m. |  | 0 | 2014-06-26
| Team identifies meeting roles |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Jill coordinates or drafts: | [6 empty] | 0 |  |  |  | Jill coordinates or drafts:
| * AC.AGENDA.06.05.14, gets team agreement | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * AC.AGENDA.06.05.14, gets team agreement
| * AC.NOTIFICATION.06.05.14 |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * AC.NOTIFICATION.06.05.14
| * adds meeting to DEQ Online Calendar (password = dudeman) | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| * releases unneeded venues |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| START OPTION - Presentation Select option > | Y | [5 empty] | 0
| Enter staff name here | [6 empty] | 0
| * drafts optional AC.PRESENTATION.06.05.14 | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * drafts optional AC.PRESENTATION.06.05.14
| Enter staff name here | [6 empty] | 0
| * involves stakeholder presenters, if any |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team approves presentation materials |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Jill submits Web Request to post materials | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | Jill submits Web Request to post materials
| Team practices presentation |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Jill sends meeting notice with link to Web page |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | Jill sends meeting notice with link to Web page
| Team facilitates/holds meeting |  | Set above at Meeting 3 title |  |  | 2014-07-30 |  | 0 |  | 2014-07-30
| Jill drafts AC.MINUTES06.05.14 | i |  | 1 | 2014-06-05 | 2014-06-05 |  | 0 | 2014-07-30 | 2014-06-05 |  | Jill drafts AC.MINUTES06.05.14
| Team holds debrief meeting |  |  | 1 | 2014-06-05 | 2014-06-05 |  | 0 | 2014-07-30 | 2014-06-05
| Meeting 4 | N |  |  | 2014-07-30 | 6:00 p.m. |  | 0 | 2014-07-30
| Team identifies meeting roles |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Jill coordinates or drafts: | [6 empty] | 0 |  |  |  | Jill coordinates or drafts:
| * AC.AGENDA.06.05.14, gets team agreement | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * AC.AGENDA.06.05.14, gets team agreement
| * AC.NOTIFICATION.06.05.14 |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * AC.NOTIFICATION.06.05.14
| * adds meeting to DEQ Online Calendar (password = dudeman) | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| * releases unneeded venues |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| START OPTION - Presentation Select option > | Y | [5 empty] | 0
| Enter staff name here | [6 empty] | 0
| * drafts optional AC.PRESENTATION.06.05.14 | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * drafts optional AC.PRESENTATION.06.05.14
| Enter staff name here | [6 empty] | 0
| * involves stakeholder presenters, if any |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team approves presentation materials |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Jill submits Web Request to post materials | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | Jill submits Web Request to post materials
| Team practices presentation |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Jill sends meeting notice with link to Web page |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | Jill sends meeting notice with link to Web page
| Team facilitates/holds meeting |  | Set above at Meeting 4 title |  |  | 2014-07-30 |  | 0 |  | 2014-07-30
| Jill drafts AC.MINUTES06.05.14 | i |  | 1 | 2014-07-30 | 2014-07-30 |  | 0 | 2014-07-30 | 2014-07-30 |  | Jill drafts AC.MINUTES06.05.14
| Team holds debrief meeting |  |  | 1 | 2014-07-30 | 2014-07-30 |  | 0 | 2014-07-30 | 2014-07-30
| Meeting 5 | N |  |  | 2014-07-30 | 6:00 p.m. |  | 0 | 2014-07-30
| Team identifies meeting roles |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Jill coordinates or drafts: | [6 empty] | 0 |  |  |  | Jill coordinates or drafts:
| * AC.AGENDA.06.05.14, gets team agreement | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * AC.AGENDA.06.05.14, gets team agreement
| * AC.NOTIFICATION.06.05.14 |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * AC.NOTIFICATION.06.05.14
| * adds meeting to DEQ Online Calendar (password = dudeman) | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| * releases unneeded venues |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team assigns custom task here |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| START OPTION - Presentation Select option > | Y | [5 empty] | 0
| Enter staff name here | [6 empty] | 0
| * drafts optional AC.PRESENTATION.06.05.14 | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | * drafts optional AC.PRESENTATION.06.05.14
| Enter staff name here | [6 empty] | 0
| * involves stakeholder presenters, if any |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Team approves presentation materials |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Jill submits Web Request to post materials | i |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | Jill submits Web Request to post materials
| Team practices presentation |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16
| Jill sends meeting notice with link to Web page |  |  | 1 | 2014-07-16 | 2014-07-16 |  | 0 | 2014-07-16 | 2014-07-16 |  | Jill sends meeting notice with link to Web page
| Team facilitates/holds meeting |  | From Meeting 5 title |  |  | 2014-07-30 |  | 0 |  | 2014-07-30
| Jill drafts AC.MINUTES06.05.14 | i |  | 1 | 2014-07-30 | 2014-07-30 |  | 0 | 2014-07-30 | 2014-07-30 |  | Jill drafts AC.MINUTES06.05.14
| Team holds debrief meeting |  |  | 1 | 2014-07-30 | 2014-07-30 |  | 0 | 2014-07-30 | 2014-07-30
| Jill gathers all advisory committee emails for the Rule Record and saves as: | i |  |  | 2014-01-02 | 2015-01-29 |  | 0 | 2014-01-02 | 2015-01-29 |  | Jill gathers all advisory committee emails for the Rule Record and saves as:
| Rule_Development¦3-FeesApproval¦EMAILS.Fees.pdf | [6 empty] | 0
| Fees - not involved | [10 empty] | Fees - not involved
[5 empty] | Start | End
[5 empty] | 0 | 0 |  |  | 0 | 0
| Review version history to help maintaining rulemaking record > | i
| Jill: | [6 empty] | 0 |  |  |  | Jill:
| * devlopes Fee Approval Packet, resources: team and Maggie | i |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | * devlopes Fee Approval Packet, resources: team and Maggie
| Fee Approval Packet includes: | [6 empty] | 0
| a. FEE.ANALYSIS (blank in folder 3) | [6 empty] | 0 |  |  |  | a. FEE.ANALYSIS (blank in folder 3)
| b. FEE.SUPPORT.DOCS | [6 empty] | 0 |  |  |  | b. FEE.SUPPORT.DOCS
| c. FEE.APPROVAL | i | [5 empty] | 0 |  |  |  | c. FEE.APPROVAL
| d. FEE.DETAIL | i | [5 empty] | 0 |  |  |  | d. FEE.DETAIL
| * requests Maggie's review for sufficiency, tone, plain English, style guide |  |  | 4 | 0 | 1900-01-04 |  | 0 | 0 | 1900-01-04 |  | * requests Maggie's review for sufficiency, tone, plain English, style guide
| considering documents will become part of Notice and EQC packets | [6 empty] | 0
| * initiates Leah's Fee Approval Packet review, addresses suggestions |  |  |  |  | 1900-01-04 |  | 0 |  | 1900-01-04 |  | * initiates Leah's Fee Approval Packet review, addresses suggestions
| 1st loop of Leah's Fee Approval Packet review and approval |  |  | -4 | 1900-01-04 | 0 |  | 0 | 1900-01-04 | 0 |  | 1st loop of Leah's Fee Approval Packet review and approval
| 2nd loop of Leah's Fee Approval Packet review and approval | N |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2nd loop of Leah's Fee Approval Packet review and approval
| 3rd loop of Leah's Fee Approval Packet review and approval | N |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 3rd loop of Leah's Fee Approval Packet review and approval
| 4th loop of Leah's Fee Approval Packet review and approval | N |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 4th loop of Leah's Fee Approval Packet review and approval
| AndreaG coordinates: | [6 empty] | 0 |  |  |  | AndreaG coordinates:
| * sending EMAIL.DAS.APPROVAL with Fee Approval Packet attached |  |  |  |  | 0 |  | 0 |  | 0
| - in Outlook, request delivery and read receipts | [6 empty] | 0
| - save receipts to Rule_Dev.¦3-Fee.Approval¦PROOF.DAS.REQUEST.pdf | [6 empty] | 0
| * following up on status about 15 days after sending |  |  |  |  | 0 |  | 0 |  | 0
| DAS sends Jill response |  |  |  |  | 0 |  | 0 |  | 0 |  | DAS sends Jill response
| If denied, Jill coordinates addressing DAS response |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | If denied, Jill coordinates addressing DAS response
| 1st loop of Leah's approval of response to DAS denial |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1st loop of Leah's approval of response to DAS denial
| 2nd loop of Leah's approval of response to DAS denial | N |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2nd loop of Leah's approval of response to DAS denial
| 3rd loop of Leah's approval of response to DAS denial | N |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 3rd loop of Leah's approval of response to DAS denial
| 4th loop of Leah's approval of response to DAS denial | N |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 4th loop of Leah's approval of response to DAS denial
| If approved, Jill scans and files DAS.PART1.pdf |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | If approved, Jill scans and files DAS.PART1.pdf
| Next step happens under 4-Public Notice section | [6 empty] | 0
| Jill gathers all fee emails for the Rule Record and saves as: | i |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Jill gathers all fee emails for the Rule Record and saves as:
| Rule_Development¦3-FeesApproval¦EMAILS.Fees.pdf | [6 empty] | 0
Public Notice
| AQPerm |  |  |  | Start | End
[5 empty] | 2014-01-02 | 2014-09-15 |  |  | 2014-01-02 | 2014-09-15
1900-04-20
| Review version history to help maintain rulemaking record > | i
| DRAFT NOTICE PACKET | [6 empty] | 1
| Jill leads drafting of Notice Packet with core team adhering to plain language |  |  |  | 2014-01-02 | 2014-04-02 |  | 1 | 2014-01-02 | 2014-04-02 |  | Jill leads drafting of Notice Packet with core team adhering to plain language
| and rule conventions outlined in CHECKLIST.PublicDocumentReview | i | [5 empty] | 1
| Notice Packet includes: | [6 empty] | 1
| * INVITATION.TO.COMMENT (develop after Notice is stable ) | [6 empty] | 1
| * PROPOSED.RULES | [6 empty] | 1
| * NOTICE | [6 empty] | 1
| - Overview | [6 empty] | 1
| - Statement of Need | [6 empty] | 1
| - Rules affected, authorities, supporting documents | [6 empty] | 1
| - Fee Analysis | [6 empty] | 1
| - Statement of fiscal and economic impact | [6 empty] | 1
| - Federal relationship | [6 empty] | 1
| - Land use | [6 empty] | 1 |  | 2014-04-25
| - Stakeholder and public involvement | [6 empty] | 1
| * SUPPORTING.DOCS - optional | [6 empty] | 1
| Jill asks RESOURCES for help and input, especially: |  |  |  | 2014-01-02 | 2014-04-02 |  | 1 | 2014-01-02 | 2014-04-02 |  | Jill asks RESOURCES for help and input, especially:
| This is information gathering - not a review | [6 empty] | 1
| * Advisory Committee-for fiscal impact |  |  |  | 2014-01-02 | 2014-04-02 |  | 1 | 2014-01-02 | 2014-04-02 |  | * Advisory Committee-for fiscal impact
| * Affected staff, including regional staff, for contributions |  |  |  | 2014-01-02 | 2014-04-02 |  | 1 | 2014-01-02 | 2014-04-02
| * AndreaG, for SIP consultation |  |  |  | 2014-01-02 | 2014-04-02 |  | 1 | 2014-01-02 | 2014-04-02 |  | * AndreaG, for SIP consultation
| * Leah for direction and subject consultation, especially to ensure drafts: |  |  |  | 2014-01-02 | 2014-04-02 |  | 1 | 2014-01-02 | 2014-04-02 |  | * Leah for direction and subject consultation, especially to ensure drafts:
| - meet program goals for rulemaking | [6 empty] | 1
| - align with section, division and agency goals | [6 empty] | 1
| * AndreaG for rulemaking best practices consultation |  |  |  | 2014-01-02 | 2014-04-02 |  | 1 | 2014-01-02 | 2014-04-02 |  | * AndreaG for rulemaking best practices consultation
| -blank- |  |  |  | 2014-01-02 | 2014-04-02 |  | 1 | 2014-01-02 | 2014-04-02 |  | -blank-
| * Paul, if needed for legal consultation |  |  |  | 2014-01-02 | 2014-04-02 |  | 1 | 2014-01-02 | 2014-04-02 |  | * Paul, if needed for legal consultation
| * Enter custom resource here |  |  |  | 2014-01-02 | 2014-04-02 |  | 1 | 2014-01-02 | 2014-04-02
| * Enter custom resource here |  |  |  | 2014-01-02 | 2014-04-02 |  | 1 | 2014-01-02 | 2014-04-02
| * Enter custom resource here |  |  |  | 2014-01-02 | 2014-04-02 |  | 1 | 2014-01-02 | 2014-04-02
| Jill continually refines draft Notice Packet to consider RESOURCES input |  |  |  | 2014-01-02 | 2014-04-02 |  | 1 | 2014-01-02 | 2014-04-02 |  | Jill continually refines draft Notice Packet to consider RESOURCES input
| * validates approach with RESOURCES as needed | [6 empty] | 1
| * verifies/adjusts previously scheduled briefing & review with Lydia | [6 empty] | 1 |  |  |  | * verifies/adjusts previously scheduled briefing & review with Lydia
| * asks Paul for legal sufficiency if warranted | [6 empty] | 1 |  |  |  | * asks Paul for legal sufficiency if warranted
| * addresses Paul concerns and discusses with Leah as needed | [6 empty] | 1 |  |  |  | * addresses Paul concerns and discusses with Leah as needed
| * informs Leah about the approach, issues and potential delays | [6 empty] | 1 |  |  |  | * informs Leah about the approach, issues and potential delays
| * raises unanticipated rulemaking risks to appropriate level | [6 empty] | 1
| * raises unanticipated rule implementation risks to appropriate level | [6 empty] | 1
| * informs AndreaG about potential delays for and develop contingency, if needed | [6 empty] | 1 |  |  |  | * informs AndreaG about potential delays for and develop contingency, if needed
| Jill asks subject contributors, including Leah for consensus on |  |  |  | 2014-01-02 | 2014-04-02 |  | 1 | 2014-01-02 | 2014-04-02 |  | Jill asks subject contributors, including Leah for consensus on
| completeness and accuracy of technical and program content | [6 empty] | 1
| Jill verifies draft rules to ensure: | [6 empty] | 1 |  |  |  | Jill verifies draft rules to ensure:
| * they are current compared to Oregon State Archives | i | [5 empty] | 1
| * they consider other rulemakings that may affect subject rules | [6 empty] | 1
| * all references to rules and documents within PROPOSED.RULES are current | [6 empty] | 1
| * statutory authorities are correct for each rule | [6 empty] | 1
| * statutes implemented are correct for each rules | [6 empty] | 1
| * SIP note is at bottom of all SIP rules | [6 empty] | 1 |  |  |  | * SIP note is at bottom of all SIP rules
| KEEP MANAGEMENT INFORMED | [6 empty] | 1
| Jill asks Carol to schedule future time on Lydia's calendar for: | Schedule by |  |  |  | 2014-03-24 |  | 1 |  | 2014-03-24 |  | Jill asks Carol to schedule future time on Lydia's calendar for:
| * Lydia briefing meeting with Jill, Leah and AndreaG | Meeting will be |  |  |  | 2014-05-22 |  | 1 |  | 2014-05-22 |  | * Lydia briefing meeting with Jill, Leah and AndreaG
| * time on Lydia's calendar to review Notice Packet during preview week | Review begins on |  |  |  | 2014-05-23 |  | 1 |  | 2014-05-23 |  | * time on Lydia's calendar to review Notice Packet during preview week
| Jill schedules time on Leah calendar to review Notice Packet | [6 empty] | 1 |  |  |  | Jill schedules time on Leah calendar to review Notice Packet
| Jill keeps Leah informed about progress | Review begins on |  |  |  | 2014-04-04 |  | 1 |  | 2014-04-04 |  | Jill keeps Leah informed about progress
| Leah keeps Lydia informed about progress | [6 empty] | 1 |  |  |  | Leah keeps Lydia informed about progress
| Lydia keeps Lydia informed about potential risks & delays | [6 empty] | 1 |  |  |  | Lydia keeps Lydia informed about potential risks & delays
| AndreaG keeps Lydia informed about risks & progress | [6 empty] | 1 |  |  |  | AndreaG keeps Lydia informed about risks & progress
| CUSTOM SEQUENCE | [6 empty] | 1
| Name initiator and subject for custom review loop 1 | N |  |  | 2014-01-02 | 2014-05-21 |  | 1 | 2014-01-02 | 2014-05-21
| * enter custom action word and reviewer |  |  |  | 2014-01-02 | 2014-05-21 |  | 1 | 2014-01-02 | 2014-05-21
| * enter custom action word and reviewer |  |  |  | 2014-01-02 | 2014-05-21 |  | 1 | 2014-01-02 | 2014-05-21
| * enter custom action word and reviewer |  |  |  | 2014-01-02 | 2014-05-21 |  | 1 | 2014-01-02 | 2014-05-21
| Name initiator and subject for custom review loop 2 | N |  |  | 2014-01-02 | 2014-05-21 |  | 1 | 2014-01-02 | 2014-05-21
| * enter custom action word and reviewer |  |  |  | 2014-01-02 | 2014-05-21 |  | 1 | 2014-01-02 | 2014-05-21
| * enter custom action word and reviewer |  |  |  | 2014-01-02 | 2014-05-21 |  | 1 | 2014-01-02 | 2014-05-21
| * enter custom action word and reviewer |  |  |  | 2014-01-02 | 2014-05-21 |  | 1 | 2014-01-02 | 2014-05-21
| Name initiator and subject for custom review loop 3 | N |  |  | 2014-01-02 | 2014-05-21 |  | 1 | 2014-01-02 | 2014-05-21
| * enter custom action word and reviewer |  |  |  | 2014-01-02 | 2014-05-21 |  | 1 | 2014-01-02 | 2014-05-21
| * enter custom action word and reviewer |  |  |  | 2014-01-02 | 2014-05-21 |  | 1 | 2014-01-02 | 2014-05-21
| * enter custom action word and reviewer |  |  |  | 2014-01-02 | 2014-05-21 |  | 1 | 2014-01-02 | 2014-05-21
1
| RULE PUBLICATION WORK | [6 empty] | 1
| Jill prepares Notice, Proposed rules and public Supporting Documents: |  |  |  |  | 2014-04-24 |  | 1 |  | 2014-04-24 |  | Jill prepares Notice, Proposed rules and public Supporting Documents:
| * saves each public document as a Major version | [6 empty] | 1
| * deletes resolved comments in each public document | [6 empty] | 1
| * accepts All changes in Notice | [6 empty] | 1
| * turns on track changes in each public document | [6 empty] | 1
| Jill sends email to AndreaG for Rule Publication work when |  |  |  |  | 2014-04-24 |  | 1 |  | 2014-04-24 |  | Jill sends email to AndreaG for Rule Publication work when
| Notice, Proposed Rules and public Supporting Documents are complete | i | [5 empty] | 1
| Loop 1 - Restart Rule Publication | N |  |  |  | 0 |  | 0 |  | 0
| Loop 2 - Restart Rule Publication | N |  |  |  | 0 |  | 0 |  | 0
| Loop 3 - Restart Rule Publication | N |  |  |  | 0 |  | 0 |  | 0
| Rule Publication work includes: | [6 empty] | 1
| a. establishing, but not activating the following: | [6 empty] | 1 |  | 2014-04-24
| - Outlook comment box for University students with Jill as owner | [6 empty] | 1 |  |  |  | - Outlook comment box for University students with Jill as owner
| - Reminds Jill to set auto reply on Outlook comment box | i | [5 empty] | 1 |  |  |  | - Reminds Jill to set auto reply on Outlook comment box
| - Rulemaking Activities Web page for proposed rule | i | [5 empty] | 1
| - Online public comment form | [6 empty] | 1
| b. determining whether documents are complete and ready for Rule Publication | [6 empty] | 1
| c. determining fiscal and economic impact analysis sufficiency | [6 empty] | 1
| d. reviewing rules using CHECKLIST.PublicDocumentReview | i | [5 empty] | 1
| e. determining whether work products meet rulemaking goals |  |  |  | Rule Publication Work Period |  |  | 1
| f. determining accuracy of work product |  |  |  | Start | Complete by |  | 1
| g. resolving comments among Rule Publication reviewers |  |  |  | 2014-04-25 | 2014-05-09 |  | 1
| h. accepting non substantive edits | [6 empty] | 1
| i. approving documents for publication | [6 empty] | 1
| Rule Publication work involves: | [6 empty] | 1
| AndreaG | [6 empty] | 1 |  |  |  | AndreaG
| * leads Rule Publication work a. | [6 empty] | 1 | ` |  |  | AndreaG who performs initial document readiness review
| * performs initial document readiness work b. | [6 empty] | 1 |  |  |  | AndreaG who performs initial document readiness review
| IF INCOMPLETE, notifies Leah who works with Jill | [6 empty] | 1 |  |  |  | IF INCOMPLETE, notifies Leah who works with Jill
| - renegotiates schedule with Leah & Jill as needed | [6 empty] | 1 |  |  |  | - renegotiates schedule with Leah & Jill as needed
| - reminds Jill to reschedule Lydia briefing as needed | [6 empty] | 1 |  |  |  | - reminds Jill to reschedule Lydia briefing as needed
| - suspends Rule Publication work until Jill resubmits documents | [6 empty] | 1 |  |  |  | - suspends Rule Publication work until Jill resubmits documents
| IF COMPLETE, | [6 empty] | 1
| - performs reviews c. and d. | [6 empty] | 1
| - asks BrianW, StephanieC & Maggie & AndreaG for input as needed | [6 empty] | 1 |  |  |  | - asks BrianW, StephanieC & Maggie & AndreaG for input as needed
| - addresses input to ensure edits and comments speak with one voice | [6 empty] | 1
| - asks Leah for input | [6 empty] | 1 |  |  |  | - asks Leah for input
| Leah | [6 empty] | 1 |  |  |  | Leah
| * performs program review, especially e. and f. | [6 empty] | 1
| * asks AndreaG for concurrance, indicating need to review certain changes | [6 empty] | 1 |  |  |  | * asks AndreaG for concurrance, indicating need to review certain changes
| AndreaG | [6 empty] | 1 |  |  |  | AndreaG
| * addresses input to ensures edits and comments speak with one voice | [6 empty] | 1
| * accepts non substantive edits | [6 empty] | 1
| * asks Leah for concurrence on any changes as indicated | [6 empty] | 1 |  |  |  | * asks Leah for concurrence on any changes as indicated
| - discusses/resolves any editorial differences | [6 empty] | 1 |  |  |  | - discusses/resolves any editorial differences
| * notifies Leah when finished, indicating need to review certain changes | [6 empty] | 1 |  |  |  | * notifies Leah when finished, indicating need to review certain changes
| Leah discusses the following with Jill | [6 empty] | 1 |  |  |  | Leah discusses the following with Jill
| * outstanding work |  |  |  | 2014-05-12 | 2014-04-24 |  | 1 | 2014-05-12 | 2014-04-24 |  | * discusses any outstanding work with Jill
| * need for Paul review | [6 empty] | 1 |  |  |  | * need for Paul review
| Jill: |  |  |  | 1900-01-01 | 1900-01-04 |  | 1 | 1900-01-01 | 1900-01-04 |  | Jill:
| * addresses outstanding edits and comments | [6 empty] | 1
| * asks Paul for review if indicated, addresses input | [6 empty] | 1 |  |  |  | * asks Paul for review if indicated, addresses input
| * asks AndreaG & Leah for concurrence on changes as indicated | [6 empty] | 1 |  |  |  | * asks AndreaG & Leah for concurrence on changes as indicated
| * addresses outstanding edits and comments | [6 empty] | 1 |  |  |  | * addresses Rule Publication concerns
| * notifies AndreaG & Leah when complete and ready for preview | [6 empty] | 1 |  |  |  | * notifies AndreaG & Leah when complete and ready for preview
| PREVIEW PERIOD | [6 empty] | 1
| Jill drafts EMAIL.PREVIEW - instructions in template | i |  |  |  | #REF! |  | 1 |  | #REF! |  | Jill drafts EMAIL.PREVIEW - instructions in template
| * sends draft to Lydia just before briefing - links to preview documents included | [6 empty] | 1 |  |  |  | * sends draft to Lydia just before briefing - links to preview documents included
| * reminds Lydia review starts today | [6 empty] | 1 |  |  |  | * reminds Lydia review starts today
| * copies Leah & AndreaG on email | [6 empty] | 1 |  |  |  | * copies Leah & AndreaG on email
| Jill, Leah brief Lydia |  |  |  | Meeting > | 2014-05-22 |  | 1 |  | 2014-05-22 |  | Jill, Leah brief Lydia
| Lydia personalizes and sends EMAIL.PREVIEW 3 work days after briefing |  |  |  | Preview Period |  |  | 1 |  |  |  | Lydia personalizes and sends EMAIL.PREVIEW 3 work days after briefing
| To… Dick, Lydia, Leadership Team & StephanieC |  |  |  | Start | End |  | 1 |  |  |  | To… Dick, Lydia, Leadership Team & StephanieC
| Cc…to all contributing and affected staff |  |  |  | 2014-05-27 | 2014-05-30 |  | 1 | 2014-05-27 | 2014-05-30
[5 empty] | allow 7-14 days |  |  | 1
1
| Jill: |  |  |  | 2014-05-27 | 2014-06-04 |  | 1 | 2014-05-27 | 2014-06-04 |  | Jill:
| * saves EMAIL.PREVIEW.pdf to Rule_Development¦4-Notice | i | [5 empty] | 1
| * talks with Leah, decides how to address any feedback from preview | [6 empty] | 1 |  |  |  | * talks with Leah, decides how to address any feedback from preview
| * modifies documents as needed | [6 empty] | 1
| * verifies PROPOSED.RULES are still based on current compilation | [6 empty] | 1
| * finalizes public documents with Leah | [6 empty] | 1 |  |  |  | * finalizes public documents with Leah
| Leah: | [6 empty] | 1 |  |  |  | Leah:
| * determines whether Lydia needs a second review 'Y' if 2nd review needed> | Y |  |  | 2014-05-30 | 2014-06-04 |  | 1 | 2014-05-30 | 2014-06-04 |  | * determines whether Lydia needs a second review 'Y' if 2nd review needed>
| * manages Lydia's 2nd review and approval | [6 empty] | 1 |  |  |  | * manages Lydia's 2nd review and approval
| * emails approval to move forward with Notice to Jill & AndreaG |  |  |  |  | 2014-06-05 |  | 1 |  | 2014-06-05 |  | * emails approval to move forward with Notice to Jill & AndreaG
| AndreaG: |  |  |  | 2014-06-06 |  |  | 1 | 2014-06-06 |  |  | AndreaG:
| * compares work products to earlier reviews to determine need for additional edits | [6 empty] | 1
| * obtains additional Rule Publication edits on changes if needed | [6 empty] | 1
| * verifies/clarifies additional edits with Jill & Leah as warranted | [6 empty] | 1 |  |  |  | * verifies/clarifies additional edits with Jill & Leah as warranted
| Jill drafts Invitation to Comment modeled after APPROVED Notice | [6 empty] | 1 |  |  |  | Jill drafts Invitation to Comment modeled after APPROVED Notice
| Leah emails Jill & AndreaG approval to publish notice | Approval to publish notice |  |  |  | 2014-06-10 |  | 1 |  | 2014-06-10 |  | Leah emails Jill & AndreaG approval to publish notice
| Jill: | [6 empty] | 1 |  |  |  | Jill:
| * saves email as Rule_Development¦4-Notice¦MGR.APPROVAL.Notice.pdf | [6 empty] | 1
| NOTIFICATIONS | [6 empty] | 1
| Jill: | [6 empty] | 1 |  |  |  | Jill:
| * submits of Notice to EPA |  |  |  |  | 2014-06-10 |  | 1 |  | 2014-06-10
| AndreaG: |  |  |  | 2014-06-06 |  |  | 1 | 2014-06-06 |  |  | AndreaG:
| * prepares and submits notice to SOS for publication in Oregon Bulletin | i | [5 empty] | 1
| * emails DAS notification of fees that don't require DAS approval | [6 empty] | 0
| * submits SOS CERTIFICATE and REDLINE.RULES Legislative Counsel | [6 empty] | 1
| * saves all evidence on Rule_Development ¦ 4-Notice using naming conventions | i | [5 empty] | 1
| Jill leads: | [6 empty] | 1 |  |  |  | Jill leads:
| * submitting newspaper notices to contractor |  | Set under Planning |  |  | 2014-06-02 |  | 1 |  | 2014-06-02 |  | * modifies documents as needed
| * adding hearings to DEQ online calendar | i |  |  |  | 2014-06-16 |  | 1 |  | 2014-06-16
| * creating an auto reply to Outlook account for University students | i | [5 empty] | 1
| * validating Web page, comment form and Outlook account | [6 empty] | 1 |  |  |  | * validates Web page, comment form, hearing date accuracy with Jill
| * opening public comment by notifying agency rulemaking list that includes: |  |  |  |  | 2014-06-16 |  | 1 |  | 2014-06-16
| - GovDelivery | [6 empty] | 1
| - advisory committee | [6 empty] | 1
| - program-specific list | [6 empty] | 1
| * verifying newspaper advertisements are correct | [6 empty] | 1
| * obtaining copies of affidavits of publication from Accounting | [6 empty] | 1
| * saves all evidence, lists and affidavits on Rule_Development ¦ 4-Notice | i | [5 empty] | 1
` | Jill drafts EMAIL.NOTICE.TO.KEY.LEGISLATORS - instruction in template: | i |  |  |  | 2014-06-09 |  | 1 | 2014-05-27 | 2014-06-09 |  | Jill drafts EMAIL.NOTICE.TO.KEY.LEGISLATORS - instruction in template:
| * sends draft to MargaretO | [6 empty] | 1 |  |  |  | * sends draft to MargaretO
| MargaretO: | [6 empty] | 1 |  |  |  | MargaretO:
| * determines key legislators requiring ORS 183.335(5) notification | i | [5 empty] | 1
| * adapts email as needed | [6 empty] | 1
| * emails to recipients with Return Receipt (redirects receipt to Jill) |  |  |  |  | 2014-06-16 |  | 1 | ` | 2014-06-16 |  | * emails to recipients with Return Receipt (redirects receipt to Jill)
| * copies Jill | [6 empty] | 1 |  |  |  | * copies Jill
| * saves receipts under Rule_Development¦4-Notice using naming conventions | [6 empty] | 1
| AndreaG & Michele maintain Rukemaking Activities Web page |  |  |  | 2014-06-16 | 2014-09-15 |  | 1 | 2014-06-16 | 2014-09-15 |  | AndreaG & Michele maintain Rukemaking Activities Web page
| Jill gathers and saves all emails on | i |  |  | 2014-01-02 | 2014-09-15 |  | 1 | 2014-01-02 | 2014-09-15 |  | Jill gathers and saves all emails on
| Rule_Development¦4-Notice using naming conventions | [6 empty] | 1
Public Comment and Testimony
[5 empty] | Start | End
[5 empty] | 2014-01-02 | 2015-01-28 |  |  | 2014-01-02 | 2015-01-28
| Review version history to help maintaining rulemaking record > | i
| Jill verifies venues and equipment, gathers supplies | i |  |  | 2014-06-13 | 2014-07-16 |  | 1 | 2014-06-13 | 2014-07-16 |  | Jill verifies venues and equipment, gathers supplies
| Team does not plan to hold information meeting | [6 empty] | 0 |  |  |  | Team does not plan to hold information meeting
| Jill: |  |  |  | 2014-06-13 | 2014-06-13 |  | 1 | 2014-06-13 | 2014-06-13 |  | Jill:
| * develops INFO.MEETING.TEXT | [6 empty] | 0 | 0 | 0
| * modifies MESSAGE.MAP | i | [5 empty] | 0 | 0 | 0
| * develops INFO.PRESENTATION | [6 empty] | 0 | 0 | 0
| * practices presentation | [6 empty] | 0 | 0 | 0
| * makes presentation adjustments | [6 empty] | 0 | 0 | 0
| * initiates Leah's review/approval, addresses suggestions |  |  |  | 2014-06-13 | 2014-06-13 |  | 0 | 2014-06-13 | 2014-06-13 |  | * initiates Leah's review/approval, addresses suggestions
| 1st loop Leah reviews/approves optional presentation |  |  |  | 2014-06-13 | 2014-06-13 |  | 0 | 2014-06-13 | 2014-06-13 |  | 1st loop Leah reviews/approves optional presentation
| 2nd loop Leah reviews/approves optional presentation | N |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 2nd loop Leah reviews/approves optional presentation
| 3rd loop Leah reviews/approves optional presentation | N |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 3rd loop Leah reviews/approves optional presentation
| 4th loop Leah reviews/approves optional presentation | N |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 4th loop Leah reviews/approves optional presentation
| Hearings Officers: | [6 empty] | 1
| * reviews responsibilities of hearings officer |  |  |  | 2014-06-13 | 2014-07-16 |  | 1 | 2014-06-13 | 2014-07-16
| * develops introductory and logistics script | i |  |  | 2014-06-13 | 2014-07-16 |  | 1 | 2014-06-13 | 2014-07-16
| * holds the following hearings with assigned team: | [6 empty] | 1 |  |  |  | * holds the following hearings with assigned team:
| 1. Portland hearing |  |  |  |  | 2014-07-16 |  | 1 |  | 2014-07-16 |  | 1. Portland hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.1.mp3 | [6 empty] | 1
| 2. Enter city name hearing |  |  |  |  | 0 |  | 0 |  | 0 |  | 2. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.2.mp3 | [6 empty] | 0
| 3. Enter city name hearing |  |  |  |  | 0 |  | 0 |  | 0 |  | 3. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.3.mp3 | [6 empty] | 0
| 4. Enter city name hearing |  |  |  |  | 0 |  | 0 |  | 0 |  | 4. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.4.mp3 | [6 empty] | 0
| 5. Enter city name hearing |  |  |  |  | 0 |  | 0 |  | 0 |  | 5. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.5.mp3 | [6 empty] | 0
| 6. Enter city name hearing |  |  |  |  | 0 |  | 0 |  | 0 |  | 6. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.6.mp3 | [6 empty] | 0
| 7. Enter city name hearing |  |  |  |  | 0 |  | 0 |  | 0 |  | 7. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.7.mp3 | [6 empty] | 0
| 8. Enter city name hearing |  |  |  |  | 0 |  | 0 |  | 0 |  | 8. Enter city name hearing
| - save audio as Rule_Development¦5-PublicComment¦HEARING.8.mp3 | [6 empty] | 0
| Jill, for comments not received through online form: |  |  | 135 | 2014-07-16 | 2015-01-28 |  | 1 | 2014-07-16 | 2015-01-28 |  | Jill, for comments not received through online form:
| * stamps DEQ receipt date on mailed comments | [6 empty] | 1
| * adds commenter and comment to COMMENTS | [6 empty] | 1
| * scans and links comments by ID###.pdf - optional | [6 empty] | 1
|  |  | Close public comment |  |  | 2014-09-15 |  | 1 |  | 2014-09-15
| Jill: |  |  |  | 2014-09-15 | 2014-11-07 |  | 1 | 2014-09-15 | 2014-11-07 |  | Jill:
| * saves public comment information to COMMENTS | [6 empty] | 1
| * coordinates with team to: | [6 empty] | 1
| - develop category titles to bundle similar comments | [6 empty] | 1
| - organize comments into categories | [6 empty] | 1
| - draft DEQ responses to each categories of comments | [6 empty] | 1
| * leads team work finalizing DEQ responses to public comment | [6 empty] | 1
| DO NOT MAIL TO COMMENTERS UNTIL EQC ASSISTANT FINALIZES STAFF REPORT | [6 empty] | 1
| Jill asks Maggie for Rule Publication work | i |  |  |  | 2014-11-10 |  | 1 |  | 2014-11-10 |  | Jill asks Maggie for Rule Publication work
| Maggie coordinates Rule Publication work: |  |  |  | 2014-11-10 | 2014-11-10 |  | 1 | 2014-11-10 | 2014-11-10 |  | Maggie coordinates Rule Publication work:
| * edits for plain English, style guide and tone | [6 empty] | 1
| since this will become part of the EQC Packet | [6 empty] | 1
| * contacts Jill with questions, clarifications and suggestions | [6 empty] | 1 |  |  |  | * contacts Jill with questions, clarifications and suggestions
| * notifies Jill when complete | [6 empty] | 1 |  |  |  | * notifies Jill when complete
| Jill: | [6 empty] | 1 |  |  |  | Jill:
| * shares comments/responses to comments with Leah & Lydia |  |  |  |  | 2014-11-10 |  | 1 |  | 2014-11-10 |  | * shares comments/responses to comments with Leah & Lydia
| 1st loop - team modifies responses to get to approval |  |  |  | 2014-11-10 | 2014-11-10 |  | 1 | 2014-11-10 | 2014-11-10
| 2nd loop - team modifies responses to get to approval | Y |  |  | 2014-11-10 | 2014-11-10 |  | 1 | 2014-11-10 | 2014-11-10
| 3rd loop - team modifies responses to get to approval | N |  |  | 0 | 0 |  | 0 | 0 | 0
| Final loop - team modifies responses to get to approval | N |  |  | 0 | 0 |  | 0 | 0 | 0
| Jill: | [6 empty] | 1 |  |  |  | Jill:
| * gathers emails ABOUT comments, not actual comments, for Rule Record | i |  |  |  | 2014-11-10 |  | 1 |  | 2014-11-10
| * saves them as Rule_Development¦5-PublicComment...¦EMAIL.Comment.pdf | [6 empty] | 1
EQC Preparation
[5 empty] | Start | End
[5 empty] | 2014-09-15 | 2015-01-29 |  |  | 2014-09-15 | 2015-01-29
| Review version history to help maintaining rulemaking record > | i
| Jill: | [6 empty] | 1 |  |  |  | Jill:
| * drafts content of Director's Report to EQC | [6 empty] | 1 |  |  |  | * drafts content of Director's Report to EQC
| * drafts EQC Information Item | i |  |  | 2014-09-15 | 2014-12-29 |  | 1 | 2014-09-15 | 2014-12-29 |  | * drafts EQC Information Item
| * leads EQC material review |  |  |  | 2014-09-15 | 2015-01-29 |  | 1 | 2014-09-15 | 2015-01-29 |  | * leads EQC material review
| Jill: | [6 empty] | 1 |  |  |  | Jill:
| * discusses need for 1¦1 commissioners briefings with Leah & Lydia | Y |  |  | 2014-09-15 | 2015-01-29 |  | #REF! | 2014-09-15 | 2015-01-29 |  | * discusses need for 1¦1 commissioners briefings with Leah & Lydia
| Enter name of staff who will brief each commissioner - | MEden@neea.org | [5 empty] | #REF!
| Enter name of staff who will brief each commissioner - | JoKRanch@hotmail.com | [5 empty] | #REF!
| Enter name of staff who will brief each commissioner - | EdArmstrong2@gmail.com | [5 empty] | #REF!
| Enter name of staff who will brief each commissioner - | MorganRider@gmail.com | [5 empty] | #REF!
| Enter name of staff who will brief each commissioner - | cjohnson@eou.edu | [5 empty] | #REF!
| Jill develops STAFF.RPT.Permanent preloaded in folder 6 by: |  |  |  | 2014-09-15 | 2014-11-07 |  | 1 | 2014-09-15 | 2014-11-07 |  | Jill develops STAFF.RPT.Permanent preloaded in folder 6 by:
| * selecting EQC recommendation in staff report | [6 empty] | 1
| * integrating NOTICE into STAFF REPORT.Permanent by | [6 empty] | 1 |  |  |  | * integrating NOTICE into STAFF REPORT.Permanent by
| inserting message into header according to instructions in staff report: | [6 empty] | 1
| - Statement of need | [6 empty] | 1
| - Federal relationships | [6 empty] | 1
| - Fiscal impact statement | [6 empty] | 1
| - Fees | [6 empty] | 1
| - Land use | [6 empty] | 1
| - NAME OTHER SECTION UNCHANGED SINCE PUBLIC NOTICE REVIEW | [6 empty] | 1
| - NAME OTHER SECTION UNCHANGED SINCE PUBLIC NOTICE REVIEW | [6 empty] | 1
| * verifies PROPOSED.RULES use latest compilation compared | i | [5 empty] | 1
| compared to Oregon State Archives | [6 empty] | 1
| * coordinates work on STAFF.RPT.Permanent sections: | [6 empty] | 1 |  |  |  | * coordinates work on STAFF.RPT.Permanent sections:
| - may update the following as needed, highlight changes since Notice: | [6 empty] | 1
| > change past tense to present tense throughout document as appropriate | [6 empty] | 1
| > Overview section | [6 empty] | 1
| > Background (optional) section | [6 empty] | 1
| > Rules affected, authorities, supporting documentation | [6 empty] | 1
| > Stakeholder involvement section | [6 empty] | 1
| - draft Implementation section | [6 empty] | 1
| - Insert Summary of comments and DEQ responses | [6 empty] | 1
| > inserts message above to indicate previous reviews | [6 empty] | 1
| - Commenters | [6 empty] | 1
| *Submit to PaulG if needed | [6 empty] | 1 |  |  |  | - Paul, if needed
| * finalizes draft of EQC Packet: | [6 empty] | 1
| - STAFF.RPT.Permanent | [6 empty] | 1 |  |  |  | - STAFF.RPT.Permanent
| - PROPOSED.RULES | [6 empty] | 1
| - SUPPORTING.DOCUMENTS | [6 empty] | 1
| * notifies AndreaG that Staff Report is ready for Rule Publication work | [6 empty] | 1 |  |  |  | * notifies AndreaG that Staff Report is ready for Rule Publication work
| AndreaG leads initial Rule Publication work that includes: |  |  |  | Rule Publication Work Period |  |  | 1 |  |  |  | AndreaG leads initial Rule Publication work that includes:
| * comparing Notice to EQC Staff Report to determine what needs review |  |  |  | 2014-11-07 | 2014-12-04 |  | 1 | 2014-11-07 | 2014-12-04
| * obtaining/consolidating BrianW, StephanieC & AndreaG edits if needed | [6 empty] | 1 |  |  |  | * obtaining/consolidating BrianW, StephanieC & AndreaG edits if needed
| including style guide, grammar, plain English, organization, clarity, tone | [6 empty] | 1
| * accepting all style guide and format edits | [6 empty] | 1
| * facilitates Leah's review | [6 empty] | 1
| * contacts Jill with questions or modifications and when work is complete | [6 empty] | 1 |  |  |  | * contacts Jill with questions or modifications and when work is complete
| AndreaG lets Jill know when work is complete | [6 empty] | 1 |  |  |  | AndreaG lets Jill know when work is complete
| - Enter custom reviewer and action |  |  |  | 2014-09-15 | 2015-01-29 |  | 1 | 2014-09-15 | 2015-01-29
| - Enter custom reviewer and action |  |  |  | 2014-09-15 | 2015-01-29 |  | 1 | 2014-09-15 | 2015-01-29
| - Enter custom reviewer and perspective |  |  |  | 2014-09-15 | 2015-01-29 |  | 1 | 2014-09-15 | 2015-01-29
| Enter custom review loop 1 | Y |  |  | 0 | 0 |  | 1 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 1 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 1 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 1 | 0 | 0
| Name initiator and subject for custom review loop 2 | Y |  |  | 0 | 0 |  | 1 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 1 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 1 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 1 | 0 | 0
| Name initiator and subject for custom review loop 3 | Y |  |  | 0 | 0 |  | 1 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 1 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 1 | 0 | 0
| * enter custom action word and reviewer |  |  |  | 0 | 0 |  | 1 | 0 | 0
| Jill addresses Rules Publication work |  |  |  | 2014-12-04 | 2014-12-22 |  | 1 | 2014-12-04 | 2014-12-22 |  | * drafts content of Director's Report to EQC
| * obtains approval to publish EQC Packet from: | [6 empty] | 1
| - AndreaG for Rules Publications |  |  |  | 2014-12-22 | 2015-01-02 |  | 1 | 2014-12-22 | 2015-01-02 |  | - Leah for lead manager approval
| - Leah for lead manager approval |  |  |  | 2015-01-09 | 2015-01-14 |  | 1 | 2015-01-09 | 2015-01-14 |  | - Leah for lead manager approval
| - Lydia for division administrator approval |  |  |  | 2015-01-21 | 2015-01-28 |  | 1 | 2015-01-21 | 2015-01-28 |  | - Lydia for division administrator approval
| EQC Packet is due to StephanieC: |  |  |  |  | 2015-01-29 |  | 1 | 2014-09-15 | 2015-01-29 |  | - Lydia for division administrator approval
| * notifies the following according to division's best practice |  |  |  |  | 2015-02-19 |  | 1 |  | 2015-02-19
| - staff contributors | [6 empty] | 1
| - key stakeholders | [6 empty] | 1
| - advisory committee members | [6 empty] | 1
| - commenters | [6 empty] | 1
| - interested parties (optional) | [6 empty] | 1
[8 empty] | 1 |  |  |  | Jill:
| * leads team development of EQC presentation |  |  |  | 2014-09-15 | 2015-02-17 |  | 1 | 2014-09-15 | 2015-02-17
| * coordinates presentation practices | [6 empty] | 1 | 2014-09-15 | 2015-02-17
| * makes any presentation adjustments | [6 empty] | 1 | 0 | 2015-02-17
| * submits presentation to StephanieC by deadline (Estimate due date 2/17/15) | [6 empty] | 1 | 0 | 2015-02-17
[8 empty] | 1 |  |  |  | Jill:
| Presentation team ATTENDS EQC MEETING |  |  |  | 0 | 2015-03-11 |  | 1 |  | 2015-03-11
| Jill collects emails about EQC preparations for Rule Record and saves as: | i |  |  | 2015-03-11 | 2015-03-11 |  | 1 | 2015-03-11 | 2015-03-11 |  | Jill collects emails about EQC preparations for Rule Record and saves as:
| Rule_Development¦6-EQCPreparation¦EMAILS.EQC.Prep.pdf | [6 empty] | 1
Post EQC
[5 empty] | Start | End
[5 empty] | 2015-03-11 | 2015-06-09 |  |  | 2015-03-11 | 2015-06-09
| Review version history to help maintaining rulemaking record > | i
| Work shifts from SharePoint to Rule_Development | [6 empty] | 1
| Jill: | [6 empty] | 1 |  |  |  | Jill:
| * prepares/saves documents to Rule_Development¦7-PostEQC |  |  |  |  | 2015-03-11 |  | 1 |  | 2015-03-11
| - ADDENDUM.TO.STAFF.RPT (if presented to EQC) | [6 empty] | 1
| - RULES.docx (clean version) | [6 empty] | 1
| - REDLINE.docx (showing changes in strikethrough and underscore) | [6 empty] | 1
| - TABLES.340-###-####.docx (1 .docx per rule contains ALL tables in rule) | [6 empty] | 1
| - TABLES.340-###-####.docx (1 .docx per rule contains ALL tables in rule) | [6 empty] | 1
| * emails Maggie to affirm EQC action and document readiness | [6 empty] | 1 |  |  |  | * emails Maggie to affirm EQC action and document readiness
| * emails optional STAKEHOLDER.NOTIFICATION of EQC action | Y |  |  |  | 2015-03-11 |  | 1 |  | 2015-03-11
| * coordinates EPA.SIP.SUBMITAL with AndreaG |  |  |  |  | 2015-03-11 |  | 1 |  | 2015-03-11 |  | * coordinates EPA.SIP.SUBMITAL with AndreaG
| * coordinates AC.THANK.YOU email or letter with Leah | i |  |  |  | 2015-03-11 |  | 1 |  | 2015-03-11 |  | * coordinates AC.THANK.YOU email or letter with Leah
| * coordinates AC.SURVEY with Leah | i |  |  |  | 2015-03-11 |  | 1 |  | 2015-03-11 |  | * coordinates AC.SURVEY with Leah
| * coordinates optional discussion on project evaluation, lessons learned |  |  |  |  | 2015-03-11 |  | 1 |  | 2015-03-11
| AndreaG: | [6 empty] | 1 |  |  |  | AndreaG:
| * submits Part 2 of signed DAS approval within 10 days of effective date |  |  |  |  | 0 |  | 0 |  | 0 |  | * submits Part 2 of signed DAS approval within 10 days of effective date
| * scans/saves as Rule_Development¦7-PostEQC¦DAS.PART2.pdf |  |  |  |  | 0 |  | 0 |  | 0 |  | * scans/saves as Rule_Development¦7-PostEQC¦DAS.PART2.pdf
| * emails DAS.PART2.pdf to DAS (requests delivery receipt) |  |  |  |  | 0 |  | 0 |  | 0 |  | * emails DAS.PART2.pdf to DAS (requests delivery receipt)
| * saves receipts as Rule_Dev.¦7-PostEQC¦PROOF.DAS.DELIVERY.pdf |  |  |  |  | 0 |  | 0 |  | 0 |  | * saves receipts as Rule_Dev.¦7-PostEQC¦PROOF.DAS.DELIVERY.pdf
| Maggie: | [6 empty] | 1 |  |  |  | Maggie:
| * prepares and e-files ADOPTED RULES with Secretary of State | i |  |  |  | 2015-03-13 |  | 1 |  | 2015-03-13
| EFFECTIVE DATE |  |  |  |  | 2015-03-13 |  | 1 |  | 2015-03-13
| * shuttles Legislative Counsel notification by return receipt | i |  |  |  | 2015-03-13 |  | 1 |  | 2015-03-13
| - Certificate.SOS-Stamped.pdf | [6 empty] | 1
| - Redline.LC.pdf | [6 empty] | 1
| - self-addressed envelope, fold underside of flap over a 2nd certificate" | [6 empty] | 1
| write "Please date stamp certificate and return." on underside of flap | [6 empty] | 1
| * combine/save following PDFs as Rule_Development¦7-PostEQC | i |  |  |  | 2015-03-13 |  | 1 |  | 2015-03-13
| ¦CERTIFICATE.SOS.LC.Documentation.pdf | [6 empty] | 1
| 1 Certificate.SOS-stamped.pdf | [6 empty] | 1
| reserved for temporary rules | [6 empty] | 0 |  |  |  | reserved for temporary rules
| 2 Rules.SOS.pdf | [6 empty] | 1
| 2a 340-### Tables.SOS.pdf | [6 empty] | 1
| 2b 340-### Tables.SOS.pdf | [6 empty] | 1
| 3 HousingCosts.SOS.pdf | [6 empty] | 1
| 4 Authorization.SOS.pdf | [6 empty] | 1
| 5 Certificate.LC-stamped.pdf | [6 empty] | 1
| 6 Redline.LC.pdf | [6 empty] | 1
| 7 ShuttleTracking.LC.pdf | [6 empty] | 1
| * coordinates with Jill to: | i |  | 1 | 2015-03-13 | 2015-03-13 |  | 1 | 2015-03-13 | 2015-03-13 |  | * coordinates with Jill to:
| - archive records | i | [5 empty] | 1
| - retire SharePoint | [6 empty] | 1
| - close Outlook account |  |  |  |  | 2015-03-13 |  | 1 |  | 2015-03-13
| - update Web page | [6 empty] | 1
| Jill: | [6 empty] | 1 |  |  |  | Jill:
| * gathers emails about post EQC activities for the Rule Record and saves as: |  |  | 1 | 2015-03-13 | 2015-03-13 |  | 1 | 2015-03-13 | 2015-03-13
| Rule_Development¦7-PostEQC¦EMAILS.PostEQC.pdf | [6 empty] | 1
| * verifies accuracy of rules published in Oregon Bulletin |  |  | 1 | 2015-03-30 | 2015-03-30 |  | 1 | 2015-03-30 | 2015-03-30
| If errors, Jill works with Maggie to correct and selects 'Y' > | Y |  | 1 | 2015-03-30 | 2015-03-30 |  | 1 | 2015-03-30 | 2015-03-30 |  | If errors, Jill works with Maggie to correct and selects 'Y' >
| AndreaG submits SIP to EPA within 60 days AFTER adoption |  |  | 34 | 2015-03-11 | 2015-04-27 |  | 1 | 2015-03-11 | 2015-04-27 |  | AndreaG submits SIP to EPA within 60 days AFTER adoption
| Jill: | [6 empty] | 1 |  |  |  | Jill:
| * places all physical records in archival box - do not print electronic records |  |  | 62 | 2015-03-13 | 2015-06-09 |  | 1 | 2015-03-13 | 2015-06-09
| * labels the box by SOS certificate and order number "DEQ ##-yyyy" |  |  |  |  | 2015-06-09 |  | 1 | 0 | 2015-06-09
| * delivers archival box to Maggie |  |  |  |  | 2015-06-09 |  | 1 | 0 | 2015-06-09 |  | * delivers archival box to Maggie
| AndreaG coordinates retiring Q-Time number(s) with RobertB |  |  | 1 | 2015-03-13 | 2015-03-13 |  | 1 | 2015-03-13 | 2015-03-13 |  | AndreaG coordinates retiring Q-Time number(s) with RobertB
| At the close of the rulemaking records, Maggie archives the record | [6 empty] | 1 |  |  |  | At the close of the rulemaking records, Maggie archives the record
| FROM: \\deqhq1\Rule_Development | i | [5 empty] | 1
| TO: \\deqhq1\Rule_Archives | [6 empty] | 1
| TEAM CELEBRATES |  |  | 62 | 2015-03-13 | 2015-06-09 |  | 1 | 2015-03-13 | 2015-06-09
| Jill takes a vacation | [6 empty] | 1 |  |  |  | Jill takes a vacation
$H$910
mm/dd/yy
Subject
Your name
Your message
DEQ Closed

## ConditionalFormat
|  | Format | Calculation | Applies to | Last row
Place cursor in first cell of range in column E calculation before applying conditional format.
On ScheduleOfTasks
Tiered Approach - Selections made in Column C of Schedule |  |  | =IF($AF6=0,TRUE) | $B$6:$H$896
Selection turns row is ON based formula in AF |  | Teal on white | 1 = FALSE
Selection turns row OFF based on formula in AF |  | Grey on white | 0 = TRUE
Office Closure
S.DDL_DEQClosed is the "holiday" table in WORKDAY function. |  | Office Closure date | =IF(WORKDAY($G6-1,1,S.DDL_DEQClosed)<>$G6,TRUE) | $G$6:$G$896 (or last row)
|  | Office Closure date | =IF(WORKDAY($H12-1,1,S.DDL_DEQClosed)<>$H12,TRUE) | $H$12:$H$896 (or last row)
Gantt
| An 'X' in $J10 identifies the row as for Gantt to format | Workday | =AND($J10<>"X",$G10<=L$7,$H10>=K$7) | $K10:$AHC$450
|  | Weekend | =IF(OR(WEEKDAY(K$7)=1,WEEKDAY(K$7)=7),TRUE) | $K10:$AHC$450
|  | Closed | =IF(ISERROR(VLOOKUP(K$7,S.DDL_DEQClosed,1,FALSE)),0,1) | $K10:$AHC$450
S.LastCellGantt
s.LastCellschedule

## WQTrade.Calendar (hidden)
AQ Permitting |  |  |  | AQPerm
starting |  |  |  | 2014-10-06 | [6 empty] | 2014-10-13 | [6 empty] | 2014-10-20 | [6 empty] | 2014-10-27 | [6 empty] | 2014-11-03 | [6 empty] | 2014-11-10 | [6 empty] | 2014-11-17 | [6 empty] | 2014-11-24
2014-10-06 |  |  |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Adjust start date +/- from today |  |  | 0 | 2014-10-06 | 2014-10-07 | 2014-10-08 | 2014-10-09 | 2014-10-10 | 2014-10-11 | 2014-10-12 | 2014-10-13 | 2014-10-14 | 2014-10-15 | 2014-10-16 | 2014-10-17 | 2014-10-18 | 2014-10-19 | 2014-10-20 | 2014-10-21 | 2014-10-22 | 2014-10-23 | 2014-10-24 | 2014-10-25 | 2014-10-26 | 2014-10-27 | 2014-10-28 | 2014-10-29 | 2014-10-30 | 2014-10-31 | 2014-11-01 | 2014-11-02 | 2014-11-03 | 2014-11-04 | 2014-11-05 | 2014-11-06 | 2014-11-07 | 2014-11-08 | 2014-11-09 | 2014-11-10 | 2014-11-11 | 2014-11-12 | 2014-11-13 | 2014-11-14 | 2014-11-15 | 2014-11-16 | 2014-11-17 | 2014-11-18 | 2014-11-19 | 2014-11-20 | 2014-11-21 | 2014-11-22 | 2014-11-23 | 2014-11-24 | 2014-11-25 | 2014-11-26 | 2014-11-27 | 2014-11-28 | 2014-11-29 | 2014-11-30
| Start | End
Add to DEQ Rulemaking Plan |  |  | 0: 0
Establish Q-time numbers | 0 | 2014-01-02 | bar: 0
Setup shared sites | 2014-01-02 | 2014-01-02 | bar: 0
Kickoff worksession | 2014-01-02 | 2014-01-02 | bar: 0
Planning Sequence |  |  | 0: 0
Draft workbooks | 2014-01-02 | 2014-01-02 | bar: 0
Communications Meeting | 2014-01-02 | 2014-01-02 | bar: 0
Rules Sequence | 2014-01-02 | 2015-06-09 | 0: 0
@ Start | 0 | 0 | bar: 0
@ Notice | 2014-01-02 | 0 | bar: 0
@ EQC Preparation | 0 | 0 | bar: 0
@ Filing | 0 | 0 | bar: 0
SIP Sequence | bar: 0
@ Notice EPA/SIP 180 days | 2013-12-16 | 2013-12-16 | bar: 0
@ Notice: EPA/SIP 45 days | #NAME? | #NAME? | 0: #NAME?
@ Post EQC: Submit to EPA | 2015-05-11 | 2015-05-11 | 0: 0
Fee Sequence |  |  | 0: 0
@ Fee Approval: Part 1 to DAS | 0 | 0 | bar: 0
@ Post EQC: Part 2 to DAS | 2015-03-16 | 2015-03-16 | 0: 0
@ Notice Email DAS for exempt fees | 0 | 0 | bar: 0
Advisory Committee Sequence |  |  | 0: 0
Invitation | 2014-01-02 | 2014-01-02 | bar: 0
Meeting 1 | 2014-06-05 | 2014-06-05 | bar: 0
Meeting 2 | 2014-06-26 | 2014-06-26 | bar: 0
Meeting 3 | 2014-07-30 | 2014-07-30 | bar: 0
Meeting 4 | 2014-07-30 | 2014-07-30 | bar: 0
Meeting 5 | 2014-07-30 | 2014-07-30 | bar: 0
Involve EQC Sequence |  |  | 0: 0
Directors Report 1 | 0 | 0 | bar: 0
Directors Report 2 | 0 | 0 | bar: 0
Info Item 1 | 2015-01-07 | 2015-01-07 | 0: 0
Info Item 2 | 2015-01-07 | 2015-01-07 | 0: 0
Notice Sequence |  |  | 0: 0
EPA/SIP 180 days | 2013-12-16 | 2013-12-16 | bar: 0
EPA/SIP 45 days | #NAME? | #NAME? | 0: #NAME?
Involve DEQ RESOURCES | #REF! | #REF! | 0: #REF!
Send Ad to contract services | 2014-06-02 | 2014-06-02 | bar: 0
Manager approval | 2014-06-05 | 2014-06-05 | bar: 0
Open/Close Comment | 2014-06-16 | 2014-09-15 | bar: 0
DA briefing schedule/meeting | 2014-05-22 | 2014-05-22 | bar: 0
Email DAS for exempt fees | 0 | 0 | bar: 0
Preview period | 2014-05-27 | 2014-05-30 | bar: 0
SOS Bulletin submit/publish | 2014-06-13 | 2014-07-01 | bar: 0
Hearing: first/last | 2014-07-16 | 2014-07-16 | bar: 0
EQC Preparation Sequence |  |  | 0: 0
EQC Meeting | 2015-03-11 | 2015-03-11 | 0: 0
Post EQC Sequence |  |  | 0: 0
Filing/effective | 2015-03-13 | 2015-03-13 | 0: 0
Part 2 to DAS | 2015-03-16 | 2015-03-16 | 0: 0
Submit to EPA | 2015-05-11 | 2015-05-11 | 0: 0
1
1

## GetStarted
Title | CodeName
AQ Permitting | AQPerm | i
Names entered under this area will become part of the Schedule of Tasks and Partnershup Agreement
| Enter first name for Schedule | Enter full name for Agreement | Division | Program | Pronoun
Subject Expert | Jill
Sponsoring Manager | Leah
Sponsoring Partner Manager | Lydia
Rules Group Partner | AndreaG
Standardization (ARC) | Maggie
Public Affairs Representative | BrianW
EQC Assistant | StephanieC |  |  | GET STARTED
State Implementation Plan Coordinator | AndreaG |  |  | Enter names and codes on this worksheet
Web Master | Michele
FiscalReviewer | Maggie |  |  | ON SCHEDULE
Budget analyst | Maggie |  |  | Enter Title in header
Assistant Attorney General | Paul |  |  | Enter start date in G6
Legislative liaison | MargaretO |  |  | When Directors adds to plan, enter date in G9
Support staff | Jill | <<<<< If support staff is not available, include Lead staff's name |  | Select Y/N options in C9:C50
Time Accounting | RobertB |  |  | All banner dates set on Overview of Key dates
Director | Dick |  |  | Drop down lists
Hearings Officer | HearingOfficer |  |  | EQC optional involvement G39:H41
Division Administrator - Rules | Lydia |  |  | SOS Bulletin H31
Division Administrator - Program | Lydia |  |  | EQC meeting H44
DA Assistant | Carol
Chief Public Affairs Officer | N/A
Media Manager
Jennifer | WQ
Wendy | LQ
Uri | AQ
Budget Analyst
AdamC | WQ
SandraM | LQ
MargaretO | AQ
Legislative Liason
KarenT | WQ
TomR | LQ
MargaretO | AQ

## HearingAndAdDates
AQ Permitting |  |  |  | 2014-10-06
Hearings
|  |  | Hearings Officer | Notes
City | Date | Time
Portland | 2014-07-16 | 6 p.m. | 6 p.m.
-blank - | -blank - | -blank - | -blank -
-blank - | -blank - | -blank - | -blank -
-blank - | -blank - | -blank - | -blank -
-blank - | -blank - | -blank - | -blank -
-blank - | -blank - | -blank - | -blank -
-blank - | -blank - | -blank - | -blank -
-blank - | -blank - | -blank - | -blank -
Newspaper Advertisements
NOTICE.AD1Oregonian | 2014-06-16
NOTICE.AD2None | 2014-06-16
NOTICE.AD3None | 2014-06-16
NOTICE.AD4None | 2014-06-16
NOTICE.AD5None | 2014-06-16
NOTICE.AD6None | 2014-06-16
NOTICE.AD7None | 2014-06-16
NOTICE.AD8None | 2014-06-16

## DDLs
DDLs called from ScheduleTasks
1 | 2 | 3 | 4 | 5 | 6
DDL_EQCMeeting | EQCStaffRptDue | EQCMaterialsDue | Days to next | Next | Last
2013-03-20 | 2013-02-11 | 2013-03-13 | 91 | 2013-06-19 | 2012-12-16 | When updating EQC table, leave rows for previous year.
2013-06-19 | 2013-05-10 | 2013-06-12 | 63 | 2013-08-21 | 2013-03-20
2013-08-21 | 2013-07-16 | 2013-08-14 | 56 | 2013-10-16 | 2013-06-19
2013-10-16 | 2013-09-10 | 2013-10-09 | 56 | 2013-12-11 | 2013-08-21
2013-12-11 | 2013-11-01 | 2013-12-04 | 99 | 2014-03-20 | 2013-10-16
2014-03-20 | 2014-02-13 | 2014-02-24 | 293 | 2015-01-07 | 2012-12-16 |  | 2014-01-24
2014-06-18 | 2014-05-12 | 2014-05-26 | 70 | 2014-08-27 | 2013-08-29 |  | 2014-03-20
2014-08-27 | 2014-07-24 | 2014-08-04 | 70 | 2014-11-05 | 2014-06-18 |  | 2014-06-18
2014-11-05 | 2014-09-29 | 2014-10-13 | 63 | 2015-01-07 | 2014-08-27 |  | 2014-08-20
2015-01-07 | 2014-12-02 | 2014-12-10 | 63 | 2015-03-11 | 2014-11-05 |  | 2014-10-22
2015-03-11 | 2015-01-29 | 2015-02-27 | 98 | 2015-06-17 | 2015-01-07 |  | 2014-12-17
2015-06-17 | 2015-05-07 | 2015-06-05 | 63 | 2015-08-19 | 2015-03-11 |  | 2015-03-18
2015-08-19 | 2015-07-09 | 2015-08-07 | 63 | 2015-10-21 | 2015-06-17 |  | 2015-06-17
2015-10-21 | 2015-09-10 | 2015-10-09 | 56 | 2015-12-16 | 2015-08-19 |  | 2015-08-19
2015-12-16 | 2015-11-05 | 2015-12-04 | 98 | 2016-03-23 | 2015-10-21 |  | 2015-10-21
2016-03-23 | 2016-02-11 | 2016-03-11 | 91 | 2016-06-22 | 2015-12-16 |  | 2015-12-16
2016-06-22 | 2016-05-12 | 2016-06-10 | 56 | 2016-08-17 | 2016-03-23 |  | 2016-03-23
2016-08-17 | 2016-07-07 | 2016-08-05 | 63 | 2016-10-19 | 2016-06-22 |  | 2016-06-22
2016-10-19 | 2016-09-08 | 2016-10-07 | 63 | 2016-12-21 | 2016-08-17
2016-12-21 | 2016-11-10 | 2016-12-09 | 91 | 2017-03-22 | 2016-10-19
2017-03-22 | 2017-02-09 | 2017-03-10 | 91 | 2017-06-21 | 2016-12-21
2017-06-21 | 2017-05-11 | 2017-06-09 | 91
http://www.leg.state.or.us/ors/187.html
DEQClosed | [7 empty] | LEGAL HOLIDAYS 187.010 Legal holidays; acts deferred to next business day; effect on labor agreements. (1) The following days are legal holidays in this state: (a) Each Sunday. (b) New Year’s Day on January 1. (c) Martin Luther King, Jr.’s Birthday on the third Monday in January. (d) Presidents Day, for the purpose of commemorating Presidents Washington and Lincoln, on the third Monday in February. (e) Memorial Day on the last Monday in May. (f) Independence Day on July 4. (g) Labor Day on the first Monday in September. (h) Veterans Day on November 11. (i) Thanksgiving Day on the fourth Thursday in November. (j) Christmas Day on December 25. (2) Each time a holiday, other than Sunday, listed in subsection (1) of this section falls on Sunday, the succeeding Monday shall be a legal holiday. Each time a holiday listed in subsection (1) of this section falls on Saturday, the preceding Friday shall be a legal holiday. (3) Any act authorized, required or permitted to be performed on a holiday as designated in this section may be performed on the next succeeding business day; and no liability or loss of rights of any kind shall result from such delay. (4) In enumerating legal holidays in subsection (1) of this section, the Legislative Assembly does not intend to limit or otherwise affect public or private collective bargaining or collective bargaining agreements. [Amended by 1955 c.4 §1; 1969 c.455 §1; 1973 c.51 §1; 1975 c.633 §1; 1977 c.135 §1; 1977 c.321 §1; 1985 c.518 §1] 187.020 Additional legal holidays. In addition to those specified in ORS 187.010, the following days are legal holidays in this state: (1) Every day appointed by the Governor as a holiday. (2) Every day appointed by the President of the United States as a day of mourning, rejoicing or other special observance only when the Governor also appoints that day as a holiday. [Amended by 1969 c.455 §2; 1975 c.633 §2; 1977 c.135 §2; 1977 c.321 §2; 1985 c.518 §2]
2013-01-01 | New Year | 2013-01-01
2013-01-18 | furlough | 2013-01-18
2013-01-21 | MLK Jr. | 2013-01-21
2013-02-18 | Presidents | 2013-02-18
2013-04-19 | furlough | 2013-04-19
2013-05-24 | furlough | 2013-05-24
2013-05-27 | Memorial | 2013-05-27
2013-07-04 | Independence | 2013-07-04
2013-09-02 | Labor | 2013-09-02
2013-11-11 | Veterans | 2013-11-11
2013-11-28 | Thanksgiving | 2013-11-28
2013-12-25 | Christmas | 2013-12-25
2014-01-01 | New Year | 2014-01-01
2014-01-20 | MLK Jr. | 2014-01-20
2014-02-17 | Presidents | 2014-02-17
2014-05-26 | Memorial | 2014-05-26
2014-07-04 | Independence | 2014-07-04
2014-09-02 | Labor | 2014-09-02
2014-11-11 | Veterans | 2014-11-11
2014-11-27 | Thanksgiving | 2014-11-27
2014-12-25 | Christmas | 2014-12-25
2015-01-01 | New Year | 2015-01-01
2015-01-19 | MLK Jr. | 2015-01-19
2015-02-16 | Presidents | 2015-02-16
2015-05-25 | Memorial | 2015-05-25
2015-07-03 | Independence | 2015-07-03
2015-09-07 | Labor | 2015-09-07
2015-11-11 | Veterans | 2015-11-11
2015-11-26 | Thanksgiving | 2015-11-26
2015-12-25 | Christmas | 2015-12-25
2016-01-01 | New Year | 2016-01-01
2016-01-18 | MLK Jr. | 2016-01-18
2016-02-15 | Presidents | 2016-02-15
2016-05-30 | Memorial | 2016-05-30
2016-07-04 | Independence | 2016-07-04
2016-09-05 | Labor | 2016-09-05
2016-11-11 | Veterans | 2016-11-11
2016-11-24 | Thanksgiving | 2016-11-24
2016-12-26 | Christmas | 2016-12-26
2017-01-02 | New Year | 2017-01-02
2017-01-16 | MLK Jr. | 2017-01-16
2017-02-20 | Presidents | 2017-02-20
2017-05-29 | Memorial | 2017-05-29
2017-07-04 | Independence | 2017-07-04
2017-09-04 | Labor | 2017-09-04
2017-11-10 | Veterans | 2017-11-10
2017-11-23 | Thanksgiving | 2017-11-23
2017-12-25 | Christmas | 2017-12-25
2018-01-01 | New Year | 2018-01-01
Called from ScheduleTasks
DDL_Bulletin | VL_Bulletin
2013-01-01 | 2012-12-14 | 2012-12-14
2013-02-01 | 2013-01-15 | 2013-01-15
2013-03-01 | 2013-02-15 | 2013-02-15
2013-04-01 | 2013-03-15 | 2013-03-15
2013-05-01 | 2013-04-15 | 2013-04-15
2013-06-01 | 2013-05-15 | 2013-05-15
2013-07-01 | 2013-06-14 | 2013-06-14
2013-08-01 | 2013-07-15 | 2013-07-15
2013-09-01 | 2013-08-15 | 2013-08-15
2013-10-01 | 2013-09-13 | 2013-09-13
2013-11-01 | 2013-10-15 | 2013-10-15
2013-12-01 | 2013-11-15 | 2013-11-15
2014-01-01 | 2013-12-13 | 2013-12-13
2014-02-01 | 2014-01-15 | 2014-01-15
2014-03-01 | 2014-02-14 | 2014-02-14
2014-04-01 | 2014-03-14 | 2014-03-14
2014-05-01 | 2014-04-15 | 2014-04-15
2014-06-01 | 2014-05-15 | 2014-05-15
2014-07-01 | 2014-06-13 | 2014-06-13
2014-08-01 | 2014-07-15 | 2014-07-15
2014-09-01 | 2014-08-15 | 2014-08-15
2014-10-01 | 2014-09-15 | 2014-09-15
2014-11-01 | 2014-10-15 | 2014-10-15
2014-12-01 | 2014-11-14 | 2014-11-14
2015-01-01 | 2014-12-15 | 2014-12-15
2015-02-01 | 2015-01-15 | 2015-01-15
2015-03-01 | 2015-02-13 | 2015-02-13
2015-04-01 | 2015-03-13 | 2015-03-13
2015-05-01 | 2015-04-15 | 2015-04-15
2015-06-01 | 2015-05-15 | 2015-05-15
2015-07-01 | 2015-06-15 | 2015-06-15
2015-08-01 | 2015-07-15 | 2015-07-15
2015-09-01 | 2015-08-15 | 2015-08-15
2015-10-01 | 2015-09-15 | 2015-09-15
2015-11-01 | 2015-10-15 | 2015-10-15
2015-12-01 | 2015-11-13 | 2015-11-13
2016-01-01 | 2015-12-15 | 2015-12-15
2016-02-01 | 2016-01-15 | 2016-01-15
2016-03-01 | 2016-02-15 | 2016-02-15
2016-04-01 | 2016-03-15 | 2016-03-15
2016-05-01 | 2016-04-15 | 2016-04-15
2016-06-01 | 2016-05-13 | 2016-05-13
2016-07-01 | 2016-06-15 | 2016-06-15
2016-08-01 | 2016-07-15 | 2016-07-15
2016-09-01 | 2016-08-15 | 2016-08-15
2016-10-01 | 2016-09-15 | 2016-09-15
2016-11-01 | 2016-10-14 | 2016-10-14
2016-12-01 | 2016-11-15 | 2016-11-15
2017-01-01 | 2016-12-15 | 2016-12-15
2017-02-01 | 2017-01-13 | 2017-01-13
2017-03-01 | 2017-02-15 | 2017-02-15
2017-04-01 | 2017-03-15 | 2017-03-15
2017-05-01 | 2017-04-14 | 2017-04-14
2017-06-01 | 2017-05-15 | 2017-05-15
2017-07-01 | 2017-06-15 | 2017-06-15
2017-08-01 | 2017-07-14 | 2017-07-14
2017-09-01 | 2017-08-15 | 2017-08-15
2017-10-01 | 2017-09-15 | 2017-09-15
2017-11-01 | 2017-10-13 | 2017-10-13
2017-12-01 | 2017-11-15 | 2017-11-15
2018-01-01 | 2017-12-15 | 2017-12-15
2018-02-01 | 2018-01-15 | 2018-01-15
2018-03-01 | 2018-02-15 | 2018-02-15
2018-04-01 | 2018-03-14 | 2018-03-14
2018-05-01 | 2018-04-13 | 2018-04-13
2018-06-01 | 2018-05-15 | 2018-05-15
2018-07-01 | 2018-06-15 | 2018-06-15
2018-08-01 | 2018-07-13 | 2018-07-13
2018-09-01 | 2018-08-15 | 2018-08-15
2018-10-01 | 2018-09-14 | 2018-09-14
2018-11-01 | 2018-10-15 | 2018-10-15
2018-12-01 | 2018-11-15 | 2018-11-15
2019-01-01 | 2018-12-14 | 2018-12-14
2019-02-01 | 2019-01-15 | 2019-01-15
2019-03-01 | 2019-02-15 | 2019-02-15
2019-04-01 | 2019-03-15 | 2019-03-15
2019-05-01 | 2019-04-15 | 2019-04-15
2019-06-01 | 2019-05-15 | 2019-05-15
2019-07-01 | 2019-06-14 | 2019-06-14
2019-08-01 | 2019-07-15 | 2019-07-15
2019-09-01 | 2019-08-15 | 2019-08-15
2019-10-01 | 2019-09-13 | 2019-09-13
2019-11-01 | 2019-10-15 | 2019-10-15
2019-12-01 | 2019-11-15 | 2019-11-15
2020-01-01 | 2019-12-13 | 2019-12-13
2020-02-01 | 2020-01-15 | 2020-01-15
2020-03-01 | 2020-02-14 | 2020-02-14
2020-04-01 | 2020-03-13 | 2020-03-13
2020-05-01 | 2020-04-15 | 2020-04-15
2020-06-01 | 2020-05-15 | 2020-05-15
2020-07-01 | 2020-06-15 | 2020-06-15
2020-08-01 | 2020-07-15 | 2020-07-15
2020-09-01 | 2020-08-14 | 2020-08-14
2020-10-01 | 2020-09-15 | 2020-09-15
2020-11-01 | 2020-10-15 | 2020-10-15
2020-12-01 | 2020-11-13 | 2020-11-13
2021-01-01 | 2020-12-15 | 2020-12-15
2021-02-01 | 2021-01-15 | 2021-01-15
2021-03-01 | 2021-02-15 | 2021-02-15
2021-04-01 | 2021-03-15 | 2021-03-15
2021-05-01 | 2021-04-15 | 2021-04-15
2021-06-01 | 2021-05-14 | 2021-05-14
2021-07-01 | 2021-06-15 | 2021-06-15
2021-08-01 | 2021-07-15 | 2021-07-15
2021-09-01 | 2021-08-13 | 2021-08-13
2021-10-01 | 2021-09-15 | 2021-09-15
2021-11-01 | 2021-10-15 | 2021-10-15
2021-12-01 | 2021-11-15 | 2021-11-15
Called from ScheduleTasks
| Newapapers | EQC Facilitated Hearing
Oregonian
EastOregon
RegisterGuard
MailTribune
KlamathHerald
LaGrandeObserver
JournalOfCommerce
None
Other
Formulas:
Next = [DDL_EQCMeeting]+[Days to next]
Last = [DDL_EQCMeeting]-[Days to next, row above]
EQCStaffRptDue = WORKDAY([DDL_EQCMeeting]-40,-1,S.DDL_DEQClosed)
EQCMaterialsDue = WORKDAY([DDL_EQCMeeting]-9,-1,S.DDL_DEQClosed)
EQCMaterialsDue = [DDL_EQCMeeting]

## ActivitySequence
INTERIM RULEMAKING PARTNERSHIP AGREEMENT
AQ Permitting
Code: AQPerm
Description
Enter short description from CONSIDERATIONS
Objectives
Enter objectives from CONSIDERATIONS
Assumptions and Contraints
Enter assumption and contraints identified in CONSIDERATIONS
Managing Partners
Changes to this agreement require the approval and signature of both Partners. A change in scope and missed deadlines may result in re-prioritizing this rulemaking.
| Sponsoring Partner | , :
| Subject Expert | , :
| Rules Group Partner | , :
Deliverables
Activity Sequence – Add to DEQ Rulemaking Plan
Deadline | Responsibility for Meeting Deadline | Deliverable | Purpose | Recipiant | Done
2014-01-02 | Rules Group Partner: | Shared drive Draft workbooks | Worksession | 0 | N
2014-01-02 | Sponsoring Partner: | Draft workbooks CONSIDERATIONS RESOURCES | Input | and AndreaG | N
2014-01-02 | Sponsoring Partner's Manager: Lydia | Draft workbooks with edits CONSIDERATIONS RESOURCES | Input | Leah and AndreaG | N
| Rules Group Partner: AndreaG | Updated Rulemaking Projects Priorities list | Determine capacity Prioritize rulemakings Validate with Leah | Rules Group | N
| Rules Group Partner: AndreaG | Proposed addition to DEQ Rulemaking Plan | Approve, postpone, reject | Dick | N
Activity Sequence - Planning for Director-approved rulemaking priorities
Deadline | Resonsibility for Meeting Deadline | Deliverable | Purpose | Recipient | Done
| Sponsoring Partner: Leah | Refine workbooks Considerations Resources Schedule | Input, notification | People identified in RESOURCES workbook | N
| Sponsoring Partner: Leah | Communications Plan | Input, advice | People identified in RESOURCES workbook | N
Activity Sequence - Notice Packet
Invitation to Comment
Notice
Proposed Rules
Supporting Documents
Deadline | Resonsibility for Meeting Deadline | Deliverable | Purpose | Recipient | Done
#REF! | Sponsoring Partner: Leah | Draft notice & rules | Input, notification | People identified in RESOURCES workbook | N
#REF! | People identified in RESOURCES workbook | Input | Expand knowledge | Leah | N
| Sponsoring Partner: Leah | Draft notice & rules | Input, advice, review | AndreaG | N
| Rules Group Partner: AndreaG | Draft notice & rules | Initial review to ensure standardization, organization, preliminary review of fiscal and economic impact statement, small business analysis | Leah | N
| Sponsoring Partner: Leah | Notice Packet | Confirm adequacy of rulemaking materials | AndreaG | N
2014-05-27 | Sponsoring Partner: Leah | Notice Packet Preview Email: LT, EQC Assistant, RESOURCES | Inform | Lydia | N
2014-05-30 | Sponsoring Partner's Manager: Lydia | Notice Packet | Review and approval | Leah
| Division Administrator Lydia | Notice Packet with edits; Approval | Approval | Leah
| Sponsoring Partner's Manager: Lydia | Final Notice Packet | OK to publish | AndreaG
| Rules Group Partner: AndreaG | Final minor edit | Publication ready | Web staff
| Sponsoring Partner: Leah | Confirm accuracy of published rules | Inform | AndreaG
| Sponsoring Partner: Leah | List of hearing participants and their roles; Finalized hearing materials and presentation | Input, advice, review | #NAME?
Activity Sequence – Publication
Deadline | Responsibility for Meeting Deadline | Deliverable | Purpose | Recipient | Done
| Sponsoring Partner: Leah | Approved Newspaper ad(s), Notification lists, Notice content (legislators email, GovDelivery and Interested Parties) | Input, advice, review | AndreaG | N
| Rules Group Partner: AndreaG | Activate Web page, Online comment form. Submit Newspaper ad, SOS Notice, Notification Lists, DAS | Publication | Carol, Legislative staff and Web staff | N
Activity Sequence – EQC Packet
Staff Report
Proposed Rules
Deadline | Responsibility for Meeting Deadline | Deliverable | Purpose | Recipient | Done
| Sponsoring Partner: Leah | EQC Packet | Input, notification | People identified in RESOURCES workbook | N
| Rules Group Partner: AndreaG | EQC Packet | Input, advice, review | Leah | N
| EPA, DOJ | EQC Packet | Review as needed | Leah | N
| Sponsoring Partner: Leah | EQC Packet - finalized | Review and approval | Lydia | N
| Division Administrator: Lydia | EQC Packet with edits, Approval | Approval | Leah | N
| Sponsoring Partner: Leah | Final EQC Packet | OK to publish | AndreaG | N
| Rules Group Partner: AndreaG | Final minor edit | EQC ready | StephanieC | N
Activity Sequence – EQC Presentation
Deadline | Responsibility for Meeting Deadline | Deliverable | Purpose | Send to | Done
| Sponsoring Partner: Leah | List of EQC presenters, their roles and responsibilities; Final EQC Presentation | Input, advice, review | AndreaG | N
| Rules Group Partner: AndreaG | Presentation with minor edit | EQC ready | StephanieC | N
| Rules Group Partner: AndreaG | Update Web page, Online comment form. SOS Filing, DAS, Legislative Counsel | Rules become effective | SOS; Legislative Counsel; DAS | N
Activity Sequence – Rulemaking Record
Deadline | Responsibility for Meeting Deadline | Deliverable | Purpose | Send to | Done
| Sponsoring Partner: Leah | Confirm accuracy of published rules Submit supporting documents for record | Inform | AndreaG | N
| Rules Group Partner: AndreaG | Archive records; Retire SharePoint; Close Outlook account; Update Web page | Complete rulemaking |  | N
Activity Sequence - Rule Development
Deadline | Resonsibility for Meeting Deadline | Deliverable | Purpose | Send to | Done
Sponsoring Manager
, : DATE
Rules Group Partner
, : DATE