SIP Development Plan

Updated 4.22.2013

Title:  	Oregon Permitting Program Updates

EPA Team:  Justin Spenillo (lead), Dave Bray (technical), Donna Deneen (technical), Julie Vergeront (legal), Lucita Valiere (Title V), Katie McClintock (Enforcement/Permitting)

ODEQ Team:  Jill Inahara (lead), Gary Andes (technical), George David, (technical), Mark Fisher (technical), Karen White-Fallon (technical), Paul Garrahan/DOJ (legal).

Subject: Air Quality Permitting Program Update

- rule restructure:

  - move all of the procedures out of definitions into specific rules;

  - repeal outdated rules (aluminum, sulfite pulp mill, ferronickel, spray paint);

  - include test methods with all standards;

- repeal 40% grain loading and 0.2 grain/dscf;

- add zero for standards that do not have 2 significant figures (grain loading standards);

- revise minor source NSR;

- clarify rules (splitting sources, NSR/PSD extensions);

- spray paint rules;

- Heat Smart reporting requirements;

- Oxy fuel changes; and

- National SSM (potential).

Schedule

| Action | ODEQ / LRAPA Submit to EPA | EPA Feedback |
| --- | --- | --- |
| October meeting – Kickoff, discuss revisions and provide preliminary comments on feasibility and suggestions | October 24, 2012 |  |
| December meeting: Discuss updated proposed permitting rule revisions, potential issues (technical/legal/policy). | Week of December 10, 2012 (phone) |  |
| Check-in call with ODEQ/LRAPA | January 10, 2013 |  |
| Early rule revisions drafts to EPA | March 12, 2013 | March 25, 2013 |
| Updated rule revisions drafts and crosswalk | April 1, 2013 |  |
| April meeting: Later rule revisions drafts / follow-up questions | April 3, 2013 (video/in person) |  |
| Internal Review Emission Limit Rules 200, 206, 208, 212, 214 (less CAM provisions),226, 228, 232, 234, 236, 240, 242, 262) – EPA internal Focused revision review 3 (cluster 3 = Title V Rules 218, 220, 214 CAM provisions) | June 4, 2013 |  |
| VTC with ODEQ | June 5, 2013 |  |
| Internal Review: Permitting Rules 200, 202, 204, 209, 210, 216, 222, 224, 225, 268) – EPA internal | June 11, 2013 |  |
| VTC with ODEQ | June 13, 2013 |  |
| Rulemaking Package to EPA | July 12, 2013 |  |
| EPA Final Comments – internal | August 20, 2013 |  |
| EPA Final Comments Meeting – VTC or in person | August 21, 2013 |  |
| Public Comment Period Opens | October 1, 2013 |  |
| Public Hearings | November 12, 2013 |  |
| EQC Meeting | March 20, 2014 |  |
| Submittal to EPA | March 25, 2014 |  |
| Process Evaluation | Summer 2014 |  |