SIP Development Plan

Updated 4.5.2013

Title:  	Oregon Permitting Program Updates

EPA Team:  Justin Spenillo (lead), Dave Bray (technical), Donna Deneen (technical), Julie Vergeront (legal)

ODEQ Team:  Jill Inahara (lead), Gary Andes (technical), George David, (technical), Mark Fisher (technical), Karen White-Fallon (technical), Paul Garrahan/DOJ (legal).

Subject: Air Quality Permitting Program Update

- rule restructure:

  - move all of the procedures out of definitions into specific rules;

  - repeal outdated rules (aluminum, sulfite pulp mill, ferronickel, spray paint);

  - include test methods with all standards;

- repeal 40% grain loading and 0.2 grain/dscf;

- add zero for standards that do not have 2 significant figures (grain loading standards);

- revise minor source NSR;

- clarify rules (splitting sources, NSR/PSD extensions);

- spray paint rules;

- Heat Smart reporting requirements;

- Oxy fuel changes; and

- National SSM (potential).

Schedule

| Action | ODEQ / LRAPA Submit to EPA | EPA Feedback |
| --- | --- | --- |
| October meeting – Kickoff, discuss revisions and provide preliminary comments on feasibility and suggestions | October 24, 2012 |  |
| December meeting: Discuss updated proposed permitting rule revisions, potential issues (technical/legal/policy). | Week of December 10, 2012 (phone) |  |
| Check-in call with ODEQ/LRAPA | January 10, 2013 |  |
| Early rule revisions drafts to EPA | March 12, 2013 | March 25, 2013 |
| Updated rule revisions drafts and crosswalk | April 1, 2013 |  |
| April meeting: Later rule revisions drafts / follow-up questions | April 3, 2013 (video/in person) |  |
| Focused revisions review 1 (cluster 1 = Rules 200, 202, 206, 208, 209, 210, 212, 214 (CAM provisions if CAA relevant), (218, 220 – Title V discussion), 226, 228, 232, 234, 236, 240, 242, 262, 268) – EPA internal | Tuesday May 21, 2013 I moved some rules in this this cluster because we will not be changing them in our internal rulemaking meetings in May. They are pretty much done for now and ready for EPA review. |  |
| Focused revisions review 1 – VTC with ODEQ | Wednesday May 22, 2013 |  |
| Focused revision review 2 (cluster 2 = Rules 200, 204, 216, , 222, 224, 225) – EPA internal | June 11, 2013 I think I can get you new versions of these rules by May 17 at the latest. |  |
| Focused revision review 2 – VTC with ODEQ | June 12, 2013Could we do this the previous week, Justin? My rulemaking team will be in town June 4-7 and we can head over to your PDX office for the VTC |  |
| Rulemaking Package to EPA | July 12, 2013 |  |
| EPA Final Comments – internal | August 13, 2013 |  |
| EPA Final Comments Meeting – VTC or in person | August 14, 2013 |  |
| Public Comment Period Opens | October 1, 2013 |  |
| Public Hearings | November 1, 2013 November 12, 2013 |  |
| EQC Meeting | December 13, 2013 March 20, 2014 |  |
| Submittal to EPA | December 21, 2013 March 25, 2014 |  |
| Process Evaluation | Summer 2014 |  |