## Database Format
Rule | Task # | Date
AQ Permitting Program Update | 1 | 0
AQ Permitting Program Update | 2 | 0
AQ Permitting Program Update | 3 | 0
AQ Permitting Program Update | 4 | 0
AQ Permitting Program Update | 5 | 0
AQ Permitting Program Update | 6 | 0
AQ Permitting Program Update | 7 | 0
AQ Permitting Program Update | 8 | 0
AQ Permitting Program Update | 9 | 0
AQ Permitting Program Update | 10 | 0
AQ Permitting Program Update | 11 | 0
AQ Permitting Program Update | 12 | 0
AQ Permitting Program Update | 13 | 0
AQ Permitting Program Update | 14 | 0
AQ Permitting Program Update | 15 | 0
AQ Permitting Program Update | 16 | 0
AQ Permitting Program Update | 17 | 0
AQ Permitting Program Update | 18 | 0
AQ Permitting Program Update | 19 | 0
AQ Permitting Program Update | 20 | 0
AQ Permitting Program Update | 21 | 0
AQ Permitting Program Update | 22 | 0
AQ Permitting Program Update | 23 | 0
AQ Permitting Program Update | 24 | 0
AQ Permitting Program Update | 25 | 0
AQ Permitting Program Update | 26 | 0
AQ Permitting Program Update | 27 | 0
AQ Permitting Program Update | 28 | 0
AQ Permitting Program Update | 29 | 0
AQ Permitting Program Update | 30 | 0
AQ Permitting Program Update | 31 | 0
AQ Permitting Program Update | 32 | 0
AQ Permitting Program Update | 33 | 0
AQ Permitting Program Update | 34 | 0
AQ Permitting Program Update | 35 | 0
AQ Permitting Program Update | 36 | 0
AQ Permitting Program Update | 37 | 0

## AQ Rulemaking Schedule
Air Quality Worksheet for Rulemaking Schedule
Rule Title: AQ Permitting Program Update |  |  |  |  | Clear All Blackouts
Project Lead & Phone: Jill Inahara 503.229.5001 |  |  |  |  | Date | [5 empty] | Day of Week |  |  | Days since previous act
DA | # | DB | Develop Rulemaking | N/A | Option 1 | Calc 1 | Option 2 | Calc 2 | Option 3 | Calc 3 | Option 1 | Option 2 | Option 3 | Option 1 | Option 2 | Option 3
Current Option in Use >
|  |  | Start Rulemaking Proposal | [13 empty] | 1 | Sunday
| NA |  | Route Start Rulemaking Proposal to Section Mgr (at least 5 days prior to DA due date) | [13 empty] | 2 | Monday
IN | NA |  | Route Start Rulemaking Proposal to Division Administrator (at least 1 week prior to OD due date) | [13 empty] | 3 | Tuesday
OUT |  | 1 | Submit Start Rulemaking Proposal to OD (9:00 a.m.) | [13 empty] | 4 | Wednesday
APT |  |  | Dry Run Start Rulemaking Proposal w/Division Administrator & others (the Thursday before the EMT meeting) | [13 empty] | 5 | Thursday
|  | 2 | Start Rulemaking Proposal meeting – EMT | [13 empty] | 6 | Friday
|  |  | Fee Approval | [13 empty] | 7 | Saturday
| NA |  | *Request DAS to approve new & increased fees (at least 30 days prior to filing notice w/SOS or date rule is effective)
|  |  | *Obtain DAS approval or denial of fees (goal = within 30 days of submittal) If DAS Approval is Not Required, DAS must still be notified of Fee Changes. DAS enters all agency fees into a database. | [13 empty] | 1
Draft Notice of Proposed Rulemaking Package
| NA |  | Route draft Notice of Proposed Rulemaking package to Section Mgr (at least 5 days prior to DA due date) | [13 empty] | Project Lead & Phone:
IN | NA |  | Route draft Notice of Proposed Rulemaking package to Division Administrator (at least 1 week prior to submitting to reviewers) | [13 empty] | Aida Biberic 503.229.5280
OUT |  | 3 | Submit draft Notice of Proposed Rulemaking package to reviewers (author) | [13 empty] | Andrea Curtis 503.229.6866 | Project Lead & Phone: Andrea Curtis 503.229.6866
|  |  | Reviewer comments to author | [13 empty] | Brandy Albertson 503.229.6459 | Project Lead & Phone: Brandy Albertson 503.229.6459
[17 empty] | Brian Finneran 503.229.6278 | Project Lead & Phone: Brian Finneran 503.229.6278
|  |  | Final Notice of Proposed Rulemaking Package | [13 empty] | Carrie Ann Capp 503.229-5035 | Project Lead & Phone: Carrie Ann Capp 503.229-5035
| NA |  | Route final Notice of Proposed Rulemaking package to Section Mgr (at least 5 days prior to DA due date) |  | 2013-06-03 | 2013-06-03 | 2013-04-05 | 2013-04-05 | 2013-07-29 | 2013-07-29 | Monday | Friday | Monday |  |  |  | Cory Ann Wind 503.229.5388 | Project Lead & Phone: Cory Ann Wind 503.229.5388
IN | NA |  | Route final Notice of Proposed Rulemaking package to Division Administrator (at least 1 week prior to submitting to reviewers) |  | 2013-06-10 | 2013-06-10 | 2013-04-10 | 2013-04-10 | 2013-08-05 | 2013-08-05 | Monday | Wednesday | Monday | 7 | 5 | 7 | Dave Nordberg 503.229.5519 | Project Lead & Phone: Dave Nordberg 503.229.5519
OUT |  | 4 | Submit final Notice of Proposed Rulemaking package for concurrence review |  | 2013-06-17 | 2013-06-17 | 2013-04-17 | 2013-04-17 | 2013-08-16 | 2013-08-16 | Monday | Wednesday | Friday | 7 | 7 | 11 | Esther Westbrook 503.229.5547 | Project Lead & Phone: Esther Westbrook 503.229.5547
|  |  | Concurrence reviews due to author |  | 2013-06-24 | 2013-06-24 | 2013-04-24 | 2013-04-24 | 2013-08-23 | 2013-08-23 | Monday | Wednesday | Friday | 7 | 7 | 7 | Gregg Dahmen 503.229.5108 | Project Lead & Phone: Gregg Dahmen 503.229.5108
|  |  | Submit final Notice of Proposed Rulemaking package for Division Administrator for approval |  | 2013-07-01 | 2013-07-01 | 2013-05-01 | 2013-05-01 | 2013-08-30 | 2013-08-30 | Monday | Wednesday | Friday | 7 | 7 | 7 | Jerry Ebersole 503.229.6974 | Project Lead & Phone: Jerry Ebersole 503.229.6974
IN |  |  | Division Administrator authorizes publication of Notice |  | 2013-07-08 | 2013-07-08 | 2013-05-08 | 2013-05-08 | 2013-09-06 | 2013-09-06 | Monday | Wednesday | Friday | 7 | 7 | 7 | Jill Inahara 503.229.5001 | Project Lead & Phone: Jill Inahara 503.229.5001
|  |  | Public Notice, Hearing & Comment | [13 empty] | Kevin Downing 503.229.6549 | Project Lead & Phone: Kevin Downing 503.229.6549
OUT |  | 5 | Send Notice to Secretary of State for Bulletin (by 15th;earlier if weekend/holiday) |  | 2013-07-15 | 2013-07-15 | 2013-05-15 | 2013-05-15 | 2013-09-13 | 2013-09-13 | Monday | Wednesday | Friday | 7 | 7 | 7 | Larry Calkins 541.567.8297 x25 | Project Lead & Phone: Larry Calkins 541.567.8297 x25
| NA |  | Send Notice to EPA (at least 45 days prior to hearing) Only applies to SIP rules – make sure the AG’s office has reviewed the rule prior to submitting it to EPA |  | 2013-07-05 | 2013-07-05 | 2013-05-15 | 2013-05-15 | 2013-08-26 | 2013-08-26 | Friday | Wednesday | Monday | -10 | 0 | -18 | Phil Allen 503.229.6904 | Project Lead & Phone: Phil Allen 503.229.6904
| NA |  | Mail Notice to mailing & e-mail lists (at least 28 days prior to hearing, excluding mailing date, if a SIP rule, must be mailed 30 days prior to hearing) |  | 2013-07-22 | 2013-07-22 | 2013-05-31 | 2013-05-31 | 2013-10-11 | 2013-10-11 | Monday | Friday | Friday | 17 | 16 | 46 | Rachel Sakata 503.229.5659 | Project Lead & Phone: Rachel Sakata 503.229.5659
| NA |  | Publish legal ad in local newspapers (at least 30 days prior to hearing, excluding publication and hearing date) Applies whenever hearings held. |  | 2013-07-22 | 2013-07-22 | 2013-05-31 | 2013-05-31 | 2013-10-11 | 2013-10-11 | Monday | Friday | Friday | 0 | 0 | 0 | Sarah Armitage 503.229.5186 | Project Lead & Phone: Sarah Armitage 503.229.5186
| NA | 6 | Notice published in Bulletin (1st of Month; 21 days before effective date) |  | 2013-08-01 | 2013-08-01 | 2013-06-01 | 2013-06-01 | 2013-10-01 | 2013-10-01 | Thursday | Saturday | Tuesday | 10 | 1 | -10 | Sue Langston 503.229.5215 | Project Lead & Phone: Sue Langston 503.229.5215
| NA | 7 | Public Hearing(s) (At least 15 days after notice in Bulletin, excluding pub date) (An evening time slot will allow the working public a greater opportunity to attend. This is STRONGLY advised!) |  | 2013-08-21 | 2013-08-21 | 2013-07-01 | 2013-07-01 | 2013-11-12 | 2013-11-12 | Wednesday | Monday | Tuesday | 20 | 30 | 42 | Jill Inahara 503.229.5001 | Project Lead & Phone: Jill Inahara 503.229.5001
| NA | 8 | Public Comment deadline (usually 3 to 7 days after hearing) |  | 2013-08-28 | 2013-08-28 | 2013-07-10 | 2013-07-10 | 2013-11-19 | 2013-11-19 | Wednesday | Wednesday | Tuesday | 7 | 9 | 7
Adopt Rule - EQC
Draft Final Rulemaking Package
| NA |  | Route draft Final Rulemaking package to Section Mgr (at least 5 days prior to DA due date)
IN | NA |  | Route draft Final Rulemaking package to Division Administrator (at least 1 week prior to submitting to reviewers)
OUT |  | 9 | Distribute draft Final Rulemaking package to reviewers (author)
|  | 10 | Reviewer comments due to author
Final Rulemaking Package
| NA |  | Route Final Rulemaking package to Section Mgr (at least 5 days prior to DA due date) |  | 2013-09-25 | 2013-09-25 | 2013-08-07 | 2013-08-07 | 2014-01-03 | 2014-01-03 | Wednesday | Wednesday | Friday
IN | NA |  | Route Final Rulemaking package to Division Administrator (at least 1 week prior to submitting to reviewers) |  | 2013-09-30 | 2013-09-30 | 2013-08-12 | 2013-08-12 | 2014-01-10 | 2014-01-10 | Monday | Monday | Friday | 5 | 5 | 7
OUT |  | 11 | Route Final Rulemaking package for concurrence review |  | 2013-10-07 | 2013-10-07 | 2013-08-19 | 2013-08-19 | 2014-01-17 | 2014-01-17 | Monday | Monday | Friday | 7 | 7 | 7
|  | 12 | Concurrence reviews due to author |  | 2013-10-14 | 2013-10-14 | 2013-08-26 | 2013-08-26 | 2014-01-24 | 2014-01-24 | Monday | Monday | Friday | 7 | 7 | 7
IN |  | 13 | Route Final Rulemaking package to Division Administrator for approval for submittal to OD |  | 2013-10-18 | 2013-10-18 | 2013-08-30 | 2013-08-30 | 2014-01-31 | 2014-01-31 | Friday | Friday | Friday | 4 | 4 | 7
OUT | NA |  | Submit Final Rulemaking package to OD for signature and distribution (5:00 p.m.) (e-mail and 1 hard copy w/signed staff report) (At least 17 days before mailing to EQC. |  | 2013-11-01 | 2013-11-01 | 2013-09-13 | 2013-09-13 | 2014-02-07 | 2014-02-07 | Friday | Friday | Friday | 14 | 14 | 7
| NA | 14 | OD mails EQC Staff Report w/attachments to EQC (At least 24 days before EQC meeting date.) |  | 2013-11-18 | 2013-11-18 | 2013-09-30 | 2013-09-30 | 2014-02-24 | 2014-02-24 | Monday | Monday | Monday | 17 | 17 | 17
| NA | 15 | Submit presentation slides and handouts to OD (at least 8 days before EQC meeting date.) |  | 2013-12-04 | 2013-12-04 | 2013-10-16 | 2013-10-16 | 2014-03-12 | 2014-03-12 | Wednesday | Wednesday | Wednesday | 16 | 16 | 16
EQC Meeting
APT |  |  | Dry run EQC Presentation w/ Division Administrator & others | [5 empty] | 2014-03-10 | 2014-03-10 |  |  | Monday |  |  | 14
|  | 16 | EQC meeting date |  | 2013-12-12 | 2013-12-12 | 2013-10-24 | 2013-10-24 | 2014-03-20 | 2014-03-20 | Thursday | Thursday | Thursday |  |  | 10
|  | Key: | Column 'DA' are dates rulemaking involves the DA. Some are by appointment.
|  |  | Column '#' is the calculation of days for the row requirement. Red is bad! | Days
|  |  | Column 'DB' is for the rule coordinator. | Mths
Formulas:
Option 1 = [Option 1, row below]-7
Calc 1 = IF([N/A]="",IF([Option 1]<>"",[Option 1],""),[Calc 1, row above])
Option 2 = [Option 2, row below]-5
Calc 2 = IF([N/A]="",IF([Option 2]<>"",[Option 2],""),I19)
Calc 2 = IF([N/A]="",IF([Option 2]<>"",[Option 2],""),[Calc 2, row above])
Option 3 = [Option 3, row below]-7
Calc 3 = IF([N/A]="",IF([Option 3]<>"",[Option 3],""),K19)
Calc 3 = IF([N/A]="",IF([Option 3]<>"",[Option 3],""),[Calc 3, row above])
Note on B31: Gary Beyer: This calculated number of days must be: If SIP related; at least 30. If NOT SIP related; at least 28.
Note on B32: Gary Beyer: This calculated number of days must be at least 30. Only applies to SIP rules!
Note on D30: Gary Beyer: See LA column (A) for calculated number of days. If the number is RED it does not meet the SIP requirement. Option 1, 2, or 3 (above) must be selected for this calculation to occur.
Note on D31: Gary Beyer: See LA column (A) for calculated number of days. If the number is RED it does not meet the SIP requirement. Option 1, 2, or 3 (above) must be selected for this calculation to occur.
Note on D32: Gary Beyer: See LA column (A) for calculated number of days. If the number is RED it does not meet the SIP requirement. Option 1, 2, or 3 (above) must be selected for this calculation to occur.
Note on D33: Gary Beyer: See LA column (A) for calculated number of days. If the number is RED it does not meet the SIP requirement. Option 1, 2, or 3 (above) must be selected for this calculation to occur.
Note on D34: Gary Beyer: See LA column (A) for calculated number of days. If the number is RED it does not meet the SIP requirement. Option 1, 2, or 3 (above) must be selected for this calculation to occur.