SIP Development Plan

Title:  	Oregon Permitting Program Updates

EPA Team:  Justin Spenillo (lead), Dave Bray (technical), Donna Deneen (technical), Julie Vergeront (legal)

ODEQ Team:  Jill Inahara (lead), Gary Andes (technical), George David, (technical), Mark Fisher (technical), Karen White-Fallon (technical), Paul Garrahan/DOJ (legal).

Subject: Air Quality Permitting Program Update

- move all of the procedures out of definitions into specific rules;

- repeal outdated rules (aluminum, sulfite pulp mill, ferronickel, spray paint);

- include test methods with all standards;

- repeal 40% grain loading and 0.2 grain/dscf (tentative);

- add zero for standards that do not have 2 significant figures;

- revise minor source NSR; and

- clarify rules (splitting sources, NSR/PSD extensions).

Schedule

| Action | ODEQ / LRAPA Submit to EPA | EPA Feedback |
| --- | --- | --- |
| December meeting: Discuss updated proposed permitting rule revisions, potential issues (technical/legal/policy), and needed documentation. Amend schedule if needed. | Week of December 10, 2012 (phone/video) |  |
| Early rule revisions drafts | January 21, 2013 | February 21, 2013 |
| April meeting: Later rule revisions drafts / follow-up questions | April 2013 (video/in person) |  |
| Rulemaking Package to EPA (45 days prior to public notice) | May15, 2013 | June 21, 2013 |
| Public Comment Period Opens | July 1, 2013 |  |
| Public Hearings | August 1, 2013 |  |
| EQC Meeting | December 13, 2013 |  |
| Submittal to EPA | December 21, 2013 |  |
| Process Evaluation | Winter/Spring 2013/2014 |  |