## Sheet1
PROPOSED FOR MEETING ON: |  |  |  |  | 2012-07-12 |  | TIME NEEDED | 30 minutes
AGENDA ITEM PROPOSED BY: |  |  |  |  | Linda & Joanie/Andy |  | PRESENTER | Linda/AQ Rule Making Team
TOPIC: |  | Restart Postponed Rulemaking for Air Quality Permitting Program Overhaul Rule
PRESENTATION TIME PREFERENCE (am/pm) | [5 empty] | am | EQUIPMENT | none
Nature of the topic:
X | For short-term decision
For future decision
For information only
RECOMMENDED DECISION:
Restart postponed rulemaking for air quality permitting program overhaul rule. This was one of 10 agency rulemakings put on our Stop/Postpone list (12/13/11) to create time for the breakthroughs. The request is to restart this rulemaking when the Permit Breakthrough is completed and resources are available and not in competition with the implementation of the permitting breakthrough. Staff: Jill Inahara, hours: 1600 ; other staff, Hours: 770, Manager Oversight: 65. Reviewers 20;
DECISIONMAKER: |  |  | EMT
DECISION DUE DATE: |  |  |  | 2012-07-12 | [8 empty] | Estimate of hours by Task | [6 empty] | Initial estimate of total hours
This item relates to the following criteria (check all that apply): | [10 empty] | NSR/PSD |  |  | Breakthrough |  |  | Reorg |  | TOTAL HOURS | weeks | hours/week | total hours
| Completion of framework for outcome-based management (to move to full implementation) | [8 empty] | weeks | hours/week | Total Hours | weeks | hours/week | Total Hours | weeks | hours/week | Total Hours
| High level implementation of OCBM (measures review, breakthrough assignment and tracking) | [7 empty] | Jill | 18 | 30 | 540 | 4 | 5 | 20 | 35 | 28 | 980 | 1540 | 53 | 30 | 1590
| Budget development and budget operation (i.e. hiring, prioritization) | [7 empty] | GGM | 10 | 36 | 360 | 1 | 5 | 5 | 11 | 36 | 396 | 761 | 20 | 36 | 720
| Other items of agency wide significance as determined by Director and/or Deputy Director) | [7 empty] | Rachel | 10 | 5 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 10 | 5 | 50
X | Politically significant (e.g. rulemaking) | [7 empty] | Tom/Uri/David | 2 | 5 | 10 | 1 | 2 | 2 | 5 | 6 | 30 | 42 | 8 | 5 | 40
| Impacts multiple divisions within the agency | [7 empty] | Andy | 2 | 5 | 10 | 1 | 2 | 2 | 3 | 5 | 15 | 27 | 5 | 5 | 25
X | Impacts agency/statewide policy | [7 empty] | Review Team | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 2 | 2 | 4 | 2 | 10 | 20
| Impacts the legislative agenda | [9 empty] | Total | 972 |  | Total | 29 |  | Total | 1423 | 2424 |  | TOTAL | 2445
X | Involves significant resource allocation *will use existing rulemaking staff whose time is already planned
Information items that are requested to inform a future decision
FACTS AND INFORMATION NEEDED FOR MAKING THE DECISION | [7 empty] | attach as needed
This rulemaking will include new streamlining items identified through the Permitting Breakthrough process as well as addresses a number of need-to-fix items in the current AQ permitting rules. Another issue to be rolled into the rulemaking will provide regulatory relief to small and medium -sized AQ regulated businesses in nonattainment areas. This rule revision needs to be addressed as soon as is practicable because the Klamath Falls attainment plan is scheduled for adoption this December and EPA will then have 18 months to approve it. Once the area attains the standard, we can then submit a maintenance plan and re-designation request, and EPA will have 18 months to approve that also. So, from approval of the attainment plan until the area is re-designated could be five or more years. During this entire time, new and expanding point sources over 15 tons/year will need to install the most expensive control technology and obtain offsets (which are in scarce supply). However, our analysis shows that woodstoves are the main cause of nonattainment - not industry. We would like to explore a rule revision that would eliminate the offset requirement for sources that are below the federal major level of 100 tons/year. If this option can be done in a way that does not harm the environment and is approvable by EPA, then the Klamath Falls community and other nonattainment communities will not have industry penalized for woodstove smoke and will be more attractive to incoming industry. This rulemaking is also necessary for the Lakeview area which is actually a nonattainment area but not designated as such. Larger new businesses and major modifications are not approvable because they cannot show compliance with the modeling requirements since the background concentration is already over the ambient air standard.
OUTCOME OR DECISION MADE (including time line) | [6 empty] | record decision or outcome
| Approved |  |  | Approved for Agenda by |  |  |  | For Agenda Date
Not Approved/Reason