|  | PERMANENT Rulemaking x | P |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Rule proposal complexity (1=Minimal, 2= Moderate, 3=Complex) | 1 |  |  |  |  |
|  | Advisory Committee - not involved | N | i |  | 1/0/00 | 1/0/00 |
|  | Fees - not involved | N |  | 0 | 1/0/00 | 1/0/00 |
|  | -blank- | Y | i | 0 |  |  |
|  | -blank- |  |  | 30 |  | 1/0/00 |
|  | State Implementation Plan (AQ rules) | Y |  | 0 |  |  |
|  | EPA - submit SIP Development Plan 6 months before comment period opens |  |  |  |  | 12/18/14 |
|  | EPA - submit at least 90 days before submittig notice to SOS |  |  | 0 |  | 3/16/15 |
|  | Public Notice | Y |  | Adj | 3/20/15 | 7/20/15 |
|  | Due to DavidC - approval to submit Notice Packet to Rule Publication |  |  | 10 | 4/7/15 | 4/17/15 |
|  | Due to Rule Publication (RGLead) - final edits and validations |  |  | 14 | 4/29/15 | 5/13/15 |
|  | Due to WendyW for input and approval to publish Notice Packet |  |  | 5 | 5/27/15 | 6/1/15 |
|  | SOS - submit on workday no later than 15th of month BEFORE Bulletin |  |  |  |  | 6/15/15 |
|  | SOS - Oregon Bulletin always publishes on the 1st of month | Drop down list > |  |  |  | 7/1/15 |
|  | Public Comment and Testimony | Y |  |  | 6/16/15 | 7/20/15 |
|  | Open public comment |  |  |  |  | 6/16/15 |
|  | Hold 1st hearing at least 30 days AFTER open comment - EPA SIP requirement | Y |  |  |  | 7/16/15 |
|  | Close public comment - DEQ best practice, 3 days after last hearing |  |  |  |  | 7/20/15 |
|  | EQC Preparation |  |  |  | 6/16/15 | 10/14/15 |
|  | No EQC involvement before Action Item meeting |  |  |  | Option 1 ↓ | Option 2 ↓ |
|  | No Director's report requested | N | i |  | 1/0/00 | 1/0/00 |
|  | No information item requested | N | i |  | 1/0/00 | 1/0/00 |
|  | No facilitated hearing requested | N |  |  | 1/0/00 | 1/0/00 |
|  | Rule Publication - submit STAFF.REPORT.permanent |  |  |  |  | 9/3/15 |
|  | EQC meeting - PERMANENT Rulemaking Action Item | Drop down list > |  |  |  | 10/14/15 |
|  | Post EQC Activities |  |  |  | 10/14/15 | 1/12/16 |
|  | SOS - file rules |  |  |  |  | 10/16/15 |
|  | Rules become effective select 'Y' if effective upon filing > | Y |  |  |  | 10/16/15 |
|  | START RULEMAKING |  |  |  |  |  |
|  | - Newspaper advertisements 'Y' to develop | Y |  |  |  |  |
|  | - Newspaper release 'Y' to develop | Y |  |  |  |  |
|  | - Program Web page 'Y' to develop | Y |  |  |  |  |
|  | - Information Meetings before hearing 'Y' to develop | Y |  |  |  |  |
|  | ProgLead leads communication option review and approval loops for: |  |  |  |  |  |
|  | * drafting COMMUNICATION.PLAN with BrianW using information | i |  |  | 3/20/15 | 3/20/15 |
|  | from CONSIDERATIONS and RESOURCES workbooks |  |  |  |  |  |
|  | * drafting MESSAGE.MAP with BrianW | i |  |  | 3/20/15 | 3/20/15 |
|  | * drafting PROGRAM.WEB.PAGE content with team and WebRep |  |  |  | 3/20/15 | 3/20/15 |
|  | DavidC shares information with DA.Program |  |  |  |  |  |
|  | ProgLead: |  |  |  | 3/20/15 | 3/20/15 |
|  | * submits Web Request for program Web page |  |  |  |  |  |
|  | * verifies Web content meets team expectations |  |  |  |  |  |
|  | * works with WebRep to make adjustments |  |  |  |  |  |
|  |  |  |  |  | 3/20/15 | 6/16/15 |
|  | ProgLead: | Publication Table |  |  |  |  |
|  | * identifies newspaper and publication date | # | Publication |  |  |  | Pub Date |
|  | NOTICE.AD1Oregonian | 1 | Oregonian |  |  | 6/16/15 |  |
|  | NOTICE.AD2None | 2 | None |  |  | 6/16/15 |  |
|  | NOTICE.AD3None | 3 | None |  |  | 6/16/15 |  |
|  | NOTICE.AD4None | 4 | None |  |  | 6/16/15 |  |
|  | NOTICE.AD5None | 5 | None |  |  | 6/16/15 |  |
|  | NOTICE.AD6None | 6 | None |  |  | 6/16/15 |  |
|  | NOTICE.AD7None | 7 | None |  |  | 6/16/15 |  |
|  | NOTICE.AD8None | 8 | None |  |  | 6/16/15 |  |
|  | * develops an AD.STANDARD for each hearing if required | e |  |  |  |  |  |
|  | * develops AD.LEGAL for each hearing if required | t |  |  |  |  |  |
|  | * saves as NOTICE.AD.Hearing1, etc. on Rule_Development folder 4 |  |  |  |  |  |  |
|  | * determines when ADs need to be submitted to contractor | AD to contractor > |  |  |  | 7/6/15 |  |
|  | * shares contents of HearingAndAdDates TAB with DavidC | i |  |  | 3/20/15 | 6/16/15 |  |
|  | * obtains DavidC's email approval |  |  |  | 3/20/15 | 6/16/15 |  |
|  | PREPLANNING FOR HEARINGS |  |  |  |  |  |  |
|  |  |  | Hearing Table |  |  |  |  |
|  | Team identifies hearing locations, dates and times |  | # |  | Date | Time |  |
|  | Portland | Y | 1 |  | 7/16/15 | 6 p.m. |  |
|  | Enter city name | N | 2 |  | 1/0/00 | 6 p.m. |  |
|  | Proposed Rules |  |  |  |  |  |  |
|  | SIP2.5.2015 |  |  |  | Start | End |  |
|  |  |  |  |  | 3/20/15 | 10/14/15 |  |
|  | Do not turn off track changes in PROPOSED.RULES |  |  |  |  |  |  |
|  | ProgLead coordinates with Team to: |  |  |  | 3/20/15 | 3/20/15 |  |
|  | * determine need for a crosswalk |  |  |  |  |  |  |
|  | * identify rules to amend or repeal |  |  |  |  |  |  |
|  | * identify new rules to adopt |  |  |  |  |  |  |
|  | * identify land use rules | i |  |  |  |  |  |
|  | * identify SIP rules, talk with AndreaG if unclear |  |  |  |  |  |  |
|  | ProgLead asks Meyer to: |  |  |  |  |  |  |
|  | * pull rules to amend or repeal from SOS-Archives |  |  |  |  |  |  |
|  | * determine availability of any new (adopted) rule or division numbers |  |  |  |  |  |  |
|  | Meyer: |  |  |  |  |  |  |
|  | * adds PROPOSED.RULES.Pristine template to Rule_Development ¦ 0.ProposedRules |  |  |  |  |  |  |
|  | * copies subject rules from SOS into template | i |  |  |  | 3/20/15 |  |
|  | * saves PROPOSED.RULES.Pristine |  |  |  |  |  |  |
|  | * uploads a copy to SharePoint into 0.ProposedRules as PROPOSED.RULES |  |  |  |  |  |  |
|  | * protects PROPOSED.RULES.Pristine on Rule_Development ¦ 0. Draft Rules |  |  |  |  |  |  |
|  | * obtains, verifies, provides previously unused rule numbers for new rules/divisions |  |  |  |  |  |  |
|  | * shares information about rules that may be involved in other rulemakings |  |  |  |  |  |  |
|  | Meyer or RGLead: |  |  |  |  |  |  |
|  | * performs 1st plain language, style guide edits on SharePoint PROPOSED.RULES |  |  |  |  |  |  |
|  | * offers organizational comments and examples |  |  |  |  |  |  |
|  | ProgLead leads rule writing on SharePoint PROPOSED.RULES to: |  |  |  |  |  |  |
|  | * consider regulations, policies, programs and systems that may affect subject rules |  |  |  |  |  |  |
|  | * validate/correct all citations, tables, formulas and document references within rule |  |  |  |  |  |  |
|  | * validate/correct statutory authorities at bottom of each rule |  |  |  |  |  |  |
|  | * validate/correct statutes implemented at bottom of each rule |  |  |  |  |  |  |
|  | * validate/correct and NOTE(s) |  |  |  |  |  |  |
|  | * does not delete or change Hist. or ED.NOTES for any rule |  |  |  |  |  |  |
|  | * SIP note is at bottom of all SIP rules and it is accurate |  |  |  |  |  |  |
|  | All drafters and reviewers work on SharePoint PROPOSED.RULES |  |  |  |  |  |  |
|  | ProgLead, before submitting Notice Packet and EQC Packet: |  |  |  |  |  |  |
|  | * verifies each rule in PROPOSED.RULES is current with SOS compilation |  |  |  |  |  |  |
|  | * verifies no rule adoptions could affect PROPOSED.RULES |  |  |  |  |  |  |
|  | ProgLead gathers all fee emails for the Rule Record and saves as: | i |  |  | 1/0/00 | 1/0/00 |  |
|  | Rule_Development¦3-FeesApproval¦EMAILS.Fees.pdf |  |  |  |  |  |  |
|  | Public Notice |  |  |  |  |  |  |
|  | SIP2.5.2015 |  |  |  | Start | End |  |
|  |  |  |  |  | 3/20/15 | 7/20/15 |  |
|  | Review version history to help maintain rulemaking record > | i |  |  |  |  |  |
|  | SAVE DOCUMENTS ON: SharePoint folder 4-Public Notice |  |  |  |  |  |  |
|  | DRAFT NOTICE PACKET |  |  |  |  |  |  |
|  | ProgLead leads core team in developing Notice Packet that includes: |  |  |  | 3/20/15 | 4/3/15 |  |
|  | * PROPOSED.RULES SharePoint ¦ 0 Proposed Rules |  |  |  |  |  |  |
|  | See Proposed Rules section above |  |  |  |  |  |  |
|  | Do not turn off track changes in PROPOSED.RULES |  |  |  |  |  |  |
|  | * NOTICE SharePoint ¦ 4 Public Notice |  |  |  |  |  |  |
|  | - Overview |  |  |  |  |  |  |
|  | - Statement of Need |  |  |  |  |  |  |
|  | - Rules affected, authorities, supporting documents |  |  |  |  |  |  |
|  | - Fee Analysis |  |  |  |  |  |  |
|  | - Statement of fiscal and economic impact |  |  |  |  |  |  |
|  | - Federal relationship |  |  |  |  |  |  |
|  | - Land use |  |  |  |  |  |  |
|  | - Stakeholder and public involvement |  |  |  |  |  |  |
|  | * SUPPORTING.DOCS - optional SharePoint ¦ 4 Public Notice |  |  |  |  |  |  |
|  | * INVITATION.TO.COMMENT (after Notice approved) SharePoint ¦ 4 Public Notice |  |  |  |  |  |  |
|  | RESOURCE INPUT - THIS IS NOT A REVIEW |  |  |  |  |  |  |
|  | ProgLead asks RESOURCES for help and input, especially: |  |  |  | 3/20/15 | 4/3/15 |  |
|  | * RGLead for process, organization, edits, plain language |  |  |  |  |  |  |
|  | * Affected staff, including regional staff, for subject matter contributions |  |  |  |  |  |  |
|  | * AndreaG, for SIP consultation |  |  |  |  |  |  |
|  | * DavidC for direction and subject consultation, especially to ensure drafts: |  |  |  |  |  |  |
|  | - meet program goals for rulemaking |  |  |  |  |  |  |
|  | - align with section, division and agency goals |  |  |  |  |  |  |
|  | * BrianW for any updates to communication plan, message map, news release |  |  |  |  |  |  |
|  | * Meyer for legal consultation and discuss need for AAG input |  |  |  |  |  |  |
|  | * Enter custom resource here |  |  |  |  |  |  |
|  | * Enter custom resource here |  |  |  |  |  |  |
|  | * Enter custom resource here |  |  |  |  |  |  |
|  | ProgLead continually refines draft Notice Packet and |  |  |  |  |  |  |
|  | * considers RESOURCES input |  |  |  |  |  |  |
|  | * validates approach with staff who provided input |  |  |  |  |  |  |
|  | * asks AAG for input if needed & copies Meyer on all AAG emails |  |  |  |  |  |  |
|  | * addresses legal concerns and discusses with DavidC as needed |  |  |  |  |  |  |
|  | * informs DavidC about the approach, issues and potential delays |  |  |  |  |  |  |
|  | * raises unanticipated rulemaking and implementation risks to appropriate level |  |  |  |  |  |  |
|  | * informs RGLead about potential delays and develop contingency, if needed |  |  |  |  |  |  |
|  | ProgLead asks contributors, including DavidC for consensus on |  |  |  | 3/20/15 | 4/3/15 |  |
|  | subject completeness and accuracy |  |  |  |  |  |  |
|  | KEEP MANAGEMENT INFORMED |  |  |  |  |  |  |
|  | ProgLead asks DAAssistant to schedule future time on WendyW's calendar for: | Schedule by |  |  |  | 3/27/15 |  |
|  | * briefing meeting with ProgLead, DavidC and RGLead | Meeting will be |  |  |  | 5/26/15 |  |
|  | * decument review by blocking time to review Notice Packet during preview week | Review begins on |  |  |  | 5/27/15 |  |
|  | ProgLead schedules time on DavidC calendar to review Notice Packet |  |  |  |  |  |  |
|  | ProgLead verifies/adjusts previously scheduled briefing & review with management |  |  |  |  |  |  |
|  | ProgLead keeps DavidC informed about progress, risks & delays | Review begins on |  |  |  | 4/7/15 |  |
|  | DavidC keeps her or his management teams informed about progress, risks & delays |  |  |  |  |  |  |
|  | CUSTOM SEQUENCE |  |  |  |  |  |  |
|  | Name initiator and subject for custom review loop 1 | N |  |  | 3/20/15 | 5/22/15 |  |
|  | * enter custom action word and reviewer |  |  |  | 3/20/15 | 5/22/15 |  |
|  | * enter custom action word and reviewer |  |  |  | 3/20/15 | 5/22/15 |  |
|  | * enter custom action word and reviewer |  |  |  | 3/20/15 | 5/22/15 |  |
|  | Name initiator and subject for custom review loop 2 | N |  |  | 3/20/15 | 5/22/15 |  |
|  | * enter custom action word and reviewer |  |  |  | 3/20/15 | 5/22/15 |  |
|  | * enter custom action word and reviewer |  |  |  | 3/20/15 | 5/22/15 |  |
|  | * enter custom action word and reviewer |  |  |  | 3/20/15 | 5/22/15 |  |
|  | Name initiator and subject for custom review loop 3 | N |  |  | 3/20/15 | 5/22/15 |  |
|  | * enter custom action word and reviewer |  |  |  | 3/20/15 | 5/22/15 |  |
|  | * enter custom action word and reviewer |  |  |  | 3/20/15 | 5/22/15 |  |
|  | * enter custom action word and reviewer |  |  |  | 3/20/15 | 5/22/15 |  |
|  | RULE PUBLICATION WORK |  |  |  |  |  |  |
|  | ProgLead prepares NOTICE, PROPOSED.RULES & optional SUPPORTING.DOCUMENTS: |  |  |  |  | 4/28/15 |  |
|  | * addresses all comments, but does not delete them |  |  |  |  |  |  |
|  | * saves each document as Major version to capture all comments and tracked changes |  |  |  |  |  |  |
|  | * in NOTICE & optional SUPPORTING.DOCUMENTS: |  |  |  |  |  |  |
|  | - accepts all changes |  |  |  |  |  |  |
|  | - deletes addressed comments |  |  |  |  |  |  |
|  | - ensures Word's track changes is turned on |  |  |  |  |  |  |
|  | - saves documents as Minor versions |  |  |  |  |  |  |
|  | * emails RGLead for Rule Publication work when complete |  |  |  |  | 4/28/15 |  |
|  | During Rule Publication work: |  |  |  | Rule Publication Work Period |  |  |
|  | RGLead |  |  |  | Start | Complete by |  |
|  | * determines whether NOTICE & SUPPORTING DOCUMENTS |  |  |  | 4/29/15 | 5/13/15 |  |
|  | are ready for Rule Publication |  |  |  |  |  |  |
|  | - IF INCOMPLETE |  |  |  |  |  |  |
|  | > notifies DavidC who works with ProgLead |  |  |  |  |  |  |
|  | > renegotiates schedule with DavidC & ProgLead as needed |  |  |  |  |  |  |
|  | > reminds ProgLead to reschedule managers' briefing if needed |  |  |  |  |  |  |
|  | > suspends Rule Publication work until ProgLead resubmits documents |  |  |  |  |  |  |
|  | Loop 1 - Restart Rule Publication | N |  |  |  | 1/0/00 |  |
|  | Loop 2 - Restart Rule Publication | N |  |  |  | 1/0/00 |  |
|  | Loop 3 - Restart Rule Publication | N |  |  |  | 1/0/00 |  |
|  | - IF COMPLETE |  |  |  |  |  |  |
|  | > asks Meyer to apply CHECKLIST review to PROPOSED.RULES | i |  |  |  |  |  |
|  | > leads review to determine fiscal and economic impact analysis sufficiency |  |  |  |  |  |  |
|  | > determines whether work products meet DEQ publication standards |  |  |  |  |  |  |
|  | > asks BrianW, StephanieC & Meyer & AndreaG for input as needed |  |  |  |  |  |  |
|  | > discusses/resolves any editorial differences |  |  |  |  |  |  |
|  | > addresses input to ensure edits and comments speak with one voice |  |  |  |  |  |  |
|  | > accepts non substantive edits |  |  |  |  |  |  |
|  | > asks DavidC & ProgLead for input/concurrance as needed |  |  |  |  |  |  |
|  | DavidC, ProgLead & RGLead discuss the following: |  |  |  |  |  |  |
|  | * outstanding work |  |  |  |  |  |  |
|  | * need for AAG review |  |  |  |  |  |  |
|  | * need to renegotiate schedule |  |  |  |  |  |  |
|  | ProgLead: |  |  |  | 4/29/15 | 5/27/15 |  |
|  | * addresses outstanding edits and comments |  |  |  |  |  |  |
|  | * asks AAG for review, if indicated, copies Meyer and addresses input |  |  |  |  |  |  |
|  | * asks RGLead & DavidC for concurrence on changes if indicated |  |  |  |  |  |  |
|  | * addresses outstanding edits and comments |  |  |  |  |  |  |
|  | * notifies RGLead & DavidC when complete and ready for preview |  |  |  |  |  |  |
|  | * initializes DavidC's publication review |  |  |  |  |  |  |
|  | PREVIEW PERIOD |  |  |  |  |  |  |
|  | ProgLead drafts EMAIL.PREVIEW (instructions in template) | i |  |  |  | 5/22/15 |  |
|  | * sends draft to WendyW just before briefing - links to preview documents included |  |  |  |  |  |  |
|  | * reminds WendyW the review starts today |  |  |  |  |  |  |
|  | * copies DavidC & RGLead on email |  |  |  |  |  |  |
|  | ProgLead, DavidC brief WendyW |  |  |  | Meeting > | 5/26/15 |  |
|  | WendyW personalizes and sends EMAIL.PREVIEW 3 work days after briefing |  |  |  | Preview Period |  |  |
|  | To… Dick, DA.Program, Leadership Team & StephanieC |  |  |  | Start | End |  |
|  | Cc…to all contributing and affected staff |  |  |  | 6/1/15 | 6/10/15 |  |
|  |  |  |  |  | allow 5-7 days |  |  |
|  | ProgLead: |  |  |  |  |  |  |
|  | * saves EMAIL.PREVIEW.pdf to Rule_Development ¦ 4-Notice | i |  |  |  |  |  |
|  | * talks with DavidC, decides how to address any feedback from preview |  |  |  |  |  |  |
|  | * modifies documents as needed |  |  |  |  |  |  |
|  | * verifies PROPOSED.RULES are still based on current compilation |  |  |  |  |  |  |
|  | * finalizes public documents with DavidC |  |  |  |  |  |  |
|  | DavidC: |  |  |  |  |  |  |
|  | * determines whether WendyW needs a second review 'Y' if 2nd review needed> | Y |  |  | 6/10/15 | 6/10/15 |  |
|  | * manages WendyW's 2nd review and approval |  |  |  |  |  |  |
|  | * emails ProgLead & RGLead approval to move forward with | Approval to publish notice |  |  |  |  | 6/12/15 |
|  | NOTICE, PROPOSED.RULES & any SUPPORTING.DCUMENTS |  |  |  |  |  |  |
|  | ProgLead: |  |  |  |  |  |  |
|  | * saves email as Rule_Development ¦ 4-Notice ¦ MGR.APPROVAL.Notice.pdf |  |  |  |  |  |  |
|  | * drafts INVITATION.TO.COMMENT using information from approved NOTICE |  |  |  |  |  |  |
|  | Meyer: |  |  |  | 6/15/15 |  |  |
|  | * establishes the following using Web Request ATTACHMENT |  |  |  |  |  |  |
|  | - External Web page | i |  |  |  |  |  |
|  | - Online public comment form |  |  |  |  |  |  |
|  | - University Student Comment Account - helpdesk request with |  |  |  |  |  |  |
|  | < ProgLead & Meyer co-owning account |  |  |  |  |  |  |
|  | < SIP2.5.2015 as 'Alias' |  |  |  |  |  |  |
|  | * compares work products to earlier reviews to determine need for additional edits |  |  |  |  |  |  |
|  | * obtains additional Rule Publication edits on changes if needed |  |  |  |  |  |  |
|  | * verifies/clarifies additional edits with ProgLead & DavidC as warranted |  |  |  |  |  |  |
|  | * notifies DavidC & ProgLead when finished |  |  |  |  |  |  |
|  | * reminds ProgLead to set Outlook auto reply - instructions in Rulemaking Manual |  |  |  |  |  |  |
|  | NOTIFICATIONS |  |  |  |  |  |  |
|  | ProgLead: |  |  |  |  | 6/12/15 |  |
|  | * submits of Notice to EPA, if required |  |  |  |  |  |  |
|  | Meyer: |  |  |  |  | 6/12/15 |  |
|  | * prepares and submits notice to SOS for publication in Oregon Bulletin | i |  |  |  |  |  |
|  | * emails DAS notification of fees that don't require DAS approval |  |  |  |  |  |  |
|  | * saves all evidence on Rule_Development ¦ 4-Notice using naming conventions | i |  |  |  |  |  |
|  | ProgLead leads: |  |  |  |  |  |  |
|  | * submitting newspaper notices to contractor |  | Set under Planning |  |  | 7/6/15 |  |
|  | * verifying newspaper advertisements are correct |  |  |  |  |  |  |
|  | * obtaining copies of affidavits of publication from Accounting |  |  |  |  |  |  |
|  | * adding hearings to DEQ Event Calendar | i |  |  |  | 6/16/15 |  |
|  | * creating an auto reply to Outlook account for University students | i |  |  |  |  |  |
|  | * validating Web page, comment form and Outlook account |  |  |  |  |  |  |
|  | * opening public comment by notifying agency rulemaking list that includes: |  |  |  |  | 6/16/15 |  |
|  | - GovDelivery |  |  |  |  |  |  |
|  | - EQC members |  |  |  |  |  |  |
|  | - advisory committee |  |  |  |  |  |  |
|  | - program-specific lists |  |  |  |  |  |  |
|  | * saves all evidence, lists and affidavits on Rule_Development ¦ 4-Notice | i |  |  |  |  |  |
| ` | ProgLead drafts EMAIL.NOTICE.TO.KEY.LEGISLATORS - instruction in template: | i |  |  |  | 6/9/15 |  |
|  | * sends draft to Leg.Liason |  |  |  |  |  |  |
|  | Leg.Liason: |  |  |  |  |  |  |
|  | * determines key legislators requiring ORS 183.335(5) notification | i |  |  |  |  |  |
|  | * adapts email as needed |  |  |  |  |  |  |
|  | * emails to recipients with Return Receipt (redirects receipt to ProgLead) |  |  |  |  | 6/16/15 |  |
|  | * copies ProgLead |  |  |  |  |  |  |
|  | * saves receipts under Rule_Development¦4-Notice |  |  |  |  |  |  |
|  | RGLead & WebRep maintain Rukemaking Web page |  |  |  | 6/16/15 | 7/20/15 |  |
|  | ProgLead gathers and saves all emails on | i |  |  | 3/20/15 | 7/20/15 |  |
|  | Rule_Development¦4-Notice using naming conventions |  |  |  |  |  |  |
|  | Public Comment and Testimony |  |  |  |  |  |  |
|  | SIP2.5.2015 |  |  |  | Start | End |  |
|  |  |  |  |  | 6/16/15 | 7/20/15 |  |
|  | Review version history to help maintaining rulemaking record > | i |  |  |  |  |  |
|  | SAVE DOCUMENTS ON: SharePoint folder 5-Public Comment |  |  |  |  |  |  |
|  | ProgLead verifies venues and equipment, gathers supplies | i |  |  | 6/16/15 | 7/16/15 |  |
|  | START INFORMATION MEETING OPTION |  |  |  |  |  |  |
|  | ProgLead: |  |  |  | 6/16/15 | 6/16/15 |  |
|  | * develops INFO.MEETING.TEXT |  |  |  |  |  |  |
|  | * modifies MESSAGE.MAP | i |  |  |  |  |  |
|  | * develops INFO.PRESENTATION |  |  |  |  |  |  |
|  | * practices presentation |  |  |  |  |  |  |
|  | * makes presentation adjustments |  |  |  |  |  |  |
|  | * initiates DavidC's review/approval, addresses suggestions |  |  |  | 6/16/15 | 6/16/15 |  |
|  | 1st loop DavidC reviews/approves optional presentation |  |  |  | 6/16/15 | 6/16/15 |  |
|  | 2nd loop DavidC reviews/approves optional presentation | N |  |  | 1/0/00 | 1/0/00 |  |
|  | 3rd loop DavidC reviews/approves optional presentation | N |  |  | 1/0/00 | 1/0/00 |  |
|  | 4th loop DavidC reviews/approves optional presentation | N |  |  | 1/0/00 | 1/0/00 |  |
|  | Hearings Officers: |  |  |  | 6/16/15 | 7/16/15 |  |
|  | * reviews responsibilities of hearings officer |  |  |  |  |  |  |
|  | * develops introductory and logistics script | i |  |  |  |  |  |
|  | * holds the following hearings (identified under Planning section) with assigned team: |  |  |  |  |  |  |
|  | 1. Portland hearing |  |  |  |  | 7/16/15 |  |
|  | - save audio as Rule_Development¦5-PublicComment¦HEARING.1.mp3 |  |  |  |  |  |  |
|  | ProgLead, for comments received by mail or at hearings |  |  |  | 7/16/15 | 7/20/15 |  |
|  | * stamps DEQ receipt date on address-side of envelope and on first page of letter |  |  |  |  |  |  |
|  | * adds commenter and comment to COMMENTS |  |  |  |  |  |  |
|  | * scans mailed comments and envelopes and saves as ID###.pdf |  |  |  |  |  |  |
|  |  |  | Close public comment |  |  | 7/20/15 |  |
|  | ProgLead: |  |  |  | 7/16/15 | 7/20/15 |  |
|  | * saves online public comment information to COMMENTS |  |  |  |  |  |  |
|  | * coordinates with team to: |  |  |  |  |  |  |
|  | - develop category titles to bundle similar comments |  |  |  |  |  |  |
|  | - organize comments into categories |  |  |  |  |  |  |
|  | - draft DEQ responses to each categories of comments |  |  |  |  |  |  |
|  | * leads team work finalizing DEQ responses to public comment |  |  |  |  |  |  |
|  | DO NOT MAIL TO COMMENTERS UNTIL EQC ASSISTANT FINALIZES STAFF REPORT |  |  |  |  |  |  |
|  | ProgLead asks RGLead for Rule Publication review | i |  |  |  | 7/21/15 |  |
|  | RGLead coordinates Rule Publication work: |  |  |  | 7/21/15 | 7/21/15 |  |
|  | * edits for plain English, style guide & tone because this is part of EQC Packet |  |  |  |  |  |  |
|  | * contacts ProgLead with questions, clarifications and suggestions |  |  |  |  |  |  |
|  | * notifies ProgLead when complete |  |  |  |  |  |  |
|  | ProgLead: |  |  |  |  |  |  |
|  | * shares comments/responses to comments with DavidC & WendyW |  |  |  |  | 7/21/15 |  |
|  | 1st loop - team modifies responses to get to approval |  |  |  | 7/21/15 | 7/21/15 |  |
|  | 2nd loop - team modifies responses to get to approval | N |  |  | 1/0/00 | 1/0/00 |  |
|  | 3rd loop - team modifies responses to get to approval | N |  |  | 1/0/00 | 1/0/00 |  |
|  | Final loop - team modifies responses to get to approval | N |  |  | 1/0/00 | 1/0/00 |  |
|  | ProgLead: |  |  |  |  |  |  |
|  | * gathers emails ABOUT comments, not actual comments, for Rule Record | i |  |  |  | 7/21/15 |  |
|  | * saves them as Rule_Development¦5-PublicComment...¦EMAIL.Comment.pdf |  |  |  |  |  |  |
|  | EQC Preparation |  |  |  |  |  |  |
|  | SIP2.5.2015 |  |  |  | Start | End |  |
|  |  |  |  |  | 6/16/15 | 10/14/15 |  |
|  | Review version history to help maintaining rulemaking record > | i |  |  |  |  |  |
|  | SAVE DOCUMENTS ON: SharePoint folder 6-EQC Preparation |  |  |  |  |  |  |
|  | DEADLINE: Submit to EQC Assistant |  |  |  |  | 9/3/15 |  |
|  | No EQC involvement prior to Action Item meeting |  |  |  |  |  |  |
|  | * no Director's Report |  |  |  | 1/0/00 | 1/0/00 |  |
|  | * no EQC Information Item | i |  |  | 1/0/00 | 1/0/00 |  |
|  | * blank row |  |  |  | 1/0/00 | 1/0/00 |  |
|  | ProgLead: |  |  |  | 6/16/15 | 8/4/15 |  |
|  | *finalizes EQC Packet with core team: |  |  |  |  |  |  |
|  | - STAFF.RPT.Permanent preloaded into folder 6 using instructions in template |  |  |  |  |  |  |
|  | - PROPOSED.RULES in folder 0 |  |  |  |  |  |  |
|  | - SUPPORTING.DOCUMENTS moved from folder 4 to folder 6 |  |  |  |  |  |  |
|  | * notifies RGLead that EQC packet is ready for Rule Publication work |  |  |  |  |  |  |
|  | RGLead leads initial Rule Publication work that includes: |  |  |  | 8/5/15 | 8/14/15 |  |
|  | * comparing NOTICE to STAFF.REPORT to determine what needs review |  |  |  |  |  |  |
|  | * obtaining/consolidating BrianW, StephanieC & AndreaG edits if needed |  |  |  |  |  |  |
|  | including style guide, grammar, plain English, organization, clarity, tone |  |  |  |  |  |  |
|  | * accepting all style guide and format edits |  |  |  |  |  |  |
|  | * getting Meyer's review of PROPOSED.RULES- SOS/LC and CHECKLIST review |  |  |  |  |  |  |
|  | * contacts ProgLead with questions or modifications and when work is complete |  |  |  |  |  |  |
|  | ProgLead: |  |  |  | 8/17/15 | 9/2/15 |  |
|  | * addresses rule publication edits and comments |  |  |  |  |  |  |
|  | * prepares EQC packet |  |  |  |  |  |  |
|  | * initiates management review and approval |  |  |  |  |  |  |
|  | - DavidC |  |  |  |  |  |  |
|  | - DA.Program, if indicated |  |  |  |  |  |  |
|  | - Enter custom reviewer and action |  |  |  |  |  |  |
|  | - Enter custom reviewer and action |  |  |  |  |  |  |
|  | * obtains approval from DavidC to submit EQC packet |  |  |  |  |  |  |
|  | * discusses need for 1¦1 commissioners briefings with DavidC & WendyW | N |  |  | 1/0/00 | 1/0/00 |  |
|  | MEden@neea.org |  |  |  |  |  |  |
|  | JoKRanch@hotmail.com |  |  |  |  |  |  |
|  | EdArmstrong2@gmail.com |  |  |  |  |  |  |
|  | MorganRider@gmail.com |  |  |  |  |  |  |
|  | cjohnson@eou.edu |  |  |  |  |  |  |
|  | * submits EQC packet to StephanieC |  |  |  |  | 9/3/15 |  |
|  | * notifies the following according to division's best practice after EQC Web posting |  |  |  | 6/16/15 | 10/13/15 |  |
|  | - staff contributors |  |  |  |  |  |  |
|  | - key stakeholders |  |  |  |  |  |  |
|  | - advisory committee members |  |  |  |  |  |  |
|  | - commenters |  |  |  |  |  |  |
|  | - interested parties (optional) |  |  |  |  |  |  |
|  | * leads team development of EQC presentation |  |  |  | 6/16/15 | 10/13/15 |  |
|  | * coordinates presentation practices |  |  |  | 6/16/15 | 10/13/15 |  |
|  | * makes any presentation adjustments |  |  |  | 6/16/15 | 10/13/15 |  |
|  | Presentation team ATTENDS EQC MEETING |  |  |  | ####### | 10/14/15 |  |
|  | ProgLead collects emails about EQC preparations for Rule Record and saves as: | i |  |  |  | 10/14/15 |  |
|  | Rule_Development¦6-EQCPreparation¦EMAILS.EQC.Prep.pdf |  |  |  |  |  |  |
|  | Post EQC |  |  |  |  |  |  |
|  | SIP2.5.2015 |  |  |  | Start | End |  |
|  |  |  |  |  | 10/14/15 | 1/12/16 |  |
|  | Review version history to help maintaining rulemaking record > | i |  |  |  |  |  |
|  | DOCUMENT PREPARATION |  |  |  |  |  |  |
|  | ProgLead saves following documents to 7.PostEQC folder on Rule_Develpment: |  |  |  |  |  |  |
|  | * gets documents as presented to EQC from StephanieC: |  |  |  |  | 10/14/15 |  |
|  | - STAFF.REPORT.pdf |  |  |  |  |  |  |
|  | - STAFF.REPORT.ADDENDUM.pdf (if presented to EQC) |  |  |  |  |  |  |
|  | *downloads documents as presented to EQC from SharePoint: |  |  |  |  | 10/14/15 |  |
|  | - PROPOSED.RULES (showing changes) |  |  |  |  |  |  |
|  | > saves as REDLINE.docx (showing changes in strikethrough and underscore) |  |  |  |  |  |  |
|  | > saves as RULES.docx (clean version), accepts all changes, saves again |  |  |  |  |  |  |
|  | - TABLES.340-###-####.docx (1 .docx per rule contains ALL tables in rule) |  |  |  |  |  |  |
|  | - TABLES.340-###-####.docx (1 .docx per rule contains ALL tables in rule) |  |  |  |  |  |  |
|  | * coordinates EPA.SIP.SUBMITAL with AndreaG |  |  |  |  |  |  |