## CodeName.ScheduleOfTasks
| Overview of Key Dates | [6 empty] | To ensure results of formula fits in column B, maintain column width at 60.50 wide in Cambria 10
| CodeName |  |  |  | Start ↓ | End
[5 empty] | 2015-01-05 | 0 |  | Last row = 861 |  | 2015-01-05 | 0
| To restore any cell under columns G or H to default, place cursor in cell then enter "=A" followed by the cell address. EXAMPLE: =AG13 would restore the default Start of Advisory Committee. | [7 empty] | 0
| Director added to DEQ Rulemaking Plan | N |  |  | 2015-01-05 |  |  |  | 0
| PERMANENT Rulemaking | P |  |  |  |  | 60 | PERMANENT Rulemaking | 1
| Rule proposal complexity (1=Minimal, 2= Moderate, 3=Complex) | 2 |  |  |  |  | 30 |  | 1
| Advisory Committee - not involved | N | i |  | 0 | 0 | 0 | Advisory Committee - not involved | 0 | 0 | 0
| Fees - not involved | N |  | 0 | 0 | 0 | 0 | Fees - not involved | 0 | 0 | 0
| -blank- | N | i | 0 |  |  | 0 | -blank- | 0
| -blank- |  |  | 0 |  | 0 | 0 | -blank- | 0 |  | 0
0
| State Implementation Plan (AQ rules) | Y |  | 112 |  |  | 112 | State Implementation Plan (AQ rules) | 1
| EPA - submit SIP Development Plan 6 months before comment period opens |  |  |  |  | 2014-12-16 |  | EPA - submit SIP Development Plan 6 months before comment period opens | 1 |  | 2014-12-16
| EPA - submit at least 90 days before submitting notice to SOS |  |  | 45 |  | 2015-03-16 | 45 | EPA - submit at least 90 days before submitting notice to SOS | 1 |  | 2015-03-16
[9 empty] | 0 |  |  | `
| Public Notice | Y |  | Adj |  |  |  | Public Notice | 1 | 2015-01-05 | 0 | Best practice
| Due to ProgMgr - approval to submit Notice Packet to Rule Publication |  |  | 10 | 2015-04-07 | 2015-04-17 | 10 | Due to ProgMgr - approval to submit Notice Packet to Rule Publication | 1 | 2015-04-07 | 2015-04-17 | 7
| Due to Rule Publication (RGLead) - final edits and validations |  |  | 14 | 2015-04-29 | 2015-05-13 | 14 | Due to Rule Publication (RGLead) - final edits and validations | 1 | 2015-04-29 | 2015-05-13 | 14
| Due to MediaLead for input and approval to publish Notice Packet |  |  | 5 | 2015-05-27 | 2015-06-01 | 7 | Due to MediaLead for input and approval to publish Notice Packet | 1 | 2015-05-27 | 2015-06-01 | 5
| SOS - submit on workday no later than 15th of month BEFORE Bulletin |  |  |  |  | 2015-06-15 |  | SOS - submit on workday no later than 15th of month BEFORE Bulletin | 1 |  | 2015-06-15
| SOS - Oregon Bulletin always publishes on the 1st of month | Drop down list > |  |  |  | 2015-07-01 |  | SOS - Oregon Bulletin always publishes on the 1st of month | 1 |  | 2015-09-01
| Public Comment and Testimony | N |  |  |  |  | 7 | Public Comment and Testimony | 1 | 2015-06-16 | 2015-07-20
| Open public comment |  |  |  |  | 2015-06-16 |  | Open public comment | 1 |  | 2015-06-16
| Hold 1st hearing at least 30 days AFTER open comment - EPA SIP requirement | Y |  |  |  | 2015-07-16 |  | Hold 1st hearing at least 30 days AFTER open comment - EPA SIP requirement | 1 |  | 2015-07-16
| Close public comment - DEQ best practice, 3 days after last hearing |  |  |  |  | 2015-07-20 |  | Close public comment - DEQ best practice, 3 days after last hearing | 1 |  | 2015-07-20
| EQC Preparation | [7 empty] | 1 | 2015-06-16 | 2015-12-16
| No EQC involvement before Action Item meeting |  |  |  | Option 1 ↓ | Option 2 ↓ |  | No EQC involvement before Action Item meeting | 1
| No Director's report requested | N | i |  | 0 | 0 |  | No Director's report requested | 0 | 0 | 0
| No information item requested | N | i |  | 0 | 0 | 0 | No information item requested | 0 | 0 | 0
| No facilitated hearing requested | N |  |  | 0 | 0 |  | No facilitated hearing requested | 0 | 0 | 0
| Rule Publication - submit STAFF.REPORT.permanent |  |  |  |  | #N/A | #N/A | Rule Publication - submit STAFF.REPORT.permanent | 1 |  | #N/A
| EQC meeting - PERMANENT Rulemaking Action Item | Drop down list > |  |  |  | 2015-12-16 |  | EQC meeting - PERMANENT Rulemaking Action Item | 1 |  | #N/A | Missing Column 5 in DDL
[7 empty] | -55 |  | 1 | < +/- calendar days adjustment
[7 empty] | #N/A |  | 1 | < calendar days added
Check older versions
| Post EQC Activities | [7 empty] | 1 | 2015-12-16 | 1900-03-30
| SOS - file rules |  |  |  |  | 2015-12-18 |  |  | 1 |  | 2015-12-18
| DAS - fees not involved |  |  |  |  | 2015-12-21 |  | DAS - fees not involved | 0 |  | 2015-12-21
| Rules become effective select 'Y' if effective upon filing > | Y |  |  |  | 2015-12-18 |  |  | 1 |  | 2015-12-18
| EPA - goal to submit SIP within 60 days of adoption |  |  |  |  | 2016-02-16 |  | EPA - goal to submit SIP within 60 days of adoption | 1 |  | 2016-02-16
Planning
| CodeName |  |  |  | Start | End
[5 empty] | 2015-01-05 | 0 |  |  |  |  | 0
| Review version history to help maintain rulemaking record > | i
| CONCEPT DEVELOPMENT | i | [6 empty] | 1
| Program contacts Meyer about a potential rulemaking |  |  |  |  | 2015-01-05 |  | Program contacts Meyer about a potential rulemaking | 1 |  | 2015-01-05
| Meyer points program contact to 'Add concept to plan' process diagram | [6 empty] | Meyer points program contact to 'Add concept to plan' process diagram | 1
| ProgMgr approves moving forward with about 8 hours concept development work |  |  |  |  | 2015-01-05 |  | ProgMgr approves moving forward with about 8 hours concept development work | 1 |  | 2015-01-05
| Meyer | [6 empty] | Meyer | 1
| * adds to Rules Idea list | [7 empty] | 1
| * establishes new Rule_Development folder system | i | [6 empty] | 1
| * adds TEMPLATES to 1. Planning folder and adapts to concept: | [7 empty] | 1
| - CONSIDERATIONS | [7 empty] | 1
| - RESOURCES | [7 empty] | 1
| - SCHEDULE - Overview of Key Dates | [7 empty] | 1
| - PowerPoint 'Add Concept to Plan' | [7 empty] | 1
| * schedules and facilitates 1st work session: | [7 empty] | 1
| - agenda aligns with PowerPoint | [7 empty] | 1
| - attendees: ProgMgr & ProgLead | [6 empty] | - attendees: ProgMgr & ProgLead | 1
| ProgMgr & ProgLead participate in work session |  |  |  |  | 2015-01-05 |  | ProgMgr & ProgLead participate in work session | 1 |  | 2015-01-05
| ProgLead drafts workbooks using what she or he knows now: |  |  |  | 2015-01-05 | 2015-01-05 |  | ProgLead drafts workbooks using what she or he knows now: | 1 | 2015-01-05 | 2015-01-05
| * RESOURCES to identify staff involved in rulemaking and implementation | [7 empty] | 1
| * CONSIDERATIONS to identify scope and potential risks | [7 empty] | 1
| ProgLead gets input on workbooks from ProgMgr & Meyer |  |  |  |  | 2015-01-05 |  | ProgLead gets input on workbooks from ProgMgr & Meyer | 1 |  | 2015-01-05
| ProgMgr shares concept with MediaLead who advances/delays/stops concept |  |  |  |  | 2015-01-05 |  | ProgMgr shares concept with MediaLead who advances/delays/stops concept | 1 |  | 2015-01-05
| MediaLead shares concept with DA.Program who advances/delays/stops concept |  |  |  |  | 2015-01-05 |  | MediaLead shares concept with DA.Program who advances/delays/stops concept | 1 |  | 2015-01-05
| If advanced, ProgMgr emails Meyer to approve moving forward |  |  |  |  | 2015-01-05 |  | If advanced, ProgMgr emails Meyer to approve moving forward | 1 |  | 2015-01-05
| Meyer: | [6 empty] | Meyer: | 1
| * leads Rules Group prioritization using CONSIDERATIONS and RESOURCES data that | [7 empty] | 1
| compares to other concepts, rulemakings in progress and Rules Group work load | [7 empty] | 1
| * shares priority list and factors with ProgMgr & ProgLead |  |  |  |  | 2015-01-05 |  | * shares priority list and factors with ProgMgr & ProgLead | 1 |  | 2015-01-05
| * adjusts factors as needed | [7 empty] | 1
| * shares priority listing with ProgMgr & RGLead |  |  |  |  | 2015-01-05 |  | * shares priority listing with ProgMgr & RGLead | 1 |  | 2015-01-05
| If resourced through prioritization, Meyer: | [6 empty] | If resourced through prioritization, Meyer: | 1
| * schedules 1¦1 plan review meeting with Dick |  |  |  |  | 2015-01-05 |  | * schedules 1¦1 plan review meeting with Dick | 1 |  | 2015-01-05
| * develops draft plan update email to Leadership Team for Dick | i | [5 empty] | * develops draft plan update email to Leadership Team for Dick | 1
| * attends 1¦1 plan review meeting with Dick | [6 empty] | * attends 1¦1 plan review meeting with Dick | 1
| * selects 'A' if approved, 'P' if postponed, 'R' if rejected | A |  |  |  | 2015-01-05 |  |  | 1 |  | 2015-01-05
| If rejected or postponed, Meyer: | [6 empty] | If rejected or postponed, Meyer: | 1
| * shares decision with ProgMgr | [6 empty] | * shares decision with ProgMgr | 1
| * moves Rule_Development folder with documents to Rule_Archives | [7 empty] | 1
| If approved, Meyer: | [6 empty] | If approved, Meyer: | 1
| * posts DEQ Rulemaking Plan on Rules and Regulations (external Web page) | [7 empty] | 1
| * sends Web page link with informational email: | [7 empty] | 1
| To: Leadership Team describing addition to DEQ Rulemaking Plan | [6 empty] | To: Leadership Team describing addition to DEQ Rulemaking Plan | 1
| To: StephanieC to include in monthly Director's Report | [6 empty] | To: StephanieC to include in monthly Director's Report | 1
| Cc… ProgMgr, ProgLead, RGLead & Meyer | [6 empty] | Cc… ProgMgr, ProgLead, RGLead & Meyer | 1
| * sends Dick draft EQC email, links to DEQ Rulemaking Plan online and asks how | [6 empty] | * sends Dick draft EQC email, links to DEQ Rulemaking Plan online and asks how | 1
| they want to be involved before making final decision, directs responses to Meyer | [6 empty] | they want to be involved before making final decision, directs responses to Meyer | 1
[9 empty] | 1 |  |  | `
| START RULEMAKING | [7 empty] | 1
| Meyer: | [6 empty] | Meyer: | 1
| * saves email Rule_Development ¦ 1-Planning ¦ APPROVAL.ToMoveForward.pdf | i | [5 empty] | * saves email Rule_Development ¦ 1-Planning ¦ APPROVAL.ToMoveForward.pdf | 1
| * establishes SharePoint sub-site | i | [5 empty] | Meyer establishes SharePoint sub-site | 1
| * moves SCHEDULE from Rule_Development into SharePoint to first page of sub-site | [7 empty] | 1
| * moves other workbooks from Rule_Development into SharePoint folder 1. Planning | [7 empty] | 1
| ProgMgr, ProgLead & RGLead decide whether to expand team 'Y' to expand > | Y |  |  |  | 2015-01-05 |  | ProgMgr, ProgLead & RGLead decide whether to expand team 'Y' to expand > | 1 |  | 2015-01-05
| ProgMgr is responsible for: | [6 empty] | ProgMgr is responsible for: | 1
| * getting new team members' manager approval | [7 empty] | 1
| * adding rulemaking to work plans as appropriate | [7 empty] | 1
| ProgMgr works with BudgetAnalyst to get unique Q-Time number(s) |  |  |  |  | 2015-01-05 |  | ProgMgr works with BudgetAnalyst to get unique Q-Time number(s) | 1 |  | 2015-01-05
| for this rulemaking from RobertB | [6 empty] | for this rulemaking from RobertB | 1
| RGLead drafts SCHEDULE: |  |  |  |  | 2015-01-05 |  | RGLead drafts SCHEDULE: | 1 |  | 2015-01-05
| ProgLead & RGLead refine & agree on draft schedule: |  |  |  |  | 2015-01-05 |  | ProgLead & RGLead refine & agree on draft schedule: | 1 |  | 2015-01-05
| ProgLead schedules/holds team meeting(s) for consensus on: |  |  |  | 2015-01-05 | 2015-01-05 |  | ProgLead schedules/holds team meeting(s) for consensus on: | 1 | 2015-01-05 | 2015-01-05
| * RESOURCES workbook identifies rulemaking and implementation needs | [7 empty] | 1
| * CONSIDERATIONS workbook reflects scope of work accurately | [7 empty] | 1
| * CONSIDERATIONS workbook identifies potential risks accurately | [7 empty] | 1
| * SCHEDULE of tasks and deadlines | [7 empty] | 1
| ProgMgr ensures program staff meets agreed upon dates in SCHEDULE | [6 empty] | ProgMgr ensures program staff meets agreed upon dates in SCHEDULE | 1
`
| COMMUNICATIONS PLANNING | [7 empty] | 1
| ProgLead schedules/facilitates meeting with team, including ProgMgr, RGLead, |  |  |  | 2015-01-05 | 2015-01-05 |  | ProgLead schedules/facilitates meeting with team, including ProgMgr, RGLead, | 1 | 2015-01-05 | 2015-01-05
| BrianW, AndreaG and Meyer to discuss/determine need for: | [6 empty] | BrianW, AndreaG and Meyer to discuss/determine need for: | 1
| - Communications Plan 'Y' to develop | Y | [6 empty] | 1 |  |  | Y
| - Message Map 'Y' to develop | Y | [6 empty] | 1
| - Newspaper advertisements 'Y' to develop | Y | [6 empty] | 1
| - Newspaper release 'Y' to develop | Y | [6 empty] | 1
| - Program Web page 'Y' to develop | Y | [6 empty] | 1
| - Information Meetings before hearing 'Y' to develop | Y | [6 empty] | 1
| ProgLead leads communication option review and approval loops for: | [6 empty] | ProgLead leads communication option review and approval loops for: | 1
| * drafting COMMUNICATION.PLAN with BrianW using information | i |  |  | 2015-01-05 | 2015-01-05 |  | * drafting COMMUNICATION.PLAN with BrianW using information | 1 | 2015-01-05 | 2015-01-05
| from CONSIDERATIONS and RESOURCES workbooks | [7 empty] | 1
| * drafting MESSAGE.MAP with BrianW | i |  |  | 2015-01-05 | 2015-01-05 |  | * drafting MESSAGE.MAP with BrianW | 1 | 2015-01-05 | 2015-01-05
| * drafting PROGRAM.WEB.PAGE content with team and WebRep |  |  |  | 2015-01-05 | 2015-01-05 |  | * drafting PROGRAM.WEB.PAGE content with team and WebRep | 1 | 2015-01-05 | 2015-01-05
| ProgMgr shares information with DA.Program | [6 empty] | ProgMgr shares information with DA.Program | 1
| ProgLead: |  |  |  | 2015-01-05 | 2015-01-05 |  | ProgLead: | 1 | 2015-01-05 | 2015-01-05
| * submits Web Request for program Web page | [7 empty] | 1
| * verifies Web content meets team expectations | [7 empty] | 1
| * works with WebRep to make adjustments | [6 empty] | * works with WebRep to make adjustments | 1
[5 empty] | 2015-01-05 | 2015-06-16 |  | ProgLead: | 1 | 2015-01-05 | 2015-06-16
1
| ProgLead: | Publication Table | [6 empty] | 1
| * identifies newspaper and publication date | # | Publication |  |  | Pub Date |  |  | 1
| NOTICE.AD1Oregonian | 1 | Oregonian |  |  | 2015-06-16 |  | NOTICE.AD1Oregonian | 1 |  | 2015-06-16
| NOTICE.AD2None | 2 | None |  |  | 2015-06-16 |  | NOTICE.AD2None | 1 |  | 2015-06-16
| NOTICE.AD3None | 3 | None |  |  | 2015-06-16 |  | NOTICE.AD3None | 1 |  | 2015-06-16
| NOTICE.AD4None | 4 | None |  |  | 2015-06-16 |  | NOTICE.AD4None | 1 |  | 2015-06-16
| NOTICE.AD5None | 5 | None |  |  | 2015-06-16 |  | NOTICE.AD5None | 1 |  | 2015-06-16
| NOTICE.AD6None | 6 | None |  |  | 2015-06-16 |  | NOTICE.AD6None | 1 |  | 2015-06-16
| NOTICE.AD7None | 7 | None |  |  | 2015-06-16 |  | NOTICE.AD7None | 1 |  | 2015-06-16
| NOTICE.AD8None | 8 | None |  |  | 2015-06-16 |  | NOTICE.AD8None | 1 |  | 2015-06-16
| * develops an AD.STANDARD for each hearing if required | e | [6 empty] | 1
| * develops AD.LEGAL for each hearing if required | t | [6 empty] | 1
| * saves as NOTICE.AD.Hearing1, etc. on Rule_Development folder 4 | [7 empty] | 1
| * determines when ADs need to be submitted to contractor | AD to contractor > |  |  |  | 2015-07-06 |  |  | 1 |  | 2015-07-06
| * shares contents of HearingAndAdDates TAB with ProgMgr | i |  |  | 2015-01-05 | 2015-06-16 |  | * shares contents of HearingAndAdDates TAB with ProgMgr | 1 | 2015-01-05 | 2015-06-16
| * obtains ProgMgr's email approval |  |  |  | 2015-01-05 | 2015-06-16 |  | * obtains ProgMgr's email approval | 1 | 2015-01-05 | 2015-06-16
`
| PREPLANNING FOR HEARINGS | [7 empty] | 1
|  |  | Hearing Table |  |  |  |  | Team identifies hearing locations, dates and times | 1
| Team identifies hearing locations, dates and times |  | # |  | Date | Time |  | Technical Lead enters hearings locations, dates and times: | 1
| Portland | Y | 1 |  | 2015-07-16 | 6 p.m. |  |  | 1 | 2015-07-16 | 5 p.m.
| Enter city name | N | 2 |  | 0 | 6 p.m. |  |  | 0 | 0 | 6 p.m.
| Enter city name | N | 3 |  | 0 | 6 p.m. |  |  | 0 | 0 | 6 p.m.
| Enter city name | N | 4 |  | 0 | 6 p.m. |  |  | 0 | 0 | 6 p.m.
| Enter city name | N | 5 |  | 0 | 6 p.m. |  |  | 0 | 0 | 6 p.m.
| Enter city name | N | 6 |  | 0 | 6 p.m. |  |  | 0 | 0 | 6 p.m.
| Enter city name | N | 7 |  | 0 | 6 p.m. |  |  | 0 | 0 | 6 p.m.
| Enter city name | N |  |  | 0 | 6 p.m. |  |  | 0 | 0 | 6 p.m.
| Last hearing: |  |  |  | 2015-07-16 |  |  |  | 1 | 2015-07-16
1
| Technical Lead reserves venues/equipment for hearings |  |  |  | 2015-01-05 | 2015-07-16 |  | Technical Lead reserves venues/equipment for hearings | 1 | 2015-01-05 | 2015-07-16
| RGLead adds hearings officer(s) on HearingAndAdDates TAB | i | [5 empty] | RGLead adds hearings officer(s) on HearingAndAdDates TAB | 1
| EQC FACILITATED HEARINGS | [7 empty] | 0
| ProgLead: | [6 empty] | ProgLead: | 0
| * observe EQC quorum notification requirements (ORS 192.630) | i | [6 empty] | 0
| * identifies EQC facilitated hearing, coordinate with commissioner: | [7 empty] | 0
| MEden@neea.org | N |  |  |  | 2015-11-16 |  |  | 0 | X | 0
| JoKRanch@hotmail.com | N |  |  |  | 2015-11-16 |  |  | 0 | X
| EdArmstrong2@gmail.com | N |  |  |  | 2015-11-16 |  |  | 0 | X
| MorganRider@gmail.com | N |  |  |  | 2015-11-16 |  |  | 0 | X
| cjohnson@eou.edu | N |  |  |  | 2015-11-16 |  |  | 0 | X
`
| ProgLead gathers all planning emails for the Rule Record and saves as: | i |  |  |  | 0 |  | ProgLead gathers all planning emails for the Rule Record and saves as: | 1 |  | 0
| Rule_Development¦1-Planning¦EMAILS.Planning.pdf | [7 empty] | 1
1
Proposed Rules
| CodeName |  |  |  | Start | End
[5 empty] | 2015-01-05 | 0
| Do not turn off track changes in PROPOSED.RULES | [7 empty] | 1
| ProgLead coordinates with Team to: |  |  |  | 2015-01-05 | 2015-01-05 |  | ProgLead coordinates with Team to: | 1 | 2015-01-05 | 2015-01-05
| * determine need for a crosswalk | [7 empty] | 1 | Add link to crosswalk
| * identify rules to amend or repeal | [7 empty] | 1
| * identify new rules to adopt | [7 empty] | 1
| * identify land use rules | i | [6 empty] | 1
| * identify SIP rules, talk with AndreaG if unclear | [6 empty] | * identify SIP rules, talk with AndreaG if unclear | 1
| ProgLead asks Meyer to: | [6 empty] | ProgLead asks Meyer to: | 1
| * pull rules to amend or repeal from SOS-Archives | [6 empty] | ProgLead asks Meyer to pull rules from SOS | 1
| * determine availability of any new (adopted) rule or division numbers | [6 empty] | Meyer: | 1
| Meyer: | [6 empty] | Meyer: | 1
| * adds PROPOSED.RULES.Pristine template to Rule_Development ¦ 0.ProposedRules | [7 empty] | 1
| * copies subject rules from SOS into template | i |  |  |  | 2015-01-05 |  |  | 1 | 2015-01-05
| * saves PROPOSED.RULES.Pristine | [7 empty] | 1
| * uploads a copy to SharePoint into 0.ProposedRules as PROPOSED.RULES | [7 empty] | 1
| * protects PROPOSED.RULES.Pristine on Rule_Development ¦ 0. Draft Rules | [7 empty] | 1
| * obtains, verifies, provides previously unused rule numbers for new rules/divisions | [6 empty] | Meyer obtains, verifies, provides previously unused numbers for new rules | 1
| * shares information about rules that may be involved in other rulemakings | [6 empty] | Meyer identifies rules that may be involved in other rulemakings | 1
| Meyer or RGLead: | [6 empty] | Meyer or RGLead: | 1
| * performs 1st plain language, style guide edits on SharePoint PROPOSED.RULES | [6 empty] | * works with RGLead to start initial plain language, style guide, rule style edits | 1
| * offers organizational comments and examples | [7 empty] | 1
| ProgLead leads rule writing on SharePoint PROPOSED.RULES to: | [6 empty] | ProgLead leads rule writing on SharePoint PROPOSED.RULES to: | 1
| * consider regulations, policies, programs and systems that may affect subject rules | [7 empty] | 1
| * validate/correct all citations, tables, formulas and document references within rule | [7 empty] | 1
| * validate/correct statutory authorities at bottom of each rule | [7 empty] | 1
| * validate/correct statutes implemented at bottom of each rule | [7 empty] | 1
| * validate/correct and NOTE(s) | [7 empty] | 1
| * does not delete or change Hist. or ED.NOTES for any rule | [7 empty] | 1
| * SIP note is at bottom of all SIP rules and it is accurate | [7 empty] | 1
| All drafters and reviewers work on SharePoint PROPOSED.RULES | [7 empty] | 1
| ProgLead, before submitting Notice Packet and EQC Packet: | [6 empty] | ProgLead, before submitting Notice Packet and EQC Packet: | 1
| * verifies each rule in PROPOSED.RULES is current with SOS compilation | [7 empty] | 1
| * verifies no rule adoptions could affect PROPOSED.RULES | [7 empty] | 1
1
Advisory Committee - not involved
| CodeName |  |  |  | Start | End
[5 empty] | 0 | 0 |  |  |  | 0 | 0
| Review version history to help maintaining rulemaking record | i | [6 empty] | 0
| SAVE DOCUMENTS ON: SharePoint folder 2-Advisory Committee | [7 empty] | 0
| DEADLINE: Notice committee meetings 2 weeks before meeting | [7 empty] | 0
| Meyer: | [6 empty] | Meyer: | 0
| * schedules 4-hour Advisory Committee work session |  |  |  | 0 | 1900-01-12 |  | Meyer schedules Advisory Committee work session | 0 | 0 | 1900-01-12
| * adapts Advisory Committee PowerPoint to rulemaking | [6 empty] | Meyer asks team to prepare for work session by reviewing: | 0
| * asks team to prepare for work session by reviewing: | [6 empty] | Meyer asks team to prepare for work session by reviewing: | 0
| - advisory committee guidelines | i | [6 empty] | 0
| - Public Involvement Resources | i | [5 empty] | * reviewing Public Involvement Resources and when to engage BrianW | 0
| - EQC quorum notification requirements (ORS 192.630) | i | [5 empty] | * Oregon Transparency law (not required for Advisory Committees) | 0 |  |  |  | i
| - examples of the required Advisory Committee Web pages | i | [6 empty] | 0
| - optional committee AC.CHARTER | [7 empty] | 0
| - CONSIDERATIONS workbook in SharePoint folder 1 | [7 empty] | 0
| * asks ProgLead to prepare the following work session items: |  |  |  | 0 | 1900-01-12 |  | * asks ProgLead to prepare the following work session items: | 0 | 0 | 1900-01-12
| - add potential committee members to draft AC.ROSTER | [7 empty] | 0
| - list potential meeting dates and venues | [7 empty] | 0
| - draft AC.MEMBER.INVITATION | [7 empty] | 0
| - identify all GovDelivery topics that include affected parties | i | [6 empty] | 0
| - draft AC.AFFECTED.PARTIES.INVITATION to sign up for GovDelivery notices | [7 empty] | 0
| - draft AC.EQC.INVITATION to sign up for GovDelivery notices in folder 2 | [7 empty] | 0
| - draft AC.WebPage | i | [6 empty] | 0
| * facilitates Advisory Committee work session that: | [7 empty] | 0
| - follows PowerPoint discussion and decision items | [7 empty] | 0
| - discusses need to engage BrianW | [6 empty] | - discusses need to engage BrianW | 0
| - decides whether to use optional AC.CHARTER | Y | [6 empty] | 0
| - advises ProgLead on deliverables | [6 empty] | - advises ProgLead on deliverables | 0
| ProgLead coordinates with team & ProgMgr for agreement on: |  |  |  | 0 | 0 |  | ProgLead coordinates with team & ProgMgr for agreement on: | 0 | 0 | 0
| * AC.WebPage | [7 empty] | 0
| * AC.CHARTER to include AC.ROSTER, meeting dates, venues | [6 empty] | * AC.CHARTER to include AC.ROSTER, meeting dates, venues | 0
| * AC.MEMBER.INVITATION (includes URL and reminder to Sign-up for GovDelivery) | [7 empty] | 0
| * GovDelivery topic subscribers to get AC.AFFECTED.PARTIES.INVITATION | [7 empty] | 0
| * AC.AFFECTED.PARTIES.INVITATION to sign up for GovDelivery notices | [7 empty] | 0
| * AC.EQC.INVITATION to sign up for GovDelivery notices | [7 empty] | 0
| * meeting dates and venues | [7 empty] | 0
| ProgMgr & ProgLead: |  |  |  | 0 | 0 |  | ProgMgr & ProgLead: | 0 | 0 | 0
| * share Advisory Committee deliverables and decisions with MediaLead | [6 empty] | * share Advisory Committee deliverables and decisions with MediaLead | 0
| * team addresses any concerns and validates accuracy of how addressed | [7 empty] | 0
| ProgMgr approves deliverables including AC.ROSTER |  |  |  |  | 0 |  | ProgMgr approves deliverables including AC.ROSTER | 0 |  | 0
| ProgLead coordinates with team to: | [6 empty] | ProgLead coordinates with team to: | 0
| * talk with potential committee members to determine interest |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| * finalize AC.ROSTER based on responses |  |  |  |  | 0 |  |  | 0 |  | 0
| Meyer works with WebRep to establish: |  |  |  |  | 0 |  | Meyer works with WebRep to establish: | 0 |  | 0
| *Advisory Committee page | i | [6 empty] | 0
| http://www.oregon.gov/deq/RulesandRegulations/Pages/Advisory/Acodename.aspx | [6 empty] | http://www.oregon.gov/deq/RulesandRegulations/Pages/Advisory/Acodename.aspx | 0
| * Advisory Committee meeting page | [7 empty] | 0
| http://www.oregon.gov/deq/RulesandRegulations/Pages/Advisory/AMcodename.aspx | [6 empty] | http://www.oregon.gov/deq/RulesandRegulations/Pages/Advisory/AMcodename.aspx | 0
| * Advisory Committee GovDelivery sign up | [7 empty] | 0
| ProgMgr: |  |  |  |  | 0 |  | ProgMgr: | 0 |  | 0
| * emails AC.MEMBER.INVITATION with links and instructions | [6 empty] | ProgMgr sends AC.MEMBER.INVITATION email with meeting schedule | 0
| * emails AC.EQC.INVITATION to sign up for Advisory Committee notices | [7 empty] | 0
| MEden@neea.org | [7 empty] | 0
| JoKRanch@hotmail.com | [7 empty] | 0
| EdArmstrong2@gmail.com | [7 empty] | 0
| MorganRider@gmail.com | [7 empty] | 0
| cjohnson@eou.edu | [7 empty] | 0
| ProgLead: | [6 empty] | ProgLead: | 0
| * sends AC.AFFECTED.PARTIES.INVITATION to GovDelivery topic subscribers | [7 empty] | 0
| * submits Web Request anytime when Advisory Committee Web page needs updating | [7 empty] | 0
| * maintains Advisory Committee record | [7 empty] | 0
| Meeting 1 | Y |  |  | 1900-01-15 | 9.00 am |  |  | 0 | 1900-01-15
| Team identifies meeting roles | [7 empty] | 0
| ProgLead: |  |  |  | #NUM! | #NUM! |  | ProgLead: | 0 | #NUM! | #NUM!
| * coordinates or leads drafting: | [6 empty] | ProgLead coordinates drafting: | 0
| - AC.AGENDA.01.16.00 | i | [5 empty] | - AC.AGENDA.01.16.00 | 0
| - AC.GovDelivery.NOTICE.01.16.00 | [6 empty] | - AC.GovDelivery.NOTICE.01.16.00 | 0
| - AC.WebRequest.ATTACHMENT.01.16.00 | [6 empty] | - AC.WebRequest.ATTACHMENT.01.16.00 | 0
| * obtains team and ProgMgr input on agenda and GovDelivery notice |  |  |  |  | #NUM! |  | * obtains team and ProgMgr input on agenda and GovDelivery notice | 0 |  | #NUM!
| * submits Web Request 2 weeks before meeting using AC.WebRequest.ATTACHMENT | i |  |  |  | #NUM! |  |  | 0 |  | #NUM! | 1900-01-08
| * sends AC.GovDelivery.NOTICE.01.16.00 to committee Web page subscribers | [6 empty] | * sends AC.GovDelivery.NOTICE.01.16.00 to committee Web page subscribers | 0
| * releases unneeded venues | [7 empty] | 0
| Team assigns custom task here |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| Team assigns custom task here |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| Team assigns custom task here |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| Team assigns custom task here |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| START OPTION - Presentation Select option > | Y | [6 empty] | 0
| Enter staff name here | [7 empty] | 0
| * drafts optional AC.PRESENTATION.01.16.00 |  |  |  | 0 | 0 |  | * drafts optional AC.PRESENTATION.01.16.00 | 0 | 0 | 0
| Enter staff name here | [7 empty] | 0
| * involves stakeholder presenters, if any |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| Team approves presentation materials |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| ProgLead submits Web Request to post presentation materials | i | [5 empty] | ProgLead submits Web Request to post presentation materials | 0
| Team practices presentation | [7 empty] | 0
| ProgLead facilitates, leads or supports: |  |  |  | 0 | 0 |  | ProgLead facilitates, leads or supports: | 0 | 0 | 0
| * Advisory Committee meeting |  |  |  |  | 1900-01-15 |  |  | 0 |  | 1900-01-15
| * drafting of AC.MINUTES 01.16.00 | i |  |  | 1900-01-15 | 1900-01-15 |  | * drafting of AC.MINUTES 01.16.00 | 0 | 1900-01-15 | 1900-01-15
| * team debrief meeting |  |  |  | 1900-01-15 | 1900-01-15 |  |  | 0 | 1900-01-15 | 1900-01-15
1
| Meeting 2 | Y |  |  | 1900-01-15 | 9.00 a.m. |  |  | 0 | 1900-01-15
| Team identifies meeting roles | [7 empty] | 0
| ProgLead: |  |  |  | #NUM! | #NUM! |  | ProgLead: | 0 | #NUM! | #NUM!
| * coordinates or leads drafting: | [6 empty] | ProgLead coordinates drafting: | 0
| - AC.AGENDA.01.16.00 | i | [5 empty] | - AC.AGENDA.01.16.00 | 0
| - AC.GovDelivery.NOTICE.01.16.00 | [6 empty] | - AC.GovDelivery.NOTICE.01.16.00 | 0
| - AC.WebRequest.ATTACHMENT.01.16.00 | [6 empty] | - AC.WebRequest.ATTACHMENT.01.16.00 | 0
| * obtains team and ProgMgr input on agenda and GovDelivery notice |  |  |  |  | #NUM! |  | * obtains team and ProgMgr input on agenda and GovDelivery notice | 0 |  | #NUM!
| * submits Web Request 2 weeks before meeting using AC.WebRequest.ATTACHMENT | i |  |  |  | #NUM! |  |  | 0 |  | #NUM! | 1900-01-08
| * sends AC.GovDelivery.NOTICE.01.16.00 to committee Web page subscribers | [6 empty] | * sends AC.GovDelivery.NOTICE.01.16.00 to committee Web page subscribers | 0
| * releases unneeded venues | [7 empty] | 0
| Team assigns custom task here |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| Team assigns custom task here |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| Team assigns custom task here |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| Team assigns custom task here |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| START OPTION - Presentation Select option > | Y | [6 empty] | 0
| Enter staff name here | [7 empty] | 0
| * drafts optional AC.PRESENTATION.01.16.00 |  |  |  | 0 | 0 |  | * drafts optional AC.PRESENTATION.01.16.00 | 0 | 0 | 0
| Enter staff name here | [7 empty] | 0
| * involves stakeholder presenters, if any |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| Team approves presentation materials |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| ProgLead submits Web Request to post presentation materials | i | [5 empty] | ProgLead submits Web Request to post presentation materials | 0
| Team practices presentation | [7 empty] | 0
| ProgLead facilitates, leads or supports: |  |  |  | 0 | 0 |  | ProgLead facilitates, leads or supports: | 0 | 0 | 0
| * Advisory Committee meeting |  |  |  |  | 1900-01-15 |  |  | 0 |  | 1900-01-15
| * drafting of AC.MINUTES 01.16.00 | i |  |  | 1900-01-15 | 1900-01-15 |  | * drafting of AC.MINUTES 01.16.00 | 0 | 1900-01-15 | 1900-01-15
| * team debrief meeting |  |  |  | 1900-01-15 | 1900-01-15 |  |  | 0 | 1900-01-15 | 1900-01-15
1
| Meeting 3 | Y |  |  | 1900-01-15 | 9.00 a.m. |  |  | 0 | 1900-01-15
| Team identifies meeting roles | [7 empty] | 0
| ProgLead: |  |  |  | #NUM! | #NUM! |  | ProgLead: | 0 | #NUM! | #NUM!
| * coordinates or leads drafting: | [6 empty] | ProgLead coordinates drafting: | 0
| - AC.AGENDA.01.16.00 | i | [5 empty] | - AC.AGENDA.01.16.00 | 0
| - AC.GovDelivery.NOTICE.01.16.00 | [6 empty] | - AC.GovDelivery.NOTICE.01.16.00 | 0
| - AC.WebRequest.ATTACHMENT.01.16.00 | [6 empty] | - AC.WebRequest.ATTACHMENT.01.16.00 | 0
| * obtains team and ProgMgr input on agenda and GovDelivery notice |  |  |  |  | #NUM! |  | * obtains team and ProgMgr input on agenda and GovDelivery notice | 0 |  | #NUM!
| * submits Web Request 2 weeks before meeting using AC.WebRequest.ATTACHMENT | i |  |  |  | #NUM! |  |  | 0 |  | #NUM! | 1900-01-08
| * sends AC.GovDelivery.NOTICE.01.16.00 to committee Web page subscribers | [6 empty] | * sends AC.GovDelivery.NOTICE.01.16.00 to committee Web page subscribers | 0
| * releases unneeded venues | [7 empty] | 0
| Team assigns custom task here |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| Team assigns custom task here |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| Team assigns custom task here |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| Team assigns custom task here |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| START OPTION - Presentation Select option > | Y | [6 empty] | 0
| Enter staff name here | [7 empty] | 0
| * drafts optional AC.PRESENTATION.01.16.00 |  |  |  | 0 | 0 |  | * drafts optional AC.PRESENTATION.01.16.00 | 0 | 0 | 0
| Enter staff name here | [7 empty] | 0
| * involves stakeholder presenters, if any |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| Team approves presentation materials |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| ProgLead submits Web Request to post presentation materials | i | [5 empty] | ProgLead submits Web Request to post presentation materials | 0
| Team practices presentation | [7 empty] | 0
| ProgLead facilitates, leads or supports: |  |  |  | 0 | 0 |  | ProgLead facilitates, leads or supports: | 0 | 0 | 0
| * Advisory Committee meeting |  |  |  |  | 1900-01-15 |  |  | 0 |  | 1900-01-15
| * drafting of AC.MINUTES 01.16.00 | i |  |  | 1900-01-15 | 1900-01-15 |  | * drafting of AC.MINUTES 01.16.00 | 0 | 1900-01-15 | 1900-01-15
| * team debrief meeting |  |  |  | 1900-01-15 | 1900-01-15 |  |  | 0 | 1900-01-15 | 1900-01-15
1
| Meeting 4 | Y |  |  | 1900-01-15 | 6:00 p.m. |  |  | 0 | 1900-01-15
| Team identifies meeting roles | [7 empty] | 0
| ProgLead: |  |  |  | #NUM! | #NUM! |  | ProgLead: | 0 | #NUM! | #NUM!
| * coordinates or leads drafting: | [6 empty] | ProgLead coordinates drafting: | 0
| - AC.AGENDA.01.16.00 | i | [5 empty] | - AC.AGENDA.01.16.00 | 0
| - AC.GovDelivery.NOTICE.01.16.00 | [6 empty] | - AC.GovDelivery.NOTICE.01.16.00 | 0
| - AC.WebRequest.ATTACHMENT.01.16.00 | [6 empty] | - AC.WebRequest.ATTACHMENT.01.16.00 | 0
| * obtains team and ProgMgr input on agenda and GovDelivery notice |  |  |  |  | #NUM! |  | * obtains team and ProgMgr input on agenda and GovDelivery notice | 0 |  | #NUM!
| * submits Web Request 2 weeks before meeting using AC.WebRequest.ATTACHMENT | i |  |  |  | #NUM! |  |  | 0 |  | #NUM! | 1900-01-08
| * sends AC.GovDelivery.NOTICE.01.16.00 to committee Web page subscribers | [6 empty] | * sends AC.GovDelivery.NOTICE.01.16.00 to committee Web page subscribers | 0
| * releases unneeded venues | [7 empty] | 0
| Team assigns custom task here |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| Team assigns custom task here |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| Team assigns custom task here |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| Team assigns custom task here |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| START OPTION - Presentation Select option > | Y | [6 empty] | 0
| Enter staff name here | [7 empty] | 0
| * drafts optional AC.PRESENTATION.01.16.00 |  |  |  | 0 | 0 |  | * drafts optional AC.PRESENTATION.01.16.00 | 0 | 0 | 0
| Enter staff name here | [7 empty] | 0
| * involves stakeholder presenters, if any |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| Team approves presentation materials |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| ProgLead submits Web Request to post presentation materials | i | [5 empty] | ProgLead submits Web Request to post presentation materials | 0
| Team practices presentation | [7 empty] | 0
| ProgLead facilitates, leads or supports: |  |  |  | 0 | 0 |  | ProgLead facilitates, leads or supports: | 0 | 0 | 0
| * Advisory Committee meeting |  |  |  |  | 1900-01-15 |  |  | 0 |  | 1900-01-15
| * drafting of AC.MINUTES 01.16.00 | i |  |  | 1900-01-15 | 1900-01-15 |  | * drafting of AC.MINUTES 01.16.00 | 0 | 1900-01-15 | 1900-01-15
| * team debrief meeting |  |  |  | 1900-01-15 | 1900-01-15 |  |  | 0 | 1900-01-15 | 1900-01-15
1
| Meeting 5 | Y |  |  | 1900-01-15 | 6:00 p.m. |  |  | 0 | 1900-01-15
| Team identifies meeting roles | [7 empty] | 0
| ProgLead: |  |  |  | #NUM! | #NUM! |  | ProgLead: | 0 | #NUM! | #NUM!
| * coordinates or leads drafting: | [6 empty] | ProgLead coordinates drafting: | 0
| - AC.AGENDA.01.16.00 | i | [5 empty] | - AC.AGENDA.01.16.00 | 0
| - AC.GovDelivery.NOTICE.01.16.00 | [6 empty] | - AC.GovDelivery.NOTICE.01.16.00 | 0
| - AC.WebRequest.ATTACHMENT.01.16.00 | [6 empty] | - AC.WebRequest.ATTACHMENT.01.16.00 | 0
| * obtains team and ProgMgr input on agenda and GovDelivery notice |  |  |  |  | #NUM! |  | * obtains team and ProgMgr input on agenda and GovDelivery notice | 0 |  | #NUM!
| * submits Web Request 2 weeks before meeting using AC.WebRequest.ATTACHMENT | i |  |  |  | #NUM! |  |  | 0 |  | #NUM! | 1900-01-08
| * sends AC.GovDelivery.NOTICE.01.16.00 to committee Web page subscribers | [6 empty] | * sends AC.GovDelivery.NOTICE.01.16.00 to committee Web page subscribers | 0
| * releases unneeded venues | [7 empty] | 0
| Team assigns custom task here |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| Team assigns custom task here |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| Team assigns custom task here |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| Team assigns custom task here |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| START OPTION - Presentation Select option > | N | [6 empty] | 0
| Enter staff name here | [7 empty] | 0
| * drafts optional AC.PRESENTATION.01.16.00 |  |  |  | 0 | 0 |  | * drafts optional AC.PRESENTATION.01.16.00 | 0 | 0 | 0
| Enter staff name here | [7 empty] | 0
| * involves stakeholder presenters, if any |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| Team approves presentation materials |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
| ProgLead submits Web Request to post presentation materials | i | [5 empty] | ProgLead submits Web Request to post presentation materials | 0
| Team practices presentation | [7 empty] | 0
| ProgLead facilitates, leads or supports: |  |  |  | 0 | 0 |  | ProgLead facilitates, leads or supports: | 0 | 0 | 0
| * Advisory Committee meeting |  |  |  |  | 1900-01-15 |  |  | 0 |  | 1900-01-15
| * drafting of AC.MINUTES 01.16.00 | i |  |  | 1900-01-15 | 1900-01-15 |  | * drafting of AC.MINUTES 01.16.00 | 0 | 1900-01-15 | 1900-01-15
| * team debrief meeting |  |  |  | 1900-01-15 | 1900-01-15 |  |  | 0 | 1900-01-15 | 1900-01-15
1
| ProgLead gathers all advisory committee emails for the Rule Record and saves as: | i |  |  | 0 | 0 |  | ProgLead gathers all advisory committee emails for the Rule Record and saves as: | 0 | 0 | 0
| Rule_Development¦3-FeesApproval¦EMAILS.Fees.pdf | [7 empty] | 0
| Fees - not involved | [6 empty] | Fees - not involved
| CodeName |  |  |  | Start | End
[5 empty] | 0 | 0
| Review version history to help maintaining rulemaking record > | i
| ProgLead leads development of: | [6 empty] | ProgLead leads development of: | 0
| * Fee Approval Packet, with team and BudgetAnalyst | i |  |  | 0 | 0 |  | * Fee Approval Packet, with team and BudgetAnalyst | 0 | 0 | 0
| blank row | [6 empty] | blank row | 0
| blank row | [6 empty] | blank row | 0
| blank line | i | [5 empty] | blank line | 0
| blank row | i | [5 empty] | blank row | 0
| * requests RGLead's review for sufficiency, tone, plain language, style guide |  |  |  | 0 | 1900-01-04 |  | * requests RGLead's review for sufficiency, tone, plain language, style guide | 0 | 0 | 1900-01-04
| (documents become part of Notice and EQC packets) | [7 empty] | 0
| * initiates ProgMgr's Fee Approval Packet review, addresses suggestions |  |  |  |  | 1900-01-04 |  | * initiates ProgMgr's Fee Approval Packet review, addresses suggestions | 0 |  | 1900-01-04
| 1st loop of ProgMgr's Fee Approval Packet review and approval |  |  |  | 1900-01-04 | 1900-01-11 |  | 1st loop of ProgMgr's Fee Approval Packet review and approval | 0 | 1900-01-04 | 1900-01-11
| 2nd loop of ProgMgr's Fee Approval Packet review and approval | N |  |  | 0 | 0 |  | 2nd loop of ProgMgr's Fee Approval Packet review and approval | 0 | 0 | 0
| 3rd loop of ProgMgr's Fee Approval Packet review and approval | N |  |  | 0 | 0 |  | 3rd loop of ProgMgr's Fee Approval Packet review and approval | 0 | 0 | 0
| 4th loop of ProgMgr's Fee Approval Packet review and approval | N |  |  | 0 | 0 |  | 4th loop of ProgMgr's Fee Approval Packet review and approval | 0 | 0 | 0
| RGLead coordinates: | [6 empty] | RGLead coordinates: | 0
| * sending EMAIL.DAS.APPROVAL with Fee Approval Packet attached |  |  |  |  | 0 |  |  | 0 |  | 0
| - in Outlook, request delivery and read receipts | [7 empty] | 0
| - save receipts to Rule_Development¦3-Fee.Approval¦PROOF.DAS.REQUEST.pdf | [7 empty] | 0
| * following up on status about 15 days after sending |  |  |  |  | 0 |  |  | 0 |  | 0
| DAS sends ProgLead response |  |  |  |  | 0 |  | DAS sends ProgLead response | 0 |  | 0
| If denied, ProgLead coordinates addressing DAS response |  |  |  | 0 | 0 |  | If denied, ProgLead coordinates addressing DAS response | 0 | 0 | 0
| 1st loop of ProgMgr's approval of response to DAS denial |  |  |  | 0 | 0 |  | 1st loop of ProgMgr's approval of response to DAS denial | 0 | 0 | 0
| 2nd loop of ProgMgr's approval of response to DAS denial | N |  |  | 0 | 0 |  | 2nd loop of ProgMgr's approval of response to DAS denial | 0 | 0 | 0
| 3rd loop of ProgMgr's approval of response to DAS denial | N |  |  | 0 | 0 |  | 3rd loop of ProgMgr's approval of response to DAS denial | 0 | 0 | 0
| 4th loop of ProgMgr's approval of response to DAS denial | N |  |  | 0 | 0 |  | 4th loop of ProgMgr's approval of response to DAS denial | 0 | 0 | 0
| If approved, ProgLead scans and files DAS.PART1.pdf |  |  |  | 0 | 0 |  | If approved, ProgLead scans and files DAS.PART1.pdf | 0 | 0 | 0
| (DAS.PART1 used 7.Post EQC) | [7 empty] | 0
| ProgLead gathers all fee emails for the Rule Record and saves as: | i |  |  | 0 | 0 |  | ProgLead gathers all fee emails for the Rule Record and saves as: | 0 | 0 | 0
| Rule_Development¦3-FeesApproval¦EMAILS.Fees.pdf | [7 empty] | 0
Public Notice
| CodeName |  |  |  | Start | End
[5 empty] | 0 | 0
1900-04-20
| Review version history to help maintain rulemaking record > | i
| SAVE DOCUMENTS ON: SharePoint folder 4-Public Notice | [7 empty] | 0
| DRAFT NOTICE PACKET | [7 empty] | 1
| ProgLead leads core team in developing Notice Packet that includes: |  |  |  | 0 | 2015-04-03 |  | ProgLead leads core team in developing Notice Packet that includes: | 1 | 0 | 2015-04-03
| * PROPOSED.RULES SharePoint ¦ 0 Proposed Rules | [7 empty] | 1
| See Proposed Rules section above | [7 empty] | 1
| Do not turn off track changes in PROPOSED.RULES | [7 empty] | 1
| * NOTICE SharePoint ¦ 4 Public Notice | [7 empty] | 1
| - Overview | [7 empty] | 1
| - Statement of Need | [7 empty] | 1
| - Rules affected, authorities, supporting documents | [7 empty] | 1
| - Fee Analysis | [7 empty] | 1
| - Statement of fiscal and economic impact | [7 empty] | 1
| - Federal relationship | [7 empty] | 1
| - Land use | [7 empty] | 1
| - Stakeholder and public involvement | [7 empty] | 1
| * SUPPORTING.DOCS - optional SharePoint ¦ 4 Public Notice | [7 empty] | 1
| * INVITATION.TO.COMMENT (after Notice approved) SharePoint ¦ 4 Public Notice | [7 empty] | 1
1
| RESOURCE INPUT - THIS IS NOT A REVIEW | [7 empty] | 1
| ProgLead asks RESOURCES for help and input, especially: |  |  |  | 0 | 2015-04-03 |  | ProgLead asks RESOURCES for help and input, especially: | 1 | 0 | 2015-04-03
| * RGLead for process, organization, edits, plain language | [6 empty] | * RGLead for process, organization, edits, plain language | 1
| * Affected staff, including regional staff, for subject matter contributions | [7 empty] | 1
| * AndreaG, for SIP consultation | [6 empty] | * AndreaG, for SIP consultation | 1
| * ProgMgr for direction and subject consultation, especially to ensure drafts: | [6 empty] | * ProgMgr for direction and subject consultation, especially to ensure drafts: | 1
| - meet program goals for rulemaking | [7 empty] | 1
| - align with section, division and agency goals | [7 empty] | 1
| * BrianW for any updates to communication plan, message map, news release | [6 empty] | * BrianW for any updates to communication plan, message map, news release | 1
| * Meyer for legal consultation and discuss need for AAG input | [6 empty] | * Meyer for legal consultation and discuss need for AAG input | 1
0
| * Enter custom resource here | [7 empty] | 1
| * Enter custom resource here | [7 empty] | 1
| * Enter custom resource here | [7 empty] | 1
| ProgLead continually refines draft Notice Packet and | [6 empty] | ProgLead continually refines draft Notice Packet and | 1
| * considers RESOURCES input | [7 empty] | 1
| * validates approach with staff who provided input | [7 empty] | 1
| * asks AAG for input if needed & copies Meyer on all AAG emails | [6 empty] | * asks AAG for input if needed & copies Meyer on all AAG emails | 1
| * addresses legal concerns and discusses with ProgMgr as needed | [6 empty] | * addresses legal concerns and discusses with ProgMgr as needed | 1
| * informs ProgMgr about the approach, issues and potential delays | [6 empty] | * informs ProgMgr about the approach, issues and potential delays | 1
| * raises unanticipated rulemaking and implementation risks to appropriate level | [7 empty] | 1
| * informs RGLead about potential delays and develop contingency, if needed | [6 empty] | * informs RGLead about potential delays and develop contingency, if needed | 1
| ProgLead asks contributors, including ProgMgr for consensus on |  |  |  | 0 | 2015-04-03 |  | ProgLead asks contributors, including ProgMgr for consensus on | 1 | 0 | 2015-04-03
| subject completeness and accuracy | [7 empty] | 1
| KEEP MANAGEMENT INFORMED | [7 empty] | 1
| ProgLead asks DAAssistant to schedule future time on MediaLead's calendar for: | Schedule by |  |  |  | 2015-03-27 |  | ProgLead asks DAAssistant to schedule future time on MediaLead's calendar for: | 1 |  | 2015-03-27
| * briefing meeting with ProgLead, ProgMgr and RGLead | Meeting will be |  |  |  | 2015-05-26 |  | * briefing meeting with ProgLead, ProgMgr and RGLead | 1 |  | 2015-05-26
| * decument review by blocking time to review Notice Packet during preview week | Review begins on |  |  |  | 2015-05-27 |  | * decument review by blocking time to review Notice Packet during preview week | 1 |  | 2015-05-27
| ProgLead schedules time on ProgMgr calendar to review Notice Packet | [6 empty] | ProgLead schedules time on ProgMgr calendar to review Notice Packet | 1
| ProgLead verifies/adjusts previously scheduled briefing & review with management | [6 empty] | ProgLead verifies/adjusts previously scheduled briefing & review with management | 1
| ProgLead keeps ProgMgr informed about progress, risks & delays | Review begins on |  |  |  | 2015-04-07 |  | ProgLead keeps ProgMgr informed about progress, risks & delays | 1 |  | 2015-04-07
| ProgMgr keeps her or his management teams informed about progress, risks & delays | [6 empty] | ProgMgr keeps her or his management teams informed about progress, risks & delays | 1
| CUSTOM SEQUENCE | [7 empty] | 1
| Name initiator and subject for custom review loop 1 | N |  |  | 0 | 2015-05-22 |  |  | 1 | 0 | 2015-05-22
| * enter custom action word and reviewer |  |  |  | 0 | 2015-05-22 |  |  | 1 | 0 | 2015-05-22
| * enter custom action word and reviewer |  |  |  | 0 | 2015-05-22 |  |  | 1 | 0 | 2015-05-22
| * enter custom action word and reviewer |  |  |  | 0 | 2015-05-22 |  |  | 1 | 0 | 2015-05-22
| Name initiator and subject for custom review loop 2 | N |  |  | 0 | 2015-05-22 |  |  | 1 | 0 | 2015-05-22
| * enter custom action word and reviewer |  |  |  | 0 | 2015-05-22 |  |  | 1 | 0 | 2015-05-22
| * enter custom action word and reviewer |  |  |  | 0 | 2015-05-22 |  |  | 1 | 0 | 2015-05-22
| * enter custom action word and reviewer |  |  |  | 0 | 2015-05-22 |  |  | 1 | 0 | 2015-05-22
| Name initiator and subject for custom review loop 3 | N |  |  | 0 | 2015-05-22 |  |  | 1 | 0 | 2015-05-22
| * enter custom action word and reviewer |  |  |  | 0 | 2015-05-22 |  |  | 1 | 0 | 2015-05-22
| * enter custom action word and reviewer |  |  |  | 0 | 2015-05-22 |  |  | 1 | 0 | 2015-05-22
| * enter custom action word and reviewer |  |  |  | 0 | 2015-05-22 |  |  | 1 | 0 | 2015-05-22
1
| RULE PUBLICATION WORK | [7 empty] | 1
| ProgLead prepares NOTICE, PROPOSED.RULES & optional SUPPORTING.DOCUMENTS: |  |  |  |  | 2015-04-28 |  | ProgLead prepares NOTICE, PROPOSED.RULES & optional SUPPORTING.DOCUMENTS: | 1 |  | 2015-04-28
| * addresses all comments, but does not delete them | [7 empty] | 1
| * saves each document as Major version to capture all comments and tracked changes | [7 empty] | 1
| * in NOTICE & optional SUPPORTING.DOCUMENTS: | [7 empty] | 1
| - accepts all changes | [7 empty] | 1
| - deletes addressed comments | [7 empty] | 1
| - ensures Word's track changes is turned on | [7 empty] | 1
| - saves documents as Minor versions | [7 empty] | 1
| * emails RGLead for Rule Publication work when complete |  |  |  |  | 2015-04-28 |  | * emails RGLead for Rule Publication work when complete | 1 |  | 2015-04-28
1
| During Rule Publication work: |  |  |  | Rule Publication Work Period |  |  |  | 1
| RGLead |  |  |  | Start | Complete by |  | RGLead | 1
| * determines whether NOTICE & SUPPORTING DOCUMENTS |  |  |  | 2015-04-29 | 2015-05-13 |  | RGLead who performs initial document readiness review | 1 |  | 2015-04-28
| are ready for Rule Publication | [7 empty] | 1
| - IF INCOMPLETE | [7 empty] | 1
| > notifies ProgMgr who works with ProgLead | [6 empty] | > notifies ProgMgr who works with ProgLead | 1
| > renegotiates schedule with ProgMgr & ProgLead as needed | [6 empty] | > renegotiates schedule with ProgMgr & ProgLead as needed | 1
| > reminds ProgLead to reschedule managers' briefing if needed | [6 empty] | > reminds ProgLead to reschedule managers' briefing if needed | 1
| > suspends Rule Publication work until ProgLead resubmits documents | [6 empty] | > suspends Rule Publication work until ProgLead resubmits documents | 1
| Loop 1 - Restart Rule Publication | N |  |  |  | 0 |  |  | 0 |  | 0
| Loop 2 - Restart Rule Publication | N |  |  |  | 0 |  |  | 0 |  | 0
| Loop 3 - Restart Rule Publication | N |  |  |  | 0 |  |  | 0 |  | 0
| - IF COMPLETE | [7 empty] | 1
| > asks Meyer to apply CHECKLIST review to PROPOSED.RULES | i | [5 empty] | > asks Meyer to apply CHECKLIST review to PROPOSED.RULES | 1
| > leads review to determine fiscal and economic impact analysis sufficiency | [7 empty] | 1
| > determines whether work products meet DEQ publication standards | [7 empty] | 1
| > asks BrianW, StephanieC & Meyer & AndreaG for input as needed | [6 empty] | > asks BrianW, StephanieC & Meyer & AndreaG for input as needed | 1
| > discusses/resolves any editorial differences | [7 empty] | 1
| > addresses input to ensure edits and comments speak with one voice | [7 empty] | 1
| > accepts non substantive edits | [7 empty] | 1
| > asks ProgMgr & ProgLead for input/concurrance as needed | [6 empty] | > asks ProgMgr & ProgLead for input/concurrance as needed | 1
| ProgMgr, ProgLead & RGLead discuss the following: | [6 empty] | ProgMgr, ProgLead & RGLead discuss the following: | 1
| * outstanding work | [7 empty] | 1
| * need for AAG review | [6 empty] | * need for AAG review | 1
| * need to renegotiate schedule | [7 empty] | 1
| ProgLead: |  |  |  | 2015-04-29 | 2015-05-27 |  | ProgLead: | 1 | 2015-04-29 | 2015-05-27
| * addresses outstanding edits and comments | [7 empty] | 1
| * asks AAG for review, if indicated, copies Meyer and addresses input | [6 empty] | * asks AAG for review, if indicated, copies Meyer and addresses input | 1
| * asks RGLead & ProgMgr for concurrence on changes if indicated | [6 empty] | * asks RGLead & ProgMgr for concurrence on changes if indicated | 1
| * addresses outstanding edits and comments | [6 empty] | * addresses Rule Publication concerns | 1
| * notifies RGLead & ProgMgr when complete and ready for preview | [6 empty] | * notifies RGLead & ProgMgr when complete and ready for preview | 1
| * initializes ProgMgr's publication review | [6 empty] | * initializes ProgMgr's publication review | 1
1
| PREVIEW PERIOD | [7 empty] | 1
| ProgLead drafts EMAIL.PREVIEW (instructions in template) | i |  |  |  | 2015-05-22 |  | ProgLead drafts EMAIL.PREVIEW (instructions in template) | 1 |  | 2015-05-22
| * sends draft to MediaLead just before briefing - links to preview documents included | [6 empty] | * sends draft to MediaLead just before briefing - links to preview documents included | 1
| * reminds MediaLead the review starts today | [6 empty] | * reminds MediaLead the review starts today | 1
| * copies ProgMgr & RGLead on email | [6 empty] | * copies ProgMgr & RGLead on email | 1
| ProgLead, ProgMgr brief MediaLead |  |  |  | Meeting > | 2015-05-26 |  | ProgLead, ProgMgr brief MediaLead | 1 |  | 2015-05-26
| MediaLead personalizes and sends EMAIL.PREVIEW 3 work days after briefing |  |  |  | Preview Period |  |  | MediaLead personalizes and sends EMAIL.PREVIEW 3 work days after briefing | 1
| To… Dick, DA.Program, Leadership Team & StephanieC |  |  |  | Start | End |  | To… Dick, DA.Program, Leadership Team & StephanieC | 1
| Cc…to all contributing and affected staff |  |  |  | 2015-06-01 | 2015-06-10 |  |  | 1 | 2015-06-01 | 2015-06-10
[5 empty] | allow 5-7 days |  |  |  | 1
1
| ProgLead: | [6 empty] | ProgLead: | 1
| * saves EMAIL.PREVIEW.pdf to Rule_Development ¦ 4-Notice | i | [6 empty] | 1
| * talks with ProgMgr, decides how to address any feedback from preview | [6 empty] | * talks with ProgMgr, decides how to address any feedback from preview | 1
| * modifies documents as needed | [7 empty] | 1
| * verifies PROPOSED.RULES are still based on current compilation | [7 empty] | 1
| * finalizes public documents with ProgMgr | [6 empty] | * finalizes public documents with ProgMgr | 1
| ProgMgr: | [6 empty] | ProgMgr: | 1
| * determines whether MediaLead needs a second review 'Y' if 2nd review needed> | Y |  |  | 2015-06-10 | 2015-06-10 |  | * determines whether MediaLead needs a second review 'Y' if 2nd review needed> | 1 | 2015-06-10 | 2015-06-10
| * manages MediaLead's 2nd review and approval | [6 empty] | * manages MediaLead's 2nd review and approval | 1
| * emails ProgLead & RGLead approval to move forward with | Approval to publish notice |  |  |  | 2015-06-12 |  | * emails ProgLead & RGLead approval to move forward with | 1 |  | 2015-06-12
| NOTICE, PROPOSED.RULES & any SUPPORTING.DCUMENTS | [7 empty] | 1
| ProgLead: | [6 empty] | ProgLead: | 1
| * saves email as Rule_Development ¦ 4-Notice ¦ MGR.APPROVAL.Notice.pdf | [7 empty] | 1
| * drafts INVITATION.TO.COMMENT using information from approved NOTICE | [6 empty] | ProgLead drafts INVITATION.TO.COMMENT using information from approved NOTICE | 1
| Meyer: |  |  |  | 2015-06-15 |  |  | Meyer: | 1 | 2015-06-15
| * establishes the following using Web Request ATTACHMENT | [7 empty] | 1
| - External Web page | i | [6 empty] | 1
| - Online public comment form | [7 empty] | 1
| - University Student Comment Account - helpdesk request with | [7 empty] | 1
| < ProgLead & Meyer co-owning account | [6 empty] | < ProgLead & Meyer co-owning account | 1
| < CodeName as 'Alias' | [6 empty] | < CodeName as 'Alias' | 1
| * compares work products to earlier reviews to determine need for additional edits | [7 empty] | 1
| * obtains additional Rule Publication edits on changes if needed | [7 empty] | 1
| * verifies/clarifies additional edits with ProgLead & ProgMgr as warranted | [6 empty] | * verifies/clarifies additional edits with ProgLead & ProgMgr as warranted | 1
| * notifies ProgMgr & ProgLead when finished | [6 empty] | * notifies ProgMgr & ProgLead when finished | 1
| * reminds ProgLead to set Outlook auto reply - instructions in Rulemaking Manual | [6 empty] | * reminds ProgLead to set Outlook auto reply - instructions in Rulemaking Manual | 1
| NOTIFICATIONS | [7 empty] | 1
| ProgLead: |  |  |  |  | 2015-06-12 |  | ProgLead: | 1 |  | 2015-06-12
| * submits of Notice to EPA, if required | [7 empty] | 1
| Meyer: |  |  |  |  | 2015-06-12 |  | Meyer: | 1 |  | 2015-06-12
| * prepares and submits notice to SOS for publication in Oregon Bulletin | i | [6 empty] | 1
| * emails DAS notification of fees that don't require DAS approval | [7 empty] | 0
| * saves all evidence on Rule_Development ¦ 4-Notice using naming conventions | i | [6 empty] | 1
| ProgLead leads: | [6 empty] | ProgLead leads: | 1
| * submitting newspaper notices to contractor |  | Set under Planning |  |  | 2015-07-06 |  | * modifies documents as needed | 1 |  | 2015-07-06
| * verifying newspaper advertisements are correct | [7 empty] | 1
| * obtaining copies of affidavits of publication from Accounting | [7 empty] | 1
| * adding hearings to DEQ Event Calendar | i |  |  |  | 2015-06-16 |  |  | 1 |  | 2015-06-16
| * creating an auto reply to Outlook account for University students | i | [6 empty] | 1
| * validating Web page, comment form and Outlook account | [6 empty] | * validates Web page, comment form, hearing date accuracy with ProgLead | 1
| * opening public comment by notifying agency rulemaking list that includes: |  |  |  |  | 2015-06-16 |  |  | 1 |  | 2015-06-16
| - GovDelivery | [7 empty] | 1
| - EQC members | [7 empty] | 1
| - advisory committee | [7 empty] | 1
| - program-specific lists | [7 empty] | 1
| * saves all evidence, lists and affidavits on Rule_Development ¦ 4-Notice | i | [6 empty] | 1
` | ProgLead drafts EMAIL.NOTICE.TO.KEY.LEGISLATORS - instruction in template: | i |  |  |  | 2015-06-09 |  | ProgLead drafts EMAIL.NOTICE.TO.KEY.LEGISLATORS - instruction in template: | 1 | 2015-06-16 | 2015-06-09
| * sends draft to Leg.Liason | [6 empty] | * sends draft to Leg.Liason | 1
| Leg.Liason: | [6 empty] | Leg.Liason: | 1
| * determines key legislators requiring ORS 183.335(5) notification | i | [6 empty] | 1
| * adapts email as needed | [7 empty] | 1
| * emails to recipients with Return Receipt (redirects receipt to ProgLead) |  |  |  |  | 2015-06-16 |  | * emails to recipients with Return Receipt (redirects receipt to ProgLead) | 1 | ` | 2015-06-16
| * copies ProgLead | [6 empty] | * copies ProgLead | 1
| * saves receipts under Rule_Development¦4-Notice | [7 empty] | 1
| RGLead & WebRep maintain Rukemaking Web page |  |  |  | 2015-06-16 | 0 |  | RGLead & WebRep maintain Rukemaking Web page | 1 | 2015-06-16 | 0
| ProgLead gathers and saves all emails on | i |  |  | 0 | 0 |  | ProgLead gathers and saves all emails on | 1 | 0 | 0
| Rule_Development¦4-Notice using naming conventions | [7 empty] | 1
Public Comment and Testimony
| CodeName |  |  |  | Start | End
[5 empty] | 0 | 0
| Review version history to help maintaining rulemaking record > | i
| SAVE DOCUMENTS ON: SharePoint folder 5-Public Comment | [7 empty] | 0
| Technical Lead verifies venues and equipment, gathers supplies | i |  |  | 0 | 2015-07-16 |  | Technical Lead verifies venues and equipment, gathers supplies | 1 | 0 | 2015-07-16
| START INFORMATION MEETING OPTION | [6 empty] | START INFORMATION MEETING OPTION | 1
| ProgLead: |  |  |  | 0 | 0 |  | ProgLead: | 1 | 0 | 0
| * develops INFO.MEETING.TEXT | [7 empty] | 1
| * modifies MESSAGE.MAP | i | [6 empty] | 1
| * develops INFO.PRESENTATION | [7 empty] | 1
| * practices presentation | [7 empty] | 1
| * makes presentation adjustments | [7 empty] | 1
| * initiates ProgMgr's review/approval, addresses suggestions |  |  |  | 0 | 0 |  | * initiates ProgMgr's review/approval, addresses suggestions | 1 | 0 | 0
| 1st loop ProgMgr reviews/approves optional presentation |  |  |  | 0 | 0 |  | 1st loop ProgMgr reviews/approves optional presentation | 1 | 0 | 0
| 2nd loop ProgMgr reviews/approves optional presentation | N |  |  | 0 | 0 |  | 2nd loop ProgMgr reviews/approves optional presentation | 0 | 0 | 0
| 3rd loop ProgMgr reviews/approves optional presentation | N |  |  | 0 | 0 |  | 3rd loop ProgMgr reviews/approves optional presentation | 0 | 0 | 0
| 4th loop ProgMgr reviews/approves optional presentation | N |  |  | 0 | 0 |  | 4th loop ProgMgr reviews/approves optional presentation | 0 | 0 | 0
| Hearings Officers: |  |  |  | 0 | 2015-07-16 |  |  | 1 | 0 | 2015-07-16
| * reviews responsibilities of hearings officer | [7 empty] | 1
| * develops introductory and logistics script | i | [6 empty] | 1 | 0 | 2015-07-16
| * holds the following hearings (identified under Planning section) with assigned team: | [6 empty] | * holds the following hearings (identified under Planning section) with assigned team: | 1
| 1. Portland hearing |  |  |  |  | 2015-07-16 |  | 1. Portland hearing | 1 |  | 2015-07-16
| - save audio as Rule_Development¦5-PublicComment¦HEARING.1.mp3 | [7 empty] | 1
| 2. Enter city name hearing |  |  |  |  | 0 |  | 2. Enter city name hearing | 0 |  | 0
| - save audio as Rule_Development¦5-PublicComment¦HEARING.2.mp3 | [7 empty] | 0
| 3. Enter city name hearing |  |  |  |  | 0 |  | 3. Enter city name hearing | 0 |  | 0
| - save audio as Rule_Development¦5-PublicComment¦HEARING.3.mp3 | [7 empty] | 0
| 4. Enter city name hearing |  |  |  |  | 0 |  | 4. Enter city name hearing | 0 |  | 0
| - save audio as Rule_Development¦5-PublicComment¦HEARING.4.mp3 | [7 empty] | 0
| 5. Enter city name hearing |  |  |  |  | 0 |  | 5. Enter city name hearing | 0 |  | 0
| - save audio as Rule_Development¦5-PublicComment¦HEARING.5.mp3 | [7 empty] | 0
| 6. Enter city name hearing |  |  |  |  | 0 |  | 6. Enter city name hearing | 0 |  | 0
| - save audio as Rule_Development¦5-PublicComment¦HEARING.6.mp3 | [7 empty] | 0
| 7. Enter city name hearing |  |  |  |  | 0 |  | 7. Enter city name hearing | 0 |  | 0
| - save audio as Rule_Development¦5-PublicComment¦HEARING.7.mp3 | [7 empty] | 0
| 8. Enter city name hearing |  |  |  |  | 0 |  | 8. Enter city name hearing | 0 |  | 0
| - save audio as Rule_Development¦5-PublicComment¦HEARING.8.mp3 | [7 empty] | 0
| Technical Lead, for comments received by mail or at hearings |  |  |  | 2015-07-16 | 0 |  | Technical Lead, for comments received by mail or at hearings | 1 | 2015-07-16 | 0
| * stamps DEQ receipt date on address-side of envelope and on first page of letter | [7 empty] | 1
| * adds commenter and comment to COMMENTS | [7 empty] | 1
| * scans mailed comments and envelopes and saves as ID###.pdf | [7 empty] | 1
|  |  | Close public comment |  |  | 0 |  |  | 1 |  | 0
| ProgLead: |  |  |  | 2015-07-16 | 0 |  | ProgLead: | 1 | 2015-07-16 | 0
| * saves online public comment information to COMMENTS | [7 empty] | 1
| * coordinates with team to: | [7 empty] | 1
| - develop category titles to bundle similar comments | [7 empty] | 1
| - organize comments into categories | [7 empty] | 1
| - draft DEQ responses to each categories of comments | [7 empty] | 1
| * leads team work finalizing DEQ responses to public comment | [7 empty] | 1
| DO NOT MAIL TO COMMENTERS UNTIL EQC ASSISTANT FINALIZES STAFF REPORT | [7 empty] | 1
| ProgLead asks RGLead for Rule Publication review | i |  |  |  | 1900-01-01 |  | ProgLead asks RGLead for Rule Publication review | 1 |  | 1900-01-01
| RGLead coordinates Rule Publication work: |  |  |  | 1900-01-01 | 1900-01-01 |  | RGLead coordinates Rule Publication work: | 1 | 1900-01-01 | 1900-01-01
| * edits for plain English, style guide & tone because this is part of EQC Packet | [7 empty] | 1
| * contacts ProgLead with questions, clarifications and suggestions | [6 empty] | * contacts ProgLead with questions, clarifications and suggestions | 1
| * notifies ProgLead when complete | [6 empty] | * notifies ProgLead when complete | 1
| ProgLead: | [6 empty] | ProgLead: | 1
| * shares comments/responses to comments with ProgMgr & MediaLead |  |  |  |  | 1900-01-01 |  | * shares comments/responses to comments with ProgMgr & MediaLead | 1 |  | 1900-01-01
| 1st loop - team modifies responses to get to approval |  |  |  | 1900-01-01 | 1900-01-01 |  |  | 1 | 1900-01-01 | 1900-01-01
| 2nd loop - team modifies responses to get to approval | N |  |  | 0 | 0 |  |  | 0 | 0 | 0
| 3rd loop - team modifies responses to get to approval | N |  |  | 0 | 0 |  |  | 0 | 0 | 0
| Final loop - team modifies responses to get to approval | N |  |  | 0 | 0 |  |  | 0 | 0 | 0
| ProgLead: | [6 empty] | ProgLead: | 1
| * gathers emails ABOUT comments, not actual comments, for Rule Record | i |  |  |  | 1900-01-01 |  |  | 1 |  | 1900-01-01
| * saves them as Rule_Development¦5-PublicComment...¦EMAIL.Comment.pdf | [7 empty] | 1
EQC Preparation
| CodeName |  |  |  | Start | End
[5 empty] | 0 | 0
| Review version history to help maintaining rulemaking record > | i
| SAVE DOCUMENTS ON: SharePoint folder 6-EQC Preparation | [7 empty] | 0
| DEADLINE: Submit to EQC Assistant |  |  |  |  | #N/A |  |  | 1 |  | #N/A
| No EQC involvement prior to Action Item meeting | [6 empty] | No EQC involvement prior to Action Item meeting | 1
| * no Director's Report |  |  |  | 0 | 0 |  | * no Director's Report | 0 | 0 | 0
| * no EQC Information Item | i |  |  | 0 | 0 |  | * no EQC Information Item | 0 | 0 | 0
| * blank row |  |  |  | 0 | 0 |  | * blank row | 0 | 0 | 0
| ProgLead: |  |  |  | 0 | #N/A |  | ProgLead: | 1 | 0 | #N/A
| *finalizes EQC Packet with core team: | [7 empty] | 1
| - STAFF.RPT.Permanent preloaded into folder 6 using instructions in template | [6 empty] | - STAFF.RPT.Permanent preloaded into folder 6 using instructions in template | 1
| - PROPOSED.RULES in folder 0 | [7 empty] | 1
| - SUPPORTING.DOCUMENTS moved from folder 4 to folder 6 | [7 empty] | 1
| * notifies RGLead that EQC packet is ready for Rule Publication work | [6 empty] | * notifies RGLead that EQC packet is ready for Rule Publication work | 1
| RGLead leads initial Rule Publication work that includes: |  |  |  | #N/A | #N/A |  | RGLead leads initial Rule Publication work that includes: | 1 | #N/A | #N/A
| * comparing NOTICE to STAFF.REPORT to determine what needs review | [7 empty] | 1
| * obtaining/consolidating BrianW, StephanieC & AndreaG edits if needed | [6 empty] | * obtaining/consolidating BrianW, StephanieC & AndreaG edits if needed | 1
| including style guide, grammar, plain English, organization, clarity, tone | [7 empty] | 1
| * accepting all style guide and format edits | [7 empty] | 1
| * getting Meyer's review of PROPOSED.RULES- SOS/LC and CHECKLIST review | [6 empty] | * getting Meyer's review of PROPOSED.RULES- SOS/LC and CHECKLIST review | 1
| * contacts ProgLead with questions or modifications and when work is complete | [6 empty] | * contacts ProgLead with questions or modifications and when work is complete | 1
| ProgLead: |  |  |  | #N/A | #N/A |  | ProgLead: | 1 | #N/A | #N/A
| * addresses rule publication edits and comments | [7 empty] | 1
| * prepares EQC packet | [7 empty] | 1
| * initiates management review and approval | [7 empty] | 1
| - ProgMgr | [6 empty] | - ProgMgr | 1
| - DA.Program, if indicated | [6 empty] | - DA.Program, if indicated | 1
| - Enter custom reviewer and action | [7 empty] | 1
| - Enter custom reviewer and action | [7 empty] | 1
| * obtains approval from ProgMgr to submit EQC packet | [6 empty] | * obtains approval from ProgMgr to submit EQC packet | 1
| * discusses need for 1¦1 commissioners briefings with ProgMgr & MediaLead | N |  |  | 0 | 0 |  | * discusses need for 1¦1 commissioners briefings with ProgMgr & MediaLead | 0 | 0 | 0
| MEden@neea.org | [7 empty] | 0
| JoKRanch@hotmail.com | [7 empty] | 0
| EdArmstrong2@gmail.com | [7 empty] | 0
| MorganRider@gmail.com | [7 empty] | 0
| cjohnson@eou.edu | [7 empty] | 0
| * submits EQC packet to StephanieC |  |  |  |  | #N/A |  | * submits EQC packet to StephanieC | 1 |  | #N/A
| * notifies the following according to division's best practice after EQC Web posting |  |  |  | 0 | 2015-12-15 |  |  | 1 | 0 | 2015-12-15
| - staff contributors | [7 empty] | 1
| - key stakeholders | [7 empty] | 1
| - advisory committee members | [7 empty] | 0
| - commenters | [7 empty] | 1
| - interested parties (optional) | [7 empty] | 1
| * leads team development of EQC presentation |  |  |  | 0 | 2015-12-15 |  |  | 1 | 0 | 2015-12-15
| * coordinates presentation practices |  |  |  | 0 | 2015-12-15 |  |  | 1 | 0 | 2015-12-15
| * makes any presentation adjustments |  |  |  | 0 | 2015-12-15 |  |  | 1 | 0 | 2015-12-15
| Presentation team ATTENDS EQC MEETING |  |  |  | 0 | 2015-12-16 |  |  | 1 |  | 2015-12-16
| ProgLead collects emails about EQC preparations for Rule Record and saves as: | i |  |  |  | 2015-12-16 |  | ProgLead collects emails about EQC preparations for Rule Record and saves as: | 1 |  | 2015-12-16
| Rule_Development¦6-EQCPreparation¦EMAILS.EQC.Prep.pdf | [7 empty] | 1
Post EQC
| CodeName |  |  |  | Start | End
[5 empty] | 0 | 0
| Review version history to help maintaining rulemaking record > | i
| DOCUMENT PREPARATION | [6 empty] | * no DAS involvement | 1
| ProgLead saves following documents to 7.PostEQC folder on Rule_Develpment: | [6 empty] | ProgLead saves following documents to 7.PostEQC folder on Rule_Develpment: | 1
| * gets documents as presented to EQC from StephanieC: |  |  |  |  | 0 |  | * gets documents as presented to EQC from StephanieC: | 1 |  | 0
| - STAFF.REPORT.pdf | [7 empty] | 1
| - STAFF.REPORT.ADDENDUM.pdf (if presented to EQC) | [7 empty] | 1
| *downloads documents as presented to EQC from SharePoint: |  |  |  |  | 0 |  |  | 1 |  | 0
| - PROPOSED.RULES (showing changes) | [7 empty] | 1
| > saves as REDLINE.docx (showing changes in strikethrough and underscore) | [7 empty] | 1
| > saves as RULES.docx (clean version), accepts all changes, saves again | [7 empty] | 1
| - TABLES.340-###-####.docx (1 .docx per rule contains ALL tables in rule) | [7 empty] | 1
| - TABLES.340-###-####.docx (1 .docx per rule contains ALL tables in rule) | [7 empty] | 1
| * coordinates EPA.SIP.SUBMITAL with AndreaG | [6 empty] | * coordinates EPA.SIP.SUBMITAL with AndreaG | 1
0
| FILING | [6 empty] | * no DAS involvement | 0
| More details in Rulemaking Manual | [7 empty] | 1
| DEADLINE: No Oregon deadline for filing rules after adoption - check EPA | [7 empty] | 1
| Meyer: | [6 empty] | Meyer: | 1
| * logs onto Secretary of State online filing form | i | [6 empty] | 1
| * uses information in STAFF.REPORT & ADDENDUM to populate form | [7 empty] | 1
| * reviews, prepares and uploads:: | [7 empty] | 1 |  | talk about folders original format, etc
| - RULES.docx (clean version in Word) | [7 empty] | 1
| - TABLES.340-###-####-SOS.pdf (1 .docx per rule contains ALL tables in rule) | [7 empty] | 1
| - TABLES.340-###-####-SOS.pdf (1 .docx per rule contains ALL tables in rule) | [7 empty] | 1
| * develops, scans and uploads AUTHORIZATION-SOS.pdf into online SOS form | [7 empty] | 1
| * completes SOS form, verifies and submits |  |  | Filed Date |  | 2015-12-18 |  |  | 1 |  | 2015-12-18
|  |  |  | Effective Date |  | 2015-12-18 |  |  | 1 |  | 2015-12-18
| * saves certificate that SOS sent via email as CERTIFICATE-SOS.pdf | [7 empty] | 1
| * notes sequence for Certificate and Order No. | [7 empty] | 1
| * submits Web request to update Web page | [7 empty] | 1
| * moves share drive folder system | [6 empty] | Meyer moves folders on shared drive after EQC approval: | 1
| FROM: \\deqhq1\Rule_Development\Current | i | [6 empty] | 1
| TO: \\deqhq1\Rule_Development\Filed | i | [6 empty] | 1
0
| Legislative Counsel Notification | [6 empty] | * no DAS involvement | 0
| DEADLINE: LC must receive notification within 10 days after CERTIFICATE date | [7 empty] | 1
| DEQ PRACTICE: Put in shuttle on day of SOS filing | [7 empty] | 1
| Meyer: | [6 empty] | Meyer: | 1
| * prepares Legislative Counsel notification - see Rulemaking Manual: | [7 empty] | 1
| - prints CERTIFICATE and saves copy as CERTIFICATE-LC.pdf | [7 empty] | 1
| - prints REDLINE and saves copy as REDLINE-LC.pdf | [7 empty] | 1
| - self-addressed envelope, fold underside of flap over a 2nd certificate" | [7 empty] | 1
| write "Please date stamp certificate and return." on underside of flap | [7 empty] | 1
| * prepares/scans return receipt shuttle envelope, saves as SHUTTLE.RECEIPT-LC.pdf | [7 empty] | 1
| * sends via shuttle | [7 empty] | 1
| * sends Procurement a scanned image of SHUTTLE.RECEIPT-LC | i |  |  |  | 2015-12-18 |  |  | 1 |  | 2015-12-18
1
| NO FEES INVOLVED | [6 empty] | NO FEES INVOLVED | 0
| DEADLINE: DEQ must send notification or DAS Part 2 within 10 days of EQC action | [7 empty] | 0
0
| * no DAS involvement |  |  |  |  | 0 |  | * no DAS involvement | 0 |  | 0
0
0
0
0
0
| * prepares/scans shuttle envelope, saves as SHUTTLE.RECEIPT-DAS.pdf | [7 empty] | 1
1
| * sends Procurement a scanned image of SHUTTLE.RECEIPT-DAS | i |  |  |  | 2015-12-18 |  |  | 1 |  | 2015-12-18
1
| CLOSING RECORDS AND ARCHIVAL | [7 empty] | 0
| RGLead: | [6 empty] | RGLead: | 1
| * verifies Web page is current and accurate | [7 empty] | 1
| * coordinates meeting to discuss lessons learned | [7 empty] | 1
| * ensures the final version of every document on SharePoint is Major (Published) | [7 empty] | 1
| * verifies Outlook student comment account is empty/asks helpdesk to close account | [7 empty] | 1
| * leads verification that published rules in Oregon Bulletin are correct | [7 empty] | 1
| If errors, ProgLead works with Meyer to correct and selects 'Y' > | Y | [5 empty] | If errors, ProgLead works with Meyer to correct and selects 'Y' > | 1
| AndreaG submits SIP to EPA within 60 days AFTER adoption |  |  |  | 2015-12-16 | 2016-02-01 |  | AndreaG submits SIP to EPA within 60 days AFTER adoption | 1 | 2015-12-16 | 2016-02-01
| * emails optional STAKEHOLDER.NOTIFICATION that links to Web page | Y | [6 empty] | 1
| * coordinates AC.THANK.YOU email or letter that links to Web page with ProgMgr | i | [5 empty] | * coordinates AC.THANK.YOU email or letter that links to Web page with ProgMgr | 0
| * scans physical records and save to Rule_Development | [7 empty] | 1 | 0 | 0
| * gathers emails about post EQC activities for the Rule Record and saves as: | [7 empty] | 1
| Rule_Development ¦ 7-PostEQC ¦ EMAILS.PostEQC.pdf | [7 empty] | 1
| Meyer: | [6 empty] | Meyer: | 1
| * coordinates moving major versions from SharePoint to Rule_Development | [7 empty] | 1
| * coordinates closing SharePoint sub-site | [7 empty] | 1
| * archives folders when record is complete by moving: | [7 empty] | 1
| FROM: \\deqhq1\Rule_Development | i | [6 empty] | 1
| TO: \\deqhq1\Rule_Archives | [7 empty] | 1
| * coordinates retiring Q-Time number(s) with BudgetAnalyst & RobertB | [6 empty] | * coordinates retiring Q-Time number(s) with BudgetAnalyst & RobertB | 1
| TEAM CELEBRATES | [7 empty] | 1
[5 empty] | $G$861 | $H$861
mm/dd/yy
Subject
Your name
Your message
DEQ Closed
11/30/2014
Goodbye update
Maggie
Changes to this worksheet address your feedback. For those of you new to who haven't used the schedule in a while:
o the ListTableLookup tab is the renamed DDL tab that includes drop down lists and table look up values.
o the Documentation tab provides some behind the scenes information about this workbook.
o most information accessed through the information icon in column D is now available in the Rulemaking Manual lon Rule_Resources and linked from front page of the rulemaking SharePoint.
o there is a reduced number of date entry fields.

## GetStarted
Title | CodeName
Caption | CodeName | i
Names entered under this area will become part of the Schedule of Tasks and Partnershup Agreement
| Enter first name for Schedule | Enter full name for Agreement | Division | Program | Pronoun
Program Lead (Technical Lead) | ProgLead |  |  |  | his
Sponsoring Manager (Mgr of Techical Lead) | ProgMgr |  |  |  | his
Media Lead (Issues final approvals) | MediaLead |  |  |  | her
Rules Group Lead | RGLead |  |  |  | her
Standardization (ARC) | Meyer | Meyer Goldstein
Public Affairs Representative | BrianW | Brian White
EQC Assistant | StephanieC | Stephanie Caldera |  | GET STARTED
State Implementation Plan Coordinator | AndreaG |  |  | Enter names and codes on this worksheet
Web Master | WebRep | Michele Thompson
FiscalReviewer | Meyer (Fiscal) | Meyer Goldstein |  | ON SCHEDULE
Budget analyst | BudgetAnalyst | Drop down list |  | Enter Title in header
Assistant Attorney General | AAG | Drop down list |  | Enter start date in G6
Legislative liaison | Leg.Liason |  |  | When Directors adds to plan, enter date in G9
Support staff (none available; use Tech. Lead) | Technical Lead |  |  | Select Y/N options in C9:C50
Time Accounting | RobertB | RobertB |  | All banner dates set on Overview of Key dates
Director | Dick | Dick |  | Drop down lists
Hearings Officer | HearingOfficer |  |  | EQC optional involvement G39:H41
Division Administrator - Rules | DA.Rules |  |  | SOS Bulletin H31
Division Administrator - Program | DA.Program |  |  | EQC meeting H44
DA Assistant | DAAssistant
Chief Public Affairs Officer | Jennifer Flynt
Media Lead
JenniferW | WQ
LydiaE | AQ
WendyW | LQ
MediaLead | CP
Budget Analyst
AdamC | WQ
SandraJ | LQ
MaragaretO | AQ
BudgetAnalyst | AQ
Legislative Liason
KarenT | WQ
TomR | LQ
MargaretO | AQ
Leg.Liason | AQ
AAG
LarryK | WQ
DaveV | HW
PaulG | AQ
LarryK | LQ
AAG | CP

## Lists.TableLookups
Drop down lists (S.DDL_) used through Data Validation and VLOOKUP (S.VL_) tables
1 of 4 | EQC Meeting | EQCStaffRptDue | EQCMaterialsDue
| TABLE - S.VL_EQCActivities (B5:D26) |  |  |  |  | Publications
| S.DDL_EQCMeeting (B5:B26) |  |  |  | 2 of 4 | S.DDL_Newapapers (I5:I13)
| 2013-03-20 | 2013-02-11 | 2013-03-13 | When updating EQC table, leave rows for previous year. |  | Oregonian
| 2013-06-19 | 2013-05-10 | 2013-06-12 |  |  | EastOregon
| 2013-08-21 | 2013-07-16 | 2013-08-14 |  |  | RegisterGuard
| 2013-10-16 | 2013-09-10 | 2013-10-09 |  |  | MailTribune
| 2013-12-11 | 2013-11-01 | 2013-12-04 |  |  | KlamathHerald
| 2014-03-20 | 2014-02-13 | 2014-02-24 |  |  | LaGrandeObserver
| 2014-06-18 | 2014-05-12 | 2014-05-26 |  |  | JournalOfCommerce
| 2014-08-27 | 2014-07-24 | 2014-08-04 |  |  | None
| 2014-11-05 | 2014-09-29 | 2014-10-13 |  |  | Other
| 2015-01-07 | 2014-12-02 | 2014-12-10 |  |  | Called from Planning section
| 2015-04-15 | 2015-03-05 | 2015-04-03 | Update these dates when EQC Assistant publishes actual meeting date.s
| 2015-06-10 | 2015-04-30 | 2015-05-29
| 2015-08-12 | 2015-07-02 | 2015-07-31
| 2015-10-14 | 2015-09-03 | 2015-10-02
| 2015-12-09 | 2015-10-29 | 2015-11-27
| 2016-03-23 | 2016-02-11 | 2016-03-11
| 2016-06-22 | 2016-05-12 | 2016-06-10
| 2016-08-17 | 2016-07-07 | 2016-08-05
| 2016-10-19 | 2016-09-08 | 2016-10-07
| 2016-12-21 | 2016-11-10 | 2016-12-09
| 2017-03-22 | 2017-02-09 | 2017-03-10
| 2017-06-21 | 2017-05-11 | 2017-06-09
Called from Overview of Key Tasks section
3 of 4 | S.DDL_DEQClosed (B31:B79) |  |  |  | http://www.leg.state.or.us/ors/187.html
| Legal Holiday (B31:B67) | Description |  |  | LEGAL HOLIDAYS 187.010 Legal holidays; acts deferred to next business day; effect on labor agreements. (1) The following days are legal holidays in this state: (a) Each Sunday. (b) New Year’s Day on January 1. (c) Martin Luther King, Jr.’s Birthday on the third Monday in January. (d) Presidents Day, for the purpose of commemorating Presidents Washington and Lincoln, on the third Monday in February. (e) Memorial Day on the last Monday in May. (f) Independence Day on July 4. (g) Labor Day on the first Monday in September. (h) Veterans Day on November 11. (i) Thanksgiving Day on the fourth Thursday in November. (j) Christmas Day on December 25. (2) Each time a holiday, other than Sunday, listed in subsection (1) of this section falls on Sunday, the succeeding Monday shall be a legal holiday. Each time a holiday listed in subsection (1) of this section falls on Saturday, the preceding Friday shall be a legal holiday. (3) Any act authorized, required or permitted to be performed on a holiday as designated in this section may be performed on the next succeeding business day; and no liability or loss of rights of any kind shall result from such delay. (4) In enumerating legal holidays in subsection (1) of this section, the Legislative Assembly does not intend to limit or otherwise affect public or private collective bargaining or collective bargaining agreements. [Amended by 1955 c.4 §1; 1969 c.455 §1; 1973 c.51 §1; 1975 c.633 §1; 1977 c.135 §1; 1977 c.321 §1; 1985 c.518 §1] 187.020 Additional legal holidays. In addition to those specified in ORS 187.010, the following days are legal holidays in this state: (1) Every day appointed by the Governor as a holiday. (2) Every day appointed by the President of the United States as a day of mourning, rejoicing or other special observance only when the Governor also appoints that day as a holiday. [Amended by 1969 c.455 §2; 1975 c.633 §2; 1977 c.135 §2; 1977 c.321 §2; 1985 c.518 §2]
| 2014-01-01 | New Year |  | 2014-01-01
| 2014-01-20 | MLK Jr. |  | 2014-01-20
| 2014-02-17 | Presidents |  | 2014-02-17
| 2014-05-26 | Memorial |  | 2014-05-26
| 2014-07-04 | Independence |  | 2014-07-04
| 2014-09-02 | Labor |  | 2014-09-02
| 2014-11-11 | Veterans |  | 2014-11-11
| 2014-11-27 | Thanksgiving |  | 2014-11-27
| 2014-12-25 | Christmas |  | 2014-12-25
| 2015-01-01 | New Year |  | 2015-01-01
| 2015-01-19 | MLK Jr. |  | 2015-01-19
| 2015-02-16 | Presidents |  | 2015-02-16
| 2015-05-25 | Memorial |  | 2015-05-25
| 2015-07-03 | Independence |  | 2015-07-03
| 2015-09-07 | Labor |  | 2015-09-07
| 2015-11-11 | Veterans |  | 2015-11-11
| 2015-11-26 | Thanksgiving |  | 2015-11-26
| 2015-12-25 | Christmas |  | 2015-12-25
| 2016-01-01 | New Year |  | 2016-01-01
| 2016-01-18 | MLK Jr. |  | 2016-01-18
| 2016-02-15 | Presidents |  | 2016-02-15
| 2016-05-30 | Memorial |  | 2016-05-30
| 2016-07-04 | Independence |  | 2016-07-04
| 2016-09-05 | Labor |  | 2016-09-05
| 2016-11-11 | Veterans |  | 2016-11-11
| 2016-11-24 | Thanksgiving |  | 2016-11-24
| 2016-12-26 | Christmas |  | 2016-12-26
| 2017-01-02 | New Year |  | 2017-01-02
| 2017-01-16 | MLK Jr. |  | 2017-01-16
| 2017-02-20 | Presidents |  | 2017-02-20
| 2017-05-29 | Memorial |  | 2017-05-29
| 2017-07-04 | Independence |  | 2017-07-04
| 2017-09-04 | Labor |  | 2017-09-04
| 2017-11-10 | Veterans |  | 2017-11-10
| 2017-11-23 | Thanksgiving |  | 2017-11-23
| 2017-12-25 | Christmas |  | 2017-12-25
| 2018-01-01 | New Year |  | 2018-01-01
Called throught workbook. When used in WORKDAY caculation, this is [holidays].
4 of 4 | Publication Date | Due to SOS
S.VL_Bulletin ( B74:C181)
S.DDL_Bulletin (B74:B181)
| 2013-01-01 | 2012-12-14 |  | 2012-12-14
| 2013-02-01 | 2013-01-15 |  | 2013-01-15
| 2013-03-01 | 2013-02-15 |  | 2013-02-15
| 2013-04-01 | 2013-03-15 |  | 2013-03-15
| 2013-05-01 | 2013-04-15 |  | 2013-04-15
| 2013-06-01 | 2013-05-15 |  | 2013-05-15
| 2013-07-01 | 2013-06-14 |  | 2013-06-14
| 2013-08-01 | 2013-07-15 |  | 2013-07-15
| 2013-09-01 | 2013-08-15 |  | 2013-08-15
| 2013-10-01 | 2013-09-13 |  | 2013-09-13
| 2013-11-01 | 2013-10-15 |  | 2013-10-15
| 2013-12-01 | 2013-11-15 |  | 2013-11-15
| 2014-01-01 | 2013-12-13 |  | 2013-12-13
| 2014-02-01 | 2014-01-15 |  | 2014-01-15
| 2014-03-01 | 2014-02-14 |  | 2014-02-14
| 2014-04-01 | 2014-03-14 |  | 2014-03-14
| 2014-05-01 | 2014-04-15 |  | 2014-04-15
| 2014-06-01 | 2014-05-15 |  | 2014-05-15
| 2014-07-01 | 2014-06-13 |  | 2014-06-13
| 2014-08-01 | 2014-07-15 |  | 2014-07-15
| 2014-09-01 | 2014-08-15 |  | 2014-08-15
| 2014-10-01 | 2014-09-15 |  | 2014-09-15
| 2014-11-01 | 2014-10-15 |  | 2014-10-15
| 2014-12-01 | 2014-11-14 |  | 2014-11-14
| 2015-01-01 | 2014-12-15 |  | 2014-12-15
| 2015-02-01 | 2015-01-15 |  | 2015-01-15
| 2015-03-01 | 2015-02-13 |  | 2015-02-13
| 2015-04-01 | 2015-03-13 |  | 2015-03-13
| 2015-05-01 | 2015-04-15 |  | 2015-04-15
| 2015-06-01 | 2015-05-15 |  | 2015-05-15
| 2015-07-01 | 2015-06-15 |  | 2015-06-15
| 2015-08-01 | 2015-07-15 |  | 2015-07-15
| 2015-09-01 | 2015-08-15 |  | 2015-08-15
| 2015-10-01 | 2015-09-15 |  | 2015-09-15
| 2015-11-01 | 2015-10-15 |  | 2015-10-15
| 2015-12-01 | 2015-11-13 |  | 2015-11-13
| 2016-01-01 | 2015-12-15 |  | 2015-12-15
| 2016-02-01 | 2016-01-15 |  | 2016-01-15
| 2016-03-01 | 2016-02-15 |  | 2016-02-15
| 2016-04-01 | 2016-03-15 |  | 2016-03-15
| 2016-05-01 | 2016-04-15 |  | 2016-04-15
| 2016-06-01 | 2016-05-13 |  | 2016-05-13
| 2016-07-01 | 2016-06-15 |  | 2016-06-15
| 2016-08-01 | 2016-07-15 |  | 2016-07-15
| 2016-09-01 | 2016-08-15 |  | 2016-08-15
| 2016-10-01 | 2016-09-15 |  | 2016-09-15
| 2016-11-01 | 2016-10-14 |  | 2016-10-14
| 2016-12-01 | 2016-11-15 |  | 2016-11-15
| 2017-01-01 | 2016-12-15 |  | 2016-12-15
| 2017-02-01 | 2017-01-13 |  | 2017-01-13
| 2017-03-01 | 2017-02-15 |  | 2017-02-15
| 2017-04-01 | 2017-03-15 |  | 2017-03-15
| 2017-05-01 | 2017-04-14 |  | 2017-04-14
| 2017-06-01 | 2017-05-15 |  | 2017-05-15
| 2017-07-01 | 2017-06-15 |  | 2017-06-15
| 2017-08-01 | 2017-07-14 |  | 2017-07-14
| 2017-09-01 | 2017-08-15 |  | 2017-08-15
| 2017-10-01 | 2017-09-15 |  | 2017-09-15
| 2017-11-01 | 2017-10-13 |  | 2017-10-13
| 2017-12-01 | 2017-11-15 |  | 2017-11-15
| 2018-01-01 | 2017-12-15 |  | 2017-12-15
| 2018-02-01 | 2018-01-15 |  | 2018-01-15
| 2018-03-01 | 2018-02-15 |  | 2018-02-15
| 2018-04-01 | 2018-03-14 |  | 2018-03-14
| 2018-05-01 | 2018-04-13 |  | 2018-04-13
| 2018-06-01 | 2018-05-15 |  | 2018-05-15
| 2018-07-01 | 2018-06-15 |  | 2018-06-15
| 2018-08-01 | 2018-07-13 |  | 2018-07-13
| 2018-09-01 | 2018-08-15 |  | 2018-08-15
| 2018-10-01 | 2018-09-14 |  | 2018-09-14
| 2018-11-01 | 2018-10-15 |  | 2018-10-15
| 2018-12-01 | 2018-11-15 |  | 2018-11-15
| 2019-01-01 | 2018-12-14 |  | 2018-12-14
| 2019-02-01 | 2019-01-15 |  | 2019-01-15
| 2019-03-01 | 2019-02-15 |  | 2019-02-15
| 2019-04-01 | 2019-03-15 |  | 2019-03-15
| 2019-05-01 | 2019-04-15 |  | 2019-04-15
| 2019-06-01 | 2019-05-15 |  | 2019-05-15
| 2019-07-01 | 2019-06-14 |  | 2019-06-14
| 2019-08-01 | 2019-07-15 |  | 2019-07-15
| 2019-09-01 | 2019-08-15 |  | 2019-08-15
| 2019-10-01 | 2019-09-13 |  | 2019-09-13
| 2019-11-01 | 2019-10-15 |  | 2019-10-15
| 2019-12-01 | 2019-11-15 |  | 2019-11-15
| 2020-01-01 | 2019-12-13 |  | 2019-12-13
| 2020-02-01 | 2020-01-15 |  | 2020-01-15
| 2020-03-01 | 2020-02-14 |  | 2020-02-14
| 2020-04-01 | 2020-03-13 |  | 2020-03-13
| 2020-05-01 | 2020-04-15 |  | 2020-04-15
| 2020-06-01 | 2020-05-15 |  | 2020-05-15
| 2020-07-01 | 2020-06-15 |  | 2020-06-15
| 2020-08-01 | 2020-07-15 |  | 2020-07-15
| 2020-09-01 | 2020-08-14 |  | 2020-08-14
| 2020-10-01 | 2020-09-15 |  | 2020-09-15
| 2020-11-01 | 2020-10-15 |  | 2020-10-15
| 2020-12-01 | 2020-11-13 |  | 2020-11-13
| 2021-01-01 | 2020-12-15 |  | 2020-12-15
| 2021-02-01 | 2021-01-15 |  | 2021-01-15
| 2021-03-01 | 2021-02-15 |  | 2021-02-15
| 2021-04-01 | 2021-03-15 |  | 2021-03-15
| 2021-05-01 | 2021-04-15 |  | 2021-04-15
| 2021-06-01 | 2021-05-14 |  | 2021-05-14
| 2021-07-01 | 2021-06-15 |  | 2021-06-15
| 2021-08-01 | 2021-07-15 |  | 2021-07-15
| 2021-09-01 | 2021-08-13 |  | 2021-08-13
| 2021-10-01 | 2021-09-15 |  | 2021-09-15
| 2021-11-01 | 2021-10-15 |  | 2021-10-15
| 2021-12-01 | 2021-11-15 |  | 2021-11-15
EQC Facilitated Hearing
Formulas:
EQCStaffRptDue = WORKDAY([EQC Meeting]-40,-1,S.DDL_DEQClosed)
EQCMaterialsDue = WORKDAY([EQC Meeting]-9,-1,S.DDL_DEQClosed)

## HearingAndAdDates (hidden)
Caption |  |  |  | 2015-01-05
Hearings
|  |  | Hearings Officer | Notes
City | Date | Time
Portland | 2015-07-16 | 6 p.m. | 6 p.m.
-blank - | -blank - | -blank - | -blank -
-blank - | -blank - | -blank - | -blank -
-blank - | -blank - | -blank - | -blank -
-blank - | -blank - | -blank - | -blank -
-blank - | -blank - | -blank - | -blank -
-blank - | -blank - | -blank - | -blank -
-blank - | -blank - | -blank - | -blank -
Newspaper Advertisements
NOTICE.AD1Oregonian | 2015-06-16
NOTICE.AD2None | 2015-06-16
NOTICE.AD3None | 2015-06-16
NOTICE.AD4None | 2015-06-16
NOTICE.AD5None | 2015-06-16
NOTICE.AD6None | 2015-06-16
NOTICE.AD7None | 2015-06-16
NOTICE.AD8None | 2015-06-16

## Documentation
|  |  | Template last updated |  | 2014-11-28
|  |  | Last cell on work area of ScheduleOfTasks |  | $H$861
Calculations
All ScheduleOfTasks calculations start off the main work area and start at column $AB. Column $AC calculations set the scope of the rulemaking described under Rulemaking Scope below. The main worksheet calculation start in column $AG, have a goldenrod background and are hidden in normal worksheet operations. The calculations for: |  |  | Column calculations
Column $B are in column $AB |  |  | SAMPLE =IF(S.General.RuleType="P","PERMANENT Rulemaking ","TEMPORARY Rulemaking")
text to describe task |  |  | SAMPLE =S.Staff.Subject.Expert.FirstName&" leads rule writing on SharePoint PROPOSED.RULES to:"
See names section below
Column $C are in column $AC | Y |  | SAMPLE =IF(S.AC.CommitteeInvolved="N",0,1)
sets rulemaking scope |  |  | where "S.AC.CommitteeInvolved" is the Y/N choice for whether DEQ will convene an advisory committee. The "N" or no committee choice would turn all advisory committeee tasks on the worksheet to Grey and the "Y" choice would leave them unchanged.
hyperlinks to useful information | i
Column $D are in column $AD | X |  | no calculation
task completion checkbox
Column $E are in column $AE | 10 |  | limited to several rows under Overview of Key Date. Value selected adjust dates in columns $G and $H
date adjustments
Column $F are in column $AF |  |  | place holder for days elapse - we removed this function because it cluttered the work area
hidden
Column $G are in column $AG |  |  | SAMPLE =IF(S.Hearing.1stInvolve="N",,WORKDAY(S.Notice.SubmitToSOS,1,S.DDL_DEQClosed))
task start date |  |  | where the choice "N" set in column C triggers results in no date and "Y" triggers the WORKDAY calculation to determine whether DEQ is open 1 day after submitting notice to Secretary of State
Column $H are in column $AH |  |  | SAMPLE =VLOOKUP(S.EQC.Meeting,S.VL_EQCActivities,2,FALSE)
task end date |  |  | where the calculation looks up the date the Staff Report is due to EQC Assitant in the EQC meeting table
Restore default values
To restore a cell's default value, place the cursor in that cell and enter the calculation "=A" followed by the current cell number.
Working with conditional formats
When working with Styles ¦ Conditional Formating select: * Manage Rules * Show formating rules for This Worksheet
CAUTION when applying conditional formats:
* Place cursor in first cell to be formatted
* Inserting or deleting rows, causes multiple instances of the calculation that could cause the worksheet to become sluggish. Try to keep just one instance of a calculation.
|  |  | Applies to | Format | Calculation
Rulemaking Scope
Y/N choices made in column C throughout the ScheduleOfTasks worksheet will turn rows related to that choice ON (Teal, 1) or OFF (Grey, 0). For example, if you select 'N" for Advisory Committee in cell C12, all Advisory Committee tasks will fade to grey. The calculation for turning rows on or off is in column $AC. |  | $C | ScheduleOfTasks tab |  | =IF(S.AC.CommitteeInvolved="N",0,1)
|  | Y | Cursor placement - $B6 | Teal on white | 1
|  |  | Apply to $B6:$H$861 | Grey on white | 0
$AC
1
Office Closure
If you enter a date that falls on a DEQ office closure date, the cell warns you by turning the cell red with white font. The calculation uses the WORKDAY function to exclude office closure dates where the [holidays] argument is S.DDL_DEQClosed table developed on the Lists.TableLookups tab. |  |  | ScheduleOf Tasks tab
|  |  | Cursor placement - $G6 | White on red | =IF(WORKDAY($G6,1,S.DDL_DEQClosed)<>$G6,TRUE) | #NAME?
Apply to $G6:$G$861
|  |  | Cursor placement - $H12 | White on red | =IF(WORKDAY($H12-1,1,S.DDL_DEQClosed)<>$H12,TRUE)
Apply to $H12:$H$861
Error messages |  |  |  | Red on white
The Overview of Key dates section will display a message when you need to correct a key date. |  |  | $B$18:$H$49,$C$56 |  | =IF($AC18=2,TRUE)
|  |  | $B$30,$B$32 |  | =IF(AND(S.General.RuleType="P",S.Notice.HearingInvolved="Y",S.Notice.Involved="N"),TRUE,FALSE)
|  |  | $B$19 |  | =IF(ISERROR($H$19)=TRUE,TRUE,)
|  |  | $B$32 |  | =IF($AJ$32=1,TRUE)
Names used in workbook
See the names in this workbook by opening the Name Manager dialog box, on the Formulas tab, in the Defined Names group then click Name Manager.
|  |  | Banner date parameters |  | Lookups - Lists and Tables
All names in this workbook start with "S." to identify the name as a ScheduleOfTask name while all CONSIDERATION names start with "C." and RESOURCES names start with "R." A future plan is tolink the workbooks and this convention would prevent naming conflicts. |  |  | Planning

## CodeName.Calendar (hidden)
Caption |  |  |  | CodeName
starting |  |  |  | 2015-01-05 | [6 empty] | 2015-01-12 | [6 empty] | 2015-01-19 | [6 empty] | 2015-01-26 | [6 empty] | 2015-02-02 | [6 empty] | 2015-02-09 | [6 empty] | 2015-02-16 | [6 empty] | 2015-02-23
2015-01-05 |  |  |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Adjust start date +/- from today |  |  | 0 | 2015-01-05 | 2015-01-06 | 2015-01-07 | 2015-01-08 | 2015-01-09 | 2015-01-10 | 2015-01-11 | 2015-01-12 | 2015-01-13 | 2015-01-14 | 2015-01-15 | 2015-01-16 | 2015-01-17 | 2015-01-18 | 2015-01-19 | 2015-01-20 | 2015-01-21 | 2015-01-22 | 2015-01-23 | 2015-01-24 | 2015-01-25 | 2015-01-26 | 2015-01-27 | 2015-01-28 | 2015-01-29 | 2015-01-30 | 2015-01-31 | 2015-02-01 | 2015-02-02 | 2015-02-03 | 2015-02-04 | 2015-02-05 | 2015-02-06 | 2015-02-07 | 2015-02-08 | 2015-02-09 | 2015-02-10 | 2015-02-11 | 2015-02-12 | 2015-02-13 | 2015-02-14 | 2015-02-15 | 2015-02-16 | 2015-02-17 | 2015-02-18 | 2015-02-19 | 2015-02-20 | 2015-02-21 | 2015-02-22 | 2015-02-23 | 2015-02-24 | 2015-02-25 | 2015-02-26 | 2015-02-27 | 2015-02-28 | 2015-03-01
| Start | End
Add to DEQ Rulemaking Plan |  |  | 0: 0
Establish Q-time numbers | #NAME? | 2015-01-05 | 0: 0
Setup shared sites | 2015-01-05 | 2015-01-05 | 0: 0
Kickoff worksession | 2015-01-05 | 2015-01-05 | 0: 0
Planning Sequence |  |  | 0: 0
Draft workbooks | 2015-01-05 | 2015-01-05 | 0: 0
Communications Meeting | 2015-01-05 | 2015-01-05 | 0: 0
Rules Sequence | 2015-01-05 | 0 | bar: 0
@ Start | #REF! | #REF! | 0: #REF!
@ Notice | 0 | 0 | bar: 0
@ EQC Preparation | 0 | 0 | bar: 0
@ Filing | 0 | 0 | bar: 0
SIP Sequence | bar: 0
@ Notice EPA/SIP 180 days | 2014-12-16 | 2014-12-16 | bar: 0
@ Notice: EPA/SIP 45 days | #NAME? | #NAME? | 0: #NAME?
@ Post EQC: Submit to EPA | 2016-02-16 | 2016-02-16 | 0: 0
Fee Sequence |  |  | 0: 0
@ Fee Approval: Part 1 to DAS | 0 | 0 | bar: 0
@ Post EQC: Part 2 to DAS | 2015-12-21 | 2015-12-21 | 0: 0
@ Notice Email DAS for exempt fees | 0 | 0 | bar: 0
Advisory Committee Sequence |  |  | 0: 0
Invitation | 0 | 0 | bar: 0
Meeting 1 | 1900-01-15 | 1900-01-15 | bar: 0
Meeting 2 | 1900-01-15 | 1900-01-15 | bar: 0
Meeting 3 | 1900-01-15 | 1900-01-15 | bar: 0
Meeting 4 | 1900-01-15 | 1900-01-15 | bar: 0
Meeting 5 | 1900-01-15 | 1900-01-15 | bar: 0
Involve EQC Sequence |  |  | 0: 0
Directors Report 1 | 0 | 0 | bar: 0
Directors Report 2 | 0 | 0 | bar: 0
Info Item 1 | 0 | 0 | bar: 0
Info Item 2 | 0 | 0 | bar: 0
Notice Sequence |  |  | 0: 0
EPA/SIP 180 days | 2014-12-16 | 2014-12-16 | bar: 0
EPA/SIP 45 days | #NAME? | #NAME? | 0: #NAME?
Involve DEQ RESOURCES | #NAME? | #NAME? | 0: #NAME?
Send Ad to contract services | 2015-07-06 | 2015-07-06 | 0: 0
Manager approval | #NAME? | #NAME? | 0: #NAME?
Open/Close Comment | 2015-06-16 | 2015-07-20 | 0: 0
DA briefing schedule/meeting | 2015-05-26 | 2015-05-26 | 0: 0
Email DAS for exempt fees | 0 | 0 | bar: 0
Preview period | 2015-06-01 | 2015-06-10 | 0: 0
SOS Bulletin submit/publish | 2015-06-15 | 2015-07-01 | 0: 0
Hearing: first/last | 2015-07-16 | 2015-07-16 | 0: 0
EQC Preparation Sequence |  |  | 0: 0
EQC Meeting | 2015-12-16 | 2015-12-16 | 0: 0
Post EQC Sequence |  |  | 0: 0
Filing/effective | 2015-12-18 | 2015-12-18 | 0: 0
Part 2 to DAS | 2015-12-21 | 2015-12-21 | 0: 0
Submit to EPA | 2016-02-16 | 2016-02-16 | 0: 0
1
1

## ActivitySequence (hidden)
INTERIM RULEMAKING PARTNERSHIP AGREEMENT
Caption
Code: CodeName
Description
Enter short description from CONSIDERATIONS
Objectives
Enter objectives from CONSIDERATIONS
Assumptions and Contraints
Enter assumption and contraints identified in CONSIDERATIONS
Managing Partners
Changes to this agreement require the approval and signature of both Partners. A change in scope and missed deadlines may result in re-prioritizing this rulemaking.
| Sponsoring Partner | , :
| Subject Expert | , :
| Rules Group Partner | , :
Deliverables
Activity Sequence – Add to DEQ Rulemaking Plan
Deadline | Responsibility for Meeting Deadline | Deliverable | Purpose | Recipiant | Done
2015-01-05 | Rules Group Partner: | Shared drive Draft workbooks | Worksession |  | N
2015-01-05 | Sponsoring Partner: | Draft workbooks CONSIDERATIONS RESOURCES | Input | and RGLead | N
2015-01-05 | Sponsoring Partner's Manager: MediaLead | Draft workbooks with edits CONSIDERATIONS RESOURCES | Input | ProgMgr and RGLead | N
| Rules Group Partner: RGLead | Updated Rulemaking Projects Priorities list | Determine capacity Prioritize rulemakings Validate with ProgMgr | Rules Group | N
| Rules Group Partner: RGLead | Proposed addition to DEQ Rulemaking Plan | Approve, postpone, reject | Dick | N
Activity Sequence - Planning for Director-approved rulemaking priorities
Deadline | Resonsibility for Meeting Deadline | Deliverable | Purpose | Recipient | Done
| Sponsoring Partner: ProgMgr | Refine workbooks Considerations Resources Schedule | Input, notification | People identified in RESOURCES workbook | N
| Sponsoring Partner: ProgMgr | Communications Plan | Input, advice | People identified in RESOURCES workbook | N
Activity Sequence - Notice Packet
Invitation to Comment
Notice
Proposed Rules
Supporting Documents
Deadline | Resonsibility for Meeting Deadline | Deliverable | Purpose | Recipient | Done
#NAME? | Sponsoring Partner: ProgMgr | Draft notice & rules | Input, notification | People identified in RESOURCES workbook | N
#NAME? | People identified in RESOURCES workbook | Input | Expand knowledge | ProgMgr | N
| Sponsoring Partner: ProgMgr | Draft notice & rules | Input, advice, review | RGLead | N
| Rules Group Partner: RGLead | Draft notice & rules | Initial review to ensure standardization, organization, preliminary review of fiscal and economic impact statement, small business analysis | ProgMgr | N
| Sponsoring Partner: ProgMgr | Notice Packet | Confirm adequacy of rulemaking materials | RGLead | N
2015-06-01 | Sponsoring Partner: ProgMgr | Notice Packet Preview Email: LT, EQC Assistant, RESOURCES | Inform | MediaLead | N
2015-06-10 | Sponsoring Partner's Manager: MediaLead | Notice Packet | Review and approval | ProgMgr
| Division Administrator DA.Program | Notice Packet with edits; Approval | Approval | ProgMgr
| Sponsoring Partner's Manager: MediaLead | Final Notice Packet | OK to publish | RGLead
| Rules Group Partner: RGLead | Final minor edit | Publication ready | Web staff
| Sponsoring Partner: ProgMgr | Confirm accuracy of published rules | Inform | RGLead
| Sponsoring Partner: ProgMgr | List of hearing participants and their roles; Finalized hearing materials and presentation | Input, advice, review | #NAME?
Activity Sequence – Publication
Deadline | Responsibility for Meeting Deadline | Deliverable | Purpose | Recipient | Done
| Sponsoring Partner: ProgMgr | Approved Newspaper ad(s), Notification lists, Notice content (legislators email, GovDelivery and Interested Parties) | Input, advice, review | RGLead | N
| Rules Group Partner: RGLead | Activate Web page, Online comment form. Submit Newspaper ad, SOS Notice, Notification Lists, DAS | Publication | DAAssistant, Legislative staff and Web staff | N
Activity Sequence – EQC Packet
Staff Report
Proposed Rules
Deadline | Responsibility for Meeting Deadline | Deliverable | Purpose | Recipient | Done
| Sponsoring Partner: ProgMgr | EQC Packet | Input, notification | People identified in RESOURCES workbook | N
| Rules Group Partner: RGLead | EQC Packet | Input, advice, review | ProgMgr | N
| EPA, DOJ | EQC Packet | Review as needed | ProgMgr | N
| Sponsoring Partner: ProgMgr | EQC Packet - finalized | Review and approval | MediaLead | N
| Division Administrator: DA.Program | EQC Packet with edits, Approval | Approval | ProgMgr | N
| Sponsoring Partner: ProgMgr | Final EQC Packet | OK to publish | RGLead | N
| Rules Group Partner: RGLead | Final minor edit | EQC ready | StephanieC | N
Activity Sequence – EQC Presentation
Deadline | Responsibility for Meeting Deadline | Deliverable | Purpose | Send to | Done
| Sponsoring Partner: ProgMgr | List of EQC presenters, their roles and responsibilities; Final EQC Presentation | Input, advice, review | RGLead | N
| Rules Group Partner: RGLead | Presentation with minor edit | EQC ready | StephanieC | N
| Rules Group Partner: RGLead | Update Web page, Online comment form. SOS Filing, DAS, Legislative Counsel | Rules become effective | SOS; Legislative Counsel; DAS | N
Activity Sequence – Rulemaking Record
Deadline | Responsibility for Meeting Deadline | Deliverable | Purpose | Send to | Done
| Sponsoring Partner: ProgMgr | Confirm accuracy of published rules Submit supporting documents for record | Inform | RGLead | N
| Rules Group Partner: RGLead | Archive records; Retire SharePoint; Close Outlook account; Update Web page | Complete rulemaking |  | N
Activity Sequence - Rule Development
Deadline | Resonsibility for Meeting Deadline | Deliverable | Purpose | Send to | Done
Sponsoring Manager
, : DATE
Rules Group Partner
, : DATE