## Schedule summary
Person | Action | Suggested Dates | Amended Dates
Section headings hyperlink to main Schedule worksheet
CodeName: TOXICS2017
Abbreviations
MG | Agency Rules Coordinator
WW | Division Administrator
SC | EQC Coordinator
JI | Program Lead
EH | Rules Group Lead
EH | SIP Coordinator
LF | Unit Manager
SP | SharePoint
Director | DEQ Director
Overview of Key Dates
JI | Notice Packet due to EH and LF for review | 2017-03-03
JI | Notice Packet due to DA and Communications for review | 2017-03-17
EH | File notice with SOS/open comment period | 2017-04-14
EH | Notice Published in Oregon Bulletin (DEQ standard 90 days before EQC) | 5/1/2017
JI | first public hearing - at least 30 days AFTER comment opens; DEQ standard 16 days after Bulletin Notice published | 2017-06-17
EH/JI | close public comment - 3 days after hearing | 2017-06-20
JI | Staff report due to SC | 2017-09-10
| EQC Meeting | 10/15/2017
SIP
EH | Submit SIP development plan to EPA | 0
| Submit draft rules and notice to EPA | 2016-10-18
| Submit adopted rules and SIP info to EPA | 2017-03-02
Fees
JI | Lead development of fee approval packet | 2017-01-16
| Obtain review of fee packet by LF and EH | 2017-01-16
| Finalize fee packet | 2017-03-02
EH | Submit Part I of fee packet to DAS | 2017-03-10
| Submit Part II of fee packet to DAS | 2017-03-17
Initial Work
JI/EH | Advisory Committee - work session (120 days before meeting) | 2016-10-16
LF | approves AC deliverables including AC.ROSTER (97 days before meeting) | 2016-11-15
LF/JI/EH | emails AC.MEMBER.INVITATION with links and instructions (60) days before meeting) | 2016-12-15
JI | Communications Planning: schedules/facilitates meeting with team, Communications, Rules Group to discuss/determine need for: -communications plan; message map; newspaper ads; news release; social media; rulemaking/program web page;informational meetings | 2016-12-15
Pre Notice Tasks
EH/JI | Start rule writing | 2016-12-18
JI | coordinates with Team to:
· determine need for a crosswalk
· identify rules to amend or repeal
· identify new rules to adopt
· identify land use rules
· identify SIP rules, talk with SIP Coordinator
| Public Notice-begin 90 days before filing notice | 2017-01-14
JI | begin drafting rules and notice
JI | asks WW Assistant to schedule future time on DA Schedule for reviewing notice package
JI | schedules time on LF calendar to review Notice Package
EH/JI | send web request to create rulemaking web pages | 2017-04-14
JI | SUBMIT FINAL VERSIONS OF ALL ADVISORY COMMITTEE DOCUMENTS FOR PUBLICATION | 2017-01-23
EH | emails AC.EQC.INVITATION to sign up for Advisory Committee (min. 14 days before meeting) | 2017-01-30
EH | sends AC.AFFECTED.PARTIES.INVITATION to GovDelivery topic (min. 14 days before meeting) | 2017-04-14
JI | Advisory Committee meeting (min. 60 days before filing notice) | 2017-02-13
Fee Approval Packet, with team and BudgetAnalyst
JI/EH | Preplanning for Hearings (90 days before 1st hearing) | 2017-02-17
JI | notify LF documents are ready for review (5 weeks before filing notice) | 2017-03-10
JI | on LF approval, notify WW documents are ready for review (4 weeks before filing notice) | 2017-03-19
JI | on DA approval, notify communications documents are ready for review (3 weeks before filing notice) | 2017-03-24
EH/JI | draft newspaper ads | 2017-03-19
EH | send web request to create rulemaking, comment web pages; and post notice on DEQ public notice page | 2017-03-19
EH | submit newspaper notices to contractor (14 days before filing notice- min. 30 days before hearing) | 2017-04-03
Preview Period
EH | Preview Period: (leadership review) - 5-7 days sends EMAIL.PREVIEW to Director, WW, Leadership Team, Legislature Coordinator, SC -Cc… all contributing and affected staff -saves Email.Preview .pdf to Rule_Development - 2 weeks before filing notice | 2017-03-31
Notice Period
JI | COMPLETE FINAL REVIEW OF ALL DOCUMENTS FOR PUBLICATION | 2017-04-07
EH | submits notice to SOS for publication in Oregon Bulletin (not later than 15th of the month for publication the following month) | 2017-04-14
JI | Public hearing | 2017-06-17
EH | close public comment | 2017-06-20
EQC Preparation
JI | Completes EQC packet = staff report, draft rules, attachments (EQC-9 weeks) | 2017-08-13
JI | LF completes review (EQC-8 weeks) | 2017-08-20
JI | WW completes review (EQC-7 weeks) | 2017-08-27
JI | Communications completes review (EQC-6 weeks) | 2017-09-03
JI | discusses need for 1¦1 commissioners briefings with LF/WW/SC
JI | COMPLETE FINAL VERSION OF ALL DOCUMENTS | 2017-09-03
JI/EH | submits EQC packet to SC (EQC-5 weeks) | 2017-09-10
JI | EQC meeting | 10/15/2017

## Schedule
Person | Task | Instructions | Suggested Dates | Amended Dates
Air Toxics 2016 Permanent
Instructions
Calculate Dates
-Use drop down arrow to select notice publication date in suggested "Notice Publication Date" (Cell D65) -Use drop down arrow to select EQC date in suggested "EQC Meeting" date (Cell D69) -Worksheet will populate all other dates -Manually fill in desired dates under "Amended Dates"
Expand & Collapse Sections - Find Terms
-Find any term on sheet using control + F (find) -Expand or collapse all sections by clicking on 1 or 2 in small box at the top left of this page -Expand or collapse individual sections by clicking on + or - to the left of column A
Filtering
You can filter this worksheet to display only tasks assigned to a particular person. -Expand all sections by clicking on the 2 inside a small box at the top left of this sheet -Click on the drop down arrow in the bottom right of cell A1 - labeled "Person" -Uncheck "select all" -Check the box next to the term you want to filter for -Click "ok" -To return to full display, click on "Data" in the top ribbon. Then click on "Clear."
Hyperlink Instructions
Hyperlinks in cells look like this:
Links to Task Headings
Overview of Key Dates
Concept Development
SIP
Fees
Start Rulemaking
Communications Planning
Preplanning for Hearings
EQC Facilitated Hearings
Initial Rule Work
Advisory Committee
Advisory Committee Presentation
Keep Management Informed
Public Notice
Rule Publication Work
Preview Period
Notifications
Public Comment and Testimony
Public Comment Closes
EQC Preparation
Post EQC
Document Preparation
Filing
Legislative Counsel Notification
DAS Fee Approval - Part 2
Closing Records and Archival
Abbreviations
MG | Agency Rules Coordinator
DA | Division Administrator
SC | EQC Coordinator
JI | Program Lead
EH | Rules Group Lead
EH | SIP Coordinator
LF | Program Manager
SP | SharePoint
Director | DEQ Director
Background
Permanent | P
Rule proposal | Complex
Advisory Committee | Y - Fiscal
Fees | Y
Fees- DAS approval | Y
SIP | Y/N
EQC before hearing | Y
EQC facilitated hearing | Y
Overview of Key Dates
LF | Get director approval (Jan/May/Sept)
Director | Added to Rulemaking Plan
JI | Advisory committee meeting |  | 2017-02-13
JI | Notice Packet due to EH and LF for review |  | 2017-03-03
JI | Notice Packet due to DA and Communications for review |  | 2017-03-17
EH | File notice with SOS/open comment period (no later than 15th of the month before the month notice will be published) |  | 2017-04-14
EH | NOTICE PUBLISHED in Oregon Bulletin (DEQ standard 90 days before EQC) (Notice always publishes on the 1st of the month) |  | 5/1/2017
JI | first public hearing - at least 30 days AFTER comment opens; DEQ standard 17 days after Oregon Bulletin Notice published |  | 2017-06-17
EH/JI | close public comment (3-10 days )after hearing |  | 2017-06-20
JI | Staff report due to SC (5 weeks before EQC) |  | 2017-09-10
| EQC MEETING |  | 10/15/2017
EH | file rules
Rules become effective | On date filed or later specified date
JI | EQC - Director's Report - information item
Concept Development (time frame optional)
LF | contacts MG about a potential rulemaking
MG | explains "add concept to plan" process
LF | approves completing Resources and Considerations worksheets and Schedule
MG | adds to Rules Idea list/workload spreadsheet
MG | establishes new Rule_Development folder system
MG | adds TEMJIATES to Rulemaking_Develpoment/Current Plan/ 1. planning folder and adapts to concept: CONSIDERATIONS, RESOURCES, SCHEDULE
MG JI | Meets with JI to discuss completing Resources, Considerations, Schedule
JI | With MG help, drafts Resources, Considerations, Schedule using what she or he knows now
LF | shares workbooks and prioritization info with DA
LF | emails DA approval or disapproval to MG, JI
Programs | conduct internal rule prioritization process
MG | Uses Considerations and Resources info to rank rulemaking on WORKLOAD spreadsheet
Rules Group | Meet and prioritize projects; create unitary agency-wide prioritized list
Rules group | resources prioritized projects
MG | Obtains Director approval - adds to Rulemaking Plan | -presents prioritized list (Draft DEQ Rulemaking Plan and place Mat) to Director (3 times/yr.; Feb., May, Sept.) -adds prioritized, Director-approved projects to agency rulemaking Plan -notifies DA, JI, LF, SC of Director's decision -posts DEQ Rulemaking Plan on Rules and Regulations web page and Rulemaking SP page -send draft Leadership team notification email to Director for approval, include: - Web page link - DEQ Rulemaking Plan - CONSIDERATIONS and RESOURCES Summary pages -after director approval, sends informational email to: - Leadership Team -Tribal Liaison (Christine Svetkovich) - all managers who make rules - Communications -EQC coordinator to include in monthly Director's Report -Cc… DA, JI, EH
SIP (optional - some air quality only)
SIP Coord | Submit SIP development Plan to EPA |  | 2016-10-18
SIP Coord | Submit draft rules and notice to EPA |  | 2017-03-02
SIP Coord | Submit adopted rules and SIP info to EPA |  | 2017-10-25
Fees
JI | Leads development of Fee Approval Packet |  | 2017-01-16
JI | Obtains review of fee packet by LF and EH |  | 2017-03-02
JI LF | Finalizes fee packet |  | 2017-03-10
EH | Submits Part I of fee packet to DAS (30 days before filing notice) |  | 2017-03-17
EH | Submits Part II of fee packet to DAS ( not later than 10 days after EQC) |  | 2017-10-20
Start Rulemaking
MG | Set up rulemaking SharePoint and email | Sets up SharePoint and Rulemaking email account -establishes SharePoint site -moves Schedule to SharePoint site -ask helpdesk to create Outlook mailbox for this rulemaking -help JI create Outlook email rules to forward rule-related emails to Outlook inbox -email JI and LF instructions on creating rulemaking Outlook email rules
LF JI EH | decide whether to expand team
LF | Prepares for rulemaking | -getting new team members' manager approval -adding rulemaking to work plans as appropriate -get new, unique Q time number for this rulemaking from ISS fiscal coordinator
JI EH LF | refine & agree on draft schedule
JI | schedules/holds team meeting(s) for consensus on:
MG JI LF | -Discuss if Planning documents fully capture issues: -RESOURCES workbook, identifies rulemaking and implementation need -CONSIDERATIONS workbook, reflects scope of work accurately -SCHEDULE of tasks and deadlines complete, accurate
LF | ensures program staff meets agreed upon dates in SCHEDULE
Communications Planning
JI/EH | If needed, sets up meeting to discuss communications Plan | -schedules/facilitates meeting with team, Communications, Rules Group to discuss/determine need for: -Communications Plan -Social Media -Message Map -Newspaper ads (SIP or local rulemakings only) -Newspaper release -Program web page -Information meetings before hearing | 2016-12-15
EH | verifies Web content meets team expectations
JI EH | Plan newspaper ads if necessary | Publication Planning : -identifies newspaper and publication date -develops an AD.STANDARD for each hearing if required -determines when ADs need to be submitted to contractor
| Preplanning for Hearings (90 days before 1st hearing) |  | 2017-02-17
JI and EH | discuss requirements for hearings
JI | identifies hearing locations, dates and times
Meeting 1 Location, Time
Meeting 2 Location, Time
JI | reserves venues/equipment for hearings
EQC Facilitated Hearings (Optional)
EH and JI LF | discuss need for EQC facilitated hearing
JI | observe EQC quorum notification requirements
JI | identifies EQC facilitated hearing, coordinate with EQC coordinator
| Initial Rule Work (4 mos. Before filing notice) |  | 2016-12-18
JI | Complete first rule tasks | coordinates with Team to: -determine need for a crosswalk -identify rules to amend or repeal -identify new rules to adopt - identify land use rules -identify SIP rules, talk with SIP Coordinator -identify rules that affect other divisions or other rulemakings
EH | Sets up draft rules | -gets SOS approval for new rule numbers -pulls rules to amend or repeal from SOS-Archives -copies subject rules from SOS into template -places draft rules template on SP under topic "Public Notice" -Saves copy of proposed rules in pristine form -performs first plain language and style edits
EH | shares information about rules that may be involved in other rulemakings
JI | Completes initial rule validation and review | leads rule writing on SharePoint to: -consider regulations, policies, programs and systems that may affect subject rules -validate/correct all citations, tables, formulas and document references within rule - validate/correct statutory authorities at bottom of each rule -validate/correct NOTE(s) - validate/correct statutes implemented at bottom of each rule -does not delete or change Hist. or ED.NOTES for any rule - SIP note is at bottom of all SIP rules and it is accurate
Advisory Committee
JI/EH | Advisory Committee work session (120 days before meeting) |  | 2016-10-16
EH | adapts Advisory Committee PowerPoint to rulemaking
EH/JI | Prepare for AC work session | asks team to prepare for work session by reviewing: -advisory committee guidelines -consult with other internal resources as needed (OCE, OPA, Regions, DOJ) -Review legal requirements for AC meetings -review the required Advisory Committee Web pages -optional committee AC.CHARTER -CONSIDERATIONS workbook
JI | Draft documents for AC work session | prepares the following work session items: -add potential committee members to draft AC.ROSTER -draft AC.MEMBER.INVITATION -list potential meeting dates and venues -identify all GovDelivery topics that include affected parties -Discuss need for draft AC.AFFECTED.PARTIES.INVITATION to sign up for GovDelivery notices concerning AC meetings -draft AC.EQC.INVITATION to sign up for GovDelivery notices -(Optional) - draft AC. Charter
EH/JI | facilitates pre-Advisory Committee Planning work session that follows PowerPoint discussion and decision items -advises JI on deliverables
EH/JI | discusses need to engage Communications (Jennifer, Joanie) concerning AC meetings
JI | Obtains management approval for AC deliverables | coordinates with team & LF for agreement on: -AC.WebPage -AC.CHARTER to include AC.ROSTER, meeting dates, venues -AC.MEMBER.INVITATION (includes URL and reminder to Sign-up -GovDelivery which topic subscribers should receive AC.AFFECTED.PARTIES.INVITATION to sign up for GovDelivery -AC.EQC.INVITATION to sign up for GovDelivery notices -meeting dates and venues
LF | approves deliverables including AC.ROSTER (90 days before meeting) |  | 2016-11-15
JI | coordinates with Team to: - finalize AC.ROSTER based on responses -talk with potential committee members to determine interest
EH | Sets up rulemaking web pages | works with WebRep to establish: -Rulemaking Home Page -Advisory Committee page: -Advisory Committee meeting page: -Advisory Committee GovDelivery sign up -Have web team provide preview file (.mht file) of the web page before publishing web page | 2017-01-14
JI |  | DRAFT: (Document templates posted on SharePoint page) -Formal AC documents: -agenda -charter -roster -description of AC member roles -obtains team and LF input on agenda and GovDelivery notice
EH | AC.GovDelivery.NOTICE -submits web request to post to AC Web page at least 2 weeks before meeting
JI | releases unneeded venues
JI | emails AC.MEMBER.INVITATION with links and instructions to AC members (60 days before meeting) |  | 2016-12-15
EH | Sends notices of AC and rulemaking | -sends GovDelivery notice to all possible interested groups, giving notice that rulemaking is starting, and advising interested parties to sign up for GovDelivery assigned to this rulemaking -(optional) sends AC.AFFECTED.PARTIES.INVITATION to GovDelivery topic (min. 14 days before meeting) | 2017-01-30
JI | -drafts optional AC.PRESENTATION -involves stakeholder presenters, if any
JI | DEADLINE TO SUBMIT FINAL VERSION OF ALL AC DOCUMENTS FOR PUBLICATION ON AC WEB SITE (3 weeks before meeting) |  | 2017-01-23
EH | submits Web Request to post presentation materials
JI | -Leads: Advisory Committee meeting (min. 60 days before filing notice) -drafts AC summary |  | 2017-02-13
EH | posts meeting summary and any related documents to ac web page
Public Notice Preparation (not required for temporary rules)
| (begin 90 days before filing notice) |  | 2017-01-14
JI | Begin drafting public notice documents | NOTE - Notice Template is posted on SharePoint site Leads core team in developing Notice Packet that includes: -Codename.RULES.NOTICE (template) -Overview -Statement of Need -Rules affected, authorities, supporting documents -Fee Analysis -Statement of fiscal and economic impact -Federal relationship -Land use -Stakeholder and public involvement -SUPPORTING.DOCS - optional -INVITATION.TO.COMMENT (after Notice approved) -Notify (email) LF and DA to have them save time on their schedules to review documents
Pre-Publication DA Briefing (Optional - for more challenging or controversial rulemakings)
JI | If necessary - brief DA about notice documents | determines with EH and LF whether DA needs pre-publication review briefing - based on complexity and challenges of rulemaking -asks DA Assistant to schedule future time on DA Schedule for briefing meeting (if necessary) with JI, LF and EH -asks DA Assistant to schedule future time on DA Schedule for reviewing notice package -schedules time on LF calendar to review Notice Package -verifies/adjusts previously scheduled briefing & review -keeps LF informed about progress, risks & delays | 2017-02-24
LF | keeps management teams informed about progress
Prepare public notice documents
EH | Remind JI to start finalizing rule documents | Send notice filing email to JI that describes steps necessary to get notice documents ready for publication. | 2017-03-02
JI | Prepare notice documents for management review | -prepares NOTICE, PROPOSED.RULES & optional SUPPORTING.DOCUMENTS -addresses all comments, but does not delete them -ensure track changes is on -accepts and rejects language as team agrees -notify EH documents are ready for review
EH | Review notice documents | -determines whether NOTICE & SUPPORTING DOCUMENTS are ready for Rule Publication -applies Publication Checklist review -determines whether work products meet DEQ formatting and publication standards -leads review to determine fiscal and economic impact analysis sufficiency -notify JI review is complete
JI | Notify LF documents are ready for review (5 weeks before filing notice) |  | 2017-03-12
LF | complete review and notify JI review is complete
LF, JI & EH | -discuss -outstanding work due -need for AAG review -need to adjust schedule -review suggested edits | -addresses outstanding edits and comments -if need is agreed on, asks AAG for legal review -confers with EH and LF for agreement on rule changes -notifies EH and LF when documents ready for preview
JI | Finalize notice documents | -finalizes draft rules by: o addressing and deleting all comments o rejecting all proposed edits that will not be kept in final draft rules o leaving untouched in redline/strikeout all proposed edits that will be kept in the final rules o Review final appearance of rules by changing review status to display “no markup”; after review complete, change display status back to “all markup” -draft rules remain in redline/strikethrough -finalizes Rulemaking Notice by: o turn track changes off o addressing and deleting all comments o rejecting any edits that will not be kept in the final document o accepting all edits that will be kept in the final document o Results in clean copy of Rulemaking Notice with no redline/strikeout o turn track changes on
JI | on LF approval, notify DA documents are ready for review (4 weeks before filing notice) |  | 2017-03-19
DA | completes review and emails approval to JI, LF, EH
JI | On DA approval, notify communications documents are ready for review (3 weeks before filing notice) |  | 2017-03-24
Communications | completes review and emails approval to JI EH (2 weeks before filing notice
JI EH | check documents are ready to publish | Final notice package contains: -Invitation to Comment -Notice of rulemaking and hearing -Two versions of the rules: -Draft rules (redline/strikethrough) -Draft rules (final, clean, all edits accepted, with DRAFT watermark) -Supporting documents
Preview Period (pre-publication leadership team review) (allow 5 days - begins 2 weeks before filing notice)
EH | Prepare documents for LT preview | The preview period is a period that starts two weeks before notice is published and that lasts five days, during which Leadership Team can review and comment on the rulemaking notice package. The preview package consists of: -explanatory email to LT -email includes links to SharePoint documents: -Invitation to Comment -Notice -Draft rules (clean and redline/strikethrough) -Supporting documents
EH | Start preview period | sends EMAIL.PREVIEW to: -Director, DA, Leadership Team, Legislature Coordinator, SC -Cc… all contributing and affected staff | 2017-03-31
JI, EH, LF | address any feedback from preview
EH | verifies PROPOSED.RULES are still based on current compilation
JI | finalizes public documents with LF
LF | emails JI & EH approval to move forward with NOTICE, PROPOSED.RULES & any SUPPORTING.DCUMENTS
EH | drafts INVITATION.TO.COMMENT using information from approved NOTICE
EH | Complete pre-notice release tasks | drafts request for Web Request: -Online public comment form -has notice documents uploaded to rulemaking home page -reviews to see if prior edits included -on rulemaking SharePoint page, publish a major version of each document included in notice package
Open Public Notice and Comment Period
EH JI | If necessary, draft newspaper ads | draft newspaper ads; designate newspapers ADS are not always required. They are only required for SIP rulemakings (40 CFR 51.102) - notice 30 days before hearing - ("notice given to the public by prominent advertisement in the area affected, announcing the dates, times, and Places of such hearings"); or for rules that affect a specified geographical area. | 2017-03-19
JI | DEADLINE TO COMPLETE FINAL REVIEW OF ALL DOCUMENTS BEFORE WEB PUBLICATION |  | 2017-04-07
EH | Prepare newspaper ads and email notice to legislators | -send web request to create rulemaking, comment web pages -has hearing date added to DEQ calendar -drafts EMAIL.NOTICE.TO.KEY.LEGISLATORS -obtains leg. Liaison approval of email notice to legislators -Asks leg. Liaison to identify Ors 183.335(5) key legislators -submits newspaper notices to contractor (14 days before filing notice - min. 30 days before hearing)-verifying accuracy of newspaper ads -validates web page, comment page -submits notice to EPA if required -emails DAS notification of fees that don't require DAS approval -contacts communications to draft news release and social media postings -send web request to post information on DEQ Active Public Notice page: | 2017-04-03
EH | Publish notice and open public comment period | -opens public comment by notifying agency rulemaking list that includes: -checking public comment page opened -check news release and social media postings distributed -GovDelivery -SC -advisory committee -program specific lists -GovDelivery to affected parties (optional) -DEQ communications - social media and news release -Email key legislators -submits notice to SOS for publication in Oregon Bulletin (not later than 15th of the month for publication the following month) | 2017-04-14
Public Comment and Testimony
EH JI | Prepare for hearing | -meets with JI and hearings officer to discuss hearing procedures -If hearing after hours at DEQ HQ, request guard using Guard Request Procedure | 5/1/2017
EH | Send JI email describing next steps | Remind JI of upcoming tasks: -Revise rules to address comments -Respond to comments -Draft staff report -Management review of staff report -submit staff report to SC 5 weeks before EQC meeting | 5/1/2017
JI | Prepare for hearing | -verifies venues and equipment, gathers supplies -modifies message map -develops informational presentation (optional) -obtains LF approval of presentation
LF | reviews/approves optional presentation
Hearings Officers | Prepare for hearing | -reviews responsibilities of hearings officer -develops introductory and logistics script -holds the following hearings (identified under Planning section) with assigned team
JI | Hearing 1 - Location, Time |  | 2017-06-17
JI | Hearing 2 - Location, Time
JI | Complete after-hearing procedures | -Send audio file of hearing to EH -for comments received by mail or at hearings: -date stamps and scans to PDF -adds commenter and comments to comment Excel spreadsheet EH creates -scans mailed comments and envelopes and saves to Rule_Development folder
Public Comment Closes |  |  | 2017-06-20
EH | Close public comment period | -check that comment web page has closed -downloads online public comments to Excel -convert text url's for attachments to live links -turn on word wrap -upload to SharePoint
EQC Preparation
JI | Begin drafting EQC staff report | develops response to comments by: -organizing comments into categories -developing one response to each category of comments -obtains LF and EH review of draft responses -draft EQC staff report -copy and paste applicable sections from Public Notice into staff report -Check to ensure language from Public Notice is still accurate and properly reflects timing of future/past events -edit rules as necessary -ask EH for publication review
JI | complete staff report | Finalizes proofing of EQC Staff report: -staff report -rules -supporting documents -notify EH staff report is ready for review
EH | Review staff report, notify JI when complete | leads initial Rule Publication work that includes: -prepare two versions of rules; redline/strikethrough and clean -review, consolidate, approve or reject all proposed edits -compare Notice with Staff Report for accuracy to check that language correctly reflects timing of future/past events -notify JI review is complete
JI | (EQC -9 weeks) -address reviewer edits and comments -notify LF staff report is ready for review |  | 2017-08-13
LF | completes review and emails approval to JI (EQC-8 weeks) |  | 2017-08-20
JI | on LF approval, notify DA documents are ready for review
DA | completes review and emails approval to JI LF EH (EQC-7 weeks) |  | 2017-08-27
JI | On DA approval, notify communications documents are ready for review
Communications | completes review and emails approval to JI LF EH (EQC-6 weeks) |  | 2017-09-03
JI LF | (optional) discusses need for 1 on 1 commissioners briefings
JI | DEADLINE TO SUBMIT FINAL VERSION OF ALL EQC DOCUMENTS (EQC-6 weeks) |  | 2017-09-03
EH | Distribute EQC staff report and prepare rules for filing | -submits EQC packet to SC (EQC-5 weeks) -retain one copy of rules in redline/strikethrough for filing with legislative counsel -create a clean copy of the rules, with tables, to keep for informational purposes - add a DRAFT watermark -Staff report should have two copies of rules - one showing all markup, one with DRAFT watermark with all changes accepted -remove tables from another copy of the rules, and accept all changes to get a clean copy of the rules to file with secretary of state -create pdf version of tables, one document for each rule that has a table, to submit to secretary of state -complete draft version (do not submit) of secretary of state online filing system using information from staff report and draft rules -on SharePoint, publish a major version of: -rules -staff report -save PDF of published staff report to Rule_Development -upload copy of EQC presentation materials to SharePoint | 2017-09-10
JI | (Optional) Notify interested parties staff report is available | notifies the following according to division's standard practice: -key stakeholders -advisory committee members -commenters -interested parties
JI | EQC Preparation | -develop EQC presentation -conduct dry run EQC presentation (in front of internal audience)
JI | Present rule package at EQC MEETING |  | 10/15/2017
Post EQC
Document Preparation
EH | (only for SIP) coordinates EPA.SIP.SUBMITAL with SIP Coordinator
Filing adopted rules
DEADLINE: No Oregon deadline for filing rules after adoption - check EPA
EH | File adopted rules with Secretary of State | -check information in secretary of state online rule filing form against most recent information in staff report and draft rules -submit/file rules on secretary of state online system -must print out, sign, scan, then upload to SOS filing page, copy of Authorization -rule text uploaded as Word file, and pdf of tables submitted separately -SOS will auto email two documents - Certificate and Authorization, in two separate emails - save the emails and attached documents
Filed Date
Effective Date
Legislative Counsel Notification
EH MG | DEADLINE - LC must receive notification within 10 days after CERTIFICATE date (date rules are filed)
EH MG | DEQ PRACTICE - Put in shuttle on day of SOS filing
MG EH | Submit legislative counsel notification | prepares Legislative Counsel notification: -notification consists of copy of SOS filing Certificate and hard copy printed version of redline/strikethrough rules -prints CERTIFICATE -print redl;ing/strikethrough -self-addressed envelope, send two copies of certificate so LC can date stamp one and return it -write "please date stamp certificate and return." on underside of flap -prepares/scans return receipt shuttle envelope, saves as SHUTTLE.RECEIPT-LC.pdf -sends via shuttle -email DEQ Procurement a scanned image of SHUTTLE.RECEIPT-LC
DAS Fee Approval - Part 2
MG EH | DEADLINE DEQ must send notification or DAS Part 2 within 10 days of EQC action
EH JI | Complete fee paperwork and submit to DAS | -gets signatures on Part 2 of signed DAS Fee Approval -scans/saves as DAS.PART2.pdf -excerpts fee sections from RULES, saves as FEE.RULES-DAS, print -excerpts fee sections from STAFF.REPORT, saves as FEE.REPORT-DAS, print -emails PART2-DAS.pdf to DAS (requests delivery receipt) -get preprinted return receipt shuttle envelope from MG -prepares/scans shuttle envelope, saves as SHUTTLE.RECEIPT-DAS.pdf -sends all fee documents to DAS via shuttle -sends Procurement a scanned image of SHUTTLE.RECEIPT-DAS
EH | Send post-EQC GovDelivery notice about rule adoption | -Template in EQC Preparation folder -EH sends GovDelivery notice to same parties that prior notices for this rulemaking were sent to -This notice states EQC adopted the rules and explains where to find copies of EQC staff report and the adopted rules
Closing Records and archival
MG | Complete post adoption document archiving procedures | -verifies Web page is current and accurate -saves copy of all web pages to Rule_Development/web pages folder -ensures the final version of every document on SharePoint is Major (Published) -leads verification that published rules in Oregon Bulletin are correct -Coordinates SIP submittal with EH -emails optional STAKEHOLDER.NOTIFICATION that links to Web page -coordinates AC.THANK.YOU email or letter that links to Web page -scans physical records and save to Rule_Development -PDF emails in rulemaking Outlook mailbox to Rule_Development folder -ask helpdesk to delete rulemaking Outlook inbox after all emails copied to Development folder
EH | submits SIP to EPA within 60 days AFTER adoption
MG | Wrap up | -asks Web team to move all SharePoint files to Rule_Development/sharepointafterclose folder -asks web team to delete SharePoint page -moves Rule_Development folder to Archives folder -coordinates retiring Q-Time number(s) with Budget Analyst
Formulas:
Suggested Dates = [Suggested Dates, row below]-17
Suggested Dates = [Suggested Dates, row above]+47
LINK
RULEMAKING WEB PAGE PROCEDURES
RULEMAKING WEB PAGE EXAMPLES
PUBLIC NOTICE TEMPLATE EXAMPLE
PREVIEW EMAIL TEMPLATE
EQC STAFF REPORT EXAMPLE
SECRETARY OF STATE ONLINE RULE FILING SITE
HEARING PROCEDURES
RULEMAKING SHAREPOINT HOME PAGE
PLACEMAT
STATE IMPLEMENTATION PLAN
FEE PROCEDURES
DEQ RULEMAKING PLAN
CONSIDERATIONS
RESOURCES
RULEMAKING WORKLOAD
ADVISORY COMMITTEE PROCEDURES
ADVISORY COMMITTEE POWERPOINT
OPENING COMMENT CHECKLIST
HEARING PROCEDURES
LEGISLATIVE COUNSEL NOTICE PROCEDURE
DEQ ACTIVE PUBLIC NOTICES
Notice Filing Email
EQC PREPARATION EMAIL
DOWNLOAD COMMENTS TO EXCEL

## Tasks summary
Person | Action | Suggested Dates ¦ | Amended Dates ¦
Section headings hyperlink to main Schedule worksheet
CodeName (abbreviated name)
Abbreviations
ARC | Agency Rules Coordinator
DA | Division Administrator
EQCC | EQC Coordinator
PL | Program Lead
RGL | Rules Group Lead
SIPC | SIP Coordinator
PMGR | Program Manager
SP | SharePoint
Director | DEQ Director
Overview of Key Dates
PL | Notice Packet due to RGL and PMGR for review | 2017-03-03
PL | Notice Packet due to DA and Communications for review | 2017-03-17
RGL | File notice with SOS/open comment period | 2017-04-14
| Notice Published in Oregon Bulletin (DEQ standard 90 days before EQC) | 5/1/2017
PL | first public hearing - at least 30 days AFTER comment opens; DEQ standard 16 days after Bulletin Notice published | 2017-06-17
RGL/PL | close public comment - 3 days after hearing | 2017-06-20
PL | Staff report due to EQCC | 2017-09-10
| EQC Meeting | 10/15/2017
SIP
SIP Coord | Submit SIP development plan to EPA | 2016-10-18
| Submit draft rules and notice to EPA | 2017-03-02
| Submit adopted rules and SIP info to EPA | 2017-10-25
Fees
PL | Lead development of fee approval packet | 2017-01-16
| Obtain review of fee packet by PMGR and RGL | 2017-03-02
| Finalize fee packet | 2017-03-10
RGL | Submit Part I of fee packet to DAS | 2017-03-17
| Submit Part II of fee packet to DAS | 2017-10-20
Communications Planning
PL | schedules/facilitates meeting with team, Communications, Rules Group to discuss/determine need for: -communications plan -message map -newspaper ads -news release -social media -rulemaking/program web page -informational meetings | 2016-12-15
| Preplanning for Hearings (90 days before 1st hearing) | 2017-02-17
| Initial Rule Work (4 mos. Before filing notice) | 2016-12-18
RGL and PL | discuss requirements for EQC faciliated hearing
PL | coordinates with Team to:
· determine need for a crosswalk
· identify rules to amend or repeal
· identify new rules to adopt
· identify land use rules
· identify SIP rules, talk with SIP Coordinator
Advisory Committee (4 mos. before filing notice)
| Advisory Committee work session (120 days before meeting) | 2016-10-16
PMGR | approves deliverables including AC.ROSTER (97 days before meeting) | 2016-11-15
PMGR, PL, RGL | emails AC.MEMBER.INVITATION with links and instructions (60) days before meeting) | 2016-12-15
PL | SUBMIT FINAL VERSION OF ALL DOCUMENTS FOR PUBLICATION | 2017-01-23
RGL | send web request to create rulemaking, advisory committee web pages | 2017-04-03
| emails AC.EQC.INVITATION to sign up for Advisory Committee (min. 14 days before meeting) | 2017-01-30
RGL | sends AC.AFFECTED.PARTIES.INVITATION to GovDelivery topic (min. 14 days before meeting) | 2017-04-14
| Advisory Committee meeting (min. 60 days before filing notice) | 2017-02-13
| Public Notice - not required for temporary rules (begin 90 days before filing notice) | 2017-01-14
PL | begin drafting rules and notice
asks DA Assistant to schedule future time on DA Schedule for reviewing notice package
schedules time on PMGR calendar to review Notice Package
Rule Publication Work
PL | notify PMGR notice package is ready for review (5 weeks before filing notice) | 2017-03-12
PL | on PMGR approval, forwards notice package to DA for review (4 weeks before filing notice) | 2017-03-19
PL | On DA approval, notify communications notice package is ready for review (3 weeks before filing notice) | 2017-03-24
Preview Period (leadership review) - 5-7 days - 2 weeks before filing notice
RGL | sends EMAIL.PREVIEW to: -Director, DA, Leadership Team, Legislature Coordinator, EQCC -Cc… all contributing and affected staff -saves Email.Preview .pdf to Rule_Development - 4- Notice | 2017-03-31
Notifications
RGL/PL | draft newspaper ads | 2017-03-19
RGL | send web request to create rulemaking, comment web pages; and post on DEQ public notices page | 2017-03-19
RGL | submit newspaper notices to contractor (14 days before filing notice- min. 30 days before hearing) | 2017-04-03
PL | COMPLETE FINAL REVIEW OF ALL DOCUMENTS FOR PUBLICATION | 2017-04-07
RGL | submits notice to SOS for publication in Oregon Bulletin (not later than 15th of the month for publication the following month) | 2017-04-14
Public Comment and Testimony
PL | Public hearing | 2017-06-17
| Public Comment Closes | 2017-06-20
EQC Preparation
PL | Completes EQC package = staff report, draft rules, attachments (EQC-9 weeks) | 2017-08-13
PL | PMGR completes review (EQC-8 weeks) | 2017-08-20
PL | DA completes review (EQC-7 weeks) | 2017-08-27
discusses need for 1¦1 commissioners briefings with PMGR/DA/EQCC
PL | COMPLETES FINAL VERSION OF ALL DOCUMENTS (EQC-6 weeks) | 2017-09-03
PL/RGL | submits EQC packet to EQCC (EQC-5 weeks) | 2017-09-10
PL | EQC meeting | 10/15/2017

## main sharepoint
ID | Title | Location | Start Time | End Time | Description | All Day Event | Recurrence | Workspace | Category | Resources | Free/Busy | Check Double Booking | Comments | URL | Attachments | Attendees
| Air Toxics 2016 Permanent |  | 2016-10-16 | 2016-10-16 | Advisory Committee -work session (120 days before meeting) | TRUE
| Air Toxics 2016 Permanent |  | 2016-11-15 | 2016-11-15 | approves AC deliverables including AC.ROSTER (97 days before meeting) | TRUE
| Air Toxics 2016 Permanent |  | 2016-12-15 | 2016-12-15 | emails AC.MEMBER.INVITATION with links and instructions (60) days before meeting) | TRUE
| Air Toxics 2016 Permanent |  | 2016-12-15 | 2016-12-15 | Communications Planning: schedules/facilitates meeting with team, Communications, Rules Group to discuss/determine need for: -communications plan -message map -newspaper ads -news release -social media -rulemaking/program web page -informational meetings | TRUE
| Air Toxics 2016 Permanent |  | 2016-12-18 | 2016-12-18 | Start rule writing -4 mos. before filing notice discuss requirements for EQC faciliated hearing | TRUE
| Air Toxics 2016 Permanent |  | 2017-03-02 | 2017-03-02 | SIP - submit rule package to EPA (at least 90 days before notice) | TRUE
| Air Toxics 2016 Permanent |  | 2017-01-14 | 2017-01-14 | Public Notice -not required for temporary rules -begin 90 days before filing notice | TRUE
| Air Toxics 2016 Permanent |  | #REF! | #REF! | send web request to create rulemaking, advisory committee web pages | TRUE
| Air Toxics 2016 Permanent |  | 2017-01-30 | 2017-01-30 | emails AC.EQC.INVITATION to sign up for Advisory Committee (min. 14 days before meeting) | TRUE
| Air Toxics 2016 Permanent |  | #REF! | #REF! | sends AC.AFFECTED.PARTIES.INVITATION to GovDelivery topic (min. 14 days before meeting) | TRUE
| xxxx |  | #REF! | #REF! | SUBMIT FINAL VERSIONS OF ALL DOCUMENTS FOR PUBLICATION | TRUE
| Air Toxics 2016 Permanent |  | 2017-02-13 | 2017-02-13 | Advisory Committee meeting (min. 60 days before filing notice) | TRUE
| Air Toxics 2016 Permanent |  | 2017-01-16 | 2017-01-16 | Fees - leads development of: | TRUE
| Air Toxics 2016 Permanent |  | 2017-02-17 | 2017-02-17 | Preplanning for Hearings (90 days before 1st hearing) | TRUE
| Air Toxics 2016 Permanent |  | 2017-03-02 | 2017-03-02 | initiates UMGR Fee Approval Packet review, addresses suggestions | TRUE
| Air Toxics 2016 Permanent |  | #REF! | #REF! | forwards notice package to UMGR for review (6 weeks before filing notice) | TRUE
xxxx
| Air Toxics 2016 Permanent |  | 2017-03-17 | 2017-03-17 | sends EMAIL.DAS.APPROVAL with Fee Approval Packet attached (30 days before filing notice) | TRUE
| Air Toxics 2016 Permanent |  | 2017-03-19 | 2017-03-19 | draft newspaper ads | TRUE
| Air Toxics 2016 Permanent |  | 2017-03-19 | 2017-03-19 | send web request to create rulemaking, comment web pages | TRUE
| Air Toxics 2016 Permanent |  | #REF! | #REF! | submit newspaper notices to contractor (14 days before filing notice- min. 30 days before hearing) | TRUE
| Air Toxics 2016 Permanent |  | 2017-03-31 | 2017-03-31 | Preview Period: (leadership review) - 5-7 days sends EMAIL.PREVIEW to: -Director, DA, Leadership Team, EQCC -Cc… all contributing and affected staff -saves Email.Preview .pdf to Rule_Development - 4- Notice | TRUE
|  |  | 2017-04-07 | 2017-04-07 | COMPLETE FINAL REVIEW OF ALL DOCUMENTS FOR PUBLICATION
| Air Toxics 2016 Permanent |  | 2017-04-14 | 2017-04-14 | submits notice to SOS for publication in Oregon Bulletin (not later than 15th of the month for publication the following month) | TRUE
| Air Toxics 2016 Permanent |  | 5/1/2017 | 5/1/2017 | Notice published in Oregon Bulletin
| Air Toxics 2016 Permanent |  | 2017-06-17 | 2017-06-17 | Public hearing | TRUE
| Air Toxics 2016 Permanent |  | 2017-06-20 | 2017-06-20 | close public comment | TRUE
| Air Toxics 2016 Permanent |  | 2017-08-13 | 2017-08-13 | PL completes staff report = staff report, draft rules, attachments (EQC-9 weeks) | TRUE
| Air Toxics 2016 Permanent |  | 2017-08-20 | 2017-08-20 | UMGR completes review (EQC-8 weeks) | TRUE
| xxxx |  | 2017-08-27 | 2017-08-27 | DA completes review (EQC-7 weeks)
|  |  | 2017-09-03 | 2017-09-03 | Communications completes review (EQC-6 weeks)
|  |  | 2017-09-03 | 2017-09-03 | COMPLETE FINAL VERSION OF ALL DOCUMENTS (EQC-6 weeks)
| Air Toxics 2016 Permanent |  | 2017-09-10 | 2017-09-10 | submits EQC packet to EQCC (EQC-5 weeks) | TRUE
| Air Toxics 2016 Permanent |  | 10/15/2017 | 10/15/2017 | EQC meeting | TRUE
| xxxx |  | 2016-10-18 | 2016-10-18 | Submit SIP development plan to EPA | TRUE
| xxxx |  | 2017-03-02 | 2017-03-02 | Submit draft rules and notice to EPA | TRUE
| xxxx |  | 2017-10-25 |  | Submit adopted rules and SIP docs to EPA | TRUE
| xxxx |  | 2017-01-16 | 2017-01-16 | Lead development of Fee approval packet | TRUE
| xxxx |  | 2017-03-02 | 2017-03-02 | Obtain UMGR and RGL review of fee packet | TRUE
| xxxx |  | 2017-03-10 | 2017-03-10 | Finalize fee packet | TRUE
| xxxx |  | 2017-03-17 | 2017-03-17 | Submit fee packet Part I to DAS | TRUE
| xxxx |  | 2017-10-20 | 2017-10-20 | Submit fee packet Part II to DAS | TRUE

## ind SP
ID | Title | Location | Start Time | End Time | Description | All Day Event | Recurrence | Workspace | Category | Resources | Free/Busy | Check Double Booking | Attachments | Attendees
| SIP - submit SIP development plan to EPA (6 mos. before notice) |  | 2016-10-18 | 2016-10-18 |  | TRUE
| Advisory Committee -work session (120 days before meeting) |  | 2016-10-16 | 2016-10-16 |  | TRUE
| approves AC deliverables including AC.ROSTER (97 days before meeting) |  | 2016-11-15 | 2016-11-15 |  | TRUE
| emails AC.MEMBER.INVITATION with links and instructions (60) days before meeting) |  | 2016-12-15 | 2016-12-15 |  | TRUE
| Communications Planning: schedules/facilitates meeting with team, Communications, Rules Group to discuss/determine need for: -communications plan -message map -newspaper ads -news release -social media -rulemaking/program web page -informational meetings |  | 2016-12-15 | 2016-12-15 |  | TRUE
| Start rule writing -4 mos. before filing notice discuss requirements for EQC faciliated hearing |  | 2016-12-18 | 2016-12-18 |  | TRUE
| SIP - submit rule package to EPA (at least 90 days before notice) |  | 2017-03-02 | 2017-03-02 |  | TRUE
| Public Notice -not required for temporary rules -begin 90 days before filing notice |  | 2017-01-14 | 2017-01-14 |  | TRUE
| SUBMIT FINAL VERSION OF ALL DOCUMENTS FOR PUBLICATION |  | 2017-01-23 | 2017-01-23 |  | TRUE
| send web request to create rulemaking, advisory committee web pages |  | 2017-01-14 | 2017-01-14 |  | TRUE
| emails AC.EQC.INVITATION to sign up for Advisory Committee (min. 14 days before meeting) |  | 2017-01-30 | 2017-01-30 |  | TRUE
| Advisory Committee meeting (min. 60 days before filing notice) |  | 2017-02-13 | 2017-02-13 |  | TRUE
| Fees - leads development of: |  | 2017-01-16 | 2017-01-16 |  | TRUE
| Preplanning for Hearings (90 days before 1st hearing) |  | 2017-02-17 | 2017-02-17 |  | TRUE
| initiates PMGR Fee Approval Packet review, addresses suggestions |  | 2017-03-02 | 2017-03-02 |  | TRUE
| notify PMGR notice package ready f for review (5 weeks before filing notice) |  | 2017-03-12 | 2017-03-12 |  | TRUE
| on PMGR approval, notify DA notice package ready for review (4 weeks before filing notice) |  | 2017-03-19 | 2017-03-19
| on DA approval, notify communications notice package ready for review (3 weeks before filing notice) |  | 2017-03-24 | 2017-03-24
| sends EMAIL.DAS.APPROVAL with Fee Approval Packet attached (30 days before filing notice) |  | 2017-03-17 | 2017-03-17 |  | TRUE
| draft newspaper ads |  | 2017-03-19 | 2017-03-19 |  | TRUE
| send web request to create rulemaking, comment web pages |  | 2017-03-19 | 2017-03-19 |  | TRUE
| submit newspaper notices to contractor (14 days before filing notice- min. 30 days before hearing) |  | 2017-03-19 | 2017-03-19 |  | TRUE
| Preview Period: (leadership review) - 5-7 days sends EMAIL.PREVIEW to: -Director, DA, Leadership Team, EQCC -Cc… all contributing and affected staff -saves Email.Preview .pdf to Rule_Development - 4- Notice |  | 2017-03-31 | 2017-03-31 |  | TRUE
| COMPLETE FINAL REVIEW OF ALL DOCUMENTS FOR PUBLICATION |  | 2017-04-07 | 2017-04-07 |  | TRUE
| submits notice to SOS for publication in Oregon Bulletin (not later than 15th of the month for publication the following month) |  | 2017-04-14 | 2017-04-14 |  | TRUE
| Notice published in Oregon Bulletin |  | 5/1/2017 | 5/1/2017
| Public hearing |  | 2017-06-17 | 2017-06-17 |  | TRUE
| close public comment |  | 2017-06-20 | 2017-06-20 |  | TRUE
| PL completes staff report = staff report, draft rules, attachments (EQC-9 weeks) |  | 2017-08-13 | 2017-08-13 |  | TRUE
| pmgr completes review (EQC-8 weeks) |  | 2017-08-20 | 2017-08-20 |  | TRUE
| DA completes review (EQC-7 weeks) |  | 2017-08-27 | 2017-08-27
| Communications completes review (EQC-6 weeks) |  | 2017-09-03 | 2017-09-03
| COMPLETE FINAL REVIEW OF ALL DOCUMENTS (EQC-6 weeks) |  | 2017-09-03 | 2017-09-03 |  | TRUE
| submits EQC packet to EQCC (EQC-5 weeks) |  | 2017-09-10 | 2017-09-10 |  | TRUE
| EQC meeting |  | 10/15/2017 | 10/15/2017 |  | TRUE
| Submit SIP development plan to EPA |  | 2016-10-18 | 2016-10-18 |  | TRUE
| Submit draft rules and notice to Epa |  | 2017-03-02 | 2017-03-02 |  | TRUE
| Submit adopted rules and SIP docs to EPA |  | 2017-10-25 | 2017-10-25 |  | TRUE
| Lead development of fee approval packet |  | 2017-01-16 | 2017-01-16 |  | TRUE
| Obtain review of pmgr and RGL review of fee packet |  | 2017-03-02 | 2017-03-02 |  | TRUE
| Finalize fee packet |  | 2017-03-10 | 2017-03-10 |  | TRUE
| Submit fee Packet Part I to DAS |  | 2017-03-17 | 2017-03-17 |  | TRUE
| Submit fee packet part II to DAS |  | 2017-10-20 | 2017-10-20 |  | TRUE