## Schedule
Person | Action | Suggested Dates |  | Amended Dates
| Title V CPI 2016 | Start | End | Start | End
Instructions
Enter notice publication date under Suggested "Notice Published" Date
Enter EQC date under Suggested "EQC Meeting" Date
*Worksheet will populate dates under "Suggested Start Dates" *If desired, manually fill in dates in "End" column *Manually fill in desired dates under "Amended Dates" *Find any term on sheet using control + F (find) *"Summary" tab is overview of critical tasks and dates
Links to Task Headings
Overview of Key Dates
Concept Development
| Start Rulemaking |  |  | 2016-10-15 | 2016-10-15
| SIP |  |  | N/A | N/A
| Communications Planning |  |  | 10/15/2016 - 10/22/2016 | 10/15/2016 - 10/20/2016
| Preplanning for Hearings |  |  | 10/22/2016 - 10/29/2016 | 10/20/2016 - 10/22/2016
| EQC Facilitated Hearings |  |  | N/A | N/A
| Initial Rule Work |  |  | 10/29/2016 - 12/30/2016 | 10/22/2016 - 12/3/2015
| Advisory Committee |  |  | N/A | N/A
| Fees |  |  | 2016-01-14 | 2015-12-15
| Public Notice |  |  | 2016-01-14 | 2015-12-15
| Rule Publication Work |  |  | 1/11/2016 -1/14/2016 | 12/10/2015 -12/14/2015
| Preview Period |  |  | 1/4/2016 - 1/11/2016 | 12/3/2015 - 12/9/2015
| Notifications |  |  | 2016-01-14 | 2015-12-15
| Public Comment and Testimony |  |  | 2016-02-18 | 2016-01-18
| Public Comment Closes |  |  | 2016-02-22 | 2016-01-21
| EQC Preparation |  |  | 2/22/2016 - 5/6/2016 | 1/21/2016 - 5/6/2016
| Tentative EQC Meeting |  |  | 2016-06-10 | 2016-06-10
Abbreviations
ARC | Agency Rules Coordinator
DA | Division Administrator
EQCC | EQC Coordinator
PL | Program Lead
RGL | Rules Group Lead
SIPC | SIP Coordinator
UMGR | Unit Manager
SP | SharePoint
Director | DEQ Director
Background
Temporary or Permanent | T/P | P
Rule proposal complexity | Simple/Average/Complex | S
Advisory Committee | Y/N
Fees | Y/N | Y
Fees- DAS approval required | Y/N | N
SIP | Y/N | N
EQC involvement before hearing | Y/N | N
EQC faciliated hearing? | Y/N | N
Overview of Key Dates
Director | Added to Rulemaking Plan |  |  | 2015-09-14 | 2015-09-14
` | Notice Packet due to RGL and UMGR for review
PL | Notice Packet due to DA and Communications for review
RGL | File notice with SOS/open comment period |  |  | 2016-01-14 | 2016-12-15
| Notice Published in Oregon Bulletin (DEQ standard 90 days before EQC) |  |  | 2016-02-01 | 2016-01-01
PL | first public hearing - at least 30 days AFTER comment opens; DEQ standard 17 days after Bulletin Notice published |  |  | 2016-02-18 | 2016-01-18
RGL/PL | close public comment - 3 days after hearing |  |  | 2016-02-21 | 2016-01-21
PL | Staff report due to EQCC (5 weeks before EQC) |  |  | 2016-05-06 | 2016-05-06
| EQC Meeting |  |  | 2016-06-10 | 2016-06-10
RGL | file rules |  |  | 2016-06-14 | 2016-06-14
Rules become effective | On date filed or later specified date |  |  | 2016-06-14 | 2016-06-14
Director's report | Director's Report
Information item | Information Item
Rulemaking Process
Concept Development
UMGR | contacts ARC about a potential rulemaking |  |  | 2015-08-25 | 2015-08-25
ARC | explains add concept to plan process |  |  | 2015-08-25 | 2015-08-25
Unit manager | approves completing Resources and Considerations worksheets |  |  | 2015-08-25 | 2015-08-25
ARC | adds to Rules Idea list/workload spreadsheet |  |  | 2015-08-25 | 2015-08-25
| establishes new Rule_Development folder system |  |  | 2015-08-25 | 2015-08-25
| adds TEMPLATES to 1. Planning folder and adapts to concept: CONSIDERATIONS, RESOURCES, SCHEDULE |  |  | 2015-08-25 | 2015-08-25
| Meets with PL to discuss completing workbooks |  |  | 2015-08-25 | 2015-08-25
PL | With ARC help, drafts workbooks using what she or he knows now |  |  | 2015-09-02 | 2015-09-02
PL and UMGR | Calculate rule priority based on DRIVERS and RISKS tables from Rulemaking SP page |  |  | 2015-09-02 | 2015-09-02
UMGR | shares workbooks and prioritization info with DA |  |  | 2015-09-07 | 2015-09-07
UMGR | emails DA approval or disapproval to ARC, UMGR, PL |  |  | 2015-09-09 | 2015-09-09
Units | conduct internal rule prioritization process |  |  | 2015-09-15 | 2015-09-15
ARC | Uses WORKBOOKS, DRIVERS and RISKS info to rank rulemaking on WORKLOAD spreadsheet |  |  | 2015-09-15 | 2015-09-15
Rules Group | Meet and prioritize projects; create unitary agency-wide prioritized list |  |  | 2015-09-15 | 2015-09-15
Rules group | resources prioritized projects |  |  | 2015-09-15 | 2015-09-15
ARC | presents prioritized list to Director (3 times/yr.; Jan., May, Sept.) |  |  | 2015-09-16 | 2015-09-16
ARC | adds prioritized, Director-aproved projects to agency rulemaking plan |  |  | 2015-09-16 | 2015-09-16
ARC | notifies DA, PL, UMGR of Director's decision |  |  | 2015-09-22 | 2015-09-22
| posts DEQ Rulemaking Plan on Rules and Regulations web page and Rulemaking SP page |  |  | 2015-09-22 | 2015-09-22
| send draft notification email to Director for approval, include: - Web page link - DEQ Rulemaking Plan - CONSIDERATIONS and RESOURCES Summary pages |  |  | 2015-09-22 | 2015-09-22
| after director approval, sends informational email to: - Leadership Team - all managers who make rules - Communications -EQC coordinator to include in monthly Director's Report -Cc… DA, PL, RGL |  |  | 2015-09-22 | 2015-09-22
SIP
SIP Coord | Submit SIP development plan to EPA
Submit draft rules and notice to EPA
Submit adopted rules and SIP info to EPA
Fees
PL | Leads development of Fee Approval Packet |  |  | 2015-10-19
| Obtains review of fee packet by UMGR and RGL |  |  | 2015-12-03
| Finalizes fee packet |  |  | 2015-12-11
RGL | Submits Part I of fee packet to DAS |  |  | 2015-12-18
RGL | Submits Part II of fee packet to DAS ( not later than 10 days after EQC) |  |  | 2016-06-15
Start Rulemaking
ARC:
| saves email Rule_Development ¦ 1-Planning ¦ APPROVAL.ToMoveForward |  |  | 2015-09-22 | 2015-09-22
| establishes SharePoint sub-site -simple email to web support (Michele T. - 4.2015) |  |  | 2015-09-22 | 2015-09-22
| moves SCHEDULE from Rule_Development into SharePoint |  |  | 2015-09-22 | 2015-09-22
| moves other workbooks from Rule_Development into SharePoint |  |  | 2015-09-22 | 2015-09-22
DA, UMGR, PL & RGL | decide whether to expand team |  |  | 2015-09-22 | 2015-09-22
UMGR | is responsible for:
· getting new team members' manager approval
· adding rulemaking to work plans as appropriate
ARC | gets Qtime number from ISS Fiscal Coordinator (Robert Beall 12.14) |  |  | 2015-10-01 | 2015-10-01
RGL | drafts SCHEDULE and SUMMARY |  |  | 2015-10-13 | 2015-10-13
PL & RGL | refine & agree on draft schedule |  |  | 2015-10-14 | 2015-10-14
PL | schedules/holds team meeting(s) for consensus on: |  |  | 2015-10-21 | 10/21/2015 -
| · RESOURCES workbook, identifies rulemaking and implementation need |  |  | 2015-10-21 | 2015-10-21
| · CONSIDERATIONS workbook, reflects scope of work accurately |  |  | 2015-10-21 | 2015-10-21
| · CONSIDERATIONS workbook identifies potential risks accurately |  |  | 2015-10-21 | 2015-10-21
| · SCHEDULE of tasks and deadlines |  |  | 2015-10-21 | 2015-10-21
UMGR | ensures program staff meets agreed upon dates in SCHEDULE
Communications Planning
PL | schedules/facilitates meeting with team, Communications, Rules Group to discuss/determine need for: |  |  | 2015-10-21 | 2015-10-21
| · Communications Plan |  |  | 2015-10-21 | 2015-10-21
| · Social Media |  |  | 2015-10-21 | 2015-10-21
| · Message Map |  |  | 2015-10-21 | 2015-10-21
| · Newspaper advertisements (SIP or local rulemaking only) |  |  | 2015-10-21 | 2015-10-21
| · Newspaper release |  |  | 2015-10-21 | 2015-10-21
| · Program Web page |  |  | 2015-10-21 | 2015-10-21
| · Information Meetings before hearing |  |  | 2015-10-21 | 2015-10-21
RGL
verifies Web content meets team expectations
works with WebRep to make adjustments
PL/RGL | Publication Table:
· identifies newspaper and publication date
· develops an AD.STANDARD for each hearing if required
· develops AD.LEGAL for each hearing if required
· saves as NOTICE.AD.Hearing1, etc. on Rule_Development folder
· determines when ADs need to be submitted to contractor
· shares contents of HearingAndAdDates TAB with UMGR
· obtains UMGR email approval
| Preplanning for Hearings (90 days before 1st hearing) | 2015-11-20
PL and RGL | discuss requirements for hearings |  |  | 2015-10-20 | 2015-10-20
PL | identifies hearing locations, dates and times |  |  | 2015-10-20 | 2015-10-20
| Meeting 1 Location, Time |  |  | 2015-10-20 | 2015-10-20
| Meeting 2 Location, Time |  |  | 2015-10-20 | 2015-10-20
PL | reserves venues/equipment for hearings |  |  | 2015-10-20 | 2015-10-20
EQC Facilitated Hearings
RGL and PL | discuss requirements for EQC faciliated hearing |  |  | N/A
PL | observe EQC quorum notification requirements (ORS 192.630) |  |  | N/A
| identifies EQC facilitated hearing, coordinate with commissioner |  |  | N/A
| gathers all planning emails for the Rule Record and saves PDF to Rule_Development:¦1-Planning¦EMAILS.Planning.pdf |  |  | N/A
| Initial Rule Work (4 mos. Before filing notice) | 2015-09-20
DO NOT TURN OFF TRACK CHANGES IN CODENAME.RULES
PL | coordinates with Team to: |  |  | 2015-10-21 | 2015-10-21
| · determine need for a crosswalk |  |  | N/A | N/A
| · identify rules to amend or repeal |  |  | 2015-10-21 | 2015-10-21
| · identify new rules to adopt |  |  | N/A | N/A
| · identify land use rules |  |  | 2015-10-21 | 2015-10-21
| · identify SIP rules, talk with SIP Coordinator |  |  | N/A | N/A
RGL | pulls rules to amend or repeal from SOS-Archives |  |  | 2015-10-21 | 2015-10-21
| determines availability of any new (adopted) rule or division |  |  | 2015-10-21 | 2015-10-21
| adds PROPOSED.RULES.Pristine template to Rule_Development |  |  | 2015-10-21 | 2015-10-21
| copies subject rules from SOS into template |  |  | 2015-10-21 | 2015-10-21
| saves PROPOSED.RULES.Pristine |  |  | 2015-10-21 | 2015-10-21
| uploads a copy to SharePoint under Topic: Public Notice |  |  | 2015-10-21 | 2015-10-21
| protects PROPOSED.RULES.Pristine on Rule_Development |  |  | 2015-10-21 | 2015-10-21
| obtains, verifies, provides previously unused rule numbers |  |  | N/A | N/A
| shares information about rules that may be involved in other rulemakings |  |  | 2015-10-21 | 2015-10-21
| performs 1st plain language, style guide edits on SharePoint |  |  | 2015-10-21 | 2015-10-21
| offers organizational comments and examples |  |  | 2015-10-21 | 2015-10-21
PL | leads rule writing on SharePoint CodeName.RULES to: |  |  | 2015-10-21 | 2015-10-21
| · consider regulations, policies, programs and systems that may affect subject rules |  |  | 2015-10-21 | 2015-10-21
| · validate/correct all citations, tables, formulas and document references within rule |  |  | 2015-10-21 | 2015-10-21
| · validate/correct statutory authorities at bottom of each rule |  |  | 2015-10-21 | 2015-10-21
| · validate/correct statutes implemented at bottom of each rule |  |  | 2015-10-21 | 2015-10-21
| · validate/correct NOTE(s) |  |  | 2015-10-21 | 2015-10-21
| · does not delete or change Hist. or ED.NOTES for any rule |  |  | 2015-10-21 | 2015-10-21
| · SIP note is at bottom of all SIP rules and it is accurate |  |  | N/A | N/A
All drafters and reviewers | work on SharePoint Codename.RULES |  |  | 2015-10-21 | 2015-10-21
PL | before submitting Notice Packet and EQC Packet: |  |  | 2015-10-21 | 2015-10-21
| · verifies each rule in Codename.RULES is current with SOS compilation |  |  | 2015-10-21 | 2015-10-21
| · verifies no rule adoptions could affect Codename.RULES |  |  | 2015-10-21 | 2015-10-21
Advisory Committee
SAVE DOCUMENTS ON: | SharePoint Topic: Public Notice
DEADLINE: | Notice committee meetings 2 weeks before meeting
RGL
| Advisory Committee work session (120 days before meeting) | N/A
adapts Advisory Committee PowerPoint to rulemaking
asks team to prepare for work session by reviewing:
· advisory committee guidelines
· Public Involvement Resources
· EQC quorum notification requirements (ORS 192.630)
· examples of the required Advisory Committee Web pages
· optional committee AC.CHARTER
· CONSIDERATIONS workbook in SharePoint Topic: Planning
asks PL to prepare the following work session items:
· add potential committee members to draft AC.ROSTER
· list potential meeting dates and venues
· draft AC.MEMBER.INVITATION
· identify all GovDelivery topics that include affected parties
· draft AC.AFFECTED.PARTIES.INVITATION to sign up for GovDelivery notices
· draft AC.EQC.INVITATION to sign up for GovDelivery notices
· draft AC.WebPage
facilitates Advisory Committee work session that follows PowerPoint discussion and decision items
discusses need to engage Communications (BrianW, Jennifer F.)
decides whether to use optional AC.CHARTER Y/N
advises PL on deliverables
PL | coordinates with team & UMGR for agreement on:
· AC.WebPage
· AC.CHARTER to include AC.ROSTER, meeting dates, venues
· AC.MEMBER.INVITATION (includes URL and reminder to Sign-up
· GovDelivery topic subscribers to get AC.AFFECTED.PARTIES.IN
· AC.AFFECTED.PARTIES.INVITATION to sign up for GovDelivery
· AC.EQC.INVITATION to sign up for GovDelivery notices
· meeting dates and venues
UMGR and PL | share Advisory Committee deliverables and decisions with DA
team addresses any concerns and validates accuracy of how addressed
UMGR | approves deliverables including AC.ROSTER (90 days before meeting) | 2015-08-18
PL | coordinates with team to:
· talk with potential committee members to determine interest
· finalize AC.ROSTER based on responses
RGL | works with WebRep to establish: | 2015-10-17
Advisory Committee page: http://www.oregon.gov/deq/RulesandRegulations/Pages/Advisory/A
Advisory Committee meeting page: http://www.oregon.gov/deq/RulesandRegulations/Pages/Advisory/A
Advisory Committee GovDelivery sign up
Have web team provide preview file (.mht file) before publishing web page
PL | identifies meeting roles
coordinates or leads drafting:
AC.AGENDA
AC.GovDelivery.NOTICE
AC.WebRequest.ATTACHMENT
obtains team and UMGR input on agenda and GovDelivery notice
RGL | submits Web Request 2 weeks before meeting using AC.WebRequest | 2015-11-02
sends AC.GovDelivery.NOTICE to committee Web page
PL | releases unneeded venues
UMGR, PL, RGL | emails AC.MEMBER.INVITATION with links and instructions (60) days before meeting) to AC members | 2015-09-17
| emails AC.EQC.INVITATION to sign up for Advisory Committee (min. 14 days before meeting) | 2015-11-02
RGL | sends AC.AFFECTED.PARTIES.INVITATION to GovDelivery topic (min. 14 days before meeting) | 2015-11-02
submits Web Request when Advisory Committee Web page needs updating
PL | maintains Advisory Committee record
Advisory Committee Presentation
PL | drafts optional AC.PRESENTATION
involves stakeholder presenters, if any
Team | approves presentation materials
RGL | submits Web Request to post presentation materials
PL | SUBMIT FINAL VERSION OF ALL DOCUMENTS FOR PUBLICATION | 2015-10-26
Team practices presentation
PL | facilitates, leads or supports:
| Advisory Committee meeting (min. 60 days before filing notice) | 2015-11-16
drafting of AC.MINUTES
team | debrief meeting
PL | gathers all advisory committee emails for the Rule Record - in Rule_Development¦3-FeesApproval¦EMAILS.Fees.pdf
Public Notice not required for temporary rules
| (begin 90 days before filing notice) |  |  | 2015-10-17 | 2015-09-16
| SAVE DOCUMENTS ON:SharePoint Topic: Public Notice |  |  | 2015-10-22 | 2015-10-22
DO NOT TURN OFF TRACK CHANGES IN CODENAME.RULES
PL | leads core team in developing Notice Packet that includes: -Codename.RULES SharePoint Topic: Public Notice -NOTICE SharePoint Topic: Public Notice -Overview -Statement of Need -Rules affected, authorities, supporting documents -Fee Analysis -Statement of fiscal and economic impact -Federal relationship -Land use -Stakeholder and public involvement -SUPPORTING.DOCS - optional SharePoint ¦ 4 Public Notice -INVITATION.TO.COMMENT (after Notice approved) SharePoint ¦ 4 Public Notice |  |  | 2015-10-22 | 2015-10-22
RESOURCE INPUT - THIS IS NOT A REVIEW
PL | asks RESOURCES for help and input, especially: |  |  | 2015-10-29 | 2015-10-29
| RGL for process, organization, edits, plain language |  |  | 2015-10-29 | 2015-10-29
| Affected staff, including regional staff, for subject matter |  |  | 2015-10-29 | 2015-10-29
| SIP Coordinator for SIP consultation |  |  | N/A | N/A
| UMGR: for direction and subject consultation, especially to meet program goals for rulemaking, align with section, division and agency goals |  |  | 2015-10-29 | 2015-10-29
| Communications (BrianW, Jennifer F.): for any updates to communication plan, message map, news release, social media |  |  | 2015-10-29 | 2015-10-29
| ARC: for legal consultation and discuss need for AAG input |  |  | 2015-10-29 | 2015-10-29
| Advisory Committee: for fiscal impact |  |  | N/A | N/A
PL | continually refines draft Notice Packet and considers RESOURCES input |  |  | 2015-11-02 | 2015-11-02
| validates approach with staff who provided input |  |  | 2015-11-02 | 2015-11-02
| asks AAG for input if needed & copies ARC on all AAG emails |  |  | 2015-11-02 | 2015-11-02
| addresses legal concerns and discusses with UMGR as needed |  |  | 2015-11-05 | 2015-11-05
| informs UMGR about the approach, issues and potential delays, raises unanticipated rulemaking and implementation risks to appropriate level |  |  | 2015-11-05 | 2015-11-05
| informs RGL about potential delays and develop contingency, if needed |  |  | 2015-11-05 | 2015-11-05
| asks contributors, including UMGR for consensus on subject completeness and accuracy |  |  | 2015-11-05 | 2015-11-05
Keep Management Informed
PL | determines with RGL and UMGR whether DA needs pre-publication review briefing |  |  | 2015-11-09 | 2015-11-09
PL | asks DA Assistant to schedule future time on DA Schedule for briefing meeting (if necessary) with PL, UMGR and RGL |  |  | 2015-11-09 | 2015-11-09
| asks DA Assistant to schedule future time on DA Schedule for reviewing notice package |  |  | 2015-11-09 | 2015-11-09
| schedules time on UMGR calendar to review Notice Package |  |  | 2015-11-09 | 2015-11-09
| verifies/adjusts previously scheduled briefing & review |  |  | 2015-11-09 | 2015-11-09
| keeps UMGR informed about progress, risks & delays |  |  | 2015-11-09 | 2015-11-09
UMGR | keeps management teams informed about progress |  |  | 2015-11-09 | 2015-11-09
Rule Publication Work
PL | prepares NOTICE, PROPOSED.RULES & optional SUPPORTING.DOCUMENTS |  |  | 2015-11-10 | 2015-11-09
| addresses all comments, but does not delete them |  |  | 2015-11-17 | 2015-11-12
| saves each document as Major version to capture all comments and tracked changes in NOTICE & optional SUPPORTING.DOCUMENTS: |  |  | 2015-11-17 | 2015-11-12
| accepts and rejects language changes as team agrees |  |  | 2015-11-17 | 2015-11-12
| ensures Word's track changes is turned on |  |  | 2015-11-17 | 2015-11-12
| saves documents as Minor versions |  |  | 2015-11-17 | 2015-11-12
| emails RGL for Rule Publication work when complete |  |  | 2015-11-17 | 2015-11-12
RGL | determines whether NOTICE & SUPPORTING DOCUMENTS are ready for Rule Publication |  |  | 2015-11-18 | 2015-11-16
IF INCOMPLETE
| notifies UMGR who works with PL |  |  | 2015-11-18 | 2015-11-16
| renegotiates schedule with UMGR & PL as needed |  |  | 2015-11-18 | 2015-11-16
| reminds PL to reschedule managers' briefing if needed |  |  | 2015-11-15 | 2015-11-15
| suspends Rule Publication work until PL resubmits documents |  |  | 2015-11-18 | 2015-11-16
PL | asks RGL to apply CHECKLIST review to PROPOSED.RULES |  |  | 2015-11-25 | 2015-11-19
RGL | leads review to determine fiscal and economic impact analysis sufficiency |  |  | 2015-11-25 | 2015-11-19
| determines whether work products meet DEQ publication standards |  |  | 2015-11-25 | 2015-11-19
PL | asks Communications, EQC Coordinator, ARC SIP Coordinator for input as needed |  |  | 2015-12-02 | 2015-11-19
| discusses/resolves any editorial differences |  |  | 2015-12-09 | 2015-11-25
| addresses input to ensure edits and comments speak with one voice |  |  | 2015-12-09 | 2015-11-25
| accepts non substantive edits |  |  | 2015-12-09 | 2015-11-25
| asks UMGR & PL for input/concurrence as needed |  |  | 2015-12-09 | 2015-11-25
UMGR, PL & RGL discuss:
| outstanding work |  |  | 2015-12-09 | 2015-11-25
| need for AAG review |  |  | 2015-12-09 | 2015-11-25
| need to renegotiate schedule |  |  | 2015-12-09 | 2015-11-25
PL
| addresses outstanding edits and comments |  |  | 2015-12-09 | 2015-11-25
| asks AAG for review, if indicated, copies ARC and addresses input |  |  | 2015-12-09 | 2015-11-25
| asks RGL & UMGR for concurrence on changes if indicated |  |  | 2015-12-16 | 2015-11-25
| addresses outstanding edits and comments |  |  | 2015-12-16 | 2015-11-25
| notifies RGL & UMGR when complete and ready for preview |  |  | 2015-12-16 | 2015-11-25
PL | forwards notice package to UMGR for review (6 weeks before filing notice) |  |  | 2015-12-16 | 2015-11-25
PL | on UMGR approval, forwards notice package to DA for review |  |  | 2015-12-23 | 2015-12-02
DA | completes review and emails approval to PL, UMGR, RGL |  |  | 2015-12-30 | 2015-12-07
Preview Period (leadership review) - 5-7 days
RGL | drafts EMAIL.PREVIEW (instructions in template) |  |  | 2016-01-04 | 2015-12-07
PL, UMGR | Brief DA – only if necessary; controversial, complex, unusually challenging rulemaking |  |  | 2016-01-04 | 2015-12-11
RGL | sends EMAIL.PREVIEW to: -Director, DA, Leadership Team, EQCC -Cc… all contributing and affected staff -saves Email.Preview .pdf to Rule_Development - 4- Notice |  |  | 2016-01-04 | 2015-12-11
PL. RGL, UMGR | decide how to address any feedback from preview |  |  | 2016-01-11 | 2015-12-14
PL | modifies documents as needed |  |  | 2016-01-11 | 2015-12-14
RGL | verifies PROPOSED.RULES are still based on current compilation |  |  | 2016-01-11 | 2015-12-14
PL | finalizes public documents with UMGR |  |  | 2016-01-11 | 2015-12-14
UMGR | emails PL & RGL approval to move forward with NOTICE, PROPOSED.RULES & any SUPPORTING.DCUMENTS |  |  | 2016-01-11 | 2015-12-14
RGL | saves email as Rule_Development ¦ 4-Notice ¦ MGR.APPROVAL.Notice.PDF |  |  | 2016-01-11 | 2015-12-14
PL/RGL | drafts INVITATION.TO.COMMENT using information from approved NOTICE |  |  | 2016-01-11 | 2015-12-14
RGL | establishes the following using Web Request: |  |  | 2016-01-11 | 2015-12-14
| External Web page |  |  | 2016-01-11 | 2015-12-14
| Online public comment form |  |  | 2016-01-11 | 2015-12-14
| University Student Comment Account - helpdesk request with PL & RGL co-owning account; CodeName = “Alias” |  |  | 2016-01-11 | 2015-12-14
| compares work products to earlier reviews to determine need for additional edits |  |  | 2016-01-11 | 2015-12-14
| obtains additional Rule Publication edits on changes if needed |  |  | 2016-01-11 | 2015-12-14
| verifies/clarifies additional edits with PL & UMGR as warranted |  |  | 2016-01-11 | 2015-12-14
| notifies UMGR & PL when finished |  |  | 2016-01-11 | 2015-12-14
| sets Outlook auto reply - instructions in Rulemaking Manual |  |  | 2016-01-11 | 2015-12-14
Notifications
RGL/PL | draft newspaper ads; designate newspapers ADS are not always required. They are only required for SIP rulemakings (40 CFR 51.102) - notice 30 days before hearing - ("notice given to the public by prominent advertisement in the area affected, announcing the dates, times, and places of such hearings"); or for rules that affect a specified gegraphical area. |  |  | 2015-12-20 | 2015-11-20
PL | COMPLETES FINAL REVIEW OF ALL DOCUMENTS FOR PUBLICATION |  |  | 2016-01-08 | 2015-12-14
| send web request to create rulemaking, comment web pages |  |  | 2016-01-04 | 2015-12-08
RGL | drafts EMAIL.NOTICE.TO.KEY.LEGISLATORS - instructions in template |  |  | 2016-01-04 | 2015-12-03
| sends draft to Leg.Liason |  |  | 2016-01-04 | 2015-12-03
Leg. Liason | determines key legislators requiring ORS 183.335(5) notification |  |  | 2016-01-07 | 2015-12-15
RGL | adapts email as needed |  |  | 2016-01-07 | 2015-12-15
RGL | leads: |  |  | 2016-01-07 | 2015-12-15
| submitting newspaper notices to contractor (14 days before filing notice- min. 30 days before hearing) |  |  | 2015-12-30 | 2015-12-01
| verifying newspaper advertisements are correct |  |  | 2016-01-14 | 2015-12-14
| obtaining copies of affidavits of publication from Accounting |  |  | 2016-01-14 | 2015-12-14
| adding hearings to DEQ Event Calendar |  |  | 2016-01-14 | 2015-12-14
| creating an auto reply to Outlook account for University students |  |  | 2016-01-14 | 2015-12-14
| validating Web page, comment form and Outlook account |  |  | 2016-01-14 | 2015-12-14
| if no advisory committee, submit web request for rulemaking and comment web page |  |  | 2015-01-04 | 2015-12-08
PL | submits Notice to EPA, if required |  |  | 2016-01-14 | 2015-12-15
RGL | submits notice to SOS for publication in Oregon Bulletin (not later than 15th of the month for publication the following month) |  |  | 2016-01-14 | 2015-12-15
| emails DAS notification of fees that don't require DAS approval |  |  | 2016-01-14 | 2015-12-15
| saves all evidence on Rule_Development ¦ 4-Notice using naming convention |  |  | 2016-01-14 | 2015-12-15
| opens public comment by notifying agency rulemaking list that includes: |  |  | 2016-01-14 | 2015-12-15
| GovDelivery |  |  | 2016-01-14 | 2015-12-15
| EQCC |  |  | 2016-01-14 | 2015-12-15
| advisory committee |  |  | N/A | N/A
| program-specific lists |  |  | 2016-01-14 | 2015-12-15
| DEQ communications - publications and social media |  |  | 2016-01-14 | 2015-12-15
| saves all evidence, lists and affidavits on Rule_Development ¦ 4 Notice |  |  | 2016-01-18 | 2015-12-17
RGL | emails Key Legislators with Return Receipt (redirects receipt to PL) |  |  | 2016-01-14 | 2015-12-15
| copies PL |  |  | 2016-01-14 | 2015-12-15
| saves receipts under Rule_Development¦4-Notice |  |  | 2016-01-18 | 2015-12-17
RGL & WebRep | maintain Rukemaking Web page |  |  | 2016-01-18 | 2015-12-17
PL | gathers and saves all emails on Rule_Development¦4-Notice using naming conventions |  |  | 2016-01-18 | 2015-12-17
Public Comment and Testimony
| Review version history to help maintaining rulemaking record |  |  | 2016-01-18 | 2015-12-17
| SAVE DOCUMENTS ON: SharePoint Topic: Public Notice |  |  | 2016-01-18 | 2015-12-17
RGL | meets with PL and Hearings Officers to discuss hearing procedures |  |  | 2016-02-15 | 2016-01-14
| If hearing after hours at DEQ HQ, request guard using Guard Request Procedure |  |  | 2016-01-18 | 2015-12-17
PL | verifies venues and equipment, gathers supplies |  |  | 2016-02-08 | 2016-01-04
| develops INFO.MEETING.TEXT |  |  | 2016-02-08 | 2016-01-04
| modifies MESSAGE.MAP |  |  | 2016-02-08 | 2016-01-04
| develops INFO.PRESENTATION |  |  | 2016-02-08 | 2016-01-04
| practices presentation |  |  | 2016-02-08 | 2016-01-04
| makes presentation adjustments |  |  | 2016-02-08 | 2016-01-04
| initiates UMGR review/approval, addresses suggestions |  |  | 2016-02-08 | 2016-01-04
UMGR | reviews/approves optional presentation |  |  | 2016-02-15 | 2016-01-13
Hearings Officers
| reviews responsibilities of hearings officer |  |  | 2016-02-15 | 2016-01-13
| develops introductory and logistics script |  |  | 2016-02-15 | 2016-01-13
| holds the following hearings (identified under Planning section) with assigned team |  |  | 2016-02-17 | 2016-01-14
Hearing 1 | Location, Time
| save audio as Rule_Development¦5-PublicComment¦HEARING.1.mp3 |  |  | 2016-02-18 | 2016-01-19
PL | for comments received by mail or at hearings: |  |  | 2016-02-22 | 2016-01-25
| stamps DEQ receipt date on address-side of envelope and on first page of letter |  |  | 2016-02-22 | 2016-01-25
| adds commenter and comment to COMMENTS |  |  | 2016-02-22 | 2016-01-25
| scans mailed comments and envelopes and saves as ID###.pdf |  |  | 2016-02-22 | 2016-01-25
| PUBLIC COMMENT CLOSES | 2016-02-22
RGL | downloads online public comments to Excel, Codename.public.comment; save in Development ¦ Public Comment and Testimony
Downloads email comments from student email box to Excel; Codename.student.comment; save in Development ¦ Public Comment and Testimony
PL | coordinates with team to:
develop category titles to bundle similar comments
organize comments into categories
draft DEQ responses to each categories of comments
leads team work finalizing DEQ responses to public comment
DO NOT MAIL TO COMMENTERS UNTIL EQC ASSISTANT FINALIZES STAFF REPORT
PL | asks RGL for Rule Publication review
RGL | coordinates Rule Publication work:
edits for plain English, style guide & tone because this is part of EQC packet
contacts PL with questions, clarifications and suggestions
notifies PL when complete
PL | shares comments/responses to comments with UMGR & DA
team modifies responses to get to approval
PL
gathers emails ABOUT comments, not actual comments, for Rule Record
saves them as Rule_Development¦5-PublicComment...¦EMAIL.Comment.pdf
EQC Preparation
Review version history to help maintaining rulemaking record
SAVE DOCUMENTS ON: SharePoint TopicL EQC Preparation
PL
finalizes EQC Packet with core team:
codename.staff.rpt
codename.rules
SUPPORTING.DOCUMENTS
notifies RGL that EQC packet is ready for Rule Publication
RGL | leads initial Rule Publication work that includes:
comparing NOTICE to STAFF.REPORT to determine what needs review
obtaining/consolidating Communications, EQC Coordinator, SIP Coordinator edits, including style guide, grammar, plain English, organization
accepting all style guide and format edits
getting ARC review of PROPOSED.RULES- SOS/LC and CHECKLIST review
contacts PL with questions or modifications and when work is complete
PL
addresses rule publication edits and comments
prepares EQC packet
| initiates management review and approval: UMGR and DA |  |  | 2016-04-22 | 2016-04-22
| obtains approval from UMGR to submit EQC packet |  |  | 2016-04-29 | 2016-04-29
discusses need for 1¦1 commissioners briefings with UMGR/DA/EQCC
PL | COMPLETES FINAL VERSION OF ALL DOCUMENTS |  |  | 2016-04-29 | 2016-04-29
| submits EQC packet to EQCC (5 weeks before EQC) |  |  | 2016-05-06 | 2016-05-06
notifies the following according to division's standard practice:
· staff contributors
· key stakeholders
· advisory committee members
· commenters
· interested parties (optional)
leads team development of EQC presentation
coordinates presentation practices
makes any presentation adjustments
Presentation team | ATTENDS EQC MEETING |  |  | 2016-06-10 | 2016-06-10
PL | saves emails about EQC preparations for Rule Record in Rule_Development¦6-EQCPreparation¦EMAILS.EQC.Prep.pdf
Post EQC
Review version history to help maintaining rulemaking record
Document Preparation
RGL | saves following documents to 7.PostEQC folder on Rule_Develpment:
gets documents as presented to EQC from EQC Coordinator
STAFF.REPORT.pdf
STAFF.REPORT.ADDENDUM.pdf (if presented to EQC)
downloads documents as presented to EQC from SharePoint:
PROPOSED.RULES (showing changes)
saves as REDLINE.docx (showing changes in strikethrough and
saves as RULES.docx (clean version), accepts all changes, saves again
TABLES.340-###-####.docx (1 .docx per rule contains ALL tables)
coordinates EPA.SIP.SUBMITAL with SIP Coordinator
Filing
DEADLINE: No Oregon deadline for filing rules after adoption - check EPA
ARC
logs onto Secretary of State online filing form
uses information in STAFF.REPORT & ADDENDUM to populate form
reviews, prepares and uploads:
RULES.docx (clean version in Word)
TABLES.340-###-####-SOS.pdf (1 .docx per rule contains ALL tables
develops, scans and uploads AUTHORIZATION-SOS.pdf into online SOS form
completes SOS form, verifies and submits
Filed Date
Effective Date
ARC | saves certificate that SOS sent via email as CERTIFICATE-SOS.pdf
notes sequence for Certificate and Administrative Order No.
submits Web request to update Web page
moves share drive folder system:
FROM: \\deqhq1\Rule_Development\Current
TO: \\deqhq1\Rule_Development\Filed
Legislative Counsel Notification
DEADLINE | LC must receive notification within 10 days after CERTIFICATE date
DEQ PRACTICE | Put in shuttle on day of SOS filing
ARC
prepares Legislative Counsel notification - see Rulemaking Manual:
prints | CERTIFICATE and saves copy as CERTIFICATE-LC.pdf
prints | REDLINE and saves copy as REDLINE-LC.pdf
self-addressed envelope, fold underside of flap over a 2nd certificate
write "Please date stamp certificate and return." on underside of flap
prepares/scans return receipt shuttle envelope, saves as SHUTTLE.RECEIPT-LC.pdf
sends via shuttle
sends Procurement a scanned image of SHUTTLE.RECEIPT-LC
DAS FEE APPROVAL - PART 2
DEADLINE | DEQ must send notification or DAS Part 2 within 10 days of EQC action
PL
gets signatures on Part 2 of signed DAS Fee Approval
scans/saves as DAS.PART2.pdf
excerpts fee sections from RULES, saves as FEE.RULES-DAS, print
excerpts fee sections from STAFF.REPORT, saves as FEE.REPORT-DAS, print
emails PART2-DAS.pdf to DAS (requests delivery receipt)
get preprinted return receipt shuttle envelope from ARC
prepares/scans shuttle envelope, saves as SHUTTLE.RECEIPT-DAS.pdf
sends all fee documents to DAS via shuttle
sends Procurement a scanned image of SHUTTLE.RECEIPT-DAS
Closing Records and Archival
RGL
verifies Web page is current and accurate
coordinates meeting to discuss lessons learned
ensures the final version of every document on SharePoint is Major (Published)
verifies Outlook student comment account is empty/asks helpdesk to close account
leads verification that published rules in Oregon Bulletin are correct
If errors, PL works with ARC to correct and selects
SIPC | submits SIP to EPA within 60 days AFTER adoption
emails optional STAKEHOLDER.NOTIFICATION that links to Web page
coordinates AC.THANK.YOU email or letter that links to Web page
scans physical records and save to Rule_Development
gathers emails about post EQC activities for the Rule Record and saves as: Rule_Development ¦ 7-PostEQC ¦ EMAILS.PostEQC.pdf
ARC
coordinates moving major versions from SharePoint to Rule_Development
coordinates closing SharePoint sub-site
archives folders when record is complete by moving:
FROM: \\deqhq1\Rule_Development
TO: \\deqhq1\Rule_Archives
Save copy of rulemaking Home Page as .mht file in "Web Pages" folder in this rulemaking's folder in the Rulemaking Development drive.
coordinates retiring Q-Time number(s) with BudgetAnalyst
Formulas:
Amended Dates = [Amended Dates, row above]+17
Amended Dates = [Amended Dates, row below]-35
End = [End, row below]-35

## Tasks summary
Person | Action | __Suggested Dates_ ¦ Start ¦ End | __Amended Dates__ ¦ Start ¦ End
TitleVCPI2016
Abbreviations
ARC | Agency Rules Coordinator
DA | Division Administrator
EQCC | EQC Coordinator
PL | Program Lead
RGL | Rules Group Lead
SIPC | SIP Coordinator
UMGR | Unit Manager
SP | SharePoint
Director | DEQ Director
Overview of Key Dates
PL | Notice Packet due to RGL and UMGR for review | 0
PL | Notice Packet due to DA and Communications for review | 0
RGL | File notice with SOS/open comment period | 2016-01-14
| Notice Published in Oregon Bulletin (DEQ standard 90 days before EQC) | 2016-02-01
PL | first public hearing - at least 30 days AFTER comment opens; DEQ standard 16 days after Bulletin Notice published | 2016-02-18
RGL/PL | close public comment - 3 days after hearing | 2016-02-21
PL | Staff report due to EQCC | 2016-05-06
| EQC Meeting | 2016-06-10
Schedule of Tasks
SIP
SIP Coord | Submit SIP development plan to EPA | 0
| Submit draft rules and notice to EPA | 0
| Submit adopted rules and SIP info to EPA | 0
Fees
PL | Lead development of fee approval packet | 2015-10-19
| Obtain review of fee packet by UMGR and RGL | 2015-12-03
| Finalize fee packet | 2015-12-11
RGL | Submit Part I of fee packet to DAS | 2015-12-18
| Submit Part II of fee packet to DAS | 2016-06-15
Communications Planning
PL | schedules/facilitates meeting with team, Communications, Rules Group to discuss/determine need for: -communications plan -message map -newspaper ads -news release -social media -rulemaking/program web page -informational meetings | 2015-10-21
| Preplanning for Hearings (90 days before 1st hearing) | 2015-11-20
| Initial Rule Work (4 mos. Before filing notice) | 2015-09-20
RGL and PL | discuss requirements for EQC faciliated hearing
PL | coordinates with Team to:
· determine need for a crosswalk
· identify rules to amend or repeal
· identify new rules to adopt
· identify land use rules
· identify SIP rules, talk with SIP Coordinator
Advisory Committee (4 mos. before filing notice)
| Advisory Committee work session (120 days before meeting) | N/A
UMGR | approves deliverables including AC.ROSTER (97 days before meeting) | 2015-08-18
UMGR, PL, RGL | emails AC.MEMBER.INVITATION with links and instructions (60) days before meeting) | 2015-09-17
PL | SUBMIT FINAL VERSION OF ALL DOCUMENTS FOR PUBLICATION | 2015-10-26
RGL, PL | send web request to create rulemaking, advisory committee web pages | 2015-11-02
| emails AC.EQC.INVITATION to sign up for Advisory Committee (min. 14 days before meeting) | 2015-11-02
RGL | sends AC.AFFECTED.PARTIES.INVITATION to GovDelivery topic (min. 14 days before meeting) | 2015-11-02
| Advisory Committee meeting (min. 60 days before filing notice) | 2015-11-16
| Public Notice - not required for temporary rules (begin 90 days before filing notice) | 2015-10-17
PL | begin drafting rules and notice
asks DA Assistant to schedule future time on DA Schedule for reviewing notice package
schedules time on UMGR calendar to review Notice Package
Rule Publication Work
PL | forwards notice package to UMGR for review (6 weeks before filing notice) | 2015-12-16
PL | on UMGR approval, forwards notice package to DA for review
Preview Period (leadership review) - 5-7 days
RGL | sends EMAIL.PREVIEW to: -Director, DA, Leadership Team, EQCC -Cc… all contributing and affected staff -saves Email.Preview .pdf to Rule_Development - 4- Notice | 2016-01-04
Notifications
RGL/PL | draft newspaper ads | 2015-12-20
RGL | send web request to create rulemaking, comment web pages | 2015-12-20
RGL | submit newspaper notices to contractor (14 days before filing notice- min. 30 days before hearing) | 2015-12-30
PL | COMPLETE FINAL REVIEW OF ALL DOCUMENTS FOR PUBLICATION | 2016-01-08
RGL | submits notice to SOS for publication in Oregon Bulletin (not later than 15th of the month for publication the following month) | 2016-01-14
Public Comment and Testimony
PL | Public hearing | 0
| Public Comment Closes | 2016-02-22
EQC Preparation
PL | initiates management review and approval: UMGR and DA | 2016-04-22
PL | obtains approval from UMGR to submit EQC packet | 2016-04-29
discusses need for 1¦1 commissioners briefings with UMGR/DA/EQCC
PL | COMPLETES FINAL VERSION OF ALL DOCUMENTS | 2016-04-29
PL/RGL | submits EQC packet to EQCC (5 weeks before EQC) | 2016-05-06
PL | EQC meeting | 2016-06-10

## Schedule summary
Person | Action | __Suggested Dates_ ¦ Start ¦ End | __Amended Dates__ ¦ Start ¦ End
CodeName: (abbreviated name)
Abbreviations
ARC | Agency Rules Coordinator
DA | Division Administrator
EQCC | EQC Coordinator
PL | Program Lead
RGL | Rules Group Lead
SIPC | SIP Coordinator
UMGR | Unit Manager
SP | SharePoint
Director | DEQ Director
Overview of Key Dates
PL | Notice Packet due to RGL and UMGR for review | 0
PL | Notice Packet due to DA and Communications for review | 0
RGL | File notice with SOS/open comment period | 2016-01-14
RGL | Notice Published in Oregon Bulletin (DEQ standard 90 days before EQC) | 2016-02-01
PL | first public hearing - at least 30 days AFTER comment opens; DEQ standard 16 days after Bulletin Notice published | 2016-02-18
RGL/PL | close public comment - 3 days after hearing | 2016-02-21
PL | Staff report due to EQCC | 2016-05-06
| EQC Meeting | 2016-06-10
Chronological List
SIP
SIP Coord | Submit SIP development plan to EPA | 0
| Submit draft rules and notice to EPA | 0
| Submit adopted rules and SIP info to EPA | 0
Fees
PL | Lead development of fee approval packet | 2015-10-19
| Obtain review of fee packet by UMGR and RGL | 2015-10-19
| Finalize fee packet | 2015-12-03
RGL | Submit Part I of fee packet to DAS | 2015-12-11
| Submit Part II of fee packet to DAS | 2015-12-18
PL/RGL | Advisory Committee -work session (120 days before meeting) | N/A
UMGR | approves AC deliverables including AC.ROSTER (97 days before meeting) | 2015-08-18
UMGR, PL, RGL | emails AC.MEMBER.INVITATION with links and instructions (60) days before meeting) | 2015-09-17
PL | Communications Planning: schedules/facilitates meeting with team, Communications, Rules Group to discuss/determine need for: -communications plan -message map -newspaper ads -news release -social media -rulemaking/program web page -informational meetings | 2015-10-21
RGL and PL | Start rule writing -4 mos. before filing notice discuss requirements for EQC faciliated hearing | 2015-09-20
PL | coordinates with Team to:
· determine need for a crosswalk
· identify rules to amend or repeal
· identify new rules to adopt
· identify land use rules
· identify SIP rules, talk with SIP Coordinator
| Public Notice -not required for temporary rules -begin 90 days before filing notice | 2015-10-17
PL | begin drafting rules and notice
PL | asks DA Assistant to schedule future time on DA Schedule for reviewing notice package
PL | schedules time on UMGR calendar to review Notice Package
RGL, PL | send web request to create rulemaking, advisory committee web pages | 2015-11-02
| SUBMIT FINAL VERSIONS OF ALL DOCUMENTS FOR PUBLICATION | 2015-10-26
RGL | emails AC.EQC.INVITATION to sign up for Advisory Committee (min. 14 days before meeting) | 2015-11-02
RGL | sends AC.AFFECTED.PARTIES.INVITATION to GovDelivery topic (min. 14 days before meeting) | 2015-11-02
PL | Advisory Committee meeting (min. 60 days before filing notice) | 2015-11-16
Fee Approval Packet, with team and BudgetAnalyst
PL/RGL | Preplanning for Hearings (90 days before 1st hearing) | 2015-11-20
PL | forwards notice package to UMGR for review (6 weeks before filing notice) | 2015-12-16
PL | on UMGR approval, forwards notice package to DA for review
RGL/PL | draft newspaper ads | 2015-12-20
RGL | send web request to create rulemaking, comment web pages | 2015-12-20
RGL | submit newspaper notices to contractor (14 days before filing notice- min. 30 days before hearing) | 2015-12-30
RGL | Preview Period: (leadership review) - 5-7 days sends EMAIL.PREVIEW to: -Director, DA, Leadership Team, EQCC -Cc… all contributing and affected staff -saves Email.Preview .pdf to Rule_Development - 4- Notice | 2016-01-04
PL | COMPLETE FINAL REVIEW OF ALL DOCUMENTS FOR PUBLICATION | 2016-01-08
RGL | submits notice to SOS for publication in Oregon Bulletin (not later than 15th of the month for publication the following month) | 2016-01-14
PL | Public hearing | 0
RGL | close public comment | 2016-02-22
PL | Staff report - initiates management review and approval: UMGR and DA | 2016-04-22
PL | obtains approval from UMGR to submit EQC packet | 2016-04-29
PL | discusses need for 1¦1 commissioners briefings with UMGR/DA/EQCC
PL | COMPLETE FINAL VERSION OF ALL DOCUMENTS | 2016-04-29
PL/RGL | submits EQC packet to EQCC (5 weeks before EQC) | 2016-05-06
PL | EQC meeting | 2016-06-10

## main sharepoint
ID | Title | Location | Start Time | End Time | Description | All Day Event | Recurrence | Workspace | Category | Resources | Free/Busy | Check Double Booking | Comments | URL | Attachments | Attendees
| Title V CPI 2016 |  | N/A | N/A | Advisory Committee -work session (120 days before meeting) | TRUE
| Title V CPI 2016 |  | 2015-08-18 | 2015-08-18 | approves AC deliverables including AC.ROSTER (97 days before meeting) | TRUE
| Title V CPI 2016 |  | 2015-09-17 | 2015-09-17 | emails AC.MEMBER.INVITATION with links and instructions (60) days before meeting) | TRUE
| Title V CPI 2016 |  | 2015-10-21 | 2015-10-21 | Communications Planning: schedules/facilitates meeting with team, Communications, Rules Group to discuss/determine need for: -communications plan -message map -newspaper ads -news release -social media -rulemaking/program web page -informational meetings | TRUE
| Title V CPI 2016 |  | 2015-09-20 | 2015-09-20 | Start rule writing -4 mos. before filing notice discuss requirements for EQC faciliated hearing | TRUE
| Title V CPI 2016 |  | #REF! | #REF! | SIP - submit rule package to EPA (at least 90 days before notice) | TRUE
| Title V CPI 2016 |  | 2015-10-17 | 2015-10-17 | Public Notice -not required for temporary rules -begin 90 days before filing notice | TRUE
| Title V CPI 2016 |  | 2015-11-02 | 2015-11-02 | send web request to create rulemaking, advisory committee web pages | TRUE
| Title V CPI 2016 |  | 2015-11-02 | 2015-11-02 | emails AC.EQC.INVITATION to sign up for Advisory Committee (min. 14 days before meeting) | TRUE
| Title V CPI 2016 |  | 2015-11-02 | 2015-11-02 | sends AC.AFFECTED.PARTIES.INVITATION to GovDelivery topic (min. 14 days before meeting) | TRUE
| xxxx |  | 2015-10-26 | 2015-10-26 | SUBMIT FINAL VERSIONS OF ALL DOCUMENTS FOR PUBLICATION | TRUE
| Title V CPI 2016 |  | 2015-11-16 | 2015-11-16 | Advisory Committee meeting (min. 60 days before filing notice) | TRUE
| Title V CPI 2016 |  | #REF! | #REF! | Fees - leads development of: | TRUE
| Title V CPI 2016 |  | 2015-11-20 | 2015-11-20 | Preplanning for Hearings (90 days before 1st hearing) | TRUE
| Title V CPI 2016 |  | #REF! | #REF! | initiates UMGR Fee Approval Packet review, addresses suggestions | TRUE
| Title V CPI 2016 |  | 2015-12-16 | 2015-12-16 | forwards notice package to UMGR for review (6 weeks before filing notice) | TRUE
| Title V CPI 2016 |  | #REF! | #REF! | sends EMAIL.DAS.APPROVAL with Fee Approval Packet attached (30 days before filing notice) | TRUE
| Title V CPI 2016 |  | 2015-12-20 | 2015-12-20 | draft newspaper ads | TRUE
| Title V CPI 2016 |  | 2015-12-20 | 2015-12-20 | send web request to create rulemaking, comment web pages | TRUE
| Title V CPI 2016 |  | 2015-12-30 | 2015-12-30 | submit newspaper notices to contractor (14 days before filing notice- min. 30 days before hearing) | TRUE
| Title V CPI 2016 |  | 2016-01-04 | 2016-01-04 | Preview Period: (leadership review) - 5-7 days sends EMAIL.PREVIEW to: -Director, DA, Leadership Team, EQCC -Cc… all contributing and affected staff -saves Email.Preview .pdf to Rule_Development - 4- Notice | TRUE
|  |  | 2016-01-08 | 2016-01-08 | COMPLETE FINAL REVIEW OF ALL DOCUMENTS FOR PUBLICATION
| Title V CPI 2016 |  | 2016-01-14 | 2016-01-14 | submits notice to SOS for publication in Oregon Bulletin (not later than 15th of the month for publication the following month) | TRUE
| Title V CPI 2016 |  | 2016-02-01 | 2016-02-01 | Notice published in Oregon Bulletin
| Title V CPI 2016 |  | 0 | 0 | Public hearing | TRUE
| Title V CPI 2016 |  | 2016-02-22 | 2016-02-22 | close public comment | TRUE
| Title V CPI 2016 |  | 2016-04-22 | 2016-04-22 | Staff report - initiates management review and approval: UMGR and DA | TRUE
| Title V CPI 2016 |  | 2016-04-29 | 2016-04-29 | obtains approval from UMGR to submit EQC packet | TRUE
|  |  | 2016-04-29 | 2016-04-29 | COMPLETE FINAL VERSION OF ALL DOCUMENTS
| Title V CPI 2016 |  | 2016-05-06 | 2016-05-06 | submits EQC packet to EQCC (5 weeks before EQC) | TRUE
| Title V CPI 2016 |  | 2016-06-10 | 2016-06-10 | EQC meeting | TRUE
| xxxx |  | 0 | 0 | Submit SIP development plan to EPA | TRUE
| xxxx |  | 0 | 0 | Submit draft rules and notice to EPA | TRUE
| xxxx |  | 0 |  | Submit adopted rules and SIP docs to EPA | TRUE
| xxxx |  | 2015-10-19 | 2015-10-19 | Lead development of Fee approval packet | TRUE
| xxxx |  | 2015-12-03 | 2015-12-03 | Obtain UMGR and RGL review of fee packet | TRUE
| xxxx |  | 2015-12-11 | 2015-12-11 | Finalize fee packet | TRUE
| xxxx |  | 2015-12-18 | 2015-12-18 | Submit fee packet Part I to DAS | TRUE
| xxxx |  | 2016-06-15 | 2016-06-15 | Submit fee packet Part II to DAS | TRUE

## ind SP
ID | Title | Location | Start Time | End Time | Description | All Day Event | Recurrence | Workspace | Category | Resources | Free/Busy | Check Double Booking | Attachments | Attendees
| SIP - submit SIP development plan to EPA (6 mos. before notice) |  | #REF! | #REF! |  | TRUE
| Advisory Committee -work session (120 days before meeting) |  | N/A | N/A |  | TRUE
| approves AC deliverables including AC.ROSTER (97 days before meeting) |  | 2015-08-18 | 2015-08-18 |  | TRUE
| emails AC.MEMBER.INVITATION with links and instructions (60) days before meeting) |  | 2015-09-17 | 2015-09-17 |  | TRUE
| Communications Planning: schedules/facilitates meeting with team, Communications, Rules Group to discuss/determine need for: -communications plan -message map -newspaper ads -news release -social media -rulemaking/program web page -informational meetings |  | 2015-10-21 | 2015-10-21 |  | TRUE
| Start rule writing -4 mos. before filing notice discuss requirements for EQC faciliated hearing |  | 2015-09-20 | 2015-09-20 |  | TRUE
| SIP - submit rule package to EPA (at least 90 days before notice) |  | #REF! | #REF! |  | TRUE
| Public Notice -not required for temporary rules -begin 90 days before filing notice |  | 2015-10-17 | 2015-10-17 |  | TRUE
| SUBMIT FINAL VERSION OF ALL DOCUMENTS FOR PUBLICATION |  | 2015-10-26 | 2015-10-26 |  | TRUE
| send web request to create rulemaking, advisory committee web pages |  | 2015-11-02 | 2015-11-02 |  | TRUE
| emails AC.EQC.INVITATION to sign up for Advisory Committee (min. 14 days before meeting) |  | 2015-11-02 | 2015-11-02 |  | TRUE
| sends AC.AFFECTED.PARTIES.INVITATION to GovDelivery topic (min. 14 days before meeting) |  | 2015-11-02 | 2015-11-02 |  | TRUE
| Advisory Committee meeting (min. 60 days before filing notice) |  | 2015-11-16 | 2015-11-16 |  | TRUE
| Fees - leads development of: |  | #REF! | #REF! |  | TRUE
| Preplanning for Hearings (90 days before 1st hearing) |  | 2015-11-20 | 2015-11-20 |  | TRUE
| initiates UMGR Fee Approval Packet review, addresses suggestions |  | #REF! | #REF! |  | TRUE
| forwards notice package to UMGR for review (6 weeks before filing notice) |  | 2015-12-16 | 2015-12-16 |  | TRUE
| sends EMAIL.DAS.APPROVAL with Fee Approval Packet attached (30 days before filing notice) |  | #REF! | #REF! |  | TRUE
| draft newspaper ads |  | 2015-12-20 | 2015-12-20 |  | TRUE
| send web request to create rulemaking, comment web pages |  | 2015-12-20 | 2015-12-20 |  | TRUE
| submit newspaper notices to contractor (14 days before filing notice- min. 30 days before hearing) |  | 2015-12-30 | 2015-12-30 |  | TRUE
| Preview Period: (leadership review) - 5-7 days sends EMAIL.PREVIEW to: -Director, DA, Leadership Team, EQCC -Cc… all contributing and affected staff -saves Email.Preview .pdf to Rule_Development - 4- Notice |  | 2016-01-04 | 2016-01-04 |  | TRUE
| COMPLETE FINAL REVIEW OF ALL DOCUMENTS FOR PUBLICATION |  | 2016-01-08 | 2016-01-08 |  | TRUE
| submits notice to SOS for publication in Oregon Bulletin (not later than 15th of the month for publication the following month) |  | 2016-01-14 | 2016-01-14 |  | TRUE
| Notice published in Oregon Bulletin |  | 2016-02-01 | 2016-02-01
| Public hearing |  | 0 | 0 |  | TRUE
| close public comment |  | 2016-02-22 | 2016-02-22 |  | TRUE
| Staff report - initiates management review and approval: UMGR and DA |  | 2016-04-22 | 2016-04-22 |  | TRUE
| obtains approval from UMGR to submit EQC packet |  | 2016-04-29 | 2016-04-29 |  | TRUE
| COMPLETE FINAL REVIEW OF ALL DOCUMENTS |  | 2016-04-29 | 2016-04-29 |  | TRUE
| submits EQC packet to EQCC (5 weeks before EQC) |  | 2016-05-06 | 2016-05-06 |  | TRUE
| EQC meeting |  | 2016-06-10 | 2016-06-10 |  | TRUE
| Submit SIP development plan to EPA |  | 0 | 0 |  | TRUE
| Submit draft rules and notice to Epa |  | 0 | 0 |  | TRUE
| Submit adopted rules and SIP docs to EPA |  | 0 | 0 |  | TRUE
| Lead development of fee approval packet |  | 2015-10-19 | 2015-10-19 |  | TRUE
| Obtain review of UMGR and RGL review of fee packet |  | 2015-12-03 | 2015-12-03 |  | TRUE
| Finalize fee packet |  | 2015-12-11 | 2015-12-11 |  | TRUE
| Submit fee Packet Part I to DAS |  | 2015-12-18 | 2015-12-18 |  | TRUE
| Submit fee packet part II to DAS |  | 2016-06-15 | 2016-06-15 |  | TRUE