## Schedule
Person | Action | Suggested Dates |  | Amended Dates
| Title V CPI 2016 | Start | End | Start | End
Instructions
Enter notice publication date under Suggested "Notice Published" Date
Enter EQC date under Suggested "EQC Meeting" Date
*Worksheet will populate dates under "Suggested Start Dates" *If desired, manually fill in dates in "End" column *Manually fill in desired dates under "Amended Dates" *Find any term on sheet using control + F (find) *"Summary" tab is overview of critical tasks and dates
Links to Task Headings
Overview of Key Dates
Concept Development
Start Rulemaking
SIP
Communications Planning
Preplanning for Hearings
EQC Facilitated Hearings
Initial Rule Work
Advisory Committee
Fees
Public Notice
Rule Publication Work
Preview Period
Notifications
Public Comment and Testimony
Public Comment Closes
EQC Preparation
Abbreviations
ARC | Agency Rules Coordinator
DA | Division Administrator
EQCC | EQC Coordinator
PL | Program Lead
RGL | Rules Group Lead
SIPC | SIP Coordinator
UMGR | Unit Manager
SP | SharePoint
Director | DEQ Director
Background
Temporary or Permanent | T/P | P
Rule proposal complexity | Simple/Average/Complex | S
Advisory Committee | Y/N
Fees | Y/N | Y
Fees- DAS approval required | Y/N | N
SIP | Y/N | N
EQC involvement before hearing | Y/N | N
EQC faciliated hearing? | Y/N | N
Overview of Key Dates
Director | Added to Rulemaking Plan | 2015-09-14
` | Notice Packet due to RGL and UMGR for review | 2016-12-02
PL | Notice Packet due to DA and Communications for review | 2016-12-09
RGL | File notice with SOS/open comment period | 2016-12-15
| Notice Published in Oregon Bulletin (DEQ standard 90 days before EQC) | 2016-01-01
PL | first public hearing - at least 30 days AFTER comment opens; DEQ standard 17 days after Bulletin Notice published | 2016-01-18
RGL/PL | close public comment - 3 days after hearing | 2016-01-21
PL | Staff report due to EQCC (5 weeks before EQC) | 2016-05-06
| EQC Meeting | 2016-06-10
RGL | file rules | 2016-06-14
Rules become effective | On date filed or later specified date | 2016-06-14
Director's report | Director's Report
Information item | Information Item
Rulemaking Process
Concept Development
UMGR | contacts ARC about a potential rulemaking | 2015-08-25
ARC | explains add concept to plan process | 2015-08-25
Unit manager | approves completing Resources and Considerations worksheets | 2015-08-25
ARC | adds to Rules Idea list/workload spreadsheet | 2015-08-25
| establishes new Rule_Development folder system | 2015-08-25
| adds TEMPLATES to 1. Planning folder and adapts to concept: CONSIDERATIONS, RESOURCES, SCHEDULE | 2015-08-25
| Meets with PL to discuss completing workbooks | 2015-08-25
PL | With ARC help, drafts workbooks using what she or he knows now | 2015-09-02
PL and UMGR | Calculate rule priority based on DRIVERS and RISKS tables from Rulemaking SP page | 2015-09-02
UMGR | shares workbooks and prioritization info with DA | 2015-09-07
UMGR | emails DA approval or disapproval to ARC, UMGR, PL | 2015-09-09
Units | conduct internal rule prioritization process | 2015-09-15
ARC | Uses WORKBOOKS, DRIVERS and RISKS info to rank rulemaking on WORKLOAD spreadsheet | 2015-09-15
Rules Group | Meet and prioritize projects; create unitary agency-wide prioritized list | 2015-09-15
Rules group | resources prioritized projects | 2015-09-15
ARC | presents prioritized list to Director (3 times/yr.; Jan., May, Sept.) | 2015-09-16
ARC | adds prioritized, Director-aproved projects to agency rulemaking plan | 2015-09-16
ARC | notifies DA, PL, UMGR of Director's decision | 2015-09-22
| posts DEQ Rulemaking Plan on Rules and Regulations web page and Rulemaking SP page | 2015-09-22
| send draft notification email to Director for approval, include: - Web page link - DEQ Rulemaking Plan - CONSIDERATIONS and RESOURCES Summary pages | 2015-09-22
| after director approval, sends informational email to: - Leadership Team - all managers who make rules - Communications -EQC coordinator to include in monthly Director's Report -Cc… DA, PL, RGL | 2015-09-22
SIP
SIP Coord | Submit SIP development plan to EPA | 2015-06-20
| Submit draft rules and notice to EPA | 2015-11-02
| Submit adopted rules and SIP info to EPA | 2016-06-20
Fees
PL | Leads development of Fee Approval Packet | 2015-09-18
| Obtains review of fee packet by UMGR and RGL | 2015-11-02
| Finalizes fee packet | 2015-11-10
RGL | Submits Part I of fee packet to DAS | 2015-11-17
RGL | Submits Part II of fee packet to DAS ( not later than 10 days after EQC) | 2016-06-15
Start Rulemaking
ARC:
| saves email Rule_Development ¦ 1-Planning ¦ APPROVAL.ToMoveForward | 2015-09-22
| establishes SharePoint sub-site -simple email to web support (Michele T. - 4.2015) | 2015-09-22
| moves SCHEDULE from Rule_Development into SharePoint | 2015-09-22
| moves other workbooks from Rule_Development into SharePoint | 2015-09-22
DA, UMGR, PL & RGL | decide whether to expand team | 2015-09-22
UMGR | is responsible for: | 2015-10-16
| · getting new team members' manager approval | 2015-10-16
| · adding rulemaking to work plans as appropriate | 2015-10-16
ARC | gets Qtime number from ISS Fiscal Coordinator (Robert Beall 12.14) | 2015-10-01
RGL | drafts SCHEDULE and SUMMARY | 2015-10-13
PL & RGL | refine & agree on draft schedule | 2015-10-16
PL | schedules/holds team meeting(s) for consensus on: | 2015-10-21
| · RESOURCES workbook, identifies rulemaking and implementation need | 2015-10-21
| · CONSIDERATIONS workbook, reflects scope of work accurately | 2015-10-21
| · CONSIDERATIONS workbook identifies potential risks accurately | 2015-10-21
| · SCHEDULE of tasks and deadlines | 2015-10-21
UMGR | ensures program staff meets agreed upon dates in SCHEDULE
Communications Planning
PL | schedules/facilitates meeting with team, Communications, Rules Group to discuss/determine need for: | 2015-10-21
| · Communications Plan | 2015-10-21
| · Social Media | 2015-10-21
| · Message Map | 2015-10-21
| · Newspaper advertisements (SIP or local rulemaking only) | 2015-10-21
| · Newspaper release | 2015-10-21
| · Program Web page | 2015-10-21
| · Information Meetings before hearing | 2015-10-21
RGL
verifies Web content meets team expectations
works with WebRep to make adjustments
PL/RGL | Publication Table:
· identifies newspaper and publication date
· develops an AD.STANDARD for each hearing if required
· develops AD.LEGAL for each hearing if required
· saves as NOTICE.AD.Hearing1, etc. on Rule_Development folder
· determines when ADs need to be submitted to contractor
· shares contents of HearingAndAdDates TAB with UMGR
· obtains UMGR email approval
| Preplanning for Hearings (90 days before 1st hearing) | 2015-10-20
PL and RGL | discuss requirements for hearings
PL | identifies hearing locations, dates and times
Meeting 1 Location, Time
Meeting 2 Location, Time
PL | reserves venues/equipment for hearings
EQC Facilitated Hearings
RGL and PL | discuss requirements for EQC faciliated hearing
PL | observe EQC quorum notification requirements (ORS 192.630)
identifies EQC facilitated hearing, coordinate with commissioner
gathers all planning emails for the Rule Record and saves PDF to Rule_Development:¦1-Planning¦EMAILS.Planning.pdf
| Initial Rule Work (4 mos. Before filing notice) | 2015-08-20
DO NOT TURN OFF TRACK CHANGES IN CODENAME.RULES
PL | coordinates with Team to:
· determine need for a crosswalk
· identify rules to amend or repeal
· identify new rules to adopt
· identify land use rules
· identify SIP rules, talk with SIP Coordinator
RGL | pulls rules to amend or repeal from SOS-Archives
determines availability of any new (adopted) rule or division
adds PROPOSED.RULES.Pristine template to Rule_Development
copies subject rules from SOS into template
saves PROPOSED.RULES.Pristine
uploads a copy to SharePoint under Topic: Public Notice
protects PROPOSED.RULES.Pristine on Rule_Development
obtains, verifies, provides previously unused rule numbers
shares information about rules that may be involved in other rulemakings
performs 1st plain language, style guide edits on SharePoint
offers organizational comments and examples
PL | leads rule writing on SharePoint CodeName.RULES to:
· consider regulations, policies, programs and systems that may affect subject rules
· validate/correct all citations, tables, formulas and document references within rule
· validate/correct statutory authorities at bottom of each rule
· validate/correct statutes implemented at bottom of each rule
· validate/correct NOTE(s)
· does not delete or change Hist. or ED.NOTES for any rule
· SIP note is at bottom of all SIP rules and it is accurate
All drafters and reviewers | work on SharePoint Codename.RULES
PL | before submitting Notice Packet and EQC Packet:
· verifies each rule in Codename.RULES is current with SOS compilation
· verifies no rule adoptions could affect Codename.RULES
Advisory Committee
SAVE DOCUMENTS ON: | SharePoint Topic: Public Notice
DEADLINE: | Notice committee meetings 2 weeks before meeting
RGL
| Advisory Committee work session (120 days before meeting) | 2015-06-18
adapts Advisory Committee PowerPoint to rulemaking
asks team to prepare for work session by reviewing:
· advisory committee guidelines
· Public Involvement Resources
· EQC quorum notification requirements (ORS 192.630)
· examples of the required Advisory Committee Web pages
· optional committee AC.CHARTER
· CONSIDERATIONS workbook in SharePoint Topic: Planning
asks PL to prepare the following work session items:
· add potential committee members to draft AC.ROSTER
· list potential meeting dates and venues
· draft AC.MEMBER.INVITATION
· identify all GovDelivery topics that include affected parties
· draft AC.AFFECTED.PARTIES.INVITATION to sign up for GovDelivery notices
· draft AC.EQC.INVITATION to sign up for GovDelivery notices
· draft AC.WebPage
facilitates Advisory Committee work session that follows PowerPoint discussion and decision items
discusses need to engage Communications (BrianW, Jennifer F.)
decides whether to use optional AC.CHARTER Y/N
advises PL on deliverables
PL | coordinates with team & UMGR for agreement on:
· AC.WebPage
· AC.CHARTER to include AC.ROSTER, meeting dates, venues
· AC.MEMBER.INVITATION (includes URL and reminder to Sign-up
· GovDelivery topic subscribers to get AC.AFFECTED.PARTIES.IN
· AC.AFFECTED.PARTIES.INVITATION to sign up for GovDelivery
· AC.EQC.INVITATION to sign up for GovDelivery notices
· meeting dates and venues
UMGR and PL | share Advisory Committee deliverables and decisions with DA
team addresses any concerns and validates accuracy of how addressed
UMGR | approves deliverables including AC.ROSTER (90 days before meeting) | 2015-07-18
PL | coordinates with team to:
· talk with potential committee members to determine interest
· finalize AC.ROSTER based on responses
RGL | works with WebRep to establish: | 2015-09-16
Advisory Committee page: http://www.oregon.gov/deq/RulesandRegulations/Pages/Advisory/A
Advisory Committee meeting page: http://www.oregon.gov/deq/RulesandRegulations/Pages/Advisory/A
Advisory Committee GovDelivery sign up
Have web team provide preview file (.mht file) before publishing web page
PL | identifies meeting roles
coordinates or leads drafting:
AC.AGENDA
AC.GovDelivery.NOTICE
AC.WebRequest.ATTACHMENT
obtains team and UMGR input on agenda and GovDelivery notice
RGL | submits Web Request 2 weeks before meeting using AC.WebRequest | 2015-10-02
sends AC.GovDelivery.NOTICE to committee Web page
PL | releases unneeded venues
UMGR, PL, RGL | emails AC.MEMBER.INVITATION with links and instructions (60) days before meeting) to AC members | 2015-08-17
| emails AC.EQC.INVITATION to sign up for Advisory Committee (min. 14 days before meeting) | 2015-10-02
RGL | sends AC.AFFECTED.PARTIES.INVITATION to GovDelivery topic (min. 14 days before meeting) | 2015-10-02
submits Web Request when Advisory Committee Web page needs updating
PL | maintains Advisory Committee record
Advisory Committee Presentation
PL | drafts optional AC.PRESENTATION
involves stakeholder presenters, if any
Team | approves presentation materials
RGL | submits Web Request to post presentation materials
PL | SUBMIT FINAL VERSION OF ALL DOCUMENTS FOR PUBLICATION | 2015-09-25
Team practices presentation
PL | facilitates, leads or supports:
| Advisory Committee meeting (min. 60 days before filing notice) | 2015-10-16
drafting of AC.MINUTES
team | debrief meeting
PL | gathers all advisory committee emails for the Rule Record - in Rule_Development¦3-FeesApproval¦EMAILS.Fees.pdf
Public Notice not required for temporary rules
| (begin 90 days before filing notice) | 2015-09-16
SAVE DOCUMENTS ON:SharePoint Topic: Public Notice
DO NOT TURN OFF TRACK CHANGES IN CODENAME.RULES
PL | leads core team in developing Notice Packet that includes: -Codename.RULES SharePoint Topic: Public Notice -NOTICE SharePoint Topic: Public Notice -Overview -Statement of Need -Rules affected, authorities, supporting documents -Fee Analysis -Statement of fiscal and economic impact -Federal relationship -Land use -Stakeholder and public involvement -SUPPORTING.DOCS - optional SharePoint ¦ 4 Public Notice -INVITATION.TO.COMMENT (after Notice approved) SharePoint ¦ 4 Public Notice
RESOURCE INPUT - THIS IS NOT A REVIEW
PL | asks RESOURCES for help and input, especially:
RGL for process, organization, edits, plain language
Affected staff, including regional staff, for subject matter
SIP Coordinator for SIP consultation
UMGR: for direction and subject consultation, especially to meet program goals for rulemaking, align with section, division and agency goals
Communications (BrianW, Jennifer F.): for any updates to communication plan, message map, news release, social media
ARC: for legal consultation and discuss need for AAG input
Advisory Committee: for fiscal impact
PL | continually refines draft Notice Packet and considers RESOURCES input
validates approach with staff who provided input
asks AAG for input if needed & copies ARC on all AAG emails
addresses legal concerns and discusses with UMGR as needed
informs UMGR about the approach, issues and potential delays, raises unanticipated rulemaking and implementation risks to appropriate level
informs RGL about potential delays and develop contingency, if needed
asks contributors, including UMGR for consensus on subject completeness and accuracy
Keep Management Informed
PL | determines with RGL and UMGR whether DA needs pre-publication review briefing
PL | asks DA Assistant to schedule future time on DA Schedule for briefing meeting (if necessary) with PL, UMGR and RGL
| asks DA Assistant to schedule future time on DA Schedule for reviewing notice package | 2015-10-27
| schedules time on UMGR calendar to review Notice Package | 2015-10-27
verifies/adjusts previously scheduled briefing & review
keeps UMGR informed about progress, risks & delays
UMGR | keeps management teams informed about progress
Rule Publication Work
PL | prepares NOTICE, PROPOSED.RULES & optional SUPPORTING.DOCUMENTS
addresses all comments, but does not delete them
saves each document as Major version to capture all comments and tracked changes in NOTICE & optional SUPPORTING.DOCUMENTS:
accepts and rejects language changes as team agrees
ensures Word's track changes is turned on
saves documents as Minor versions
emails RGL for Rule Publication work when complete
RGL | determines whether NOTICE & SUPPORTING DOCUMENTS are ready for Rule Publication
IF INCOMPLETE
notifies UMGR who works with PL
renegotiates schedule with UMGR & PL as needed
reminds PL to reschedule managers' briefing if needed
suspends Rule Publication work until PL resubmits documents
PL | asks RGL to apply CHECKLIST review to PROPOSED.RULES
RGL | leads review to determine fiscal and economic impact analysis sufficiency
determines whether work products meet DEQ publication standards
PL | asks Communications, EQC Coordinator, ARC SIP Coordinator for input as needed
discusses/resolves any editorial differences
addresses input to ensure edits and comments speak with one voice
accepts non substantive edits
asks UMGR & PL for input/concurrence as needed
UMGR, PL & RGL discuss:
outstanding work
need for AAG review
need to renegotiate schedule
PL
addresses outstanding edits and comments
asks AAG for review, if indicated, copies ARC and addresses input
asks RGL & UMGR for concurrence on changes if indicated
addresses outstanding edits and comments
notifies RGL & UMGR when complete and ready for preview
PL | forwards notice package to UMGR for review (6 weeks before filing notice) | 2015-11-03
PL | on UMGR approval, forwards notice package to DA for review
DA | completes review and emails approval to PL, UMGR, RGL
Preview Period (leadership review) - 5-7 days
RGL | drafts EMAIL.PREVIEW (instructions in template)
PL, UMGR | Brief DA – only if necessary; controversial, complex, unusually challenging rulemaking
RGL | sends EMAIL.PREVIEW to: -Director, DA, Leadership Team, EQCC -Cc… all contributing and affected staff -saves Email.Preview .pdf to Rule_Development - 4- Notice | 2015-12-01
PL. RGL, UMGR | decide how to address any feedback from preview
PL | modifies documents as needed
RGL | verifies PROPOSED.RULES are still based on current compilation
PL | finalizes public documents with UMGR
UMGR | emails PL & RGL approval to move forward with NOTICE, PROPOSED.RULES & any SUPPORTING.DCUMENTS
RGL | saves email as Rule_Development ¦ 4-Notice ¦ MGR.APPROVAL.Notice.PDF
PL/RGL | drafts INVITATION.TO.COMMENT using information from approved NOTICE
RGL | establishes the following using Web Request:
External Web page
Online public comment form
University Student Comment Account - helpdesk request with PL & RGL co-owning account; CodeName = “Alias”
compares work products to earlier reviews to determine need for additional edits
obtains additional Rule Publication edits on changes if needed
verifies/clarifies additional edits with PL & UMGR as warranted
notifies UMGR & PL when finished
sets Outlook auto reply - instructions in Rulemaking Manual
Notifications
RGL/PL | draft newspaper ads; designate newspapers ADS are not always required. They are only required for SIP rulemakings (40 CFR 51.102) - notice 30 days before hearing - ("notice given to the public by prominent advertisement in the area affected, announcing the dates, times, and places of such hearings"); or for rules that affect a specified gegraphical area. | 2015-11-19
PL | COMPLETES FINAL REVIEW OF ALL DOCUMENTS FOR PUBLICATION | 2015-12-08
| send web request to create rulemaking, comment web pages | 2015-12-04
RGL | drafts EMAIL.NOTICE.TO.KEY.LEGISLATORS - instructions in template
sends draft to Leg.Liason
Leg. Liason | determines key legislators requiring ORS 183.335(5) notification
RGL | adapts email as needed
RGL | leads:
| submitting newspaper notices to contractor (14 days before filing notice- min. 30 days before hearing) | 2015-12-01
verifying newspaper advertisements are correct
obtaining copies of affidavits of publication from Accounting
adding hearings to DEQ Event Calendar
creating an auto reply to Outlook account for University students
validating Web page, comment form and Outlook account
| if no advisory committee, submit web request for rulemaking and comment web page | 2015-12-01
PL | submits Notice to EPA, if required
RGL | submits notice to SOS for publication in Oregon Bulletin (not later than 15th of the month for publication the following month) | 2015-12-15
emails DAS notification of fees that don't require DAS approval
saves all evidence on Rule_Development ¦ 4-Notice using naming convention
opens public comment by notifying agency rulemaking list that includes:
GovDelivery
EQCC
advisory committee
program-specific lists
DEQ communications - publications and social media
saves all evidence, lists and affidavits on Rule_Development ¦ 4 Notice
RGL | emails Key Legislators with Return Receipt (redirects receipt to PL)
copies PL
saves receipts under Rule_Development¦4-Notice
RGL & WebRep | maintain Rukemaking Web page
PL | gathers and saves all emails on Rule_Development¦4-Notice using naming conventions
Public Comment and Testimony
Review version history to help maintaining rulemaking record
SAVE DOCUMENTS ON: SharePoint Topic: Public Notice
RGL | meets with PL and Hearings Officers to discuss hearing procedures
| If hearing after hours at DEQ HQ, request guard using Guard Request Procedure | 2016-02-01
PL | verifies venues and equipment, gathers supplies
develops INFO.MEETING.TEXT
modifies MESSAGE.MAP
develops INFO.PRESENTATION
practices presentation
makes presentation adjustments
initiates UMGR review/approval, addresses suggestions
UMGR | reviews/approves optional presentation
Hearings Officers
reviews responsibilities of hearings officer
develops introductory and logistics script
holds the following hearings (identified under Planning section) with assigned team
Hearing 1 | Location, Time | 2016-01-18
save audio as Rule_Development¦5-PublicComment¦HEARING.1.mp3
PL | for comments received by mail or at hearings:
stamps DEQ receipt date on address-side of envelope and on first page of letter
adds commenter and comment to COMMENTS
scans mailed comments and envelopes and saves as ID###.pdf
| PUBLIC COMMENT CLOSES | 2016-01-21
RGL | downloads online public comments to Excel, Codename.public.comment; save in Development ¦ Public Comment and Testimony
Downloads email comments from student email box to Excel; Codename.student.comment; save in Development ¦ Public Comment and Testimony
PL | coordinates with team to:
develop category titles to bundle similar comments
organize comments into categories
draft DEQ responses to each categories of comments
leads team work finalizing DEQ responses to public comment
DO NOT MAIL TO COMMENTERS UNTIL EQC ASSISTANT FINALIZES STAFF REPORT
PL | asks RGL for Rule Publication review
RGL | coordinates Rule Publication work:
edits for plain English, style guide & tone because this is part of EQC packet
contacts PL with questions, clarifications and suggestions
notifies PL when complete
PL | shares comments/responses to comments with UMGR & DA
team modifies responses to get to approval
PL
gathers emails ABOUT comments, not actual comments, for Rule Record
saves them as Rule_Development¦5-PublicComment...¦EMAIL.Comment.pdf
EQC Preparation
Review version history to help maintaining rulemaking record
SAVE DOCUMENTS ON: SharePoint TopicL EQC Preparation
PL
finalizes EQC Packet with core team:
codename.staff.rpt
codename.rules
SUPPORTING.DOCUMENTS
notifies RGL that EQC packet is ready for Rule Publication
RGL | leads initial Rule Publication work that includes:
comparing NOTICE to STAFF.REPORT to determine what needs review
obtaining/consolidating Communications, EQC Coordinator, SIP Coordinator edits, including style guide, grammar, plain English, organization
accepting all style guide and format edits
getting ARC review of PROPOSED.RULES- SOS/LC and CHECKLIST review
contacts PL with questions or modifications and when work is complete
PL
addresses rule publication edits and comments
prepares EQC packet
| initiates management review and approval: UMGR and DA | 2016-04-22
| obtains approval from UMGR to submit EQC packet | 2016-04-29
discusses need for 1¦1 commissioners briefings with UMGR/DA/EQCC
PL | COMPLETES FINAL VERSION OF ALL DOCUMENTS | 2016-04-29
| submits EQC packet to EQCC (5 weeks before EQC) | 2016-05-06
notifies the following according to division's standard practice:
· staff contributors
· key stakeholders
· advisory committee members
· commenters
· interested parties (optional)
leads team development of EQC presentation
coordinates presentation practices
makes any presentation adjustments
Presentation team | ATTENDS EQC MEETING | 2016-06-10
PL | saves emails about EQC preparations for Rule Record in Rule_Development¦6-EQCPreparation¦EMAILS.EQC.Prep.pdf
Post EQC
Review version history to help maintaining rulemaking record
Document Preparation
RGL | saves following documents to 7.PostEQC folder on Rule_Develpment:
gets documents as presented to EQC from EQC Coordinator
STAFF.REPORT.pdf
STAFF.REPORT.ADDENDUM.pdf (if presented to EQC)
downloads documents as presented to EQC from SharePoint:
PROPOSED.RULES (showing changes)
saves as REDLINE.docx (showing changes in strikethrough and
saves as RULES.docx (clean version), accepts all changes, saves again
TABLES.340-###-####.docx (1 .docx per rule contains ALL tables)
coordinates EPA.SIP.SUBMITAL with SIP Coordinator
Filing
DEADLINE: No Oregon deadline for filing rules after adoption - check EPA
ARC
logs onto Secretary of State online filing form
uses information in STAFF.REPORT & ADDENDUM to populate form
reviews, prepares and uploads:
RULES.docx (clean version in Word)
TABLES.340-###-####-SOS.pdf (1 .docx per rule contains ALL tables
develops, scans and uploads AUTHORIZATION-SOS.pdf into online SOS form
completes SOS form, verifies and submits
Filed Date
Effective Date
ARC | saves certificate that SOS sent via email as CERTIFICATE-SOS.pdf
notes sequence for Certificate and Administrative Order No.
submits Web request to update Web page
moves share drive folder system:
FROM: \\deqhq1\Rule_Development\Current
TO: \\deqhq1\Rule_Development\Filed
Legislative Counsel Notification
DEADLINE | LC must receive notification within 10 days after CERTIFICATE date
DEQ PRACTICE | Put in shuttle on day of SOS filing
ARC
prepares Legislative Counsel notification - see Rulemaking Manual:
prints | CERTIFICATE and saves copy as CERTIFICATE-LC.pdf
prints | REDLINE and saves copy as REDLINE-LC.pdf
self-addressed envelope, fold underside of flap over a 2nd certificate
write "Please date stamp certificate and return." on underside of flap
prepares/scans return receipt shuttle envelope, saves as SHUTTLE.RECEIPT-LC.pdf
sends via shuttle
sends Procurement a scanned image of SHUTTLE.RECEIPT-LC
DAS FEE APPROVAL - PART 2
DEADLINE | DEQ must send notification or DAS Part 2 within 10 days of EQC action
PL
gets signatures on Part 2 of signed DAS Fee Approval
scans/saves as DAS.PART2.pdf
excerpts fee sections from RULES, saves as FEE.RULES-DAS, print
excerpts fee sections from STAFF.REPORT, saves as FEE.REPORT-DAS, print
emails PART2-DAS.pdf to DAS (requests delivery receipt)
get preprinted return receipt shuttle envelope from ARC
prepares/scans shuttle envelope, saves as SHUTTLE.RECEIPT-DAS.pdf
sends all fee documents to DAS via shuttle
sends Procurement a scanned image of SHUTTLE.RECEIPT-DAS
Closing Records and Archival
RGL
verifies Web page is current and accurate
coordinates meeting to discuss lessons learned
ensures the final version of every document on SharePoint is Major (Published)
verifies Outlook student comment account is empty/asks helpdesk to close account
leads verification that published rules in Oregon Bulletin are correct
If errors, PL works with ARC to correct and selects
SIPC | submits SIP to EPA within 60 days AFTER adoption
emails optional STAKEHOLDER.NOTIFICATION that links to Web page
coordinates AC.THANK.YOU email or letter that links to Web page
scans physical records and save to Rule_Development
gathers emails about post EQC activities for the Rule Record and saves as: Rule_Development ¦ 7-PostEQC ¦ EMAILS.PostEQC.pdf
ARC
coordinates moving major versions from SharePoint to Rule_Development
coordinates closing SharePoint sub-site
archives folders when record is complete by moving:
FROM: \\deqhq1\Rule_Development
TO: \\deqhq1\Rule_Archives
Save copy of rulemaking Home Page as .mht file in "Web Pages" folder in this rulemaking's folder in the Rulemaking Development drive.
coordinates retiring Q-Time number(s) with BudgetAnalyst
Formulas:
Suggested Dates = [Suggested Dates, row above]+17
Suggested Dates = [Suggested Dates, row below]-35

## Tasks summary
Person | Action | __Suggested Dates_ ¦ Start ¦ End | __Amended Dates__ ¦ Start ¦ End
TitleVCPI2016
Abbreviations
ARC | Agency Rules Coordinator
DA | Division Administrator
EQCC | EQC Coordinator
PL | Program Lead
RGL | Rules Group Lead
SIPC | SIP Coordinator
UMGR | Unit Manager
SP | SharePoint
Director | DEQ Director
Overview of Key Dates
PL | Notice Packet due to RGL and UMGR for review | 2016-12-02
PL | Notice Packet due to DA and Communications for review | 2016-12-09
RGL | File notice with SOS/open comment period | 2016-12-15
| Notice Published in Oregon Bulletin (DEQ standard 90 days before EQC) | 2016-01-01
PL | first public hearing - at least 30 days AFTER comment opens; DEQ standard 16 days after Bulletin Notice published | 2016-01-18
RGL/PL | close public comment - 3 days after hearing | 2016-01-21
PL | Staff report due to EQCC | 2016-05-06
| EQC Meeting | 2016-06-10
Schedule of Tasks
SIP
SIP Coord | Submit SIP development plan to EPA | 2015-06-20
| Submit draft rules and notice to EPA | 2015-11-02
| Submit adopted rules and SIP info to EPA | 2016-06-20
Fees
PL | Lead development of fee approval packet | 2015-09-18
| Obtain review of fee packet by UMGR and RGL | 2015-11-02
| Finalize fee packet | 2015-11-10
RGL | Submit Part I of fee packet to DAS | 2015-11-17
| Submit Part II of fee packet to DAS | 2016-06-15
Communications Planning
PL | schedules/facilitates meeting with team, Communications, Rules Group to discuss/determine need for: -communications plan -message map -newspaper ads -news release -social media -rulemaking/program web page -informational meetings | 2015-10-21
| Preplanning for Hearings (90 days before 1st hearing) | 2015-10-20
| Initial Rule Work (4 mos. Before filing notice) | 2015-08-20
RGL and PL | discuss requirements for EQC faciliated hearing
PL | coordinates with Team to:
· determine need for a crosswalk
· identify rules to amend or repeal
· identify new rules to adopt
· identify land use rules
· identify SIP rules, talk with SIP Coordinator
Advisory Committee (4 mos. before filing notice)
| Advisory Committee work session (120 days before meeting) | 2015-06-18
UMGR | approves deliverables including AC.ROSTER (97 days before meeting) | 2015-07-18
UMGR, PL, RGL | emails AC.MEMBER.INVITATION with links and instructions (60) days before meeting) | 2015-08-17
PL | SUBMIT FINAL VERSION OF ALL DOCUMENTS FOR PUBLICATION | 2015-09-25
RGL, PL | send web request to create rulemaking, advisory committee web pages | 2015-10-02
| emails AC.EQC.INVITATION to sign up for Advisory Committee (min. 14 days before meeting) | 2015-10-02
RGL | sends AC.AFFECTED.PARTIES.INVITATION to GovDelivery topic (min. 14 days before meeting) | 2015-10-02
| Advisory Committee meeting (min. 60 days before filing notice) | 2015-10-16
| Public Notice - not required for temporary rules (begin 90 days before filing notice) | 2015-09-16
PL | begin drafting rules and notice
asks DA Assistant to schedule future time on DA Schedule for reviewing notice package
schedules time on UMGR calendar to review Notice Package
Rule Publication Work
PL | forwards notice package to UMGR for review (6 weeks before filing notice) | 2015-11-03
PL | on UMGR approval, forwards notice package to DA for review
Preview Period (leadership review) - 5-7 days
RGL | sends EMAIL.PREVIEW to: -Director, DA, Leadership Team, EQCC -Cc… all contributing and affected staff -saves Email.Preview .pdf to Rule_Development - 4- Notice | 2015-12-01
Notifications
RGL/PL | draft newspaper ads | 2015-11-19
RGL | send web request to create rulemaking, comment web pages | 2015-11-19
RGL | submit newspaper notices to contractor (14 days before filing notice- min. 30 days before hearing) | 2015-12-01
PL | COMPLETE FINAL REVIEW OF ALL DOCUMENTS FOR PUBLICATION | 2015-12-08
RGL | submits notice to SOS for publication in Oregon Bulletin (not later than 15th of the month for publication the following month) | 2015-12-15
Public Comment and Testimony
PL | Public hearing | 2016-01-18
| Public Comment Closes | 2016-01-21
EQC Preparation
PL | initiates management review and approval: UMGR and DA | 2016-04-22
PL | obtains approval from UMGR to submit EQC packet | 2016-04-29
discusses need for 1¦1 commissioners briefings with UMGR/DA/EQCC
PL | COMPLETES FINAL VERSION OF ALL DOCUMENTS | 2016-04-29
PL/RGL | submits EQC packet to EQCC (5 weeks before EQC) | 2016-05-06
PL | EQC meeting | 2016-06-10

## Schedule summary
Person | Action | __Suggested Dates_ ¦ Start ¦ End | __Amended Dates__ ¦ Start ¦ End
CodeName: (abbreviated name)
Abbreviations
ARC | Agency Rules Coordinator
DA | Division Administrator
EQCC | EQC Coordinator
PL | Program Lead
RGL | Rules Group Lead
SIPC | SIP Coordinator
UMGR | Unit Manager
SP | SharePoint
Director | DEQ Director
Overview of Key Dates
PL | Notice Packet due to RGL and UMGR for review | 2016-12-02
PL | Notice Packet due to DA and Communications for review | 2016-12-09
RGL | File notice with SOS/open comment period | 2016-12-15
RGL | Notice Published in Oregon Bulletin (DEQ standard 90 days before EQC) | 2016-01-01
PL | first public hearing - at least 30 days AFTER comment opens; DEQ standard 16 days after Bulletin Notice published | 2016-01-18
RGL/PL | close public comment - 3 days after hearing | 2016-01-21
PL | Staff report due to EQCC | 2016-05-06
| EQC Meeting | 2016-06-10
Chronological List
SIP
SIP Coord | Submit SIP development plan to EPA | 0
| Submit draft rules and notice to EPA | 2015-06-20
| Submit adopted rules and SIP info to EPA | 2015-11-02
Fees
PL | Lead development of fee approval packet | 2015-09-18
| Obtain review of fee packet by UMGR and RGL | 2015-09-18
| Finalize fee packet | 2015-11-02
RGL | Submit Part I of fee packet to DAS | 2015-11-10
| Submit Part II of fee packet to DAS | 2015-11-17
PL/RGL | Advisory Committee -work session (120 days before meeting) | 2015-06-18
UMGR | approves AC deliverables including AC.ROSTER (97 days before meeting) | 2015-07-18
UMGR, PL, RGL | emails AC.MEMBER.INVITATION with links and instructions (60) days before meeting) | 2015-08-17
PL | Communications Planning: schedules/facilitates meeting with team, Communications, Rules Group to discuss/determine need for: -communications plan -message map -newspaper ads -news release -social media -rulemaking/program web page -informational meetings | 2015-10-21
RGL and PL | Start rule writing -4 mos. before filing notice discuss requirements for EQC faciliated hearing | 2015-08-20
PL | coordinates with Team to:
· determine need for a crosswalk
· identify rules to amend or repeal
· identify new rules to adopt
· identify land use rules
· identify SIP rules, talk with SIP Coordinator
| Public Notice -not required for temporary rules -begin 90 days before filing notice | 2015-09-16
PL | begin drafting rules and notice
PL | asks DA Assistant to schedule future time on DA Schedule for reviewing notice package
PL | schedules time on UMGR calendar to review Notice Package
RGL, PL | send web request to create rulemaking, advisory committee web pages | 2015-10-02
| SUBMIT FINAL VERSIONS OF ALL DOCUMENTS FOR PUBLICATION | 2015-09-25
RGL | emails AC.EQC.INVITATION to sign up for Advisory Committee (min. 14 days before meeting) | 2015-10-02
RGL | sends AC.AFFECTED.PARTIES.INVITATION to GovDelivery topic (min. 14 days before meeting) | 2015-10-02
PL | Advisory Committee meeting (min. 60 days before filing notice) | 2015-10-16
Fee Approval Packet, with team and BudgetAnalyst
PL/RGL | Preplanning for Hearings (90 days before 1st hearing) | 2015-10-20
PL | forwards notice package to UMGR for review (6 weeks before filing notice) | 2015-11-03
PL | on UMGR approval, forwards notice package to DA for review
RGL/PL | draft newspaper ads | 2015-11-19
RGL | send web request to create rulemaking, comment web pages | 2015-11-19
RGL | submit newspaper notices to contractor (14 days before filing notice- min. 30 days before hearing) | 2015-12-01
RGL | Preview Period: (leadership review) - 5-7 days sends EMAIL.PREVIEW to: -Director, DA, Leadership Team, EQCC -Cc… all contributing and affected staff -saves Email.Preview .pdf to Rule_Development - 4- Notice | 2015-12-01
PL | COMPLETE FINAL REVIEW OF ALL DOCUMENTS FOR PUBLICATION | 2015-12-08
RGL | submits notice to SOS for publication in Oregon Bulletin (not later than 15th of the month for publication the following month) | 2015-12-15
PL | Public hearing | 2016-01-18
RGL | close public comment | 2016-01-21
PL | Staff report - initiates management review and approval: UMGR and DA | 2016-04-22
PL | obtains approval from UMGR to submit EQC packet | 2016-04-29
PL | discusses need for 1¦1 commissioners briefings with UMGR/DA/EQCC
PL | COMPLETE FINAL VERSION OF ALL DOCUMENTS | 2016-04-29
PL/RGL | submits EQC packet to EQCC (5 weeks before EQC) | 2016-05-06
PL | EQC meeting | 2016-06-10

## main sharepoint
ID | Title | Location | Start Time | End Time | Description | All Day Event | Recurrence | Workspace | Category | Resources | Free/Busy | Check Double Booking | Comments | URL | Attachments | Attendees
| Title V CPI 2016 |  | 2015-06-18 | 2015-06-18 | Advisory Committee -work session (120 days before meeting) | TRUE
| Title V CPI 2016 |  | 2015-07-18 | 2015-07-18 | approves AC deliverables including AC.ROSTER (97 days before meeting) | TRUE
| Title V CPI 2016 |  | 2015-08-17 | 2015-08-17 | emails AC.MEMBER.INVITATION with links and instructions (60) days before meeting) | TRUE
| Title V CPI 2016 |  | 2015-10-21 | 2015-10-21 | Communications Planning: schedules/facilitates meeting with team, Communications, Rules Group to discuss/determine need for: -communications plan -message map -newspaper ads -news release -social media -rulemaking/program web page -informational meetings | TRUE
| Title V CPI 2016 |  | 2015-08-20 | 2015-08-20 | Start rule writing -4 mos. before filing notice discuss requirements for EQC faciliated hearing | TRUE
| Title V CPI 2016 |  | #REF! | #REF! | SIP - submit rule package to EPA (at least 90 days before notice) | TRUE
| Title V CPI 2016 |  | 2015-09-16 | 2015-09-16 | Public Notice -not required for temporary rules -begin 90 days before filing notice | TRUE
| Title V CPI 2016 |  | 2015-10-02 | 2015-10-02 | send web request to create rulemaking, advisory committee web pages | TRUE
| Title V CPI 2016 |  | 2015-10-02 | 2015-10-02 | emails AC.EQC.INVITATION to sign up for Advisory Committee (min. 14 days before meeting) | TRUE
| Title V CPI 2016 |  | 2015-10-02 | 2015-10-02 | sends AC.AFFECTED.PARTIES.INVITATION to GovDelivery topic (min. 14 days before meeting) | TRUE
| xxxx |  | 2015-09-25 | 2015-09-25 | SUBMIT FINAL VERSIONS OF ALL DOCUMENTS FOR PUBLICATION | TRUE
| Title V CPI 2016 |  | 2015-10-16 | 2015-10-16 | Advisory Committee meeting (min. 60 days before filing notice) | TRUE
| Title V CPI 2016 |  | #REF! | #REF! | Fees - leads development of: | TRUE
| Title V CPI 2016 |  | 2015-10-20 | 2015-10-20 | Preplanning for Hearings (90 days before 1st hearing) | TRUE
| Title V CPI 2016 |  | #REF! | #REF! | initiates UMGR Fee Approval Packet review, addresses suggestions | TRUE
| Title V CPI 2016 |  | 2015-11-03 | 2015-11-03 | forwards notice package to UMGR for review (6 weeks before filing notice) | TRUE
| Title V CPI 2016 |  | #REF! | #REF! | sends EMAIL.DAS.APPROVAL with Fee Approval Packet attached (30 days before filing notice) | TRUE
| Title V CPI 2016 |  | 2015-11-19 | 2015-11-19 | draft newspaper ads | TRUE
| Title V CPI 2016 |  | 2015-11-19 | 2015-11-19 | send web request to create rulemaking, comment web pages | TRUE
| Title V CPI 2016 |  | 2015-12-01 | 2015-12-01 | submit newspaper notices to contractor (14 days before filing notice- min. 30 days before hearing) | TRUE
| Title V CPI 2016 |  | 2015-12-01 | 2015-12-01 | Preview Period: (leadership review) - 5-7 days sends EMAIL.PREVIEW to: -Director, DA, Leadership Team, EQCC -Cc… all contributing and affected staff -saves Email.Preview .pdf to Rule_Development - 4- Notice | TRUE
|  |  | 2015-12-08 | 2015-12-08 | COMPLETE FINAL REVIEW OF ALL DOCUMENTS FOR PUBLICATION
| Title V CPI 2016 |  | 2015-12-15 | 2015-12-15 | submits notice to SOS for publication in Oregon Bulletin (not later than 15th of the month for publication the following month) | TRUE
| Title V CPI 2016 |  | 2016-01-01 | 2016-01-01 | Notice published in Oregon Bulletin
| Title V CPI 2016 |  | 2016-01-18 | 2016-01-18 | Public hearing | TRUE
| Title V CPI 2016 |  | 2016-01-21 | 2016-01-21 | close public comment | TRUE
| Title V CPI 2016 |  | 2016-04-22 | 2016-04-22 | Staff report - initiates management review and approval: UMGR and DA | TRUE
| Title V CPI 2016 |  | 2016-04-29 | 2016-04-29 | obtains approval from UMGR to submit EQC packet | TRUE
|  |  | 2016-04-29 | 2016-04-29 | COMPLETE FINAL VERSION OF ALL DOCUMENTS
| Title V CPI 2016 |  | 2016-05-06 | 2016-05-06 | submits EQC packet to EQCC (5 weeks before EQC) | TRUE
| Title V CPI 2016 |  | 2016-06-10 | 2016-06-10 | EQC meeting | TRUE
| xxxx |  | 2015-06-20 | 2015-06-20 | Submit SIP development plan to EPA | TRUE
| xxxx |  | 2015-11-02 | 2015-11-02 | Submit draft rules and notice to EPA | TRUE
| xxxx |  | 2016-06-20 |  | Submit adopted rules and SIP docs to EPA | TRUE
| xxxx |  | 2015-09-18 | 2015-09-18 | Lead development of Fee approval packet | TRUE
| xxxx |  | 2015-11-02 | 2015-11-02 | Obtain UMGR and RGL review of fee packet | TRUE
| xxxx |  | 2015-11-10 | 2015-11-10 | Finalize fee packet | TRUE
| xxxx |  | 2015-11-17 | 2015-11-17 | Submit fee packet Part I to DAS | TRUE
| xxxx |  | 2016-06-15 | 2016-06-15 | Submit fee packet Part II to DAS | TRUE

## ind SP
ID | Title | Location | Start Time | End Time | Description | All Day Event | Recurrence | Workspace | Category | Resources | Free/Busy | Check Double Booking | Attachments | Attendees
| SIP - submit SIP development plan to EPA (6 mos. before notice) |  | #REF! | #REF! |  | TRUE
| Advisory Committee -work session (120 days before meeting) |  | 2015-06-18 | 2015-06-18 |  | TRUE
| approves AC deliverables including AC.ROSTER (97 days before meeting) |  | 2015-07-18 | 2015-07-18 |  | TRUE
| emails AC.MEMBER.INVITATION with links and instructions (60) days before meeting) |  | 2015-08-17 | 2015-08-17 |  | TRUE
| Communications Planning: schedules/facilitates meeting with team, Communications, Rules Group to discuss/determine need for: -communications plan -message map -newspaper ads -news release -social media -rulemaking/program web page -informational meetings |  | 2015-10-21 | 2015-10-21 |  | TRUE
| Start rule writing -4 mos. before filing notice discuss requirements for EQC faciliated hearing |  | 2015-08-20 | 2015-08-20 |  | TRUE
| SIP - submit rule package to EPA (at least 90 days before notice) |  | #REF! | #REF! |  | TRUE
| Public Notice -not required for temporary rules -begin 90 days before filing notice |  | 2015-09-16 | 2015-09-16 |  | TRUE
| SUBMIT FINAL VERSION OF ALL DOCUMENTS FOR PUBLICATION |  | 2015-09-25 | 2015-09-25 |  | TRUE
| send web request to create rulemaking, advisory committee web pages |  | 2015-10-02 | 2015-10-02 |  | TRUE
| emails AC.EQC.INVITATION to sign up for Advisory Committee (min. 14 days before meeting) |  | 2015-10-02 | 2015-10-02 |  | TRUE
| sends AC.AFFECTED.PARTIES.INVITATION to GovDelivery topic (min. 14 days before meeting) |  | 2015-10-02 | 2015-10-02 |  | TRUE
| Advisory Committee meeting (min. 60 days before filing notice) |  | 2015-10-16 | 2015-10-16 |  | TRUE
| Fees - leads development of: |  | #REF! | #REF! |  | TRUE
| Preplanning for Hearings (90 days before 1st hearing) |  | 2015-10-20 | 2015-10-20 |  | TRUE
| initiates UMGR Fee Approval Packet review, addresses suggestions |  | #REF! | #REF! |  | TRUE
| forwards notice package to UMGR for review (6 weeks before filing notice) |  | 2015-11-03 | 2015-11-03 |  | TRUE
| sends EMAIL.DAS.APPROVAL with Fee Approval Packet attached (30 days before filing notice) |  | #REF! | #REF! |  | TRUE
| draft newspaper ads |  | 2015-11-19 | 2015-11-19 |  | TRUE
| send web request to create rulemaking, comment web pages |  | 2015-11-19 | 2015-11-19 |  | TRUE
| submit newspaper notices to contractor (14 days before filing notice- min. 30 days before hearing) |  | 2015-12-01 | 2015-12-01 |  | TRUE
| Preview Period: (leadership review) - 5-7 days sends EMAIL.PREVIEW to: -Director, DA, Leadership Team, EQCC -Cc… all contributing and affected staff -saves Email.Preview .pdf to Rule_Development - 4- Notice |  | 2015-12-01 | 2015-12-01 |  | TRUE
| COMPLETE FINAL REVIEW OF ALL DOCUMENTS FOR PUBLICATION |  | 2015-12-08 | 2015-12-08 |  | TRUE
| submits notice to SOS for publication in Oregon Bulletin (not later than 15th of the month for publication the following month) |  | 2015-12-15 | 2015-12-15 |  | TRUE
| Notice published in Oregon Bulletin |  | 2016-01-01 | 2016-01-01
| Public hearing |  | 2016-01-18 | 2016-01-18 |  | TRUE
| close public comment |  | 2016-01-21 | 2016-01-21 |  | TRUE
| Staff report - initiates management review and approval: UMGR and DA |  | 2016-04-22 | 2016-04-22 |  | TRUE
| obtains approval from UMGR to submit EQC packet |  | 2016-04-29 | 2016-04-29 |  | TRUE
| COMPLETE FINAL REVIEW OF ALL DOCUMENTS |  | 2016-04-29 | 2016-04-29 |  | TRUE
| submits EQC packet to EQCC (5 weeks before EQC) |  | 2016-05-06 | 2016-05-06 |  | TRUE
| EQC meeting |  | 2016-06-10 | 2016-06-10 |  | TRUE
| Submit SIP development plan to EPA |  | 2015-06-20 | 2015-06-20 |  | TRUE
| Submit draft rules and notice to Epa |  | 2015-11-02 | 2015-11-02 |  | TRUE
| Submit adopted rules and SIP docs to EPA |  | 2016-06-20 | 2016-06-20 |  | TRUE
| Lead development of fee approval packet |  | 2015-09-18 | 2015-09-18 |  | TRUE
| Obtain review of UMGR and RGL review of fee packet |  | 2015-11-02 | 2015-11-02 |  | TRUE
| Finalize fee packet |  | 2015-11-10 | 2015-11-10 |  | TRUE
| Submit fee Packet Part I to DAS |  | 2015-11-17 | 2015-11-17 |  | TRUE
| Submit fee packet part II to DAS |  | 2016-06-15 | 2016-06-15 |  | TRUE