| ARC – Agency rules coordinator COM – Communications DA – Division administrator PL – Program lead PMGR – Program manager |  |  |  |
| --- | --- | --- | --- |
| Person | Task | Instructions | Date |
| - PL | - Begin drafting EQC staff report | Develops response to comments by: - Organizing comments into categories - Developing one response to each category of comments - Obtains PMGR and RGL review of draft responses - Draft EQC staff report - Copy and paste applicable sections from Public - Notice into staff report - Check to ensure language from Public Notice is still accurate and properly reflects timing of future/past events - Edit rules as necessary - Ask RGL for publication review | November 2016 |
|  | - Submit EQC Packet to DEQ | LRAPA | November 2016 |
| - PL | - Complete draft staff report | Finalize proofing of EQC documents: - Staff report - Rules - Supporting documents - Notify RGL staff report is ready for review | November 22, 2016 |
| - ARC | - Review staff report, notify PL when complete | Lead initial Rule Publication work that includes: - Prepare two versions of rules: - redline/strikethrough - clean - Review, consolidate, approve or reject all proposed edits - Compare Notice with Staff Report for accuracy to check that language correctly reflects timing of future/past events - Notify PL review is complete | November 25, 2016 |
| - PL | - Finalize EQC staff report (9 weeks before EQC) | - Address reviewer edits and comments - Notify PMGR staff report is ready for review | November 28, 2016 |
| - PMGR | - Completes review and emails approval to PL |  | December 1, 2016 |
| - PL | - On PMGR approval ,notify DA documents are ready for review |  |  |
| - DA | - Completes review and emails approval to PL PMGR RGL |  | December 4, 2016 |
| - PL | - On DA approval, notify communications documents are ready for review |  |  |
| - COM | - Completes review and emails approval to PL PMGR RGL (6 weeks before EQC) |  | December 7, 2016 |
| - PL | - Deadline to submit final version of all EQC documents (6 weeks before EQC) |  | December 7, 2016 |
| - ARC | - Distribute EQC staff report and prepare rules for filing | - Submits EQC packet to EQCC (EQC-5 weeks) - Retain one copy of rules in redline/strikethrough for filing with legislative counsel - Create a clean copy of the rules, with tables, to keep for informational purposes - add a DRAFT watermark - Staff report should have two copies of rules - one showing all markup, one with DRAFT watermark with all changes accepted - Remove tables from another copy of the rules, and accept all changes to get a clean copy of the rules to file with secretary of state - Create pdf version of tables, one document for each rule that has a table, to submit to secretary of state - Complete draft version (do not submit) of secretary of state online filing system using information from staff report and draft rules - On SharePoint, publish a major version of: - rules - staff report - Save PDF of published staff report to Rule_Development - Upload copy of EQC presentation materials to SharePoint | December 14, 2016 |
| - PL | - (Optional) Notify interested parties staff report is available | Notify the following according to division's standard practice: - Key stakeholders - Advisory committee members - Commenters - Interested parties |  |
| - PL | - EQC Preparation | - Develop EQC presentation - Conduct dry run EQC presentation (in front of internal audience) |  |
| - PL | - Present rule package at EQC meeting |  | January 18, 2017 |
| - ARC |  | No Oregon deadline for filing rules after adoption – check EPA |  |
| - ARC | - File adopted rules with Secretary of State | - Check information in secretary of state online rule filing form against most recent information in staff report and draft rules - Submit/file rules on secretary of state online system - Must print out, sign, scan, then upload to SOS filing page, copy of Authorization - Upload rule text as Word file - Upload tables separately as pdf, one for each rule that has tables - SOS will auto email two documents in response in two separate emails: - Certificate - Authorization - Save the emails and attached documents as PDF to Rule_Development | January 21, 2017 |
| - ARC | - Send post-EQC GovDelivery notice about rule adoption | - Template in EQC Preparation folder - RGL sends GovDelivery notice to same parties that prior notices for this rulemaking were sent to - This notice states EQC adopted the rules and explains where to find copies of EQC staff report and adopted rules | January 21, 2017 |
| - ARC | - Submits SIP to EPA |  | January 25, 2017 |