| Person | Task | Instructions | Date |
| --- | --- | --- | --- |
| PL | Begin drafting EQC staff report | Notify Program Manager, Division Administrator, Communications, of dates below when they will receive documents to review -Develops response to comments by:  Organizing comments into categories  Developing one response to each category of comments  Obtains PMGR and RGL review of draft responses  Draft EQC staff report  Copy and paste applicable sections from Public Notice into staff report  Check to ensure language from Public Notice is still accurate and properly reflects timing of future/past events  Edit rules as necessary  Ask RGL for publication review | 5/15/18 |
| PL | Complete draft staff report | Finalize proofing of EQC documents:  Staff report  Rules  Supporting documents  Notify RGL staff report is ready for review | 6/24/18 |
| RGL | Preliminary staff report review |  Prepare two versions of rules:  redline/strikethrough  clean  Compare Notice with Staff Report for accuracy to check that language correctly reflects timing of future/past events | 6/26/18 |
| PL | Send document links to PMGR for review |  | 6/28/18 |
| PMGR | Completes review and emails approval to PL | PMGR allowed one week to complete review | 7/5/2018 |
| PL | On PMGR approval, provide document links to DA for review |  | 7/5/2018 |
| DA | Completes review and emails approval to PL PMGR RGL | DA allowed two calendar weeks to complete review | 7/19/2018 |
| PL | On DA approval, provide document links to communications for review |  | 7/19/2018 |
| COM | completes review and emails approval to PL PMGR RGL | Communications allowed one calendar week to complete review | 7/26/2018 |
| RGL | begins review | one week to complete review | 7/26/2018 |
| RGL | Completes review |  | 8/2/2018 |
| PL/PMGR | (optional) discusses need for 1 on 1 commissioners briefings |  |  |
| PL | DEADLINE TO SUBMIT FINAL VERSION OF ALL EQC DOCUMENTS | 6 weeks before EQC | 8/10/2018 |
| RGL | Distribute EQC staff report and prepare rules for filing |  Submits EQC packet to EQCC (EQC-5 weeks)  Retain one copy of rules in redline/strikethrough for filing with legislative counsel  Create a clean copy of the rules, with tables, to keep for informational purposes - add a DRAFT watermark  Staff report should have two copies of rules - one showing all markup, one with DRAFT watermark with all changes accepted  Remove tables from another copy of the rules, and accept all changes to get a clean copy of the rules to file with secretary of state  Create pdf version of tables, one document for each rule that has a table, to submit to secretary of state  Complete draft version (do not submit) of secretary of state online filing system using information from staff report and draft rules  On SharePoint, publish a major version of:  rules  staff report  Save PDF of published staff report to Rule_Development  Upload copy of EQC presentation materials to SharePoint | 8/9/2018 |
| PL | (Optional) Notify interested parties staff report is available | Notify the following according to division's standard practice:  Key stakeholders  Advisory committee members  Commenters  Interested parties |  |
| PL | EQC Preparation |  Develop EQC presentation  Conduct dry run EQC presentation (in front of internal audience) |  |
| PL | Present rule package at EQC MEETING |  | 9/13/2018 |