Date:

CPP Community/City:

Administrator:

Email:                                                            Phone:

*     *     *    *    *     *     *     *     *     *     *

Year-End CPP Project Report

Dear CPP Project Manager:

Please use the below to report on the status of your project for which you received 2013/2014 Community Partnership Program (CPP) Grant Funding. This entire form constitutes the report.  Please provide responds to each question.  Year-end reporting was a condition to receiving these funds.  Return reports to: Sadie Cramer at cityrecorder@cityofmolalla.com by July 8, 2014

If your project/event wasn’t originally scheduled to be completed until after June 30, 2014, please provide a status report as of June 30.  Final performance and ROI information can be sent at a later date.  Extensions are available for extenuating circumstances only.  Contact your local CPP Administrator if you think you will need one. Requests are forwarded on to Clackamas County Tourism and Cultural Affairs (CCTCA) for consideration.   These must be received by CCTCA by June 16. Please contact Sadie Cramer at cityrecorder@cityofmolalla.com if you have questions.

Date: June 30, 2014

Name of project: Rodeo Walk of Fame

Submitted by: City of Molalla

The purpose of the Community Partnership Program is to support projects that can 1) increase overnight stays in lodging facilities within Clackamas County, 2) bring visitors in from outside your community to recreate, shop, dine or take in the arts, cultural or historic offerings, and/or 3) entice visitors to linger longer.  Please be mindful of these points as you complete this form.

Funds Provided through CPP: $ 10,500                		Project Total Costs: $24,000

- How were the funds used?  Please use the below template to report each expense.  Cells will expand to accommodate additional text.  Copy and paste additional lines as needed.

| Supplier | Expense Description | Amount |
| --- | --- | --- |
| Phat GFX | Rodeo Walk of Fame (RWF) Welcome Sign | 159.39 |
| KB Line | Coins/Geocache | 1,616.00 |
| T.E.A.M. | Rodeo Plaques/Starter Plaque | 6,000.00 |
| City of Molalla | Labor/Coordination/plaque installation | 750.00 |
| Superior Foundation | Concrete | 2,000.00 |

(Needs to equal your grant award)                   Total   10,525.39

- What would you say was the most successful element of the project? The fact that certain entities and people came together in Molalla and made a project happen that has historical significance. Sadie’s (administrator) expertise with the program and the overall goals that were set were made due to her willingness to help us and others who were granted funds achieve these positive community results.

- Do you anticipate seeking CPP funds for this project again next year? Yes

- What obstacles, if any, did you experience in executing the project? Making sure that the volunteer component met their timelines.

- How would you engineer around those in the future and/or what assistance would be helpful? We (City) would have set out more specific duties and timelines.

- How might you use funding support differently next year to recognize greater success? More advertising the construction of the project in the local paper.

- Did all expected partnerships and/or leveraged funds included in the application materialize? If not, why and what could be done to ensure they would in the future? Yes, all funding components came together to make the project work.

- How did actual return on investment (ROI) or project performance compare with what was projected in the application? The return has been positive – the public has been very supportive and interested in the final result.

- How could ROI/ performance be improved if the project is repeated next year? We would advertise early and set better timeline bench marks now that we know what to expect out of a project of this magnitude.

- From a tourism perspective, is there a better way to capture/measure ROI for this project? We will know more in the near future. The Geo Caching aspect of the project is going to be launched at the end of July. We expect all 300 coins to be collected within a 45 day. The info collected will help us determine the true ROI.

- How helpful did you find the program materials and/or what ideas do you have about how the program could be improved? Project materials were helpful. One needs to know and understand the community where the project is planned.

- How helpful did you find the program materials and/or what ideas do you have about how the program could be improved? It may be helpful to cross over fiscal years but may not be an option. I think the program is a positive infusion of “making things happen”.