Agenda

Oregon DEQ Oversight of Marquardt Brothers Garage Cleanup

(ODEQ Voluntary Letter Agreement 6462)

April 10, 2023

# Introductions

## City of Chiloquin

## DEQ

## CHA Consulting

# Goals

## ODEQ Comment on Phase I & II ESAs

## Review Scope of Cleanup

## Establish DEQ Involvement & Closeout Requirements

# Scope of Cleanup

## Asbestos & Lead

## Abandon USTs in Place (up to 2) Due to Structural Concerns – UST Closure Sampling to be completed during Design Phase Investigation

## Remove 3 hydraulic Lifts and Appurtenances

## Remove and Properly Dispose of Hydraulic Reservoir in Vault (Newly discovered feature)

## Address Break/Oil Change Pit

## Universal Waste disposal (Fluorescent light Ballasts…)

# Overall Schedule

| Date | Task |
| --- | --- |
| May 10, 2023 | Public meeting Fact sheet/Presentation Status Assessment Fact sheet/Presentation Cleanup Program |
| June 2023 | Final CIP Cleanup |
| June 2023 | Draft QAPP for Design Phase Invest & Cleanup Design |
| July/Aug 2023 | Final QAPP for Design Phase Invest & Cleanup Design |
| Sept/Oct 2023 | Design Phase Investigation |
| Oct 2023 | Draft ABCA avail 30 days |
| November/December 2023 | Prepare Final ABCA |
| November 2023 – January 2024 | Draft Cleanup Design |
| March 2023 | Community Meeting – Upcoming cleanup work focus |
| March 2023 | Final Cleanup Design |
| March – April 2024 | Bid Process for Cleanup Contractor |
| May 2024 | Begin Cleanup activities |
| July 2024 | Complete Cleanup activities |
| August 2024 | Draft Closeout Report |
| Oct 2024 | Final Closeout report |

# Design Phase Investigation

## 4-6 Additional ACM Samples

## Remove Debris from Brake/Oil Change Pit Inspect for staining/discharge point/cracking

## Supplemental Geophysical Investigation/Physical Exploration of Secondary UST area

## Clean and Inspect newly discovered vault

## Install 4-8 supplemental boings with 3-4 temp wells

# DEQ Closeout Requirements

# Open Discussion