## PROGRESS PAYMENT NO. 1
PROGRESS PAYMENT
Project Name: | Well Field Control Building |  |  |  |  | Date of Application: |  | 2012-06-29
Project Nos: | CIP #707593
[6 empty] | Payment No: |  | 4
Resolution No: | [5 empty] | Invoice Date: | 2012-06-21 | (see attached invoice)
Purchase Order No: |  | 4133
[6 empty] | Pay Period: | Final Payment
The Contract was signed by City Manager on 02/21/ 2012 for $_44,227.35
[6 empty] | Contractor: | CR Woods Trucking Inc.
A copy of the Purchase Order is attached.
Application is made for Payment, as shown below, in connection with the Contract. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Month | Work Performed - See Payment Detail Page(s) | Original Contract | Change Orders | Revised Contract | This Payment Request | This Retainage (5% overall) | Total Payment | Percentage Complete
Feb. 2012 | 04-5150-707593 | 44227.35 |  | 44227.35 | 2211.37 |  | 2211.37
|  |  | 450 | 450 | 450 |  | 450
| Total: | 44227.35 | 450 | 44677.35 | 2661.37 | 0 | 2661.37
PROGRESS INVOICE HISTORY |  |  |  | THIS PAYMENT
Pay No. | Progress Amt | % Complete
1 | 16271.6 | 36.42%
2 | 19000 | 42.53% |  | ORIGINAL CONTRACT AMOUNT |  |  | $ | 44227.35
3 | 6744.38 | 15.1% |  | Net Change by Change Order(s) |  |  | $ | 450
4 | 2661.37 | 5.957% |  | CONTRACT SUM TO DATE |  |  | $ | 44677.35
THIS PAYMENT FROM:
|  |  |  | Account # 04-5150-707593 |  |  | $ | 2661.37
$
$
CURRENT PAYMENT DUE
Total | 44677.35 | 100% |  |  |  |  | $ | 2661.37
The undersigned Contractor certifies that the work covered by this Application for Payment has been completed in accordance with the Contract Documents, and that the current payment shown herein is now due. (The same Contractor shall be responsible for paying all his/her subcontractors/suppliers.) |  |  |  |  | CITY OF NEWBERG
[5 empty] | Jason Wuertz, Project Manager |  |  | Date
See Invoice
Firm/Contractor |  |  |  |  | Jay Harris, PE, City Engineer/Engineering Manager |  |  | Date
Signature |  | Date |  |  | Daniel Danicic, MPA, PE, City Manager (if over $5,000.00)
Title
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
◊ | Contractor's copy | Check Payment: | ◊ | Please hold.
◊ | Finance file |  | s | Please mail to - Deliver to Brian Kershaw
◊ | Engineering file |  | ◊ | Other