## Bid Sheet
SCHEDULE OF PRICES
N. College Street Sidewalk Improvement Project - Newberg
Project Description: Furnish all equipment, materials, and labor necessary to complete the construction of approximately 1,400 square feet of sidewalk and 330 linear feet of curb, with 16 sidewalk ramps, one catch basin and the associated asphalt pavement restoration work. Contract payments per this schedule of prices shall include full compensation for all incidental work under the contract per §109.07.
ITEM # | DESCRIPTION | APPLICABLE SECTION (not limited to) | UNIT | QNTY | UNIT PRICE | AMOUNT | AMOUNT IN WRITING
GENERAL
1 | Mobilization (Including performance bond, payment bond, maintenance warranty bond, insurance, city business permit and all other permits) | §201 | LS | 1 |  | $
2 | Traffic Control | §202 | LS | 1 |  | $
3 | Erosion & Sediment Control Measures (Including dust control) | §204 | LS | 1 |  | $
4 | Demolition, Stripping & Excavation (Including clear and grub, sawcut concrete sidewalk, remove ramps, haul off and disposal concrete & asphalt material) | §203, §204.03.09, §205, Plan Sht. 1 and 3 | LS | 1 |  | $
5 | Site Restoration & Cleanup | §208 | LS | 1 |  | $
6 | Survey Staking (For construction of curbs, sidewalks and catch basin) | §105.06 | LS | 1 |  | $
[5 empty] | Subtotal for GENERAL = | $
ROAD IMPROVEMENTS
7 | Sawcut Asphalt | Plan Sht. 3 | LF | 370 |  | $
8 | Standard ODOT Curb | Std. Dwg. RD700 | LF | 330
9 | Standard Concrete Sidewalk (4" thick over 2" of 3/4"-0 crushed rock over compacted subgrade) | Std. Dwg. RD720 | SF | 1396 |  | $
10 | Concrete Handicap Ramp (Including forming & placing concrete, & full width truncated dome surface) | Std. Dwg. RD755 and RD759 | EA | 8 |  | $
11 | Hot Mix Asphalt Concrete, Level 3 (4" in 2 lifts, dense graded class C) | §206.02.13B, §210.03.04, §505 | SY | 73 |  | $
12 | Base Rock, 9" Depth (1-1/2"-0) | §210.03.04, §210.03.06 | SY | 73 |  | $
13 | Leveling Rock, 3" Depth (3/4"-0) | §210.03.04, §210.03.06 | SY | 73 |  | $
14 | Compaction Tests | §205.03.18D, §505.03.14 | EA | 5 |  | $
[5 empty] | Subtotal for ROAD IMPROVEMENTS = | $
STORM IMPROVEMENTS
15 | Excavate, Install & Backfill 12" C900 | §205, §601, Plan Sht. 3 | LF | 10 |  | $
16 | Concrete Catch Basin (Pelican Style) | Std. Dwg. 407, Plan Sht. 3 | EA | 1 |  | $
17 | Concrete End Wall, Reinforced (3'L x 2.5'H x 10'W at the upstream end of the culvert near the westside RR signal) | Plan Sht. 3 | LS | 1 |  | $
[5 empty] | Subtotal for STORM SYSTEM IMPROVEMENTS = | $
OPTION TO RETROFIT ADDITIONAL SIDEWALK RAMPS
18 | Remove Existing Ramp & Install New Concrete Handicap Ramp (Including sawcut and remove concrete material from existing ramp; forming & placing concrete, & full width truncated dome surface) | Plan Sht. 1 & 3 | EA | 8 |  | $
[5 empty] | Subtotal for RETROFIT OPTION = | $
Note: City reserves the right to include or exclude bid item #18 in the contract.
|  |  |  | TOTAL & COMPLETE BID (for bid items #1 to #18 inclusive) = | $
|  |  |  | TOTAL & COMPLETE BID IN WRITING = | $

## Contract Cost
SCHEDULE OF PRICES
N. College Street Sidewalk Improvement Project - Newberg
Project Description: Furnish all equipment, materials, and labor necessary to complete the construction of approximately 1,400 square feet of sidewalk and 330 linear feet of curb, with 16 sidewalk ramps, one catch basin and the associated asphalt pavement restoration work. Contract payments per this schedule of prices shall include full compensation for all incidental work under the contract per §109.07.
ITEM # | DESCRIPTION | APPLICABLE SECTION (not limited to) | UNIT | QNTY | UNIT PRICE | AMOUNT | AMOUNT IN WRITING | QNTY | UNIT PRICE | AMOUNT
GENERAL
1 | Mobilization (Including performance bond, payment bond, maintenance warranty bond, insurance, and city business permit. City to secure separate Railroad Right of Entry permit and Railroad insurance) | §201 | LS | 1 | 3000 | 3000 | three thousand | 1 | 3000 | 3000
2 | Traffic Control on Streets (City to secure RR flagging) | §202 | LS | 1 | 2500 | 2500 | two thousand five hundred | 1 | 2500 | 2500
3 | Erosion & Sediment Control Measures (Including dust control) | §204 | LS | 1 | 500 | 500 | five hundred | 1 | 500 | 500
4 | Demolition, Stripping & Excavation (Including clear and grub, sawcut concrete sidewalk, remove ramps, haul off and disposal concrete & asphalt material) | §203, §204.03.09, §205, Plan Sht. 1 and 3 | LS | 1 | 5000 | 5000 | five thousand | 1 | 5000 | 5000
5 | Site Restoration & Cleanup | §208 | LS | 1 | 1000 | 1000 | one thousand | 1 | 1000 | 1000
6 | Survey Staking (For construction of curbs, sidewalks and catch basin) | §105.06 | LS | 1 | 1500 | 1500 | one thousand five hundred | 1 | 1500 | 1500
[5 empty] | Subtotal for GENERAL = | 13500 |  |  |  | 13500
ROAD IMPROVEMENTS
7 | Sawcut Asphalt | Plan Sht. 3 | LF | 370 | 3 | 1110 | one thousand one hundred ten | 370 | 3 | 1110
8 | Standard ODOT Curb | Std. Dwg. RD700 | LF | 330 | 20 | 6600 | six thousand six hundred | 330 | 20 | 6600
9 | Standard Concrete Sidewalk (4" thick over 2" of 3/4"-0 crushed rock over compacted subgrade) | Std. Dwg. RD720 | SF | 1396 | 5 | 6980 | six thousand nine hundred eighty | 1396 | 5 | 6980
10 | Concrete Handicap Ramp (Including forming & placing concrete, & full width truncated dome surface) | Std. Dwg. RD755 and RD759 | EA | 8 | 1000 | 8000 | eight thousand | 8 | 1000 | 8000
11 | Hot Mix Asphalt Concrete, Level 3 (4" in 2 lifts) | §210.03.04, §505 | SY | 73 | 30 | 2190 | two thousand one hundred ninty | 73 | 30 | 2190
12 | Base Rock, 9" Depth (1-1/2"-0) | §210.03.04, §210.03.06 | SY | 73 | 10 | 730 | seven hundred thirty | 73 | 10 | 730
13 | Leveling Rock, 3" Depth (3/4"-0) | §210.03.04, §210.03.06 | SY | 73 | 5 | 365 | three hundred sixty five | 73 | 5 | 365
14 | Compaction Tests | §205.03.18D, §505.03.14 | EA | 5 | 100 | 500 | five hundred | 5 | 100 | 500
[5 empty] | Subtotal for ROAD IMPROVEMENTS = | 26475 |  |  |  | 26475
STORM IMPROVEMENTS
15 | Excavate, Install & Backfill 12" C900 | §205, §601, Plan Sht. 3 | LF | 10 | 50 | 500 | five hundred | 10 | 50 | 500
16 | Concrete Catch Basin (Pelican Style) | Std. Dwg. 407, Plan Sht. 3 | EA | 1 | 2000 | 2000 | two thousand | 1 | 2000 | 2000
17 | Extend the 18" diameter culvert west of the westside railroad signal | Plan Sht. 3 | LS | 1 | 300 | 300 | three hundred | 1 | 300 | 300
[5 empty] | Subtotal for STORM SYSTEM IMPROVEMENTS = | 2800 |  |  |  | 2800
OPTION TO RETROFIT ADDITIONAL SIDEWALK RAMPS
18 | Remove Existing Ramp & Install New Concrete Handicap Ramp (Including sawcut and remove concrete material from existing ramp; forming & placing concrete, & full width truncated dome surface) | Plan Sht. 1 & 3 | EA | 4 | 1300 | 5200 | five thousand two hundred | 4 | 1300 | 5200
[5 empty] | Subtotal for RETROFIT OPTION = | 5200 |  |  |  | 5200
Note: City reserves the right to include or exclude bid item #18 in the final contract.
|  |  |  | TOTAL & COMPLETE BID (for bid items #1 to #18 inclusive) = | 47975 |  |  |  |  | 47975
|  |  |  | TOTAL & COMPLETE BID IN WRITING = | Forty seven thousand nine hundred seventy five dollars.

## Estimated Costs
SCHEDULE OF PRICES
N. College Street Sidewalk Improvement Project - Newberg
Project Description: Furnish all equipment, materials, and labor necessary to complete the construction of approximately 1,400 square feet of sidewalk and 330 linear feet of curb, with 16 sidewalk ramps, one catch basin and the associated asphalt pavement restoration work. Contract payments per this schedule of prices shall include full compensation for all incidental work under the contract per §109.07.
ITEM # | DESCRIPTION | APPLICABLE SECTION (not limited to) | UNIT | QNTY | UNIT PRICE | AMOUNT | AMOUNT IN WRITING
GENERAL
1 | Mobilization (Including performance bond, payment bond, maintenance warranty bond, insurance, city business permit and all other permits) | §201 | LS | 1 | 3500 | 3500
2 | Traffic Control | §202 | LS | 1 | 1000 | 1000
3 | Erosion & Sediment Control Measures (Including dust control) | §204 | LS | 1 | 300 | 300
4 | Demolition, Stripping & Excavation (Including clear and grub, sawcut concrete sidewalk, remove ramps, haul off and disposal concrete & asphalt material) | §203, §204.03.09, §205, Plan Sht. 1 and 3 | LS | 1 | 1500 | 1500
5 | Site Restoration & Cleanup | §208 | LS | 1 | 500 | 500
6 | Survey Staking (For construction of curbs, sidewalks and catch basin) | §105.06 | LS | 1 | 3800 | 3800
[5 empty] | Subtotal for GENERAL = | 10600
ROAD IMPROVEMENTS
7 | Sawcut Asphalt | Plan Sht. 3 | LF | 370 | 1 | 370
8 | Standard ODOT Curb | Std. Dwg. RD700 | LF | 330 | 17.5 | 5775
9 | Standard Concrete Sidewalk (4" thick over 2" of 3/4"-0 crushed rock over compacted subgrade) | Std. Dwg. RD720 | SF | 1396 | 4 | 5584
10 | Concrete Handicap Ramp (Including forming & placing concrete, & full width truncated dome surface) | Std. Dwg. RD755 and RD759 | EA | 8 | 1300 | 10400
11 | Hot Mix Asphalt Concrete, Level 3 (4" in 2 lifts) | §210.03.04, §505 | SY | 73 | 20 | 1460
12 | Base Rock, 9" Depth (1-1/2"-0) | §210.03.04, §210.03.06 | SY | 73 | 8 | 584
13 | Leveling Rock, 3" Depth (3/4"-0) | §210.03.04, §210.03.06 | SY | 73 | 3 | 219
14 | Compaction Tests | §205.03.18D, §505.03.14 | EA | 5 | 50 | 250
[5 empty] | Subtotal for ROAD IMPROVEMENTS = | 24642
STORM IMPROVEMENTS
15 | Excavate, Install & Backfill 12" C900 | §205, §601, Plan Sht. 3 | LF | 10 | 50 | 500
16 | Concrete Catch Basin (Pelican Style) | Std. Dwg. 407, Plan Sht. 3 | EA | 1 | 1500 | 1500
17 | Concrete End Wall, Reinforced (3'L x 2.5'H x 10'W at the upstream end of the culvert near the westside RR signal) | Plan Sht. 3 | LS | 1 | 1500 | 1500
[5 empty] | Subtotal for STORM SYSTEM IMPROVEMENTS = | 3500
OPTION TO RETROFIT ADDITIONAL SIDEWALK RAMPS
18 | Remove Existing Ramp & Install New Concrete Handicap Ramp (Including sawcut and remove concrete material from existing ramp; forming & placing concrete, & full width truncated dome surface) | Plan Sht. 1 & 3 | EA | 8 | 1400 | 11200
[5 empty] | Subtotal for RETROFIT OPTION = | 11200
Note: City reserves the right to include or exclude bid item #18 in the final contract.
|  |  |  | TOTAL & COMPLETE BID (for bid items #1 to #18 inclusive) = | 49942
|  |  |  | TOTAL & COMPLETE BID IN WRITING = | $
15.7083
[8 empty] | 1429.4583 | 2.1992
19.7925
72.2222

## Reimb Request_2012
C I T Y O F N E W B E R G
PUBLIC WORKS DEPARTMENT / ENGINEERING DIVISION
CITY HALL, 414 EAST FIRST STREET, P. O. BOX 970, NEWBERG, OR 97132
TEL: (503) 537-1240 FAX: (503) 537-1277
REIMBURSEMENT REQUEST FOR HWY 219 / N. COLLEGE STREET EASTSIDE PEDESTRIAN PROJECT (PER IGA # 26900)
[5 empty] | Date: |  | 2012-08-02
[5 empty] | Prepared by: |  | Paul Chiu, P.E.
SCHEDULE 1 |  | ENGINEERING DESIGN, ADMINISTRATION (BY CITY PERSONNEL)
Item No. | Item Description |  | Quantity | Unit | Unit Price | Unit Price in Writing | Item Total
1.01 | Project Design & Administration |  | 1 | LS | 3743.42 |  | 3743.42
| SCHEDULE 1 SUBTOTAL = | [5 empty] | 3743.42
SCHEDULE 2A |  | CONSTRUCTION - GENERAL (BY RAUGUST EXCAVATING INC.)
Item No. | Item Description |  | Quantity | Unit | Unit Price | Unit Price in Writing | Item Total
2.01 | Mobilization |  | 0.5 | LS | 3000 |  | 1500
2.02 | Traffic Control on Streets |  | 0.5 | LS | 2500 |  | 1250
2.03 | Sediment & Erosion Control Measures |  | 0.5 | LS | 500 |  | 250
2.04 | Demolition, Stripping & Excavation |  | 0.5 | LS | 5000 |  | 2500
2.05 | Site Restoration & Cleanup |  | 0.5 | LS | 1000 |  | 500
2.06 | Survey Staking |  | 0.5 | LS | 1500 |  | 750
| SCHEDULE 2A SUBTOTAL = | [5 empty] | 6750
SCHEDULE 2B |  | CONSTRUCTION - SIDEWALK & ROADWAY IMPROVEMENTS (BY RAUGUST EXCAVATING INC.) | [5 empty] | 15021
Item No. | Item Description |  | Quantity | Unit | Unit Price | Unit Price in Writing | Item Total
2.07 | Sawcut Asphalt |  | 62 | LF | 3 |  | 186
2.08 | Standard ODOT Curb [* See note 1 below] |  | 0 | LF | 20 |  | 0
2.09 | Standard Concrete Sidewalk [* See note 1 below] |  | 0 | SF | 5 |  | 0
2.1 | Concrete Handicap Ramp |  | 2 | EA | 1000 |  | 2000
2.11 | Hot Mix Asphalt Concrete, Level 3 (4" in 2 lifts) |  | 13 | SY | 30 |  | 390
2.12 | Base Rock, 9" Depth (1-1/2"-0) |  | 13 | SY | 10 |  | 130
2.13 | Leveling Rock, 3" Depth (3/4"-0) |  | 13 | SY | 5 |  | 65 | 754.43
2.14 | Compaction Tests |  | 3 | EA | 100 |  | 300
2.15 | Excavate, Install & Backfill 12" C900 (storm pipe) [* See note 2 below] |  | 0 | LF | 50 |  | 0
2.16 | Concrete Catch Basin (Pelican Style) [* See note 2 below] |  | 0 | EA | 2000 |  | 0
2.17 | Concrete End Wall (at upstream end of culvert near westside RR signal) [* See note 2 below] |  | 0 | LS | 300 |  | 0
2.18 | Remove Existing Ramp & Install New Concrete Handicap Ramp (at Sheridan) |  | 4 | EA | 1300 |  | 5200
| SCHEDULE 2B SUBTOTAL = | [5 empty] | 8271
SCHEDULE 3 |  | CONSTRUCTION - RAILROAD PEDESTRIAN CROSSING (BY CITY PERSONNEL) | [5 empty] | 19331
Item No. | Item Description |  | Quantity | Unit | Unit Price | Unit Price in Writing | Item Total
3.01 | Pedestrian RR Crossing Pads (3) [* See note 3 below] |  | 1 | LS | 9665.5 |  | 9665.5
3.02 | Forklift Rental from Hertz Equipment Rental [* See note 4 below] |  | 1 | LS | 548 |  | 548
3.03 | Concrete Sidewalk, ADA S/W Ramp, Sidewalk between RR Tracks, Safety Yellow Truncated Domes, |  | 1 | LS | 1662.02 |  | 1662.02
3.04 | Construction Labor, Equipment, Project Management & Inspection |  | 1 | LS | 13517.63 |  | 13517.63
| SCHEDULE 3 SUBTOTAL = | [5 empty] | 25393.15
| GRAND TOTAL = | [5 empty] | 44157.57
| MAXIMUM REIMBURSEMENT PER IGA # 26900 = | [5 empty] | 42000
NOTES: 1. CURB AND SIDEWALK ON THE EAST SIDE OF N. COLLEGE STREET WERE INSTALLED BY CITY PERSONNEL. 2. CATCH BASIN, STORM CULVERT AND END WALL WERE INSTALLED FOR THE WEST SIDE TE PROJECT (NOT FOR REIMBURSEMENT). 3. PORTLAND & WESTERN RAILROAD COMPANY INSTALLED THE CROSSING PADS AT NO COST TO THE CITY OF NEWBERG AND ODOT. ITEM #3.01 IS SIMPLY THE COST OF PURCHASING THE CROSSING PAD MATERIALS FOR THE EAST SIDE. 4. FORKLIFT WAS USED TO LIFT, MOVE AND INSTALL CROSSING PADS. 5. RAILROAD FLAGGING WAS PROVIDED BY PORTLAND & WESTERN RAILROAD COMPANY. 6. THIS PROJECT (MP 19.88 to MP 19.80) FUNDED 245 LF OF NEW CONCRETE SIDEWALK (INCLUDING 3 SETS OF RAILROAD PEDESTRIAN CROSSING PADS), 5 NEW ADA SIDEWALK RAMPS, 2 SETS OF TRUNCATED DOMES AT RAILROAD CROSSING, AND 50 LF OF NEW CONCRETE CURB.

## Reimb Request Detail
18-5150-702162 | College St-RR Xing/E Sidewalk
2010-11-30 | Cap Proj Salaries - 11/30/10 | 959.3 | FY 10-11= | 1577.31 | 3743.42
2010-12-31 | Cap Proj Salaries - 12/31/10 | 65.98
2011-01-31 | Cap Proj Salaries - 01/31/11 | 90.17
2011-02-28 | Cap Proj Salaries - 02/28/11 | 32.99
2011-05-31 | Cap Proj Salaries - 05/31/11 | 32.99
2011-06-30 | Cap Proj Salaries - 06/30/11 | 395.88
2011-07-31 | Cap Proj Salaries - 07/31/11 | 321.78 | FY 11-12= | 10483.74
2011-09-30 | Cap Proj Salaries - 09/30/11 | 70
2011-10-31 | Cap Proj Salaries - 10/31/11 | 420
2011-11-30 | Cap Proj Salaries - 11/30/11 | 1354.33 |  | Design Phase
2011-12-31 | Cap Proj Salaries - 12/31/11 | 549.33 |  |  | 8317.63
2012-01-31 | Cap Proj Salaries - 01/31/12 | 172.39
2012-02-29 | Cap Proj Salaries - 02/29/12 | 3870.66
2012-03-31 | Cap Proj Salaries - 03/31/12 | 2548.1
2012-04-30 | Cap Proj Salaries - 04/30/12 | 205.42
2012-05-31 | Cap Proj Salaries - 05/31/12 | 35
2012-06-30 | Cap Proj Salaries - 06/30/12 | 936.73 |  | Construction Phase
2011-11-17 | 02858 - Hertz Equipment Rental Corp | 548
Eng#117-Forklift rental-Unload RR crossing pads
2011-11-30 | 05439 - Omega Industries Inc | 9665.5
N College St - RR Crossing Improvements
2011-11-30 | 01033 - CalPortland Company | 401.51
PWM#12095-Concrete-College & Illinois
2011-11-30 | Pcard-DELANO SUPPLY-Supplies-Expansion joints-WHITMAN HOWARD | 21
2012-02-23 | 01033 - CalPortland Company | 656.01
PWM#12125-Concrete-N College & Illinois
2012-03-30 | 01033 - CalPortland Company | 428.5
PWM#12144-Concrete for N College & Illinois
2012-03-31 | pcard-DELANO SUPPLY-Supplies-Tiles-WHITMAN HOWARD | 155
2012-06-30 | 06595 - Raugust Excavating, Inc | 12183.75
N College sidewalk improvement project
2012-08-02 | 06595 - Raugust Excavating, Inc | 2086.2
N College sidewalk improvement project
2012-08-09 | 06595 - Raugust Excavating, Inc | 751.19 |  | 15021.14
N College sidewalk improvement project
38957.71
| Equipment | 5200
|  | 44157.71 |  | including 14 cents for interest on retainage

## Compare Bids
SCHEDULE OF PRICES
N. College Street Sidewalk Improvement Project - Newberg
Project Description: Furnish all equipment, materials, and labor necessary to complete the construction of approximately 1,400 square feet of sidewalk and 330 linear feet of curb, with 16 sidewalk ramps, one catch basin and the associated asphalt pavement restoration work. Contract payments per this schedule of prices shall include full compensation for all incidental work under the contract per §109.07.
ITEM # | DESCRIPTION | APPLICABLE SECTION (not limited to) | UNIT | QNTY | UNIT PRICE | AMOUNT | AMOUNT IN WRITING | QNTY | UNIT PRICE | AMOUNT
GENERAL
1 | Mobilization (Including performance bond, payment bond, maintenance warranty bond, insurance, and city business permit. City to secure separate Railroad Right of Entry permit and Railroad insurance) | §201 | LS | 1 | 3500 | 3500 |  | 1 | 3000 | 3000
2 | Traffic Control on Streets (City to secure RR flagging) | §202 | LS | 1 | 1000 | 1000 |  | 1 | 2500 | 2500
3 | Erosion & Sediment Control Measures (Including dust control) | §204 | LS | 1 | 300 | 300 |  | 1 | 500 | 500
4 | Demolition, Stripping & Excavation (Including clear and grub, sawcut concrete sidewalk, remove ramps, haul off and disposal concrete & asphalt material) | §203, §204.03.09, §205, Plan Sht. 1 and 3 | LS | 1 | 1500 | 1500 |  | 1 | 5000 | 5000
5 | Site Restoration & Cleanup | §208 | LS | 1 | 500 | 500 |  | 1 | 1000 | 1000
6 | Survey Staking (For construction of curbs, sidewalks and catch basin) | §105.06 | LS | 1 | 3800 | 3800 |  | 1 | 1500 | 1500
[5 empty] | Subtotal for GENERAL = | 10600 |  |  |  | 13500
ROAD IMPROVEMENTS
7 | Sawcut Asphalt | Plan Sht. 3 | LF | 370 | 1 | 370 |  | 370 | 3 | 1110
8 | Standard ODOT Curb | Std. Dwg. RD700 | LF | 330 | 17.5 | 5775 |  | 330 | 20 | 6600
9 | Standard Concrete Sidewalk (4" thick over 2" of 3/4"-0 crushed rock over compacted subgrade) | Std. Dwg. RD720 | SF | 1396 | 4 | 5584 |  | 1396 | 5 | 6980
10 | Concrete Handicap Ramp (Including forming & placing concrete, & full width truncated dome surface) | Std. Dwg. RD755 and RD759 | EA | 8 | 1300 | 10400 |  | 8 | 1000 | 8000
11 | Hot Mix Asphalt Concrete, Level 3 (4" in 2 lifts) | §210.03.04, §505 | SY | 73 | 20 | 1460 |  | 73 | 30 | 2190
12 | Base Rock, 9" Depth (1-1/2"-0) | §210.03.04, §210.03.06 | SY | 73 | 8 | 584 |  | 73 | 10 | 730
13 | Leveling Rock, 3" Depth (3/4"-0) | §210.03.04, §210.03.06 | SY | 73 | 3 | 219 |  | 73 | 5 | 365
14 | Compaction Tests | §205.03.18D, §505.03.14 | EA | 5 | 50 | 250 |  | 5 | 100 | 500
[5 empty] | Subtotal for ROAD IMPROVEMENTS = | 24642 |  |  |  | 26475
STORM IMPROVEMENTS
15 | Excavate, Install & Backfill 12" C900 | §205, §601, Plan Sht. 3 | LF | 10 | 50 | 500 |  | 10 | 50 | 500
16 | Concrete Catch Basin (Pelican Style) | Std. Dwg. 407, Plan Sht. 3 | EA | 1 | 1500 | 1500 |  | 1 | 2000 | 2000
17 | Extend the 18" diameter culvert west of the westside railroad signal | Plan Sht. 3 | LS | 1 | 1500 | 1500 |  | 1 | 300 | 300
[5 empty] | Subtotal for STORM SYSTEM IMPROVEMENTS = | 3500 |  |  |  | 2800
OPTION TO RETROFIT ADDITIONAL SIDEWALK RAMPS
18 | Remove Existing Ramp & Install New Concrete Handicap Ramp (Including sawcut and remove concrete material from existing ramp; forming & placing concrete, & full width truncated dome surface) | Plan Sht. 1 & 3 | EA | 8 | 1400 | 11200 |  | 4 | 1300 | 5200
[5 empty] | Subtotal for RETROFIT OPTION = | 11200 |  |  |  | 5200
Note: City reserves the right to include or exclude bid item #18 in the final contract.
|  |  |  | TOTAL & COMPLETE BID (for bid items #1 to #18 inclusive) = | 49942 |  |  |  |  | 47975
|  |  |  | TOTAL & COMPLETE BID IN WRITING = | $

## PROGRESS PAYMENT DETAIL
PROGRESS PAYMENT DETAIL FOR KIZER EXCAVATING COMPANY | [12 empty] | Payment No. 1 |  |  | Payment No. 2 |  |  | Payment No. 3
Crestview Drive Improvements Project - Newberg
Project Description: Furnish all equipment, materials, and labor necessary to complete the construction of approximately 840 linear feet of roadway construction, with associated storm, water, streetlight, wall and landscape installation, and roadway striping and signing. Scope includes joint trench conduit installation for PGE and Comcast (for their utility extensions and relocations) and for City's street lighting. Frontier Communications and NW Natural may provide their own utility extensions and/or relocations. Trench bedding and backfill includes compacted 1-1/2"-0 granular fill. Contract payments per this schedule of prices shall include full compensation for all incidental work under the contract per §109.07.
SCHEDULE OF PRICES for N. College Street Sidewalk Improvement Project - Newberg | [7 empty] | FUNDING |  |  | SUMMARY OF PAYMENTS TO-DATE |  | MONTH OF JUNE 2012 |  |  | MONTH OF JULY 2012 |  |  | MONTH OF AUGUST 2012
ITEM # | DESCRIPTION | APPLICABLE SECTION (not limited to) | UNIT | BID QUANTITY | UNIT PRICE | AMOUNT | QUANTITY | East (18-5150-702162) | QUANTITY | West (18-5150-702165) | QUANTITY TO-DATE | PAYMENT TO-DATE | QUANTITY THIS PERIOD | UNIT PRICE | AMOUNT FOR THIS PERIOD | QUANTITY THIS PERIOD | UNIT PRICE | AMOUNT FOR THIS PERIOD | QUANTITY THIS PERIOD | UNIT PRICE | AMOUNT FOR THIS PERIOD
GENERAL
1 | Mobilization (Including performance bond, payment bond, maintenance warranty bond, insurance, and city business permit. City to secure separate Railroad Right of Entry permit and Railroad insurance) | §201 | LS | 1 | 3000 | 3000 | 0.5 | 1500 | 0.5 | 1500 | 1 | 3000 | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 3000 | 0
2 | Traffic Control on Streets (City to secure RR flagging) | §202 | LS | 1 | 2500 | 2500 | 0.5 | 1250 | 0.5 | 1250 | 1 | 2500 | 0.5 | 2500 | 1250 | 0.5 | 2500 | 1250 | 0 | 2500 | 0
3 | Erosion & Sediment Control Measures (Including dust control) | §204 | LS | 1 | 500 | 500 | 0.5 | 250 | 0.5 | 250 | 1 | 500 | 1 | 500 | 500 | 0 | 500 | 0 | 0 | 500 | 0
4 | Demolition, Stripping & Excavation (Including clear and grub, sawcut concrete sidewalk, remove ramps, haul off and disposal concrete & asphalt material) | §203, §204.03.09, §205, Plan Sht. 1 and 3 | LS | 1 | 5000 | 5000 | 0.5 | 2500 | 0.5 | 2500 | 1 | 5000 | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 5000 | 0
5 | Site Restoration & Cleanup | §208 | LS | 1 | 1000 | 1000 | 0.5 | 500 | 0.5 | 500 | 1 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 1000 | 0 | 1000 | 0
6 | Survey Staking (For construction of curbs, sidewalks and catch basin) | §105.06 | LS | 1 | 1500 | 1500 | 0.5 | 750 | 0.5 | 750 | 1 | 1500 | 1 | 1500 | 1500 | 0 | 1500 | 0 | 0 | 1500 | 0
| Subtotal for GENERAL = |  |  |  |  | 13500 |  | 6750 |  | 6750 |  | 13500 |  |  | 11250 |  |  | 2250 |  |  | 0
ROAD IMPROVEMENTS
7 | Sawcut Asphalt | Plan Sht. 3 | LF | 370 | 3 | 1110 | 62 | 186 | 370 | 1110 | 432 | 1296 | 370 | 3 | 1110 | 62 | 3 | 186 | 0 | 3 | 0
8 | Standard ODOT Curb | Std. Dwg. RD700 | LF | 330 | 20 | 6600 | 0 | 0 | 330 | 6600 | 330 | 6600 | 330 | 20 | 6600 | 0 | 20 | 0 | 0 | 20 | 0
9 | Standard Concrete Sidewalk (4" thick over 2" of 3/4"-0 crushed rock over compacted subgrade) | Std. Dwg. RD720 | SF | 1396 | 5 | 6980 | 0 | 0 | 1396 | 6980 | 1396 | 6980 | 1396 | 5 | 6980 | 0 | 5 | 0 | 0 | 5 | 0
10 | Concrete Handicap Ramp (Including forming & placing concrete, & full width truncated dome surface) | Std. Dwg. RD755 and RD759 | EA | 8 | 1000 | 8000 | 2 | 2000 | 6 | 6000 | 8 | 8000 | 8 | 1000 | 8000 | 0 | 1000 | 0 | 0 | 1000 | 0
11 | Hot Mix Asphalt Concrete, Level 3 (4" in 2 lifts) | §210.03.04, §505 | SY | 73 | 30 | 2190 | 13 | 390 | 73 | 2190 | 86 | 2580 | 0 | 30 | 0 | 86 | 30 | 2580 | 0 | 30 | 0
12 | Base Rock, 9" Depth (1-1/2"-0) | §210.03.04, §210.03.06 | SY | 73 | 10 | 730 | 13 | 130 | 73 | 730 | 86 | 860 | 73 | 10 | 730 | 13 | 10 | 130 | 0 | 10 | 0
13 | Leveling Rock, 3" Depth (3/4"-0) | §210.03.04, §210.03.06 | SY | 73 | 5 | 365 | 13 | 65 | 73 | 365 | 86 | 430 | 73 | 5 | 365 | 13 | 5 | 65 | 0 | 5 | 0
14 | Compaction Tests | §205.03.18D, §505.03.14 | EA | 5 | 100 | 500 | 3 | 300 | 2 | 200 | 5 | 500 | 0 | 100 | 0 | 5 | 100 | 500 | 0 | 100 | 0
| Subtotal for ROAD IMPROVEMENTS = |  |  |  |  | 26475 |  | 3071 |  | 24175 |  | 27246 |  |  | 23785 |  |  | 3461 |  |  | 0
STORM IMPROVEMENTS
15 | Excavate, Install & Backfill 12" C900 | §205, §601, Plan Sht. 3 | LF | 10 | 50 | 500 | 0 | 0 | 10 | 500 | 10 | 500 | 10 | 50 | 500 | 0 | 50 | 0 | 0 | 50 | 0
16 | Concrete Catch Basin (Pelican Style) | Std. Dwg. 407, Plan Sht. 3 | EA | 1 | 2000 | 2000 | 0 | 0 | 1 | 2000 | 1 | 2000 | 1 | 2000 | 2000 | 0 | 2000 | 0 | 0 | 2000 | 0
17 | Extend the 18" diameter culvert west of the westside railroad signal | Plan Sht. 3 | LS | 1 | 300 | 300 | 0 | 0 | 1 | 300 | 1 | 300 | 1 | 300 | 300 | 0 | 300 | 0 | 0 | 300 | 0
| Subtotal for STORM SYSTEM IMPROV. = |  |  |  |  | 2800 |  | 0 |  | 2800 |  | 2800 |  |  | 2800 |  |  | 0 |  |  | 0
OPTION TO RETROFIT ADDITIONAL SIDEWALK RAMPS
18 | Remove Existing Ramp & Install New Concrete Handicap Ramp (Including sawcut and remove concrete material from existing ramp; forming & placing concrete, & full width truncated dome surface) | Plan Sht. 1 & 3 | EA | 4 | 1300 | 5200 | 4 | 5200 | 0 | 0 | 4 | 5200 | 4 | 1300 | 5200 | 0 | 1300 | 0 | 0 | 1300 | 0
| Subtotal for ADDITIONAL RETROFIT = |  |  |  |  | 5200 |  | 5200 |  | 0 |  | 5200 |  |  | 5200 |  |  | 0 |  |  | 0
CHANGE ORDER #0
1.1 |  | §- | LS | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | 15021 | §- | LS | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 |  | §- | LS | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal for CHANGE ORDER #1 = |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| GRAND TOTAL = |  |  |  |  | 47975 |  | 15021 |  | 33725 |  | 48746 |  |  | 43035 |  |  | 5711 |  |  | 0
[8 empty] | 48746 |  | 771
Account # 18-5150-702162 (street-E) | [9 empty] | 15021 |  | 15021 |  |  | 12825 |  |  | 2196 |  |  | 0
Account # 18-5150-702165 (street-W) | [9 empty] | 33725 |  | 33725 |  |  | 30210 |  |  | 3515 |  |  | 0
Verify if this total = Grand Total above | [6 empty] | Verified Not OK | Verified OK |  | 48746 | Verified OK | 48746 | Verified OK |  | 43035 | Verified OK |  | 5711 | Verified OK |  | 0

## HISTORY OF PROGRESS
PROGRESS PAYMENT HISTORY
Project Name: | Crestview Drive Improvement Project | [5 empty] | Date of Application: |  | 2012-03-09
Project Nos: | 18-5150-702167 (street)
| 04-5150-707607 (water) | [5 empty] | Payment No: |  | 6 (FINAL)
04-5150-717727 (storm)
Resolution No: | 2011-2949 | [5 empty] | Invoice Date: | 2012-02-27 | (see attached invoice)
Purchase Order No: |  | 4000
[7 empty] | Pay Period: | Month of February 2012
The Contract was signed by City Manager on June 21, 2011, for $851,828.90.
[7 empty] | Contractor: | Kizer Excavating Company
A copy of the Purchase Order is attached.
A copy of Change Order #1 & #2 is attached.
PROGRESS INVOICE HISTORY
Pay No. | Progress Total (prior to retainage) | % Complete | Progress Payment | A/c #18-5150-702167 (street) | A/c #04-5150-707607 (water) | A/c #04-5150-717727 (storm) | street retainage | water retainage | storm retainage
1 | 43035 | 89.7% | 40883.25 | 12183.75 | 28699.5 | 0 | 641.25 | 1510.5 | 0
2 | 5711 | 11.72% | 5425.45 | 2086.2 | 3339.25 | 0 | 109.8 | 175.75 | 0
3 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
To Date Total | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Cont'd PROGRESS INVOICE HISTORY
Pay No. | A/c #18-5150-702167 (street retainage) | A/c #04-5150-707607 (water retainage) | A/c #04-5150-717727 (storm retainage) | Interest on street retainage | Interest on water retainage | Interest on storm retainage | street retainage & interest earned | water retainage & interest earned | storm retainage & interest earned
1 | 641.25 | 1510.5 | 0
2 | 109.8 | 175.75 | 0
3 | 0 | 0 | 0
4 | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF!
To Date Total | #REF! | #REF! | #REF! | 50.02 | 8.17 | 10.54 | #REF! | #REF! | #REF!
| = A | = B | = C | = D | = E | = F | = A + D | = B + E | = C+ F
◊ | Contractor's copy
◊ | Finance file
◊ | Engineering file

## PROGRESS PAYMENT NO. 1
PROGRESS PAYMENT
Project Name: | N. College St. Sidewalk Improv. Proj. |  |  |  |  | Date of Application: |  | 2012-07-11
Project Nos: | 18-5150-702162 (street)
| 18-5150-702165 (street) |  |  |  |  | Payment No: |  | 1
Resolution No: | N/A |  |  |  |  | Invoice Date: | 2012-06-29 | (see attached invoice)
Purchase Order No: |  | 4185
[6 empty] | Pay Period: | Month of June 2012
The Contract was signed by City Manager on June 14, 2012, for $47,975.00.
[6 empty] | Contractor: | Raugust Excavating, Inc.
A copy of the Purchase Order is attached.
Application is made for Payment, as shown below, in connection with the Contract. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Month | Work Performed - See Payment Detail Page(s) | Original Contract | Change Orders (or Final Q Adj) | Revised Contract | This Payment Request | This Retainage (5% overall) | Total Payment | Percentage Complete
June 2012 | 18-5150-702162 | 15000 |  | 15000 | 12825 | 641.25 | 12183.75 | 85.5%
| 18-5150-702165 | 32975 |  | 32975 | 30210 | 1510.5 | 28699.5 | 91.61%
| Total: | 47975 | 0 | 47975 | 43035 | 2151.75 | 40883.25 | 89.7%
PROGRESS INVOICE HISTORY |  |  |  | THIS PAYMENT
Pay No. | Progress Amt | % Complete
1 | 43035 | 89.7%
|  |  |  | ORIGINAL CONTRACT AMOUNT |  |  | $ | 47975
|  |  |  | Net Change by Change Order(s) |  |  | $ | 0
|  |  |  | CONTRACT SUM TO DATE |  |  | $ | 47975
THIS PAYMENT FROM:
|  |  |  | Account # 18-5150-702162 (street -East) |  |  | $ | 12183.75
|  |  |  | Account # 18-5150-702165 (street -West) |  |  | $ | 28699.5
CURRENT PAYMENT DUE
Total | 43035 | 89.7% |  |  |  |  | $ | 40883.25
The undersigned Contractor certifies that the work covered by this Application for Payment has been completed in accordance with the Contract Documents, and that the current payment shown herein is now due. (The same Contractor shall be responsible for paying all his/her subcontractors/suppliers.)
CITY OF NEWBERG
Firm/Contractor |  |  |  |  | Paul Chiu, PE, Senior Engineer/Project Manager |  |  | Date
Signature |  | Date |  |  | Jay Harris, PE, City Engineer/Engineering Manager |  |  | Date
Title |  |  |  |  | Daniel Danicic, MPA, PE, City Manager (if over $5,000.00) |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
◊ | Contractor's copy | Check Payment: | ◊ | Please hold.
◊ | Finance file |  | s | Please mail to - Raugust Excavating, Inc., PO Box 267, Newberg, OR 97132
◊ | Engineering file |  | ◊ | Other

## PROGRESS PAYMENT NO. 2
PROGRESS PAYMENT
Project Name: | N. College St. Sidewalk Improv. Proj. |  |  |  |  | Date of Application: |  | 2012-07-31
Project Nos: | 18-5150-702162 (street)
| 18-5150-702165 (street) |  |  |  |  | Payment No: |  | 2
Resolution No: | N/A |  |  |  |  | Invoice Date: | 2012-07-13 | (see attached invoice)
Purchase Order No: |  | 4185
[6 empty] | Pay Period: | Month of July 2012
The Contract was signed by City Manager on June 14, 2012, for $47,975.00.
[6 empty] | Contractor: | Raugust Excavating, Inc.
A copy of the Purchase Order is attached.
Application is made for Payment, as shown below, in connection with the Contract. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Month | Work Performed - See Payment Detail Page(s) | Original Contract | Final Quantity Adjustment | Revised Contract | This Payment Request | This Retainage (5% overall) | Total Payment | Percentage Complete
July 2012 | 18-5150-702162 | 15000 | 21 | 15021 | 2196 | 109.8 | 2086.2 | 14.62%
| 18-5150-702165 | 32975 | 750 | 33725 | 3515 | 175.75 | 3339.25 | 10.42%
| Total: | 47975 | 771 | 48746 | 5711 | 285.55 | 5425.45 | 11.72%
PROGRESS INVOICE HISTORY |  |  |  | THIS PAYMENT
Pay No. | Progress Amt | % Complete
1 | 43035 | 88.3%
2 | 5711 | 11.72% |  | ORIGINAL CONTRACT AMOUNT |  |  | $ | 47975
|  |  |  | Net Change by Final Quantity Adjustment |  |  | $ | 771
|  |  |  | CONTRACT SUM TO DATE |  |  | $ | 48746
THIS PAYMENT FROM:
|  |  |  | Account # 18-5150-702162 (street -East) |  |  | $ | 2086.2
|  |  |  | Account # 18-5150-702165 (street -West) |  |  | $ | 3339.25
CURRENT PAYMENT DUE
Total | 48746 | 100% |  |  |  |  | $ | 5425.45
The undersigned Contractor certifies that the work covered by this Application for Payment has been completed in accordance with the Contract Documents, and that the current payment shown herein is now due. (The same Contractor shall be responsible for paying all his/her subcontractors/suppliers.)
CITY OF NEWBERG
Firm/Contractor |  |  |  |  | Paul Chiu, PE, Senior Engineer/Project Manager |  |  | Date
Signature |  | Date |  |  | Jay Harris, PE, City Engineer/Engineering Manager |  |  | Date
Title |  |  |  |  | Daniel Danicic, MPA, PE, City Manager (if over $5,000.00) |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
◊ | Contractor's copy | Check Payment: | ◊ | Please hold.
◊ | Finance file |  | s | Please mail to - Raugust Excavating, Inc., PO Box 267, Newberg, OR 97132
◊ | Engineering file |  | ◊ | Other

## FINAL PAYMENT NO. 3
PROGRESS PAYMENT
Project Name: | N. College St. Sidewalk Improv. Proj. |  |  |  |  | Date of Application: |  | 2012-08-01
Project Nos: | 18-5150-702162 (street)
| 18-5150-702165 (street) |  |  |  |  | Payment No: |  | 3 (FINAL)
Resolution No: | N/A |  |  |  |  | Invoice Date: | N/A
Purchase Order No: |  | 4185
[6 empty] | Pay Period: | RELEASE OF RETAINAGE
The Contract was signed by City Manager on June 21, 2011, for $851,828.90.
[6 empty] | Contractor: | Raugust Excavating, Inc.
A copy of the Purchase Order is attached.
Application is made for Payment, as shown below, in connection with the Contract. Payment due date per Contract specification. The present status of the account(s) for this Contract is as follows:
THIS PAYMENT
Month | Work Performed - See Payment Detail Page(s) | Original Contract | Final Quantity Adjustment | Revised Contract | This Payment Request | This Retainage (5% overall) | Total Payment | Percentage Complete
July 2012 | 18-5150-702162 | 15000 | 21 | 15021 | 0 | 0 | 0 | 0%
| 18-5150-702165 | 32975 | 750 | 33725 | 0 | 0 | 0 | 0%
RELEASE OF RETAINAGE | Account # | Original Contract | Final Quantity Adjustment | RETAINAGE on PROGRESS PAYMENTS #1 & #2 |  | INTEREST | TOTAL PAYMENT (Retainage & Interest)
| 18-5150-702162 | 15000 | 21 | 641.25 | 109.8 | 0.14 | 751.19
| 18-5150-702165 | 32975 | 750 | 1510.5 | 175.75 | 0.32 | 1686.57
Total: |  | 47975 | 771 | 48746 | 0 | 0 | 2437.76 | 0%
PROGRESS INVOICE HISTORY |  |  |  | THIS PAYMENT
Pay No. | Progress Amt | % Complete
1 | 43035 | 88.3%
2 | 5711 | 11.72% |  | ORIGINAL CONTRACT AMOUNT |  |  | $ | 47975
|  |  |  | Net Change by Final Quantity Adjustment |  |  | $ | 771
|  |  |  | CONTRACT SUM TO DATE |  |  | $ | 48746
THIS PAYMENT FROM:
|  |  |  | Account # 18-5150-702162 (street -East) |  |  | $ | 751.19
|  |  |  | Account # 18-5150-702165 (street -West) |  |  | $ | 1686.57
CURRENT PAYMENT DUE
Total | 48746 | 100% |  |  |  |  | $ | 2437.76
The undersigned Contractor certifies that the work covered by this Application for Payment has been completed in accordance with the Contract Documents, and that the current payment shown herein is now due. (The same Contractor shall be responsible for paying all his/her subcontractors/suppliers.)
CITY OF NEWBERG
Firm/Contractor |  |  |  |  | Paul Chiu, PE, Senior Engineer/Project Manager |  |  | Date
Signature |  | Date |  |  | Jay Harris, PE, City Engineer/Engineering Manager |  |  | Date
Title |  |  |  |  | Daniel Danicic, MPA, PE, City Manager (if over $5,000.00) |  |  | Date
This certificate is not negotiable. It is payable only to the payee named herein and its issuance, payment and acceptance are without prejudice to any rights of the Owner or Contractor under their Contract.
◊ | Contractor's copy | Check Payment: | ◊ | Please hold.
◊ | Finance file |  | s | Please mail to - Raugust Excavating, Inc., PO Box 267, Newberg, OR 97132
◊ | Engineering file |  | ◊ | Other